Type of Review: Annual Review (Multilateral Organisation Core funding)

Title of funding stream: UNITAID

Date started:	Date review undertaken: December 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The UK is one of the 5 founding members of UNITAID, alongside France, Chile, Norway and Brazil. UK contributions, in accordance with our MoU with UNITAID, are approximately £53 million per annum. Full disbursement is dependent on performance. / The UK is the second largest donor after France, and takes an active role in strategy and policy discussions through the Policy and Strategy Committee, as well as providing the Chair for UNITAID’s Finance and Accountability Committee to provide financial and administrative oversight.

What are the expected results?
UNITAID funds projects and programmes which will have a positive market impact and positive health outcomes. / Core expected results in the period to 2016 are: / Increased access to diagnostic testing for HIV/AIDS, TB and malaria; / Increased access to affordable, paediatric medicines to treat HIV/AIDS, TB and malaria; / Increased access to emerging medicines and/or regimens as well as new formulations, dosage forms, or strengths of existing medicines that will improve the treatment of HIV/AIDS and co-infections such as viral hepatitis; / Increased access to Artemisinin-based combination therapies (ACTs) - and emerging medicines, which, in combination with appropriate diagnostic testing - will improve the treatment of malaria; / Secured supply of second-line TB medicines, and increased access to emerging medicines and regimens that will improve treatment of both drug-sensitive and Multi-Drug Resistant TB (MDR TB); / Increased access to products for the prevention of HIV, TB, and malaria, notably to improve the availability of devices for male circumcision and of microbicides, once they are approved; and to increase access to vector control tools to prevent malaria transmission.

What is the context in which UK support is provided?
UNITAID was created in 2006 to reduce the costs of, and speed up access to, high quality drugs and diagnostics in the fight against HIV/AIDS, TB and Malaria. It is well known that there are numerous health and market challenges surrounding the three diseases – unmet need for drugs, high prices, poor access, fragmented markets, inadequate diagnostics, poor forecasting of demand etc. / UNITAID seeks to intervene as a market shaper, market fixer or market catalyst where the needs are greatest. It spends the majority of its resources for the benefit of Low Income Countries (90%). / UNITAID’s funding is primarily based on ‘innovative finance’. For example, several countries apply an air ticket levy in their countries to provide funds e.g. France, UNITAID’s largest funder. The UK does not raise funds in this way, although we do have a forward looking 20 year MoU with UNITAID to give greater predictability and visibility of future support as a positive signal to markets. Within that overarching MoU, we agree financial contributions in a series of three or four year agreements with UNITAID, and full disbursement is dependent on performance. / UNITAID top 5 donors in 2013 / Donor 2013 contribution (‘000 US dollars) % of total / France 143, 000 52 / UK 87,171 32 / Norway 21,368 8 / Gates Foundation 10,000 4 / Korea 4,000 1 / The UK MAR assessed UNITAID as providing good value for money, recognising that it faced several challenges; and it set out our reform priorities as follows: / Driving up operational efficiency; / Improvements in UNITAID’s Strategy and Business Model; including a coherent funding strategy, a credible and functional policy on transition of grants away from UNITAID funding and more predictable and reliable donor support; / Development of internal systems; improved arrangements for appraising and prioritising proposals that offer the greatest value for money; / Stronger leadership and management capacity delivering an efficient and well-led Secretariat. / The 2013 UK MAR up-date concluded the following: / Overall, progress has been reasonable against important components such as Financial and Resource Management – including risk management – and there has been some progress on Cost and Value Consciousness. Systems for financial accountability have improved. Overall systems and policies have improved, though the Board itself can still be inconsistent, for example in the way it reaches funding decisions. The recently approved Strategy 2013-2016 is an improvement over the previous Strategy 2010-2012. The independent Five Year Evaluation is positive about many aspects of UNITAID’s performance, while noting that challenges remain. / Positive findings of the MAR include: / UNITAID’s focus on malaria and contribution to reproductive, maternal and newborn health (RMNH) means that it has a good fit with DFID’s strategic priorities; / Price reductions have been significant, and should lead to a sustainable benefit for countries, donors and international agencies; / The views of partners and intended beneficiaries are built in to UNITAID’s decision making structures; and / Financial management has improved with the recruitment of high quality senior personnel. / Several weaknesses were also identified: / There is little evidence that management actively manages for results; / The Board has applied value for money criteria unevenly in funding decisions; and / UNITAID’s publication of documentation is patchy and often very slow. / DFID’s reform priorities for the MAR 2013 update were: / Improvements in UNITAID’s Strategy and Business Model, a coherent funding strategy, stronger leadership and management capacity delivering an efficient and well-led Secretariat – assessed under strategic and performance management; / A credible and functional policy on transition of grants away from UNITAID funding and more predictable and reliable donor support – assessed under financial and resource management; and / Development of internal systems, improved arrangements for appraising and prioritising proposals that offer the greatest value for money – assessed under cost and value consciousness and transparency and accountability. / DFID oversight of UNITAID and formal project management is led by the Global Funds Department, with close collaboration with the Human Development Department, who provide the policy lead to the three diseases.

Section A: Detailed Output Scoring

Output 1: The Secretariat monitors achievements of UNITAID’s short to medium term funding on the market for products to treat, diagnose and prevent HIV/AIDS, TB and Malaria
Output 1 score: B / The output is not entirely clear, although UNITAID has provided little evidence of the monitoring of achievements. UNITAID has conducted some relevant activities, including dissemination events. However, there is little evidence of practical outcomes from the market forum, or impact of monitoring / dissemination as a whole; we also need further information on the functioning of the Market Dynamics Advisory Group (MDAG)
Progress against expected results: / Complete, reliable, and up-to-date information on trends in the markets for products to treat, diagnose and prevent HIV, TB and malaria is needed to effectively monitor the achievements of UNITAID’s funding on the markets for these products. This market information allows UNIATID to prioritize and plan how to best spend its monies on the type of grants that will help shape these markets and improve the health of those living with disease in low income countries. UNITAID’s Market Dynamics team provides this intelligence through landscape analyses and market fora that identify key products that are coming to market or are in the product pipeline. The markets for these products are constantly changing, and capturing these changes is critical for UNITAID to be able to make timely, strategic interventions to shift market conditions. The frequency at which these reports are updated reflects this need to keep up to date with the latest developments. The table (below) shows the reports available now on www.unitaid.org by disease area. / Two market fora were held in 2013. The first, co-sponsored with USAID, focused on TB products and was held in July. The second targeting malaria products was held in September in conjunction with the Bill and Melinda Gates Foundation (BMGF). These fora provided an opportunity for academics, industry and global health donors to come together and discuss innovative solutions to address age old problems in HIV, TB and malaria. Many of these solutions will eventually be implemented through UNITAID grants. / Table of UNITAID landscape reports produced to the end of 2013. / Disease Area Report type Date / Malaria / Malaria vector control commodities technology and market landscape 1st edition December 2013 / Malaria diagnostic technology landscape Semi-annual update November 2013 / Malaria Diagnostics Market Landscape Diagnostics landscape October 2012 / Malaria Diagnostics Technologies Landscape Semi-annual update December 2012 / HIV/AIDS / HIV/AIDs diagnostic technology landscape semi-annual update November 2013 / Hepatitis C medicines and diagnostics in the context of HIV/HCV co-infection: A scoping report October 2013 / HIV preventives technology landscape 1st edition August 2013 / HIV/AIDS diagnostics technology landscape 3rd edition June 2013 / HIV/AIDS diagnostic technology landscape 2nd edition June 2012 / HIV/AIDS diagnostic technology landscape Semi-annual update October 2012 / HIV/AIDS medicines and pipeline overview Medicines landscape November 2012 / Tuberculosis / Tuberculosis medicines technology and market landscape 1st edition September 2013 / Tuberculosis diagnostics technology and market landscape 2nd edition July 2013 / Tuberculosis diagnostic technology & market landscape First report July 2012 / Tuberculosis medicines technology landscape Medicines landscape August 2012 / Tuberculosis diagnostic technology & market landscape Semi-annual update December 2012 / HIV/ TB/ malaria / HIV, TB and malaria medicines landscape Medicines landscape report January 2012 / Malaria-ACT Forecasting / Policy Brief- ACT Forecasting May 2012 / ACT Forecasting Quarterly update (Q1 2012) May 2012 / ACT Forecasting Quarterly update (Q2 2012) July 2012 / ACT Forecasting Quarterly update (Q3 2012) December 2012 / Recommendations: Focus more on application of market data and concrete actions / next steps arising from the market forum. Provide regular up-dates on the strategic direction and UNITAID’s constructive inputs into the MDAG. / Impact Weighting (%):8 / Revised since last Annual Review? N / Risk: Low / Revised since last Annual Review? N

Output 2: Generate long term price reductions on medicines and diagnostics
Output 2 score: A++
Progress against expected results: UNITAID have set out a comprehensive and convincing data set recording very significant price reductions in the commodity areas they have most intensively engaged in. This also sets out clearly their comparative advantage and added value on 2nd line ART and TB treatment, paediatric ART treatment, ACTs and TB diagnostics. / HIV and ART / There have been positive progress in the 2nd Line Anti Retroviral Therapy (ART) market: / Table 1: Percentage change in price for selected WHO recommended 2nd line ART / purchased with UNITAID funds / Generic 2nd line ART % change in 2011 - 2012 % change across all years / ABC 300 mg na -48% / ATV/r (300 / 100 mg) -10% na / LPV/r (200/50 mg) Tab (HS) -17% -33% / TDF 300 mg -24% -73% / TDF / 3TC (300 / 300 mg) -35% -61% / TDF / FTC 300/200mg -25% -73% / TDF/3TC (300/300 mg) & LPV/r (200/50 mg) -20% -40% / TDF/FTC (300/200 mg) & LPV/r (200/50 mg) -19% -49% / Price reductions of 20% were made against the 2011 purchase price for leading second line ART formulations (TDF/3TC (300 mg/300 mg) & LPV/r (200mg/50 mg). 35% price reduction in TDF/3TC (300/300mg), 24% price reduction for TDF (300mg), and 25% for TDF/FTC 300/200mg; / Cumulatively, price reductions of 40% were achieved for (TDF/3TC (300 mg/300 mg) & LPV/r (200mg/50 mg), 61% on TDF/3TC (300/300mg), and 73% for TDF/FTC 300/200mg against the 2008 purchase price; / ATV/r fixed dose combination introduced to 2nd line ART project in 2011 was purchased by 11 countries in 2012 at a reduced price; / The 2012 selection process saw an increase in the number of manufacturers making high quality ART available with six new SRA approved manufacturers to make UNITAID funded ART. / Price decreases that continue to be realised on 2nd Line ART are consistent with the number of generic manufacturers that continue to make these products, thereby generating healthy competition within this market: / The market for paediatric ART has also seen improvements over the past year, including: / Key products achieving a 6-9% price reduction (6% for AZT/3TC (300 mg/150mg) and 9% for LPV/r (80mg/20 mg), compared with purchase prices in 2011. The prices of other key products remained relatively constant for the reporting period; / Cumulatively, price reductions of 13% were achieved for AZT/3TC (300/150) and AZT/3TC (60/30mg), 17% for AZT/3TC/NVP (300/150/200mg) and nearly a quarter percent reduction for LPV/r (80/20.g) against the 2008 purchase price; / 16 new SRA approvals for ART formulations used in the UNITAID financed programme; / The market for early infant diagnostics (EID) saw the entry of a second supplier for DBS collection bundles. / Table 2: Percentage change in price for selected WHO recommended paediatric ARVs / purchased with UNITAID funds / Paediatric ART % change in 2011 - 2012 % change across all years / ABC/3TC (60/30 mg)* 7% -9% / AZT/3TC 300/150 mg -6% -13% / AZT/3TC (60/30 mg)* -1% -13% / AZT/3TC/NVP 60/30/50mg -1% -4% / AZT/3TC/NVP (300/150/200 mg) -7% -17% / LPV/r (80/20 mg/ml) (brand price only) -9% -25% / NVP (50 mg) -5% na / *In 2012, AZT/3TC (60/30 mg) and ABC/3TC (60/30 mg) include prices for both dispersible and non-dispersible formulations. / As a result of UNITAID funding, the Clinton Health Access Initiative (CHAI) has been working with countries to order fixed dose combinations that facilitate improved adherence. As a result, there has been a percentage increase in IATT optimal products that countries are ordering from 52% in 2010 to 82% in 2012. / Malaria and Artemisinin Combination Therapy (ACT): / UNITAID's interventions in the market for effective malaria medicines have contributed to considerable change since 2006 when there was only one manufacturer of an ACT co-blistered formulation. UNITAID currently supports two projects related to the market challenge of quickly replacing ineffective anti-malarial medicines with ACTs, the Affordable Medicines for Malaria facility (AMFm) - implemented by the Global Fund for AIDS, TB and Malaria (GFATM); and the ‘Assure’ Artemisinin supply project (A2S2, with i+ Solutions). Price tracking of the AMFm phase 1 by HAI in September 2012 showed that end users were paying less for anti-malarial treatments relative to the start of the AMFm grant. The per cent price reductions vary by country, with five of the participating countries paying between 50 and 82% less than before the subsidy: to the private sector suppliers of ACTs. The purchase prices for key products bought in non-government regulated outlets are the same or slightly lower than those in the government regulated outlets in countries where these comparisons have been made. This indicates that the AMFm mechanism is having the desired effect on the private sector markets in these countries by keeping the prices low in the places where people will purchase the medicines. UNITAID’s intervention was catalytic and with additional UK funding in 2014, AMFm will be sustained (and possibly expanded) as a private sector co-payment mechanism within GFATM. / Tuberculosis and anti-TB medicines: / UNITAID has achieved 40% price reduction on diagnostic cartridges from $17 to less than $10 for use in the GeneXpert machine. This price is available not only to countries directly supported by the UNITAID funded grants (21 countries) but to all 145 eligible countries and public sector purchases in low and middle income countries. In the second line anti-TB medicines market, an unprecedented 19 manufacturers of second and third line anti-TB medicines made bids to GDF to supply UNITAID funded grants. A total of 54 medicine/manufacturers were eligible for supply in the GDF 2012 catalogue. This type of activity has led to price reductions in Cycloserine with the result that the high range MDR-TB treatment regimen costs 16% less than it did in 2011. Prices of medicines for both second line and paediatric TB treatments remain stable with no changes. / Recommendations: Additional focus on second line TB and paediatric TB treatment. / Impact Weighting (%): 12 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 3: Improve quality of medicines, diagnostics and related products
Output 3 score: A
Progress against expected results: An impressive range of priority products pre-qualified (which indicates that these products have achieved a standard quality level) but little in terms of linking this to evidence on improved quality of the products used at country level. / Additional 17 UNITAID priority products prequalified between January and June 2013 which leads to a cumulative result of 118 priority products prequalified since January 2009. / Product type From 2009 to 2012 Jan-Jun 2013 Total / HIV Medicines 49 4 53 / Malaria Medicines 16 3 19 / TB Medicines 36 10 46 / Total 101 17 118 / Additional 5 UNITAID priority diagnostic tests prequalified between January and June 2013 which leads to a cumulative result of 24 priority products prequalified since January 2009. / Test From 2009 to 2012 Jan-Jun 2013 Total / HIV RDTs 6 2 8 / Malaria RDTs 2 - 2 / CD4 Technologies 3 - 3 / HIV Virological Technologies 8 2 10 / Male Circumcision Device - 1 1 / Total 19 5 24 / Recommendations: Systematic analysis on the relationship between the improved range of products and improved quality at country level needed (either directly or drawing on the analysis of others) / Impact Weighting (%): 12 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 4: Shorten lead time for the delivery of medicines, diagnostics and related products to countries
Output 4 score: A
Progress against expected results: Clear evidence of progress with malaria and a mixed picture with HIV and TB. It could be argued that UNITAID should have predicted and stimulated global action on increased demand for 2nd line TB treatments – but the problem has been identified and action is proposed. / HIV / ESTHER and UNITAID are working together on ‘ESTHERAID’, a grant that is building capacity in five Francophone West African countries (Benin, Burkina Faso, Central African Republic, Cameroon and Mali) to manage the supply of ART and diagnostic tests for HIV/AIDs. This includes identifying stock outs and shortages in Central and Regional medical stores and at treatment centres throughout the countries. UNITAID is an active participant in the Coordinated Procurement Planning Initiative that has monitors the status of stocks of ART and other essential medicines for HIV/AIDS patients. In 2012, 11 countries reported stock outs of ART for various reasons such as delays due to political strife, procurement delays through the GFATM VPP, budget shortfalls and lengthy lead times from manufactures. These challenges were addressed through emergency procurements and early order placement. / Tuberculosis / In 2012, 67 country programmes ordered from the strategic rotating stockpile (SRS) that is funded by UNITAID for MDR-TB medicines. An additional 17 countries placed and received emergency orders with the median lead time for delivery of treatments being 55 days, an increase over the 31 days reported to UNITAID by GDF in 2011. The increase in the lead times was due to the increase in the demand for 2nd line TB treatments without a commensurate increase in supply. In addition, case detection of MDR-TB is expected to increase in the near future, particularly because UNITAID is funding grants that will increase detection of MDR-TB (expand MDR-TB diagnostics (FIND, GDF, WHO) and TB GeneXpert (GDF)). This has led to concerns that the 5,800 treatments in the SRS are no longer sufficient. To meet the increased demand for 2nd line MDR TB medicines, a proposal to increase the capacity of the stockpile is being reviewed by UNITAID’s Board for decision in December 2013. / Malaria / The ACT scale up project with UNICEF and GFATM concluded at the end of 2012. This grant has reported manufacturer lead times for deliveries to countries in 2012. CIPLA reported the lowest lead time of 34 days while Novartis Pharma Services reported 164 days. The grant did not report any stock shortages of ACTs related to countries benefiting from these grants. / Recommendations: UNITAID to demonstrate better ability to predict areas of increased demand and potential stock outs of priority commodities moving forward. / Impact Weighting (%): 12 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 5: Promote the development of user friendly drugs appropriate for use in developing countries
Output 5 score: A
Sound progress against expected results: Clear evidence of on-going relevant and important work in this area across the three diseases with results being demonstrated as different projects, supported by UNITAID, deliver. / HIV/AIDS / UNITAID has made significant progress in the area of new child adapted ART products through its project with Drugs for Neglected Diseases Initiative (DNDi) in 2013. Agreement was reached with CIPLA to start manufacturing these new medicines. Bioavailability and bio-equivalence studies of the two optimal PI-based ARV FDCs (ABC/3TC/LPV/r and AZT/3TC/LPV/r ) are currently underway. / Most of the achievements in creating a market for child adapted fixed dose combinations of paediatric ART were made in 2008 and 2009 with the introduction of generic manufacturers. In 2012, the work of CHAI and UNITAID has been to ensure the continued availability and accessibility of these fixed dose combinations (FDCs) . The supplier selection process in 2012 saw 15 new SRA-approvals for paediatric formulations being used in the grant. For the 2nd Line ART project, there were five newly SRA-approved suppliers of formulations for much needed FDCs in 2012. The 2nd line ART project has successfully transitioned largely to the GFATM and PEPFAR. The majority of 40 countries supported by the paediatric ART project have also successfully transitioned with the exception of three countries (Malawi, Mozambique and Uganda): these countries are interim applicants to GFATM’s New Funding Model. / TB / UNITAID is working with TB Alliance to develop correctly dosed and quality-assured child-friendly first-line TB treatment that adheres to the 2010 WHO recommendations. The project has made significant progress with the pharmaceutical company Svizera on board to develop and market fixed dose paediatric TB formulations in appropriate dosages. This product is expected to be available in three years. / In December 2010, WHO published the "Rapid Advice" guidelines which recommend higher doses for paediatric treatment than has been historically used: in 2012, the existing formulations and FDCs still do not accommodate these recommendations as there is no pre-qualified drug manufacturer manufacturing these medicines.UNITAID is working with TB Alliance to develop correctly dosed and quality-assured child-friendly first-line TB treatment that adheres to the 2010 WHO recommendations. The project has made significant progress with the pharmaceutical company Svizera on board to develop and market fixed dose paediatric TB formulations in appropriate dosages. This product is expected to be available in three years. / In addition to the development of new products, several key paediatric products are available today due to UNITAID funding of the GDF paediatric TB project. One product, Isoniazid (H100 bulk) was prequalified in 2010 and the addition of others in 2011 brings the number of prequalified paediatric products to 13 products consisting of both blister and bulk packaging. More needs to be done to ensure that manufacturers now start to make paediatric medicines that meet the revised WHO guidelines. A consortium including the WHO Essential Medicines Programme (WHO EMP), GDF and WHO Prequalification are preparing a plan for supporting paediatric treatment that takes into account that this is a nascent market (new formulations) and there is a need for on-going treatment while new formulations are being developed. UNITAID funds the Prequalification of Medicines and Diagnostics Programme in WHO EMP thereby ensuring that new products enterin the market and supported by UNITAID grants will meet the pre-qualification standards for quality assurance. / Malaria / UNITAID is working with Medicines for Malaria Venture(MMV) to accelerate the adoption and market uptake of injectable artesunate that is more efficacious than quinine in reducing mortality in children with severe malaria. Quantification forecasts are already underway in target countries and procurement plan has been approved. First delivery of injectable artesunate for six countries is expected in Quarter1 of2014. In parallel, UNITAID and MMV are also working on the regulatory approval of intra-rectal artesunate for pre-referral treatment of children with malaria. Currently there is no WHO prequalified or SRA approved product on the market. WHO PQ has provided a bioequivalence comparator product and MMV has published a request for expression of interest from manufacturers to submit product dossier / The unavailability of an eligible Dihydroartemisinin-Piperaquine (DHA-PPQ) had prevented the launch of AMFm Phase 1 in Cambodia. The launch of AMFm in Cambodia was finally realized in Quarter 1 2012, because of the work of the AMFm project team to redesign the DHA-PPQ packaging of Sigma-Tau to meet Cambodian and AMFm requirements. The supply of this product to Cambodia is a milestone in the treatment of uncomplicated malaria in a geographic region of the world which has demonstrated resistance to Artemisinin. These efforts mean that effective malaria treatments can, at last, be provided through the private sector at reduced prices to a population in great need. / In addition, both Ipca and Guilin achieved WHO Prequalification for Artesunate/Amodiaquine FDC tablets (ASAQ FDC) during 2012, increasing the number of quality-assured sources of ASAQ FDC from one to three. / Recommendations: None / Impact Weighting (%): 12 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 6: Monitor UNITAID's compliance with its constitutional requirement to allocate the majority of its funding to implementing partners for projects
Output 6 score: A
Progress against expected results: Complied. Although this is a ‘light output’ in the sense that the ‘majority’ of funding is not clear / 2011: 89% / 2012: 90% / 2013 (Projected): 84% / In addition 95% of funds allocated to Low income countries, 3% allocated to Lower Middle income countries and 2 % to Upper middle income countries. Note: Income groupings for countries are as defined by the World Bank and updated on 01 July of each calendar year. / Recommendations: To develop a more robust organisational / secretariat performance indicator for the new log-frame / Impact Weighting (%): 12 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 7: Optimise UNITAID Secretariat performance
Output 7 score: B
Progress against expected results: Results indicate a sub-optimal performance and the reasons given do not indicate robust management of the organisation and the taking of tough decisions to deliver optimal value for money. We would contest the assertion that on resource mobilisation. / The table below presents the results of several indicators that measure Secretariat performance. / Measure 2011 2012 2013 / (projected) 2014 (projected) / 1. % of Secretariat costs relative to disbursements to implementing partners 10% 10% 16% 11% / 2. Value of active portfolio under management by FTE (all units) $25.5m $19.5m $18.6m $20m / 3. Number of FTE (all units) per grant 4 5 3 2.90 / While indicator 1 is popular for measuring the performance of grant making organisations, it has several limitations, including: / Disbursement levels are linked to the size of the active portfolio under management assuming all grants perform reasonably well. The size of the portfolio is impacted by the level of funding for new proposals that was available one or two years back and on the general size of the grants themselves. It is not linked to the current performance of the Secretariat. This is evident in 2013 as the portfolio was entering a new phase with many grants coming to an end and others just starting. / UNITAID is a small organization (60 staff). The Operations team manages grants and is supported by all other units in the Secretariat. While about 55% of the Secretariat costs could be directly attributed to the support of grant development and management, the balance or 45% of its costs is independent of the size or number or age of grants, let alone disbursement levels: / Staff costs represent 63% of the budget and the costs of being hosted at WHO including under-market rental rates make up 11% of expenses. / While grant making is naturally the core business of UNITAID, an increasing level of activities surrounding grant making has taken place to enhance its quality and is somewhat independent of the number of grants, let alone their value or the value of the disbursements made to grantees: The Market Dynamics outputs such as the landscape reports have substantially increased in the last two years and provide value to the entire global health community, well beyond UNITAID’s grants. UNITAID wants to enhance transparency. Investments in data management and reporting are critical and have only started in 2012. / Given the uncertainty in donor funding, UNITAID had to devote an increased proportion of its resource to seeking new donors in 2013. / The two other indicators show that the Secretariat has kept its staffing under control. Grant management workload is dependent more on the number of grants than on the value of those grants. The third indicator clearly shows that the number of grants has increased much faster than the increase in staffing. In spite of the quick changes in the portfolio make up, the value of grants under management by FTE has remained stable. / Recommendations: That UNITAID focus on this issue in 2014 and introduces a culture of delivering ‘more with less’, as has been the case over the last 4 years with the Governments of France and the UK. This will be properly reflected in the KPIs and revised log-frame, and will help shape the organisational review proposed for 1st quarter 2014. A revised and up-dated resource mobilisation strategy (that meets the Boards approval) is needed as a matter of priority. / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 8: Optimise UNITAID financial accountability
Output 8 score: A
Progress against expected results: Good progress, including the work on the risk framework. / The table below shows the implementation process of the UNITAID budget: / 2011 2012 2013 (projected) / Budget implementation rate 56% 89% 96% / Implementing partners budget variance 30% 25% Not yet available / The improved budget implementation rate is a reflection of improved planning mechanisms both at grant level and at Secretariat level. Budget management is one of the areas assessed semi-annually for each grant. While it is clear that a number of grantees plan and budget better than others, the general level of budget implementation is relatively good. Budget management is taken seriously by grantees. / Grantees capacity to detect and handle cases of fraud is systematically assessed before a grant is signed. Grantees have to present a plan inthis area and bear the responsibility to report any suspected or confirmed fraud or loss incident immediately. They also bear the financial responsibility for the result of any fraudulent activity. Reports of loss have been received. All those losses occurred once the products had been handled by the grantee. The level of transparency from non-UN grantees and their commitment to disclose and handle such cases is quite strong. / UNITAID is bound to comply with all WHO financial and administrative regulations. This compliance is tested during the annual external audit organized by WHO. External audits have been conducted annually since 2009 and have not given rise to any material finding. Only one recommendation remains open and its closure depends on Board rather than Secretariat action. The recent approvals of a Risk Policy by the Board or of an audit guideline by the Finance and Accountability Committee show the level of importance set on risk and compliance within the Secretariat. An internal audit plan is being implemented. Reports so far do not show any control issue although efficiency gains are sometimes possible. An updated analysis of the risk of fraud has also just been performed and will be integrated into an updated work plan. / Recommendations: To provide UK with the up-dated analysis of risk and the up-dated work-plan for review when completed. To provide clearer information and evidence on any mis-use of funds at grant level and actions taken. Attention to partner budgets will continue to be needed. There are very few partners with experience of implementing novel, market based projects, and as the numbers of partners sought increases, their inexperience will continue to be challenging. / Impact Weighting (%): 5 / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N

Output 9: Track treatments, diagnostics and related products delivered, and estimated patients treated, by UNITAID funded projects by beneficiary country over time.
Output 9 score: A
Progress against expected results: Strong evidence of improvements. Needs secondary analysis on relative contribution / attribution of UNITAID. / Paediatric ART, from January to June 2013: An additional 16,769 new children were put on HIV treatment in 4 countries[1], which leads to a cumulative result of 439,676 new children on treatment as of June 2013 in 35 countries. / Country Cumulative as of Dec 2012 Jan - June 2013 Total / MALAWI 35,466 2,148 59,396 / MOZAMBIQUE 25,800 7,053 58,653 / SWAZILAND 7,431 212 15,074 / UGANDA 33,729 7,356 74,814 / Grand total 16,769 / ACT treatments from January to June 2013: An additional 61,287,574 ACT treatments were delivered, which leads to a cumulative result of 351,431,864 treatments delivered as of June 2013. / Country Cumulative as of Dec 2012 Jan - June 2013 Total / CAMBODIA 251,229 236,243 487,472 / GHANA 45,104,816 8,158,923 53,263,739 / KENYA 46,257,838 8,327,146 54,584,984 / MADAGASCAR 2,838,472 1,269,955 4,108,427 / NIGER 4,206,870 395,255 4,602,125 / NIGERIA 111,588,360 26,427,637 138,015,997 / TANZANIA, UNITED REPUBLIC OF 34,859,525 6,742,050 41,601,575 / UGANDA 45,037,180 9,730,365 54,767,545 / Grand Total 290,144,290 61,287,574 351,431,864 / Paediatric TB treatments from January to June 2013: An additional 18,070 curative treatments and 8,937 prophylaxis treatments were delivered in 6 countries, which leads to a cumulative result of 481,574 curative treatments delivered and 690,919 prophylaxis treatments delivered as of June 2013 in 57 countries. / Country Paediatric TB (curative) patient treatments delivered Paediatric TB (prophylaxis) patient treatments delivered / Cumulative as of Dec 2012 Jan-June 2013 Total Cumulative as of Dec 2012 Jan-June 2013 Total / BANGLADESH 18,942 4,799 23,741 7,667 - 7,667 / CAMBODIA 11,792 10,262 22,054 7,917 - 7,917 / KOREA, REPUBLIC OF 16,304 350 16,654 - 4,393 4,393 / MACEDONIA, FORMER YUGOSLAV REPUBLIC OF 174 39 213 875 171 1,046 / MAURITANIA 301 157 458 180 - 180 / TANZANIA, UNITED REPUBLIC OF 14,586 2,463 17,049 9,508 4,373 13,881 / Grand Total 18,070 8,937 / Case detection of MDR TB from January to June 2013: An additional 16,852 cases were detected in 25 countries which leads to a cumulative result of 90,782 cases detected as of June 2013. / Country Cumulative as of Dec 2012 Jan - June 2013 Total / AZERBAIJAN 631 267 1,529 / BANGLADESH 247 149 643 / BELARUS 192 532 916 / CAMEROON 217 89 523 / CÔTE D'IVOIRE 235 182 652 / DJIBOUTI 58 56 172 / ETHIOPIA 1,127 408 2,662 / GEORGIA 1,458 273 3,189 / HAITI 172 56 400 / INDIA 20,215 9,959 50,389 / INDONESIA 0 0 0 / KAZAKHSTAN 0 0 0 / KENYA 228 76 532 / KYRGYZSTAN 1,766 602 4,134 / LESOTHO 583 78 1,244 / MOLDOVA, REPUBLIC OF 1,304 311 2,919 / MOZAMBIQUE 29 137 195 / MYANMAR 1,440 877 3,757 / PERU 0 549 549 / RWANDA 16 23 55 / SENEGAL 29 32 90 / SWAZILAND 656 153 1,465 / TAJIKISTAN 805 616 2,226 / TANZANIA, UNITED REPUBLIC OF 76 38 190 / UGANDA 343 87 773 / UZBEKISTAN 4,894 1,036 10,824 / VIET NAM 244 266 754 / Grand Total 36,965 16,852 90,782 / Recommendations: To be included in KPI framework and in revised DFID log-frame – with baseline, milestones and a target. Secondary analysis to be performed on attribution / contribution issues. / Impact Weighting (%): 11% / Revised since last Annual Review? N / Risk: Medium / Revised since last Annual Review? N
[1] Zimbabwe will report 2013 annual results only (semi-annual results not available)

## Section B: Results and Value for Money.

1. Progress and results
UNITAID currently has investments in 54 countries through its 20 active grants. / Achievements, challenges and main actions taken in the management of these grants are recorded in the tables displayed below by Strategic Objective, based on the Strategy 2013-2016. / STRATEGIC OBJECTIVE 1: INCREASE ACCESS TO SIMPLE, POC DIAGNOSTICS FOR HIV/AIDS, TB AND MALARIA. / GRANT ACHIEVEMENTS CHALLENGES ACTIONS TAKEN / HIV 3 grants / Accelerating access to Innovative POC HIV diagnostics (Phase 1) (CHAI/UNICEF) First deliveries of HIV POC diagnostics to Kenya, Malawi and Mozambique Longer timeline for new POC CD4 test to enter the Market / New WHO guidelines required introduction of VL to the project and scale –down of CD4 diagnostics Volume cap placed on procurement of existing CD4 diagnostic (PIMA) to leave room for competing projects / Phase 2 proposal submitted to PRC including changes stemming from new WHO guidelines / Implementation of CD4 and VL testing in decentralized, resource-limited settings (MSF) Early research findings already being used to set national policy e.g. decentralization of lab-based diagnostics for VL testing in Malawi MoU with South Africa pending / Room for improved synergy between CHAI/UNICEF project MSF is working with South Africa to finalize MoU / More frequent meetings between diagnostic grantees planned for 2014 / Open polyvalent platforms (OPP) for sustainable and quality access to VL in resource limited settings (OPP-ERA) (FEI) Launch of competitive tender to select multiple source products for OPP. Forecasting of demand for OPP is difficult FEI is working with target countries to improve forecasting OPP VL test demand / TB 2 grants / Multi Drug Resistant TB Diagnostics (EXPAND) 86,687 liquid cultures, 8,111 liquid culture DSTs, 71,839 line probe assays and 16,034 Xpert tests were carried out in the Project countries.[2] Increased diagnostic testing is increasing MDR-TB treatment demand Transition plan to be completed by May 2014 / Scaling up access to contemporary TB diagnostics (GeneXpert) Xpert roll out has resulted in 3 million cartridges being ordered by eligible countries. Prices of Xpert are unlikely to come down unless there is a fast-follower TB test on the market. Ongoing discussion with GDF on how to facilitate the introduction of new TB diagnostics in the market / Malaria 2 grants / Sustainable Global and National Quality Control for Malaria Rapid Diagnostics Tests (FIND, WHO) Projects initiated and first disbursements made No significant challenges / Creating a Private Sector Market for Quality Assured RDTs in Malaria-Endemic Countries (PSI, WHO) Projects initiated and first disbursements made Pending finalization and approval of the procurement plans PSI and UNITAID are finalizing the procurement plan / Cross cutting 1 grant / Quality Assurance of Diagnostics (WHO) 5 new UNITAID priority products prequalified in the first half of 2013 Delay in launching the Expert Review Panel for Diagnostics (EPRD) / Quality of reporting from PQP medicines Key stakeholders meeting to finalize EPRD held in October. / New agreements will have standard reporting template finalized / STRATEGIC OBJECTIVE 2: INCREASE ACCESS TO AFFORDABLE, PAEDIATRIC MEDICINES TO TREAT HIV/AIDS, TB AND MALARIA. / GRANT ACHIEVEMENTS CHALLENGES ACTIONS TAKEN / HIV 2 grants / Paediatric ARV Program (CHAI) CHAI agreement with Abbott Molecular Diagnostics of up to 50% cost reduction of lab-based EID reagents/consumables. Transition funding needed for Malawi, Mozambique, and Uganda for the CHAI Paediatric ARV project UNITAID and CHAI are working with GFATM to include paediatric treatments for these countries in 2015 plans / Market entry of an improved solid protease inhibitor-based first-line ARV combination therapy for infants and young children with HIV/AIDS (DNDi) Project initiated Poor results from Cipla’s Phase I comparative bioavailability study of LPV/r granules Cipla has now developed several improved formulations for retesting / TB 2 grants / STEP TB (TB alliance, WHO) Major milestone met in Oct 2013 to sign on MoU with the first prospective manufacturer No significant challenges / Paediatric TB Program (GDF) Deliveries have been made to countries requesting support Countries lack much need new paediatric TB formulations GDF to provide a new proposal to UNITAID to support new paediatric formulations being developed by TB Alliance / Malaria 1 grant / Improving severe malaria outcome (MMV) Grant agreement signed on 5 June 2013 Pending finalization and approval of the procurement plans UNITAID and MMV to finalize the procurement plan / Cross cutting 1 grant / Pre-qualification of Medicines (WHO): SO2,3,4 & 5 PQ of 109 finished pharmaceutical products and 39 active pharmaceutical ingredients (cumulative) / A new submitted for a decision by EB19 on new 3-year funding Diversified and additional funding sources for PQP still lacking Assessment of new funding model options for PQ / Special project 1 grant / Medicines Patent Pool (MPP): SO2, SO3 See SO3 / STRATEGIC OBJECTIVE 3: INCREASE ACCESS TO EMERGING MEDICINES AND/OR REGIMENS AS WELL AS NEW FORMULATIONS, DOSAGE FORMS, OR STRENGTHS OF EXISTING MEDICINES THAT WILL IMPROVE THE TREATMENT OF HIV/AIDS AND CO-INFECTIONS SUCH AS VIRAL HEPATITIS. / GRANT ACHIEVEMENTS CHALLENGES ACTIONS TAKEN / HIV 1 grant / Easing and safeguarding the availability of ARV treatment (ESTHERAID) Standardized patient and cohort monitoring systems work in five countries Long delay in development of ART stock management software Decision to use existing software, adding specific ARV management modules in Benin and Burkina Faso / Cross cutting 2 grants / Pre-qualification of Medicines (SO2,3,4,5) See SO2 / Preventing Patent Barriers (Lawyers collective) Grant has started No significant challenge / Special project 1 grant / Medicines Patent Pool (MPP): SO2, SO3 MPP and ViiV Healthcare launched a license agreement on paediatric abacavir. / Three additional sub-licenses with Shasun Pharma Solutions, Shilpa Medicare and Aurobindo. Delay in recruiting three business development specialists (for out-licensing). Positions are being advertised more widely and recruitment status update will be available in early 2014. / STRATEGIC OBJECTIVE 4: Increase access to artemisinin-based combination therapies (ACTs) and emerging medicines, which, in combination with appropriate diagnostic testing, will improve the treatment of malaria. / GRANT ACHIEVEMENTS CHALLENGES ACTIONS TAKEN / Malaria 1 grant / Affordable Medicines for Malaria (AMFm) Transfer of Round 6 undisbursed (US$ 10.9m) funds to AMFm Reconciliation of Round 6 undisbursed funds between GFATM and UNITAID Agreement was reached in Q2 2013 / Cross cutting 1 grant / Pre-qualification of Medicines (WHO): SO2,3,4 & 5 See SO2 / STRATEGIC OBJECTIVE 5: Secure supply of second-line tuberculosis medicines, and increase access to emerging medicines and regimens that will improve treatment of both drug-sensitive and MDR TB. / GRANT ACHIEVEMENTS CHALLENGES ACTIONS TAKEN / TB 2 grants / Multi Drug Resistant Tuberculosis (MDR-TB) Scale up All requested treatments have been delivered Demand for MDR-TB treatments has increased Transition to GFATM at the end of 2013 / MDR-TB Accelerating and Access Initiative – Strategic Rotating Stockpile (SRS) Median lead time achieved in 2013 is 63 days Finding additional funding for the SRS to sustain supply of MDR-TB treatments Cost extension of 18 months requested for transition to the GF / Cross cutting 1 grant / Pre-qualification of Medicines (WHO): SO2,3,4 & 5 See SO2 / STRATEGIC OBJECTIVE 6: Increase access to products for the prevention of HIV, TB, and malaria, notably to improve the / availability of devices for male circumcision and of microbicides, once they are approved; and to increase access to vector control tools to prevent malaria transmission. / There are no active grants that relate solely to SO6.
1.1 Has the log-frame been updated since last review? N / 1.2 Overall Output Score: / To be added automatically
1.3 Summary of overall progress / UNITAID’s Operations team continues to incorporate lessons learnt from grant implementation into its work. Grant information is being presented in a new way, by strategic objective area, in order to facilitate monitoring of UNITAID’s strategy 2013-2016. Operations is highlighting the improvements it is making in grant management by improving its grant and data management systems and building the capacity of its staff. Building strong partnerships and improving engagement with countries have been priorities in 2013 and will continue to be a focus of the team’s work in 2014. / UNITAID has also improved how it captures, stores and analyses data from the grants that it supports. UNIPRO is the Portfolio Management system for UNITAID and now holds data on all UNITAID grants. UNIPRO is now linked to grant financial data to provide easy access for Portfolio managers. Using UNIPRO facilitates data sharing, data visualization displays as well as analyses and reporting. / Additional improvements in 2013 include the following: / An online reporting module for Implementers to report grant updates directly into UNIPRO has been developed. Starting in 2014, implementers will submit their semi-annual and annual progress reports into UNIPRO, making reporting easier and more standard. / A Grant Management Dashboard module, linked to notifications of upcoming grant milestones has been integrated into UNIPRO to help manage grants more efficiently. / Data on grants is now routinely reported in a series of interactive data visualizations presented on the UNITAID website. / Comprehensive guidelines are under development for assessing the capacity of new implementers to roll out grants quickly, especially in low income countries. / Performance-based disbursement enhanced by introducing a more systematic review of progress reports and disbursement request (including a new disbursement template for portfolio teams); and / Mid-term and end of project evaluations process are under review which will result in an updated guideline in early 2014.
1.4 Key challenges / Operations is changing how it engages with countries benefiting from UNITAID grants. This change provides a chance for UNITAID to actively engage with partners (implementer and other stakeholders) at the country level for the purposes of, inter alia, results verification, planning for effective transition and sustainability, partnership building, gathering lessons learned, promoting increased UNITAID visibility, and generating ideas for new investment opportunities. / A number of country visits have already been completed in 2013. Based on lessons learnt from these visits, a comprehensive framework on country engagement and transition will be developed for implementation in 2014
1.5 Annual Outcome Milestone Assessment / UNITAID is broadly on track to achieve its intended outcome. It is almost inevitable for the foreseeable future that new prevention, diagnosis and treatment products and technologies will be needed, the markets for them will change over time, and UNITAID will be expected to address them. / During the log-frame revision we will need to be sure that the milestones are sufficiently stretching to drive good performance.
[2] The EXPAND TB project countries are: Azerbaijan, Bangladesh, Belarus, Cameroon, Cote d’Ivoire, Djibouti, Ethiopia, Georgia, Haiti, India, Indonesia, Kazakhstan, Kenya, Kyrgyz republic, Lesotho, Mozambique, Myanmar, Peru, Republic of Moldova, Rwanda, Senegal, Swaziland, Tajikistan, Uganda, UR Tanzania, Uzbekistan, Viet Nam.

2. Spending profile and timescale
Is the spend profile detailed in the Business Case being followed: Yes / 2.2a. Does the review of the cash balance position raise any concerns around payment in advance of need: Y/N Yes. We have kept this aspect of performance under close review. / 2.2b.As noted in the 2013 MAR assessment, donor contributions are highly uncertain. In light of the original MAR the UK entered a 3 year funding agreement with UNITAID, and we noted in the MAR that France had also entered into a 3 year agreement. The Gates Foundation has entered into a 5 year agreement (2012-2016). Although multiyear commitments give some certainty at the outset, as they come to their end of course there is less visibility. / 2.2c. France and the UK represent 84% of donor contributions to UNITAID. Neither the French 2011-2013 agreement nor the UK 2011-2013 agreement have been replaced thus certainty of funding in 2014 and beyond is largely absent. In order to manage risk around future contributions, the Board has agreed to ‘discount’ future income in its budget forecasts. This means that forecasts of income have – deliberately – been conservative. / 2.2d. Some level of assets is necessary to signal to potential market entrants for drugs and diagnostics that funds are available to support the introduction of new products and technologies, over and above simply efficient liquidity needs. The Secretariat is projecting a minimum $184m of uncommitted assets at the end of 2014, and $124m at the end of 2015, assuming no other unconfirmed income is received (i.e. not accounting for French or UK contributions as there has been no agreement concluded on future funding). / 2.2e. The Secretariat has asked the UK to consider using Promissory Notes to manage this cash issue. Before agreeing to a new funding agreement for 2014-2016, the UK will need to make sure that adequate policies are in place to minimize the risk of excessive cash balances. / 2.3 Have additional payments linked to good performance been triggered: Y/N No.

3. Evidence and Evaluation
3.1 Assess any changes in evidence: / No analysis performed. To be picked up in analysis pre-ceeding the log-frame workshop. / 3.2 Where an evaluation is planned what progress has been made? / Mid-term and end-of-project evaluations are performed by independent, external evaluators that meet specific quality criteria for working with UNITAID. Evaluators are selected on the basis of their experience with the types of grants under review and their proposal for providing the evaluation (including budget and timeline). Most of our reviews to date have been desk reviews with few if any country visits. This will change in 2014 and country visits will be required for grants with a strong country focus and where it can be demonstrated that such visits would add value to the evaluation process. / During the 2013 calendar year, UNITAID has completed 2 mid-term and 4 end of project evaluations. These reviews have led to specific management actions that are provided in the Table below. / Name of grant Evaluator Type Programmatic response to findings / ESTHERAID (ESTHER) DMI Associates mid term Review of LogFrame and definition of new more specific indicators related to training / Prequalification of diagnostics programme (WHO) Euro Health Group mid term Review of Programme capacities and identification of support from other sources (CDC-USA) / ACT Scale up (UNICEF & GFATM) Euro Health Group final Process for formalization of revisions to MoUs and changes to targets and budgets now in place / Support to the GFATM Round 6 (GFATM) Cambridge Economic Policy Associates final LogFrames are now required for all grants. Project logs are now kept in UNIPRO to improve tracking and accountability during the course of a grant / Assured Artemisinin Supply System (I+ Solutions, Triodos Bank, FSC,Artepal) Dalberg final Implementer capacity to respond in a flexible way to changing market circumstances are now regularly assessed for new, high risk grants / Second Line HIV/AIDS Project (CHAI) Dalberg final Planning for transition is being enhanced with options to co-fund grants and/or engage potential funding sources earlier

4. Risk
4.1 Output Risk Rating: Low/Medium/High / 4.2 Assessment of the risk level – / Risk management really started at UNITAID in late 2010 when an organizational risk assessment was conducted. The risk management framework had been approved by the Finance and Accountability Committee in November 2012. A Risk Policy was approved by the UNITAID Board in June 2013. An overall organizational risk analysis is being undertaken in Q4 2013 and its results will be shared with the FAC in early 2013. / The Secretariat has also carried two risk analysis for fraud and wrondoing more generally. The first one was conducted in 2011 and the update was just presented to the FAC in November 2013. / Grantees are systematically assessed in this area before a grant is signed. They have to present a plan in this area and bear the responsibility to report any suspected or confirmed fraud or loss incident immediately. They also bear the financial responsibility for the result of any fraudulent activity. Reports of loss have been received. All those losses occurred once the products had been handed over by the grantee. / UNITAID is also planning to establish a whiste-blowing system available to external parties through its website. This requires support from WHO and will be implemented in 2014.
Risk of funds not being used as intended – / Within the Secretariat – low / In country – medium / The other element of risk is programmatic, in terms of whether the funding decisions made will deliver the intended results. This is difficult to quantify precisely, and of course the very nature of UNITAID means it is taking risks. This will continue to be addresses by sound evidence and market intelligence, strong grant management, and due diligence on potential partners. To date there have been no incidence of financial mismanagement either internally within the Secretariat or within the UNITAID grants to implementers. / 4.4 Climate and Environment Risk / The Norwegian contribution is based on a part of their carbon taxes (although, however, a majority of UNITAIDs finances comes from airline taxes. / UNTAID follows WHO environmental compliance polcies in its grants. / UNITAID has its own travel policy document and tracks carbon footprint monthly at its meetings.

5. Value for Money
5.1 Performance on VfM measures / UNITAID have produced the following self-assessment: / All UNITAID funded projects contribute to reducing the costs of medicines and tests of public health importance. The recent 5 year evaluation found that since 2007, 65% of UNITAID funded projects have achieved either good or very good market outcomes. UNITAID measures its success based on the impact of its project funding choices on the markets for medicines, diagnostics and related products of public health importance to treat HIV/AIDS, TB and malaria. UNITAID monitors how the markets respond via Key Performance Indicators developed specifically for this purpose. / Implementers report the US$ value of medicines provided to beneficiary countries as a result of project agreements with UNITAID. Two types of numbers are tracked: / Actual disbursements to implementing partners annually as well as the cumulative disbursements from the start of the project funding; and / Monies spent on medicines and diagnostics in each beneficiary country. / The data are essential for monitoring whether or not partners are providing value for money through use of UNITAID's funds. UNITAID’s current Implementers have fulfilled UNITAID's requirements for improved forecasting and product delivery at the country level. / Specific examples where UNITAID has improved supply chain management and helped to raise the alert on countries at risk of stock outs can be seen in our work with ESTHER on ESTHERAID and SCSM/PEPFAR on the Coordinated Procurement Planning initiative. Through ESTHERAID, technical support is provided to improve the management of suplly chains in 5 West African countries in need of logistical support. In supporting the CPP, UNITAID has helped to build a web-based platform to report on the ststus of countries at risk of stock outs for key ARVs so that the situations can be managed by the global public health community and donors. These projects represent value for money by ensuring the best possible use of existing resources while identifying and filling gaps that occur because of the changing nature of the three diseases. / Our work has been further strengthened by the introduction of the LogFrame and Finance pro-forma budget templates helped to improve programmatic and financial reporting on activities that implementing partners are doing in countries. The UNIPRO project monitoring system captures both disbursements to partners and the value of treatments delivered to countries, now making it easier to track monetary flows to countries. / An investment in UNITAID is good value for money because the potential cost savings achieved through UNITAID's projects far exceed the intervention costs. This is because UNITAID's partnership model requires cost-sharing of programmatic costs by partners while its market approach results in improved market conditions that facilitate costs savings to all developing countries and international organizations into the future. / UNITAID has set up additional controls to ensure better value for money in its administrative processes. UNITAID must comply with WHO Rules. This implies that procurement is made on the basis of competition and best value for money. UNITAID has been one of the WHO “units” to implement long term agreements for certain categories of service providers (report writers, translators) to ensure stability of prices and administrative efficiency. UNITAID follows the conservative WHO system to set consulting rates for individuals. UNITAID requires all consultants to be evaluated thereby ensuring that poor performers are clearly identified and are not rehired. Travel planning has been enhanced to ensure that cheaper fares can be booked. Event planning has also improved to limit the number of participants at any given event. The use of economy class when WHO Rules allow for business class is strongly supported. / 5.2 Commercial Improvement and Value for Money / Internally, UNITAID is subject to WHO commercial and other practices. As in 5.1 above, commercial improvement is one of the key elements of UNITAID’s ambition, as it assesses how and where to intervene. It operates as a market fixer, catalyser and creator, and invests in projects that seek to improve commercial outcomes. / It is also working on several areas with partners such as SCMS on various types of pooled procurement systems. It is involved in the Strategic Rotating Stockpile for TB project which seeks to address commercial limitations and is very active in improving demand forecasting across the three diseases but particularly in Malaria for ACTs.

6. Conclusions and actions
The review demonstrates reasonable overall progress from UNITAID against a back-drop of sub-optimal management practice. However, the review was made difficult by the lack of an up-to-date log-frame with indicators and annual milestones against these. This meant that progress had to be judged against rather general output statements with some (e.g. output 1) quite difficult to understand. / Key Actions Specifically Related to the Annual Review: / To finalise and have the Board endorse a new KPI framework for the next four year strategy period with each indicators having a baseline, target, and annual milestones; / As a matter of urgency to develop and finalise a new, robust DFID log-frame for the period 2014 – 2017 based on the KPI framework – it is suggested that to do this a one-day log-frame workshop is conducted in UNITAID together with DFID - and that this is preceded with UNITAID taking forward the necessary analysis of the evidence available; / (output 1): To secure improved feedback from key partner organisations on the market shaping role of UNITAID – to ensure that this is not developing into an ‘academic hub’ – but rather a live dynamic and outwardly facing team, which is useful for UNITAID grant identification and management, and well as for partner organisations and developing countries. / (output 7): To drive forward greater value for money in the secretariat with a culture of performance and ‘doing more for less’; to provide evidence that this is actually occurring rather than aspirational statements i.e. reduced staff costs in proportion to spend; reduced travel budgets; data of reduced business class travel etc. / (output 7): To develop a robust, focused resource mobilisation strategy which is focused on high-income countries – using GFATM and GAVI as examples to follow. To move away from low-income country resource mobilisation (except for encouraging increased domestic health investment including from air ticket levies as appropriate). To transition existing low-income country contributions to UNITAID towards domestic investments. / (output 8): To track and monitor grant financial management and report on any mis-use of funds and actions taken; as set out the organisational risk management framework / (climate and environment section): To develop a short policy paper on climate and environment and to include analysis of country grants – and from this to develop relevant recommendations and tracking / In taking forward the review and reading Board documents on internal UNITAID management, the following recommendation has been formulated: / To conduct a robust organisational review of UNITAID, including a focus on the Senior Management Team, to set out a series of recommendations on the optimal staffing and management structure of UNITAID to best deliver its 2014 – 2017 strategy – and then for UNITAID to implement these recommendations

7. Review Process
This review was conducted over a very short period (one week). The system used was self-reporting by UNITAID, with quality control, triangulation with other data sources, and scoring assessment from DFID. Jason Lane (Senior Health Adviser) led the review with assistance from Carlton Evans (UK UNITAID board member). The review was finalised with a half-day session in the UNITAID offices in Geneva. It has to be noted that 10 days before the review it became clear that there was no relevant DFID log-frame for the project with indicators and annual milestones to make possible a robust review. The review was therefore conducted by asking UNITAID to report evidence of progress against the 9 outputs (output 10 was removed as it was identical to output 9).