Annual Review - Summary Sheet

Title: Increasing Access to Reproductive Health commodities in Ethiopia
Programme Value: £18 million		Review Date: November 2014 / (Review Period: September 2013 to August 2014)
Programme Code: 202980	Start Date: November 2011	End Date: June 2015

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	A+	A+	A+
Risk Rating	Low	Low	Low

Summary of progress and lessons learnt since last review

The review this year has concluded that the Increasing Access to Reproductive Health Commodities in Ethiopia programme has exceeded most of its targets. At this pace of delivery the programme is expected to achieve most of its final year (2015) targets in 2014. This year, the programme has averted an estimated 755,000 unintended pregnancies and produced over 1,437,655 maternal healthy life years Disability Adjusted Life Years (DALYs). The programme is delivering excellent value-for-money, delivering at $4.92 per Couple with one Year of Protection (CYP) during the review period, in comparison to $6.20 per CYP the previous year and $8.00 per CYP estimated while developing the business case for this programme. The programme has been able to expand the types and availability of contraceptives methods which in turn has enabled women and men to use methods of their choice to plan their families. The Rural Social Marketing component of the programme, also known as rural Market Town Approach (MTA), has succeeded in increasing the proportion of sales coming from the rural areas in Ethiopia. The programme has also been transformational in its contribution to reproductive health policies in Ethiopia by facilitating the introduction and expansion of new life savings products (emergency contraceptives, medical abortion kits, Mesoprostol to prevent post-partum haemorrhage and Oral Rehydration Solution with Zinc to manage childhood diarrhoea). Ethiopia has met MDG’s child mortality goals and is on track to meet the maternal mortality goal. The country has recorded over 44% growth in contraceptive use among married women in the last four years. This project has contributed to these achievements by expanding access to lifesaving commodities and contraceptives.

Chart 1 depicts the distribution of contraceptive methods against the key performance targets of the programme. At the time of this review, the programme had completed 75% of its life but has achieved: nearly 80% of its male condom and oral contraceptive pill (OCP) final (end-of-the-programme) targets; and, nearly 90% of its emergency contraceptive pills, Injectable, Intra-Uterine Contraceptive Device (IUCD) and Implant final targets. The distribution of female condoms lags behind the planned target primarily because of the time it took to register this product in Ethiopia.

 Chart 1: Cumulative progress (green bars) as % of the total project life targets (the line represents the expected cumulative coverage during the review period)

During the review period, the programme has performed strongly on its core mandate by improving access to and creating demand for 13 different types of Reproductive Health (RH) commodities. The programme has exceeded its overall CYP target by 25% by producing 2.6 million couple-years of protection.

During this review period, delivery of Reproductive Health (RH) products has increased for most product categories in comparison to the previous year. The delivery of: OCPs has increased by 19%; Emergency Contraceptives (EC) has increased by 8%; Medical Abortion Kits has increased by 30%; and, Misoprostol has increased by 75%. However, the delivery of IUCDs and Implants has recorded an 8% and 20% decline. The decrease in IUCDs and Implants was partially due to residual stocks held by NGO partners/retailers from the previous year as both these products have a long shelf-life.

The programme has continued to increase demand for RH products and take forward activities aiming to improve the health behaviour of people, particularly of selected vulnerable groups. It has strategically used mass media to deliver: 213 television spots; 3,052 radio spots; and, a radio serial drama with 345 episodes. The majority of mass media communication was targeted at creating demand for the Family Planning (FP) products and services. Management of childhood diarrhoea through the combined use of ORS and Zinc, LemLem Plus, was also a priority of the mass media campaign.

During this review period, 5 new rural Market Town Activity (MTA) Teams were added to the existing 10 rural MTA teams. These 15 MTA teams conducted 2,163 rural market town events (2.5 times more than in the previous year), and reached a combined audience of 660,000 participants. These teams also counselled over 30,000 individuals. The MTA teams have delivered 2.7 million condoms, 228,332 OCPs, 232,340 injectable contraceptives, and 38,220 cycles of EC to communities that previously had little or no access to family planning services.

Beyond the product distribution and demand creation, sustained long-term investments in policy dialogue, application of evidence and demonstrations has contributed to transformational changes in the quality and quantity of life saving RH commodities available to Ethiopians. This programme will end in June 2015. DFID, DKT and the Federal Ministry of Health (FMOH) need to consider the future of social marketing of RH commodities in Ethiopia.

Girls and Women
- We have empowered girls and women by creating 1,437,655 healthy years of life. These healthy years, the majority of which are generated by women by planning their reproductive life, have allowed people to pursue education, employment, career and personal goals and reduced disability and death related to reproduction.
- Through the policy changes and increasing access to contraceptives, emergency pills and abortion technologies, the programme has empowered girls and women to plan their reproductive life.
- By averting unwanted pregnancies among female students, the programme has helped to keep more girls in schools and colleges.
- Increased availability of medial abortion services and emergency contraceptives has contributed to reduction in number of illegal/unsafe abortions and risk of abortion related complications and deaths.
- The rural social marketing programme (MTA) has increased access to information and negotiation power by girls and women.

Summary of recommendations for the next year
1. While the success of the rural MTA programmes is noted, this approach needs to be evaluated in terms of its scalability (ability to reach out to all rural markets), cost and value-for-money (VFM). Also, the linkages between the rural MTA initiative and primary health care delivery system (particularly with Health Extension Workers and Health Development Army) need to be strengthened.
2. The programme’s approach of promoting branded family planning products (of one agency) rather than promoting categories of family planning products needs to be evaluated in terms of its impact on: expending the overall family planning market; creating new family planning users; and, enhancing duration of method use.
3. Sustainability is the main risk for this programme, any follow on to this programme needs to clearly outline strategies that increase sustainable access of RH commodities for different socio-economic groups in Ethiopia.
4. The Value for Money (VFM) analysis for contraceptive commodities (as the principal cost driver of this programme) is strong. It is recommended that such rigorous VFM analysis should also be done for other cost drivers, in particular for the demand creation/communication/promotion activities.

A. Introduction and Context

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202980/documents/

Outline of the programme

DFID provides funding to DKT, a leading social marketing agency, to expand their ‘Social Marketing Plus’ Programme for increasing access to Reproductive Health (RH) commodities in Ethiopia. The Social Marketing Plus programme is also being supported by the Netherlands, and the Bill and Melinda Gates Foundation (BMGF). To date, the Social Marketing Plus programme has received funding of £29.3 million, of which £13.8 million (47%) has been contributed by DFID.

DKT is the primary organisation in Ethiopia engaged in the social marketing of a wide range of reproductive health commodities that include male and female condoms, short and long term contraceptives, lubricants and technologies for abortion. Furthermore, DKT distributes other health products, such as ‘ORS’ and ‘ORS with zinc’, for the management of infant and child diarrhoea.

DKT has established a strong partnership with the Federal and Regional Health Authorities, particularly for supplying contraceptives when public facilities run out of stock. However, the government’s procurement and distribution systems are improving and the frequency of contraceptive stock-outs at public health facilities are declining. Private for profit and non-profit organisations have also drawn on DKT’s RH stocks to fulfil their RH commodity needs.

As a complementary approach to the supply of RH commodities, DKT reaches different target populations through a variety of behaviour change communication (BCC) approaches to increase awareness and demand for RH commodities. Key target groups being reached by DKT are: a) rural men and women through the Market Town Activities (MTA) initiative; and, b) female sex workers and their clients through the Wise UP initiative; and, c) youth including students in higher learning institutions through the ‘Young Marketers’ initiative. The ‘Young Marketers’ initiative is DKT's flagship innovative youth engagement programme which engages youth clubs to market condoms on a commission basis.

The Social Marketing Plus programme contributes to progress towards Ethiopia’s health MDGs targets, in particular the MDG 5 targets of reducing maternal mortality by improving the Contraceptive Prevalence Rate (CPR).

What are the expected results?

The programme’s outputs are: increased supply of RH commodities; increased demand for RH commodities; and, strengthened national RH supplies system.

The programme, over four years, is expected to distribute:
•	239 million male and 147,000 female condoms;
•	14 million cycles of oral contraceptives;
•	7.2 million Injectable contraceptives;
•	5 million Emergency contraceptives; and,
•	1.68 million Misoprostol tablets to prevent post-partum haemorrhage.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The programme has 3 outcomes and 4 outcome indicators (summarized in table below).

Outcomes		Indicators
1.	Increase in consistent condom use by sex workers, their clients and regular partners in Wise-up programme intervention towns	1.1. Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 7 days with paying partners increases from 83% to 90%
		1.2. Percentage of female sex workers in DKT Wise Up towns reporting consistent condom use in the last 30 days with non- paying partners increases from 43% to 60%
2	Decrease in unprotected sex among students in DKT HEI Universities	2.1. Percentage of students reporting having unprotected sex in past 12 months declines from 78% to 70% in DKT Higher Education Initiatives (HEIs) Universities
3	Increase in CPR in DKT project areas	3.1. Percentage of Women in Reproductive Age (WRA) in Market Town project areas who use a modern method of contraception increases from baseline to end line

This Annual Review has not assessed outcome indicators at this stage. An end-term survey is being planned for 2015 to measure the outcome indicators. The results of which will be reported in the Project Completion Report in July 2015.The last Annual Review (2013) of this programme recommended that DKT could use the number of target audience reached through their behaviour change communication (BCC) initiatives to gauge progress towards the outcome indicators. During this review period, DKT has achieved its BCC targets of reaching female sex workers, students in universities, and men and women through market town activities.

Overall output score and description:

A+ for this review period. The programme has exceeded/met all three outputs.

Key lessons:
1. DKT has successfully adapted to the changing RH product procurement scenarios of the country (i.e. the public sector’s increasing reliance on its own improved procurement system) by refocusing its work on meeting the needs of the private sector actors and working in hard to reach areas;
2. DKT’s work has generated a significant amount of evidence. However, most of this evidence has been used by DKT to inform their work. DKT and its funding partners should ensure that the evidence generated by DKT also informs the work of the government and other stakeholders.
3. Timings of many of the data collection activities/annual surveys carried out by DKT did not match with DFID’s annual review timelines. In the future, the coordination between DKT and DFID could be improved to synchronize the data collection and reporting timelines.
4. The rural MTA is an innovative initiative in Ethiopia. It seemed to have led to improvements in demand for and utilization of modern contraceptive methods in rural areas. However, this approach needs to be evaluated in terms of its scalability (ability to reach out to all rural markets), cost and value-for-money. Also, the linkages between the rural MTA initiative and primary health care delivery system (particularly with Health Extension Workers and Health Development Army) need to be strengthened.

Has the logframe been updated since the last review?
Yes. Four indicators had been included in the log frame since the last annual review; these are;
1. Number of Female Sex Workers (FSW) with non-paying partners received key HIV prevention messages including 'boyfriend' messages;
2. Number counselled for FP in Market Towns
3. Number of Events with majority male target group held in DKT Higher Education Initiatives (HEIs) sites
4. Number of sessions with female target group in DKT project HEI

## C: DETAILED OUTPUT SCORING

Output 1	Improved supply of reproductive health products in rural and urban Ethiopia
Output number per LF		1	Output Score	A+
Risk:		Low	Impact weighting (%):	60%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N

Output 1: Score and performance description: Scored A+, the project moderately exceeded expectation. This core output measures the quantity of commodities distributed, the coverage and reach of products in the country. Data is gathered based on project documents and Market Penetration Surveys (MAPs).

Progress against targets: All six indicators of the Output 1 have been assessed through this annual review.
Indicator 1. 1. Couple Years Protection provided by reproductive health products sold by DKT

The programme has substantially exceeded the 2014 target. This indicator forms one of the triggers for payment to DKT in its milestone based contract with DFID.

Indicator(s)	Milestones	Progress	Score
Couple years protection provided by reproductive health products sold by DKT[1]	2,174,582	2,594,892	A++
[1] Data covers the period of July 2013- June 2014

Key Points
- The programme has achieved 119% of the target. Contraceptive commodities that contributed the highest share of the CYP are injectable and IUCD (each contributing 24% of the CYP), followed by male condoms (23%) and Implants (16%). There were reductions in the volume of sales for IUCD (-8%) and implants (-20%) during the review period, partially due to residual stock held by NGO partners. Product categories that showed an increase are: OCPs (+19%), EC (+8%), Medical Abortion (+30%), and Misoprostol (+75%).
- The sale volume of unsubsidized condoms has grown four folds this year, also the condom brands that target the middle income class has expanded by 2%. These positive trends that show that selected elements of this programme could potentially sustain themselves but may still need variable degrees of subsidies till the country reaches middle income status.
- FMOH capacity in procuring commodities and preventing stock outs has improved. There were fewer incidents when DKT’s support was sought during the review period. The FMOH has also increased the volume of long acting contraceptives imported. These are encouraging signs and DKT could focus more on non-state actors.

Indicators 1.2. to 1.6.
These sets of indicators mainly deal with measuring DKT’s efforts in expanding access through different outlets in urban and rural settings and availing a mix of RH products. These indicators were measured by Market Access Penetration (MAP) 2014 survey.

Indicator(s)	Milestones[2]	Progress	Score
% of pharmaceutical outlets in (rural) market towns stocking at least three DKT RH product categories	80	91.5%	A++
% of (rural) market town service providers (clinical outlets) stock at least three DKT RH products	80	89.6%	A++
% of urban (excluding rural market towns) pharmaceutical outlets stocking at least five DKT product categories	76%	96%	A++
% of non-pharmaceutical outlets in urban areas stock condoms	42%	30%	B
% of the urban towns meet minimum coverage standards (2outlets/1000population) for condom in non-pharmaceutical outlets	75%	38%	C
[2] All milestones are set for 2014/2015

Key Points

The level of market penetration in to rural Ethiopia has significantly increased, compared with last year’s performance the volume of products sold growth varies between 200-6000%.
- Coverage at pharmacies and clinics located in rural market towns and major urban areas has exceeded expectation.
- The penetration of products in to non-traditional (non-pharmaceutical) outlets is still very low, the reason is partly due to DKT’s focus on pharmacies that are expanding and increasingly becoming popular outlets of condoms. The MAP 2014 survey indicates that there is a space to expand among local liquor houses, kiosks, groceries and supermarkets.
- Distribution of commodities in Somali and Afar have shown a positive trend (15 – 25% increment was attained over the last year). However, sale of oral contraceptive in Somali has declined.
- The intensity of coverage for condoms (number of our condom outlets per 2,000 population) has not been as targeted, the influx of free condoms in to market from USAID has continued to put pressure on this achievement. Also, the targets for this indicator are extremely ambitious. Despite missing this target, the programme has been able to meet the total CYP and total condoms sales target. Any follow on to this project needs to be aware of the challenges of reaching high coverage standards, which has a high overhead cost in an environment whereby free condoms are excessively available.
- The sale of condoms has exceeded the target and last year’s sale figures. This indicates the impact of free condoms has not been as severe as the past. DKT needs to continue to actively participate in national taskforces and contribute to the better coordination of free, subsidized and fully commercial condom distribution.

Summary of responses to issues raised in previous annual reviews

Issues raised during previous annual reviews	Progress
a) Review some of its targets and improve the quality of demand creation and distribution of commodities for 2013/14	DKT has driven forward improvements in its behaviour change communication strategies and commodity distribution plans. Research driven plans and interventions have enabled DKT to better understand factors leading to a decline or increase in demand for its products, and as a result it has taken actions to address gaps in the private sector. DKT has responded to opportunities created by the expanding rate of urbanisation in the country and the emerging need for new distribution channels.
b) In 2013/14 DKT shall establish clinical referral models with NGOs and private clinics	With a support from Bill and Melinda Gates Foundation (BMGF) fund, the networking between DKT and NGOs such as Marie Stops International (MSI) and Family Guidance in Association Ethiopia FGAE, and private clinics, both rural and urban, is now well established.
c) DKT should actively and consistently be involved in national level universal demand forecasting and the gauging process to find the right balance between free and socially marketed condoms. Based on evidence it may revise down the male condom forecasts.	DKT is represented on the steering committee led by the Federal HIV/AIDS Prevention and Control Office and engaged in on-going dialogue. DKT is also actively participating in national technical working groups regarding Youth/ Adolescent RH, both at FMOH and MOE. Recently, DKT participated in the preparation of a National Peer Education training manual for HEI students and Sexual and Reproductive Health (SRH) curriculum development for HEI students. However, there is still work to be done in this area and this is included as a follow on recommendation.

Recommendations
- Explore options of increasing sustainability, including cost sharing mechanism, co-financing schemes and undertaking willingness to pay studies. DKT should continue to focus on shifting from free to subsidized, and from subsided to fully commercial products. Also, carry out assessments to understand the marker space for this gradual transition.
- Family planning and safe abortion service delivery should remain core to any follow on support to this project.
- The progress against respective milestone under output 1.5 and 1.6 is low. We have learnt that the targets were not set realistically. The program ends in June 2015; we prefer the keep the logframe unchanged but take the lesson to the follow-on program.
- Better understand the referral process from targeted BCC and information provision, particularly to couples through the rural MTA, to their attendance at a facility and up take of services.
- To develop a condom promotion strategy, which is totally embedded in the national strategy; and is clear on the comparative advantage of DKT’s efforts in terms of the public health impact
- Given the possibility that donor funding for the next phase may decrease and DKT remains nearly fully dependent on donor support, DKT should explore the opportunities for innovative way of sustaining key elements of their programme.
- Based on the MAP survey findings, DKT needs to understand why it has not been successful in promoting condoms and RH commodities in in urban non-traditional outlets and devise a strategy to increase coverage through these outlets.

Output 2.	Increasing demand for reproductive health (RH) products
Output number per LF		2	Output Score	A++
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Output 2: Score and performance description: Scored A++. During the review period the project has substantially exceeded targets.

Four out of the seven indicators of the Output 2 have been assessed through this annual review; the remaining indicators will be assessed during the Project Completion Report as the milestone date is 2015 and beyond this annual review period. Creating demand is important for making sure that products are purchased and used which is the main objective of this programme in order to reduce RH related death and morbidity. In this review period DKT conducted the second Behavioural Change Impact Survey (BCIS-2). This survey employs a standard methodology to measure changes in motivation, ability and opportunity factors that affect contraception use.

Indicator	Milestone	Progress	Score
2.1.Number of Female Sex Workers (FSW) with non-paying partners received key HIV prevention messages including 'boyfriend' messages	3,312	5,678	A++
2.2.a.Perceived availability score by rural women of reproductive health age (RWRHA) increased	4.0 by 2015	3.96 (Improved from 3.6 at 2012)	Not Scored (due 2015)
2.2.b.Support score among RWRHA increased	3.3 by 2015	3.1 (Improved from 2.6 at 2012)	Not Scored (due 2015)
2.2.c.Attitude score among RWRHA increases from 3.1 to 4.0	4.0 by 2015	3.23 (slight improvement from 3.1 at 2012)	Not Scored (due 2015)
2.2.d. Number counselled for FP in Market Towns	24,300	32,143	A++
2.3.d.Number of Events with majority male target group held in DKT project HEIs	228	474	A++
2.3.e.Number of sessions with female target group in DKT project HEIs	200	224	A+

Key Points
- The programme has met all targets set for activities to increase demand of RH commodities among rural and at-risk for HIV populations. It has expanded its reach into rural market towns, as well as maintained the total number of urban and higher education sites where HIV prevention and RH demand creation is being provided. During the review period, DKT has conducted 2,163 rural MTA events, 2.5 times more than the previous year (869). Audience participation has tripled and the number of individuals counselled has quadrupled compared with the previous year through these events.
- A positive trend in behaviour change has been recorded among targeted populations (see above 2.2a, 2.2b and 2.2c); there is a change in attitude and other components of behaviours that may further lead to increased uptake of contraceptives. However, the effectiveness and cost-effectiveness of the rural MTA approach in raising CPR needs to be fully understood.
- The project seemed to have managed to reduce referral and linkage challenges to meet the newly generated demand. It has strengthened the referral component by making the MTA teams collect referral slips from participating health facilities. This has led us to record a 25% traced and successful referral rate.
- The challenges in reaching the married youth with FP messages and designing socio-culturally appropriate approaches for residents in Afar and Somali region have continued. The success in Afar and Somali in demand creation was mixed. The number of market day events increased in both regions and in Somali, audience participation increased by over six-fold from 12,421 in 2012/13 to 75,708 in the year just completed. However, the number of clients counselled and referred declined slightly in Somali and Afar, respectively.
Issues raised during previous AR	Progress
Do analysis/segmentation of targeted population reached through DKT’s peer education	During the review period DKT has done a better segmentation analysis and can report that they have reached a target audience of; / a) 663,127 through rural MTA / 326,990 university students through HEI, and / 244,316 female sex worker visits by peer educators through the Wise up Project.
Rural market town activities could be slightly modified to address young yet-to-be or newly married couples during wedding sessions in large numbers	This has remained as a challenge. Although young men and women are encouraged to attend rural MTA, DKT reports that they are shy and do not fully participate in counselling actively. This requires a further refined approach and factors that can motivate this target group need to be identified. MTA teams could also consider couples counselling, but this too is difficult. Work in this area is on-going, and different approaches are being tested.
Establishment of effective referral system to increase efficiency and take up of FP services.	During the year ending in 2014, DKT strengthened the referral component of MTA by having MTA teams collect referral slips from participating health facilities. Out of 10,562 clients referred in 2013/14, DKT collected 2,696 referral slips. Nurses are accompanying referred clients to service outlets to reduce drop outs and encourage clients to make the best use of services. As a result of which, positive changes have been recorded during the last 2-3 months. Modalities for more cost effective approaches in reaching target populations are being considered, including piloting of DKT managed services, or direct support to private facilities or by further strengthening linkages with government health facilities.
Do annual tracking surveys for behaviours on family planning by rural women,	Output Tracking Survey (OTS) data collected, data analysed and result drafted.

Recommendations
- Explore approaches to target young women, just after their first birth, for promoting the use of spacing method.
- Explore what kinds of links can be created between Health Development Army, Health Extension Workers and the MTA, for improving VFM and sustainability of this programme.
- Continue assessing the opportunities and challenges in scaling up commodity distribution in Afar and Somali region. Investigate the reasons for the intermittent slowdown in the distribution of oral contraceptives in Somali region.
- Link DKT demand and supply side initiatives with DFID’s demand side programme in emerging regions (the Reproductive Health Innovation Fund – RIF). The RIF will start implementation in Afar, Somali and pastoralist Oromia and SNNPR. DKT needs to link its community mobilization programme with grass root level CSOs contracted through RIF that will create demand for RMNH commodities and services.
- To start consolidating and transitioning out of HIV prevention programmes at Higher Education facilities. This is the right time for DKT to prepare and implement a transition plan, partly because the HIV funding from DFID is likely to be reduced in future years and US Government is funding HIV programmes in Higher Education settings.
- The follow-on to this programme could investigate linking with other initiatives to empower women and girls and maximize their non- reproductive functions to help them sustain their desire to manage their family size.
- The engagement of young men and women needs to be strengthened. This should be one of the priorities of the follow on programme.

Output 3	Improved environment and capacity for the supply and promotion of RH products and services
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Score and Performance Description: Scored A, in the review period the project has moderately exceeded its planned targets.

Indicator(s)	Milestones	Progress	Score
Increased number of outlets reporting positive experience of DKT training, detailing visits	70%	78%[3]	A+
Improved policies supporting private sector distribution of RH products	Improved policies	Progress satisfactory	A
Research methodology and results shared with RH community	Rural BCIS Results	Progress below	B
[3] 78% represents the level of change in pre and post training tests taken by the trainees- this data was collected during training sessions as a proxy to measure the indicator 1.3

Key Points
- DKT has had a major impact on Ethiopia’s Reproductive, Maternal and Neonatal Health policy dialogue over the years and has been influential in negotiating for the registration, importation and decentralized use of life saving RH commodities. This year it has successfully collaborated with government and non-state actors for the decentralized distribution of life saving anti-diarrheal supplements and medical abortion drugs.
- During the review period, DKT trained 2,576 individuals, primarily pharmaceutical and clinical providers on the appropriate use of medical abortion, contraceptive technologies and HIV prevention. This total included 1,631 men and 945 women drawn from members of the Ethiopian Nurse Association, Ethiopian Druggist Association, Pharmaceuticals Association and the Medical Association of Physicians in Private Practice in Ethiopia. These training sessions focused, among others, on contraceptive technology updates and on medical abortion. Two hundred and four members of the House of Peoples Representatives also received one day training on HIV prevention.
- As in previous years, DKT continued to work with Food Medicine and Health Care Administration (FMHACA) to ensure that all products comply with standards set by the Agency. DKT also served as a number of Technical Working Groups convened by the FMOH which included the IUCD scale-up technical working group, Complete Abortion Care (CAC) working group, and the contraceptive forecasting working group.

The programme has contributes to the following transformative policy initiatives during the review period:
- Distribution of medical abortion drugs through pharmacy retail outlets, and for the service provision of medical abortion in lower health facilities;
- Use of Manual Vacuum Aspiration (MVA) at the lower level health facilities;
- Miso-Fem®, which is currently only indicated for post-partum Haemorrhage (PPH) control in Ethiopia, to be sold through pharmacy retail outlets;
- Inclusion of Chlorhexidine, an antiseptic agent used for umbilical cleansing of new-borns, as a crucial component of the Community Based New-born Care (CBNC) package for the reduction of neonatal mortality; and,
- Introduction of ORS with Zinc (LemLem Plus® brand) for more effective management of childhood diarrhoea.

During the review period the following research activities were conducted, the impact of these and previous studies will be reviewed and reported in the PCR:
1. Output Tracking Survey (OTS) of Married Women and Men in Rural Parts of Six Ethiopian Regions;
2. Behaviour Change Impact Survey (BCIS) of Married Women and Men in Rural Parts of West Arsi, Guraghe, and Siltie, Round One;
3. Measuring Access and Performance (MAP): Coverage and Quality of Coverage of DKT’s Condoms in Non-Traditional Outlets (NTOs) in Urban Ethiopia,
4. Measuring Access and Performance (MAP): Availability, Depth of Availability, and Coverage of DKT’s Products in Clinical and Pharmaceutical Outlets in West Arsi, Guraghe, and Siltie, Round One; and,
5. Formative Research on Use of Intrauterine Contraceptive Devices (IUCD).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

The programme has progressively achieved a high VFM level by as the capital investments in on promotion of commodities, logistic systems and community mobilization are increasing demand and efficiency. The programme continues to represent good VFM. This year all unit costs for this year have been lower than the last year’s unit costs and also in comparison to the international markers.

Key cost drivers and performance: During the review period, the programme/DKT received a sum of £ 5,960,000of which DFID contributed £2,000,000.0 (33%); the Embassy of Kingdom of Netherlands (EKN) contributed about £ 3,960,000. With a total expenditure of £3,619,103, commodities consumed slightly over 40% of all expenditures followed by advertising, £1,341,941 (15.7%), promotional Information, Education and Communication (IEC)/Public Relation, £1,296,136 (15.2%) and travel and transportation, $823, 490.00 (6.4%). A significant proportion of costs went to procurement, communication, and promotional activities, which is consistent with the design of the programme. This expenditure trend has been consistent throughout the project life cycle and represents where DKT’s efforts are concentrated.

VFM performance compared to the original proposition in the business case

Economy: Comparison of unit costs of commodities procured: The table below shows the unit costs of different RH commodities procured by DKT and other main suppliers, i.e. USAID and UNFPA. Of the 16 product items procured, DKT enjoyed a favourable advantage in the costs of 7 items; added to this is the fact that DKT is the sole procurer of 4 of the products for which costs can’t be compared.

Product	DKT/E 2013	DKT/E 2014	USAID 2014	UNFPA 2014
Male Condom	$0.031	$.035 - $.044	$.033 -$.036	$.033 - $.033
Female Condom	NA	$0.55	$0.55	$0.67
Combined OC	$0.08	$0.19	$0.29	$0.29
Progestin-only OC	NA	$0.32	$0.33	$0.32
Tri-phasic OC	NA	$0.363	NA	NA
Injectable (bulk)	0.54	$0.53	$0.86	$0.76
Injectable (packaged)	NA	$0.63	NA	NA
Emergency Contraceptive	NA	$0.23	NA	$0.30
IUCD (bulk)	$0.37	$0.42	$0.53	$0.55
IUCD (packaged)	NA	$0.69	NA	NA
Implant	$8.04	$8.38	$9.29	$8.95
MVA Kit (with 6 cannula)	NA	$9.63	NA	$17.38
Medical Abortion Drugs	NA	$2.75	NA	NA
Misoprostol	$0.4	$0.13	NA	$0.15
ORS	NA	$0.15	NA	$0.08
Lubricant (5 ml sachet)	NA	$0.08	$0.05	$0.02

DKT’s product costs shown in the table above also include the cost of branded packaging whereas the products from USAID and UNFPA do not. This means that the actual cost of the commodity through DKT is in fact lower than the costs quoted here. These commodity prices reflect an extremely successful negotiation process that DKT has established with the suppliers which allows very competitive prices. The four biggest cost drivers of this programme are commodity procurement, advertising, promotional activity, and travel and transports. Skilled human resources are the other major cost driver but it is harder to quantify how performance/efficiencies of DKT staff/sales team have improved over time. Nonetheless, the Cost per CYP could be considered as a summary measure of all cost drivers.

The following are some of the cost containment strategies which DKT applies to the non-procurement cost drivers:
- A strict competitive bidding process for the purchase of all services and supplies to ensure that the most reliable and efficient vendors.
- Minimising outsourcing wherever possible, and building in-house capabilities. This particularly applies to research, data analysis, and Management Information Systems.
- Maintenance of a rigorous fleet management policy to maximise the lifespan of vehicles.

Cost per CYP generated: We have continued to get a cheaper cost per CYP this year. The programme has achieved a cost per CYP of $4.92 during the review period, considerably below the previous year ($6.20 / CYP). To-date , DKT Ethiopia’s cost per CYP is $5.6, this is much lower than the average $8.00 per CYP cost estimated while developing the business case of this programme.

Cost per Health Impact: Preliminary estimates suggest that over the course of the review period, contraceptives and other RH commodities that DKT distributed have: a) prevented an estimated 755,798 unintended pregnancies, and, b) averted an estimated 11,342 HIV transmissions. These outcomes in turn have produced an estimated 1,437,655 maternal healthy life years (DALYs). With these preliminary numbers, the cost at which this programme has averted reproductive morbidity and mortality appears impressive: $16.9/unintended pregnancy; and, $9/maternal DALY. These preliminary cost estimates are significantly lower than the global average of $28 and $62 respectively. DFID Ethiopia will carry out a robust modelling exercise to finalize these cost estimates as per the global norms, and document lessons learnt while preparing the Project Completion Report (PCR) for this programme.
The improvement in operational efficiency has been gained through DKT assisted capacity building of FMOH and private sector actors/retailers in doing forecast, promotion, and distribution of RH commodities. DKT has trained and capacitated over 40 higher education institution to plan and execute reproductive health and HIV programmes for youth. Also, innovations on accessing rural markets and demand creation have also contributed to improved efficiency. In addition, about $1 million has been leveraged from BMGF to maximize the impact of the programme.

Assessment of whether the programme continues to represent value for money: This programme continues to offer good value for money, DKT’s cost per CYP is below the estimated global average of $8.00 per year per woman using contraception[4].
[4] Singh S et al. adding it Up: The Costs and Benefits of Investing in Family Planning and Maternal and Newborn Health. Guttmacher Institute and UNFPA; 2009. P. 18 (also cited in DFID’s RMNH Framework for Results, December 2010. P. 10)

Quality of financial management: This is a milestone based payment contract arrangement. DFID has received unqualified audit report for the review period. DKT’s annual report provides an accurate picture of financial data for the period under review, including comprehensive expenditure summaries, and a cash flow analysis with opening and closing cash balances. The last external audit report covered the 2013 fiscal year and was completed by March 2014. The next cycle of audit for the 2014 fiscal year is scheduled for completion February/March 2015 and will be reported on in the PCR.

Year	Budget	Disbursement	Variance
2011	6,500,000	6,500,000	Nil
2012	2,800,000	2,800,000	Nil
2013	3,000,000	3,000,000	Nil
2014	2,000,000	2,000,000	Nil

E: RISK (½ page)

Overall risk rating: Low
Overview of programme risk: DKT’s principal risk is around maintaining strategic collaboration with the government and it has managed this risk extremely well in the past. DKT has stated that free condom distribution by USAID is a risk to its condom product promotion. However, this is not a major risk for DFID given that it will not have an overall negative public health impact. The risk of DKT being required to step in for Government commodity stock outs has decreased significantly over the last two years as the Government procurement (particularly) and distribution systems have improved. There are significant risks to DKT’s sustainability as donor funding may reduce in the future. DKT urgently needs to develop strategies to mitigate this risk.

Outstanding actions from risk assessment: A number of recommendations from this review relate to risk management and are outlined in the recommendation summary section.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned time frame

DKT is on target, or ahead of schedule, for programme deliverables. In the years to come DKT has to transition from a donor dependent entity to a partially self-supporting organization. This is prompted by the following considerations:
1. Plans by the Government of Ethiopia to achieve the status of a middle income country by 2025;
2. Growing urban population with increased purchasing power will facilitate the growth of private medical and RH suppliers.
3. The public sector’s increasing reliance on its own procurement system that has reduced its dependency on DKT’s commodities and services;
4. DFID’s and other donor funding capacity for such programmes may not stay the same during and beyond the next 5 years

Performance of partnership (s)
One potential area of partnership in DKT’s work is to explore opportunities for distribution through other companies’ wholesalers’ distribution networks that could reduce distribution costs.

Asset monitoring and control
No issues have arisen during the review period.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Given that this programme does not include direct funding to the Government of Ethiopia DFID’s conditionality policy and partnership principles are not relevant.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation: Monitoring progress throughout the review period:

M&E activities undertaken during the review period include:
- Supportive supervision provided to all regions by DKT to ensure the smooth implementation of all programmatic activities.
- Developing report formats and monitoring checklists to determine MTA team performance and to identify performance gaps. As of July 2014, the DKT had mapped and analysed data on 1,154 market towns.
- DKT collected information on condom distribution outlets and RH service delivery facilities accessible to university students. This information was analysed and posted on the new TemariNet website.
- DKT has generating monthly regional sales data and compared them against performance indicators.
- Sales performance summaries and detailed reports were produced and disseminated to the Regional Offices for staff appraisal for programme monitoring, and developing action plans.
- Two key surveys (the Behavioural Change Impact Survey - BCIS-2 and Output Tracking Survey - OTS) and other research pieces (listed under output 4) have been conducted to measure success of the demand creation and distribution activities.

By using all the information collected during the life of this programme, a robust performance review will be carried out in March/April 2015 including a comprehensive VFM analysis of all cost drivers. This evaluation will not only inform the PCR of this project but will also guide the development of the next phase of DFID support to the health sector.

The core team for this annual review included: Jason Lane, Senior Health Adviser in DFID’s Global Fund Department; Hannah Langfield, Acting Policy and Programme Manager in DFID’s Global Fund Department; and, Kassa Mahammad, Health Adviser in DFID Ethiopia. The review team carried out interviews with all key stakeholders including DKT, FMOH, and BMGF, Netherland Embassy and DFID Ethiopia Human Development Team members and the economist for this programme. A number of key documents were also consulted as part of this review including: the BC, Logframe; report on Strengthening DFID Ethiopia’s Tracking of Value for Money in its Human Development Programmes; previous annual reviews; and, DKT’s quarter and annual progress reports.

This Annual Review has been Quality Assured within DFID Ethiopia by Jyoti Shankar Tewari (Senior Human Development Adviser), Angela Spilsbury (Human Development Team Leader) and DFIDE OPEX team. Comments from the DFIDE OPEX team have been incorporated.