-Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Migrating out of Poverty - Research Programme Consortium
Programme Value: £6,425,233.		Review Date: October 2014
Programme Code: 114334-101	Start Date: Implementation started in Sept 2011 (after one year inception)	End Date: June 2017

Summary of Programme Performance
Year		2012	2013	2014
Programme Score		68.75	B	A
Risk Rating		High	High	Medium

Summary of progress and lessons learnt since last review
The Migrating Out of Poverty (MOOP) Research Programme Consortium has made very good progress this year. The MOOP team have actively addressed the leadership, management, governance, and strategy weaknesses identified in the last annual review.
The Sussex team’s efforts to improve financial management across the MOOP consortium are particularly laudable. MOOP’s data collection is now translating into research outputs, and it is back on track to deliver its logframe outputs.
MOOP can thus be taken off the ‘special measures’ that were agreed last year. DFID thanks all in the MOOP team for the efforts made to deliver this change.
Summary of recommendations for the next year

1. Gender: MOOP will urgently recruit a Gender Theme Leader to create and manage a network of gender advisers across consortium, and maximise gender analysis in programme delivery and outputs.
2. Logframe: DFID and MOOP team have agreed revisions to the logframe and this annual review reflects these changes. DFID will upload the revised logframe to DFID’s management system.
3. RPC Contract: DFID will amend the MOOP contract to reflect the change in leadership etc.
4. Research communication, uptake, policy engagement: MOOP will continue to consider new and innovative approaches to research communication, including increasing the use of ‘voices of the poor’ style approaches that directly bring the voices and stories of individual migrants into MOOP outputs and publications. DFID will share examples from other research groups.
5. MOOP finances and financial management: MOOP should manage its budget dynamically, aiming to spend its full allocation and, if necessary, vire funds (with appropriate approval) between lines to reduce funding to low/slow performers and reward best performers.
6. Additionality of MOOP funding: DFID requests information on the degree to which MOOP’s consortium partners are reliant on MOOP/DFID funding as a proportion of their overall budgets.
7. Intern strategy: MOOP will re-examine the existing funding and strategy, and – if necessary - seek DFID’s approval for a revised approach.
8. Engagement with DFID: GCSD is committed to ensuring that DFID funded research is responsive to, and used by, DFID country programmes and partners. We will invite MOOP to present key research to a DFID HQ audience, and will actively make links and then encourage and monitor the two-way contact between MOOP and DFID country teams.
## A: INTRODUCTION AND CONTEXT

DevTracker Link to Business Case:	2137641
DevTracker Link to Log frame:	4619082

Outline of the programme
DFID has agreed a £6,425,233 contract with the University of Sussex (2011-17) for the Migrating Out of Poverty Research Programme Consortium (MOOP). The MOOP generates new, high quality research and evidence related to migration and poverty, creates new datasets, engages policy makers, and builds capacity. Its research aims for a better understanding of the relationship between migration and poverty and the factors that mediate it. This builds on work carried out by the DFID-funded University of Sussex Development Research Centre on Migration, Globalisation and Poverty (2003-09).
The MOOP works in five regions – East, West, and Southern Africa; South Asia; and Southeast Asia. The lead partner is the Sussex Centre for Migration Research, with five other core partners: The Refugee and Migratory Movements Research Unit (RMMRU) in Bangladesh; The Centre for Migration Studies (CMS) at the University of Ghana; the Asia Research Institute at the National University of Singapore; the African Centre for Migration & Society (ACMS) at the University of the Witwatersrand, South Africa; and The African Migration and Development Policy Centre (AMADPOC) in Kenya. The MOOP also has associate partners across the regions.
The programme results are:
Impact: state and societal actors will have utilised a strong evidence base on internal and regional migration to produce pro-poor migrant policies in in 5 countries /regions.
Outcome: improved access to and demand for internal and regional migration evidence by targeted development policy stakeholders in at least 5 countries as a result of an improved understanding of migration and poverty linkages, and how this can be used to maximise benefits of migration for development and minimise risks or negative impacts.
Outputs:
1. New research: A coherent body of high quality, policy relevant new knowledge on internal and regional migration. This will include new open access databases to provide a critical resource to migration researchers globally. It will also include at least 35 research outputs that specifically address gender dimensions, with a focus on women and girls.
2. Policy engagement: Improved engagement and dialogue with key stakeholders, to promote research uptake and understanding of findings related to internal and regional migration and poverty linkages.
3. Capacity: Enhanced strategic capacity of consortium members to conduct research, and enhanced capacity of key stakeholders in government and civil society to participate in policy framing processes.
At least 740m people migrate internally (HDR 2009) and another 80m migrate within the global South (Ratha and Shaw 2007), often to improve development prospects for themselves and their families. Research shows that migration can contribute towards achieving the MDGs by improving life choices, empowering disadvantaged groups, improving access to health and education, and reducing poverty (HDR 2009). However, it can also have negative impacts with migrants exposed to new vulnerabilities (e.g. violence) or limited access to services.
Southern governments and international donors are becoming more aware of the importance of migration for poverty reduction. However, they lack evidence and data to help maximise the benefits of migration and minimise potential harms. Existing datasets do not adequately cover the types of migration that poor people engage in, the drivers of these migrations, and the economic and social impacts on both receiving and exporting communities.
The MOOP will help to address this research gap by providing high quality, open access evidence on internal and regional migration, to provide a sound evidence base for more effective policies.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The outcome assessment is ‘A’ – Outcome meet expectations.
Overall output score and description
MOOP’s stronger leadership, management and governance this year has helped accelerate delivery of all outputs and the programme is on track to meet all of its output milestones (all three outputs score ‘A’).
The single area of marginal underperformance relates to the failure – despite significant efforts – to recruit a Gender Theme Leader. The MOOP secretariat is confident that renewed effort will result in recruitment
Key lessons
The most important lesson for DFID and for Sussex is the importance of dedicated leadership and strong management in a consortium approach, including financial management compliance by all Consortium members that are recipients of DFID funds.
We welcome the strong action taken by MOOP’s management team, which has reduced risk and accelerated delivery in the programme, but also built capacity and raised standards in financial management across the consortium partners.
Key actions
See recommendations above.
MOOP has been taken off the ‘special measures’ that were agreed last year.
Has the logframe been updated since the last review?
Yes – before the annual review we discussed with MOOP proposed amendments, and approved these during the review meeting. This annual review reports against the revised logframe.

## C: DETAILED OUTPUT SCORING

Output Title	A coherent body of high quality, policy relevant new knowledge on internal (and regional) migration
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
1.1 # of internal and regional databases made available to the research community (i) qualitative and (ii) quantitative	0		3 Qual / 3 Quant	6 Qual / 5 Quant	Milestone on track. / 2014 performance data confirms that 3 comparable household datasets are complete, enabling national and cross-country comparative analysis on internal and regional migration and poverty. / 3 global qualitative research projects on impacts of migration for construction and domestic work have been implemented, based on a common methodology.
1.2 # of internal and regional migration policy relevant projects comprising research and related engagement activities completed according to plan	0	8	18	29	Milestone on track. / Of 19 research projects noted in March 2014, 10 are complete, 5 very nearly completed and 3 will be completed in 2014-15 as planned. / One (qualitative research in Bangladesh) has been dropped due to a lack of capacity to conduct it simultaneously with important phase-2 research projects.
1.3 # of research outputs: / i) peer reviewed articles, / ii) working papers, / iii) policy briefs, / iv) conference papers/ presentations and book chapters (*added this year)	0,0,0,*	0,2,3,*	12,40,20,40	18,60,30,50	Milestone on track. / 2014 results are 17, 26, 16, 36. / During 2013-14, 12 working papers were published with a further one as an unedited version available on the MOOP website. MOOP also published 7 Policy Briefs and made 5 research reports available. / Achievements under this indicator include 1 article, 1 book, 1 chapter and 4 papers and 20 conference presentations.
1.4 # of research outputs that significantly address gender dimensions, including a focus on women and girls	0,0,0,*	0,6,1,*	4,10,7,10	6,15,10,15	Milestone marginally off track. / 2014 results to date are 1,9,6,5. / Recruitment of Gender Theme Leader and planning for 2015 Migration and Gender conference should accelerate progress.

Key Points: MOOP’s stream of Regional Research Projects is substantially complete and has generated interesting results in areas such as the capacity of South Asian Labour Attachés to serve migrants, and the lack of preparedness to receive migrants of some local authorities in South Africa.
MOOP research is improving understanding of choices made by poor people migrating into low paid, insecure occupations such as construction and domestic work. In short, these are risky but important, route to longterm improvements in living standards, and therefore development benefits should be kept in perspective when public debate focusses on the risks.
MOOP qualitative research in Ethiopia gives new insights into long-term strategies by migrants to better their lives, including multi-step migration and investing in businesses back home. Few migrants remitted money back to parents but a majority of migrants and families viewed migration as positive because it offered better prospects for exiting poverty than other options. This helps explain why migration into seemingly degrading situations continues. Ghanaian migrants similarly maintain positive attitudes to migration, despite mostly ending up in slums and informal jobs.
Indonesian quantitative and qualitative data show the importance of gender roles in determining migration: migration recruitment practices and flows are heavily gendered and having many dependents lowers the likelihood to migrate only for women.
Response to issues raised in previous reviews: MOOP’s ‘value added’ and coherence (over the sum of its parts; and addionality over what consortium members would deliver without RPC) is becoming more apparent. Portfolio-wide efforts to improve financial management and research quality have contributed to this. This should continue.
Despite considerable efforts, MOOP has not been successful in its recruitment of a Gender Theme Leader.
Recommendations
- Gender: MOOP will recruit a Gender Theme Leader to create and manage a network of gender advisers across the MOOP consortium and maximise gender analysis in programme delivery and outputs.
- Financial management: To further assess MOOP’s additionality, MOOP will collect budget information on degree to which partners are reliant on MOOP/DFID funding as a proportion of overall budgets.

Output Title	Improved engagement and dialogue with key stakeholders (Policy Makers, Media, NGOs, Migrant organisations and Research users) to promote research uptake and understanding of research findings related to internal and regional migration and poverty linkages.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
2.1 # of external events attended by MOOP partner staff in which pro-poor approaches to regional and internal migration are discussed.	20	40	70	100	Milestone on track. / 2014 performance data records that 146 MOOP staff attended external events during 2013-14 in which pro-poor approaches to internal and regional migration were discussed.
2.2 # of key stakeholder representatives participating in MOOP external facing events; % surveyed and % of these reporting enhanced understanding of pro-poor approaches to migration	30	200	600, / 60%, / 70%	900, / 75%, / 75%	Milestone on track. / To date, 495 key stakeholder representatives had attended MOOP external facing events. / Data is collected through post event attendance lists and feedback surveys. The % indicator has been added to incentivise MOOP partners to collect feedback at the end of MOOP external events.
2.3 # of MOOP external facing events sensitive to gender dimensions of migration	0	7	50	75	Milestone on track / To date, 42 externally facing MOOP events have included a focus on the gender dimensions of migration. / In 2013-14, 12 of the 18 MOOP external events included a focus on the gender dimensions of migration. This 2/3 coveage is expected to further increase with the recruitment of the Gender Theme Leader in the core team.

Key Points: MOOP’s engagement with policy makers has led to a clear influence on policy in Bangladesh, Ghana, Singapore and South Africa. ARI (Singapore) convened an unprecedented joint meeting of NGOs, Ministry of Manpower and academics to discuss concrete policy recommendations on the employment agents’ industry and improving employment conditions for foreign domestic workers. In Ghana, CMS serves on the inter-ministerial committee on migration and has continued to help draft Ghana’s national migration policy, which draws on MOOP research and has a strong pro-poor flavour.
Both partners and Secretariat contributed to MOOP’s raised profile in international fora, including through participation in the UN High Level Dialogue on International Migration and Development, a joint UN/Columbia University Expert Group Meeting on youth inequalities and marginalisation, UN Global Forum on Migration and Development, and high level discussions around post-2015 framework. In January 2014 ACMS signed a Service Level Agreement with Statistics South Africa to provide a framework for organisational collaboration to improve quality of data on migrant labour in South Africa.
Response to issues raised in previous reviews: MOOP has increased production of synthesis outputs including newsletter. It has also strengthened routine collection of feedback on MOOP events and products. This positive trajectory should continue.
Recommendations
Research communication, research uptake, and policy engagement; MOOP will continue to consider new and innovative approaches to research communication, increasing greater use of ‘voices of the poor’ style approaches that directly bring the voices and stories of individual migrants into MOOP outputs and publications. DFID will share examples of approaches by other partners.

Output Title	Strategic capacity of consortium members to conduct research, and of key stakeholders in government and civil society to participate in policy framing processes is enhanced enabling them to collectively shift the terms of the debate.
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator	Baseline / 2011	Milestone 1 / 2013	Milestone 2 / 2015	Milestone 3 / 2017	Progress
3.1 # of interns reporting improved capacity to do research (or engage with it)	0	4	11	17	Milestone on track. / To date, 8 Interns report an improved capacity to do, or engage with, migration research.
3.2 # of consortium partner staff reporting improved capacity as a result of attending a training course, placement or fellowship	0	5	40	50	Milestone on track. / To date 33 partner staff report an improved capacity. / Data is generated from reviews undertaken by partners in July/August each year, and details provided to MOOP secretariat. The number is the cumulated number of individual-event duplets, and excludes secretariat members.
3.3 # of boundary partners and key stakeholder representatives who report improved capacity after participation in consortium training sessions	15	50	300	400	Milestone on track. / 273 boundary partners report improved capacity. This year MOOP has worked to improve the method and quality of feedback following outward facing events.

Key Points
Highlighted achievement: Two former interns – to ARI and RMMU – report that their internships were critical in receiving offers of employment from organisations working on international development and migration issues.
The small budget allocation for internships has constrained applications as funds do not cover all costs for an internship, and therefore applicants need to find additional resources to undertake an internship. This may have been a barrier to access by potential developing country applicants.
Responses to issues raised in previous review: Last year’s review recommended that MOOP adopt a planned approach to capacity building and exchange. A major focus this year has been financial management capacity as well as quality-focussed work on research methods and research production. This should continue.
Recommendations
Internship strategy: MOOP will re-examine the existing funding and strategy, and – if necessary - seek DFID’s approval for a revised approach and increased budget for internships.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance
Key cost drivers are direct and indirect staff, travel costs, research consumables, and supervision and transport costs. The MOOP is fully aware of the need to maximise VfM within the planned budget. Spending on research is on track against financial forecasts.
VfM performance compared to the original VfM proposition in business case
VfM performance is in line with expectations; overall the programme is on track to meet targets, and its intended purpose (to generate new evidence and improve analysis of existing evidence on the factors that mediate the impacts of migration on poverty is used and applied by policy makers and other relevant stakeholders to address international development goals and reduce poverty) is still a good fit.

Assessment of whether the programme continues to represent value for money
The programme continues to offer good VfM. The consortium has a range of processes and safeguards to ensure that VfM is assured throughout the programme cycle. The consortium is striving to strengthen all three elements of DFID’s value for money framework. A peer review (including gender review) has been set for all new proposals. This will include reviewing the profile/experience of proposed researchers for each project; proposed budgets; and scrutinising the links between research and research uptake elements, timelines, milestones and deliverables. Expenditure on overheads for partners and Secretariat has been reviewed to ensure that these result in efficient and effective research and research uptake. DFID has agreed the revised budget for years 4, 5, and 6.
Quality of financial management

The University of Sussex is responsible for the overall financial management of the programme and its Financial regulations ensure proper and efficient use of resources and effective internal control.
In the last year the MOOP’s financial managers have taken strong action to improve Consortium-wide financial management systems. MOOP itself notes in its annual report that:
“Management and financial systems have been completely overhauled and there has been closer budgetary oversight and adherence to the Framework Agreements between the Partners and the Secretariat. The problems in reconciling accounts for Year 1 have been addressed, and full reconciliation was achieved for Year 2”.
DFID payments are made on claims as per the contract on a quarterly basis.
The University of Sussex agrees funding with partners based on workplans, and partner budgets. Workplans and financial reports are scrutinised by MOOP secretariat team and payment is made in arrears. This year two part-time appointments (Executive Director & Programme support officer) have greatly strengthened financial scrutiny and accountability across the programme.
The programme is on track against latest forecasts. MOOP is confident that the current agreed profile remains achievable. DFID will monitor this closely given that DFID has approved a revised financial profile for the remainding years of the programme.
The contract value with the University of Sussex is £6,425,233. During financial year 13/14 MOOP spent £893,155. To date the programme has spent £2,758,446.

Date of last narrative financial report	31st Septmtember 2014
Date of last audited annual statement	31st September 2014

E: RISK

Overall risk rating: Low

Overview of programme risk

There are a number of low- to medium-level risks associated with the programme, with overall risk changing little over the review period. From our review of the orginal project document and of additional emerging factors, key risks are:

Policy makers do not take account of findings due to factors outside control of the project. The consortium is seeing success in engaging policy making audiences during research definition and production, and maximising dissemination of funded research in order to give policy makers the best possible opportunity to use outputs.

Capacity building will not be effective given the lack of evidence of what works and the small scale/scope of the capacity building initiative – this risk persists and it will be important to monitor and track MOOP’s evolving strategy and progress – by the Secretariat, by DFID and by the CAG.

Lack of in-country capacity constrains ability to carry out high-level research and primary data-gathering. (Medium probability, medium impact). This risk has led to the dropping of the global qualitative research project in Bangladesh in favour of focussing capacity on new phase-2 projects that are better integrated with the revised research programme.

Outstanding actions from risk assessment
No outstanding actions. Risks are being monitored and mitigated. This should continue.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The programme is progressing according to schedule.
Performance of partnership
DFID is represented on the CAG. DFID has appreciated the consortium response to the recommendations made in last year’s appraisal. Work plans, objectives, performance measures, resource allocation and review processes have been shared openly and collaboratively with DFID.
MOOP and DFID have proved their commitment to learning and being open when programmes are not achieving their stated aims, and being prepared to adjust as necessary e.g. the AMADPOC partnership.
Asset monitoring and control
MOOP’s main assets are its staff and partners. Through its prudent management of the programme, MOOP has ensured that both have been deployed effectively.

G: CONDITIONALITY

Update on partnership principles
Not applicable.
H: MONITORING & EVALUATION

Evidence and evaluation: MOOP’s core objective is to deepen the understanding of migration within and between developing countries in order to better equip migrants, organisations supporting them and policymakers with evidence that informs their efforts to reduce poverty.
MOOP’s revised research strategy and work plan will consolidate this work and they are integrating their research uptake strategy more fully with the research programme. The latter will continue to stress producing accessible knowledge products, in a variety of formats and media, and exploring ways to bring evidence to the attention of policy makers and build better demand for evidence use.
The progress of the programme will be monitored annually using the logical framework’s indicators.

Monitoring progress throughout the review period
This annual review was carried out during October-November 2014, by a team of four DFID staff (One A1 leading, two A2s including an SDA, one B2).
The DFID review team conducted a desk-based review of key documents, including a detailed report of the programme’s performance over the review period submitted by the partners, and reviewing key research and communication outputs.
Two DFID staff visited the MOOP Secretariat in Sussex. MOOP presented their Annual Report and progress over the review period. Following discussion, MOOP and DFID agreed a commentary on progress against logframe indicators; any necessary changes to the logframe; and summary recommendations from this review.
The Annual Review report was shared in draft with MOOP and will be presented at the next CAG meeting, with responses and follow up to be documented.
Quest Documents :
2013 DFID Annual Review Report : Quest No 4237004
Email from PE Oct 2014 : Quest No 4689130
Revised budget & approval : Quest no 4597564
MOOP Annual Report Oct 2013- Sep 2014 : Quest No. 4721835