Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Supporting Tax Transparency in Developing Countries
Programme Value: £6 million		Review Date: 20/11/2014
Programme Code: 203564	Start Date: 26/07/2012	End Date: 30/09/2016

Summary of Programme Performance
Year	2014	2015	2016
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review

In its first year of operation the tax transparency programme has met all milestones but one across its four projects.

Exchange of information (Global Forum and WBG) – The Global Forum and WBG have delivered training seminars and technical assistance to prepare developing countries for joining the Global Forum and for peer reviews. This has helped six countries pass their peer reviews and one country has joined the Global Forum, though more are expected to follow. Three countries have signed the Multilateral Convention and GF/WBG have helped others expand their treaty networks through the signing of tax information exchange agreements.

Transfer pricing (OECD and WBG) – The OECD and WBG have provided technical assistance that has led to five countries agreeing and implementing action plans for legislative changes and administrative improvements for transfer pricing and related controls. Technical assistance has began to be delivered in other countries. The OECD has also responded to a commission from the G20 Development Working Group on the effects of Base Erosion and Profit Shifting (BEPS) in low income countries using technical knowledge gained through the the TP assistance programme.

Tax Inspectors Without Borders (OECD) – A small-scale Secretariat has been established to administer the initiative. The action plan was not complete by the target date of end 2013, but can now be considered to be complete across the 10 actions, with some progress still to be made on four of them. Three deployments have so far been made through the initiative.

Tax incentives for investment (OECD) - Three countries have received reviews of their tax incentives for investment and agreed action plans to implement changes to their tax incentives frameworks.

Summary of recommendations for the next year

Exchange of Information

Over the annual review period, Uganda was the only “new” DFID tier 1 priority country to receive direct tax capacity support from the Global Forum/ WBG to pass its peer review and contribute to meeting the milestones (indicator 1.1). Support was also given to tier 1 countries Ghana and Kenya, but here, support was additional to that provided during the pilot phase of the programme and support has been given to tier 1 countries Pakistan, which has yet to have its peer review, and Liberia. Additionally, South Africa is the only tier 1 country to have expanded on its treaty networks (indicator 1.2) though Kenya and Uganda have taken steps to sign the multilateral convention. For the funding to continue to deliver to DFID priorities, a larger proportion of the work should be directed at, and deliver in, DFID tier 1 priority countries or at a regional level in DFID tier 1 countries. It is nevertheless recognised that support is demand-led and so Global Forum, WBG and DFID (as well as HMT and HMRC) will need to work together to generate demand. The new Africa Initiative launched at the Global Forum at its 2014 Berlin meeting should also help in this regard.

Outcome indicator 3 should be discontinued and deleted from the logframe. Investor surveys have not taken place in programme countries as it is too costly to obtain statistically significant survey results and is not cost-effective or an efficient use of funds to conduct private sector surveys for every project country. WBG will continue to gather anecdotal evidence on private sector perceptions of transfer pricing reforms and feedback results of Kenya and south east Europe surveys to provide evidence of the link between improved transfer pricing and an improved investment climate.

Transfer pricing

Of the five countries that are delivering on transfer pricing actions plans, three are DFID tier 1 priority countries (Ethiopia, Rwanda and Zambia). Though work has also been carried out in tier 1 countries Bangladesh and Liberia (both WBG) action plans have not yet been completed. For the funding to continue to deliver to DFID priorities, work should continue to be directed at, and deliver in, DFID tier 1 priority countries. It is nevertheless recognised that support is demand-led and so OECD, WBG and DFID (as well as HMT and HMRC) will need to work together to generate demand.

TIWB

In order to provide an extra source of funding we recommend that up to 10% (£20,000) of DFID funding be allocated to meet travel and subsistence costs for HMRC to fulfil TIWB missions. This will be disbursed by DFID. It is not expected that this would impact current outputs.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4057257.docx
DevTracker Link to Log frame:	Log Frame not on DevTracker

Outline of the programme

DFID is providing £6m of funding (from 2013 to 2016) to the OECD, Global Forum on Transparency and Exchange of Information for Tax Purposes (referred to as “the Global Forum”) and the International Finance Corporation (IFC)/World Bank Group (referred to as WBG), in order to enhance the capability of tax authorities in partner countries in international tax transparency. The projects are designed to improve tax policy, administration and collection to reduce tax evasion, avoidance and tax base erosion, leading to greater tax revenue and an improved business investment climate in partner countries. There are four outputs to the funding:

- Support for developing countries to adopt and effectively implement transfer pricing rules in accordance with international principles through reviews of legislation, risk assessment and advice on implementation and transfer pricing audit. (OECD and WBG)
- Support for developing countries to participate effectively in international exchange of tax information in line with the international standards of the Global Forum on Tax Transparency and Exchange of Information, including support for securing tax information exchange agreements and preparing for peer review by the Global Forum. (Global Forum and WBG)
- Undertaking reviews of partner countries’ systems for investment tax incentives. (OECD)
- Facilitating the deployment of experienced tax audit experts on a demand-led basis to developing countries by funding a small Secretariat to establish and lead the “Tax Inspectors Without Borders” project. (OECD)

This support is being delivered jointly by the OECD’s Tax and Development Programme (£2.4m), the secretariat of the Global Forum on Transparency and Exchange of Information for Tax Purposes (Global Forum) (£1.6m), and the IFC/World Bank Group (WBG) (£2m).

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

Outcome indicator 1: Numbers of additional tax cases resolved as a result of improved transfer pricing regimes, revised thin capitalisation controls, improved audit skills or through advanced pricing agreements. Milestone 1: Average 3 for each 4 countries

The numbers of resolved tax cases resulting from technical assistance delivered over the annual review period in countries that were not part of the pilot project are not yet available, as there is a time lag while reforms are implemented and cases are administered.

Case figures resulting from the technical assistance delivered to pilot countries, which has continued this year, indicate that the outcome will be met if performance is replicated. In the countries where technical assistance was delivered as part of the pilot project and this year as part of the main programme, 45 cases have been resolved in total for OECD/WBG pilot countries (work delivered in 2013 before current programme): Kenya (13 cases), Colombia (22 cases), Vietnam (8 cases), Zambia: (2 cases). It is difficult to accurately to attribute these successful cases to a given year of support as the support is an ongoing process. However, on the basis that support will be given for up to 3 years including the current year, if one third of these cases are attributed to this year of the programme then the outcome indicator has been met.

Outcome indicator 2: Numbers of tax cases for which information is received from international partners through new information exchange mechanisms. Milestone 1: average 3 for each 4 countries

Following support given by the Global Forum, Uganda has created an EOI unit and has made over 16 information requests and responded to several requests which it has received. This is currently the only available example of information received as a result of new information exchange mechanism. It takes time for EOI to become effective and although previous examples indicate that the outcome indicator will be met, it may take time for this to become apparent.

Outcome indicator 3: % of survey respondents in each country receiving support report that implementation of the Transfer Pricing framework has improved transparency and improved the investment climate. Milestone 1: 4 countries surveyed

The survey for this indicator was not itself part of the programme but was expected to have been carried out by WBG as part of its wider activities and made available for use. This has not taken place. WBG report that the cost to obtain statistically significant survey results is high and that it is not cost-effective or an efficient use of funds to conduct private sector surveys for every project country. As a result the WBG have not completed programme specific surveys that would allow us to properly report on this outcome indicator. Non-programme specific surveys for Kenya and South-East Europe are underway that will assess the effects of transfer pricing reform, but results will not be available until 2015/16 and only Kenya is a project country.

For these reasons it is recommend that this indicator is discontinued for future reviews and instead the results of the Kenya and SEE surveys will inform overall project directions. The WBG should continue to gather evidence in whatever form available on private sector perceptions of transfer pricing reforms.

Overall output score and description

Exchange of information (output score: A+):
- Indicator 1.1 (milestone: 4 countries – Moderately exceeded): The Global Forum and WBG programme provided assistance to six countries (Colombia, Georgia, Botswana, Ghana, Jamaica and the Philippines) that then passed Global Forum peer reviews. Additionally Niger has joined the Global Forum following contact initiated at a GF/WBG led workshop.
- Indicator 1.2 (milestone: 4 countries - Moderately exceeded): Three countries (Gabon, Cameroon, and Philippines) have signed the Multilateral Convention following assistance. Kenya and Uganda have taken steps towards signing. Global Forum have facilitated an increase in South Africa’s treaty networks.

Transfer pricing programme – (output score: A+)
Indicator 2.1 (milestone: 4 countries - Moderately exceeded): Five countries (Cambodia, Ethiopia, Jamaica, Peru and Zambia) have all agreed and are implementing action plans for legislative changes and administrative improvements for TP and related controls.

TIWB (output score: B)
- Indicator 3.1 (milestone: progress action plan by end 2013 – part met) The action plan is essentially complete though further work does need to be advanced on four of the actions. Work was not complete by end 2013.
- Indicator 3.2 (milestone: 3 countries): TIWB deployments have taken place in Ghana, Rwanda (HMRC adviser) and Albania

Tax incentives for investment - (output score: A)
Indicator 4.1 (milestone: 3 countries – Met ): Nigeria, Swaziland and Southern African Development Community (SADC) all received investment reviews, which they are implementing.

Key lessons

There is a clear time lag between the work being done and the milestones being delivered. Although this is recognised in the Logframe assumptions which reflects the reality of the time taken to introduce TP legislation, join the Global Forum or complete a peer review. These are reforms that will deliver their benefits for developing countries over a longer time frame than what can be measured over the first year of a programme.

Key actions

It is proposed that one change be made to the Logframe as a result of the annual review:

Remove outcome indicator 3 due to lack of survey results in programme countries. WBG will continue to collate available qualitative evidence of the impact on the investment climate of transfer pricing reforms.

Has the logframe been updated since the last review?

This is the first annual review of the programme. The Logframe has not been updated since it was approved along with the business case in 2013.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Tax authorities able to exchange information with international peers in line with international standards
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicator 1.1 Number of countries receiving assistance join Global Forum (if they have not already done so) and pass peer review	Milestone 1 - 4 countries	Moderately exceeded. Columbia, Georgia, Botswana, Ghana, Jamaica and the Philippines all passed peer reviews following Global Forum/WBG support. Niger has joined the Global Forum.
Indicator 1.2 Number of countries expanding their information exchange treaty networks to include key regional/international partners	Milestone 1 – 4 countries	Met. Gabon, Cameroon, and Philippines have all signed the Multilateral Convention and so have increased their treaty networks. As has South Africa who has signed two TIEAs facilitated by the GF. Burkina Faso, Kenya and Uganda have all taken steps towards signing but have yet to do so.

Key Points

Indicator 1.1:
The Global Forum Secretariat and WBG have delivered three successful regional training seminars (in Turkey, Cameroon and EAC) to inform participants about the work of the Global Forum and prepare them for the peer review process. Countries involved were Bangladesh, Belarus, Benin, Bulgaria, Burundi, Congo, Cote d’Ivoire, Kyrgyzstan, Mali, Moldova, Niger, Rwanda, Tajikistan and Tanzania. The seminars include an outreach component for potential new member countries which has led to close contact with several countries interested in learning more about becoming members (the identities of these countries have not been publicly disclosed at this early stage of the process). Although so far only Niger has joined the Global Forum, the Secretariat and the WBG expect some to do so over the next year.

The Global Forum and the WBG delivered pre-phase 1 or phase 2 technical assistance (i.e. to help identify the actions that countries would need to take to meet the requirements of either phase 1 or phase 2 of the Global Forum peer review process) to developing countries. This has taken the form of either an assessment of their relevant laws and regulations or direct assistance through national seminars followed by meetings with stakeholders. Six countries which received support in the lead up to their peer reviews, successfully passed those peer reviews. This includes Colombia and Georgia passing their Phase 1 review, Botswana passing a supplementary review to move to Phase 2 and Ghana, Jamaica and the Philippines passing Phase 2 reviews. WBG has separately provided assistance to Azerbaijan to prepare for its phase 1 review.

In 2013, technical assistance was provided to the Philippines to prepare for the peer review process and to build an EOI Unit. In 2014 the country reported a recovery of more than US$1 million from just two cases as a result of exchange of information from treaty partners.

There is a clear time lag between the work being done and the milestones being delivered. For example, Niger is the only country that attended Global Forum seminars in the annual review period to have join the Global Forum so far. The experience of the Global Forum and WBG is that decision-making at ministerial level is often a protracted process, especially in developing countries where awareness of information exchange at senior levels is often lacking. Anecdotally, its possible that the emergence of the Automatic Exchange of Information standard has caused some countries to pause before signing up in the belief that it would not be possible to join the Global Forum with a view to beginning information exchange on request without then being compelled also to implement automatic exchange of information – with a risk of blacklisting or other sanctions if they were unwilling or unable to do so, even though the G20/Global Forum have confirmed that this is not the case. The possibility of a timelag was acknowledged in the Assumptions section of the logframe (but not specifically the issue around AEoI).

With respect to the time lag between support being received and peer reviews occurring, this is to some extent a reflection of the strictures of the peer review schedule, which is set in advance and relatively long (countries can wait for up to 2 years for their reviews). Global Forum and WBG have given support to countries that have yet to undergo their peer reviews: Burkina Faso, Cameroon, Gabon, Lesotho, Pakistan, Senegal and Uganda, all of which have their peer reviews scheduled for appraisal in 2015.

Indicator 1.2:
The regional and national seminars conducted by the Global Forum secretariat have included sessions on expanding their EOI relationships, with a focus on signing the Convention on Mutual Administrative Assistance in Tax Matters (MAAC), which allows countries to do exactly that. Over the last 12 months, Cameroon, Gabon and the Philippines have all signed the MAAC. It is hoped that Kenya will sign the MAAC shortly and that Uganda will sign a letter of intent. In preparation for their peer review, Ghana has also taken step to improve their EOI relationships by signing more bilateral tax information exchange agreements.

Additionally, South Africa has signed Tax Information Exchange Agreements (TIEAs) with Belize and the Cook Islands during this review period, both facilitated by the Global Forum. Global Forum has also assisted Ghana and,worked with Pakistan, in increasing their EOI relationships.

Following support given by the Global Forum, Uganda has created an EOI unit and has made over 16 information requests and responded to several requests which it has received. The unit has been engaged in training to help auditors across Uganda understand how to make information requests.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not relevant as this is the first annual review.

Recommendations

Over the annual review period, Uganda was the only “new” DFID tier 1 priority country to receive direct tax capacity support from the Global Forum/ WBG to pass its peer review and contribute to meeting the milestones (indicator 1.1). Support was also given to tier 1 countries Ghana and Kenya, but here, support was additional to that provided during the pilot phase of the programme. Support has been given to tier 1 countries Pakistan and Liberia who have yet to have their peer reviews. Additionally, South Africa is the only tier 1 country to have expanded on their treaty networks (indicator 1.2) though Kenya and Uganda have taken steps to sign the Multilateral Convention. For the funding to continue to deliver to DFID priorities, a larger proportion of the work should be directed at, and deliver in, DFID tier 1 priority countries or at a regional level in DFID tier 1 countries. It is nevertheless recognised that support is demand-led and so Global Forum, WBG and DFID (as well as HMT and HMRC) will need to work together to generate demand. The new Africa Initiative launched at the Global Forum at its 2014 Berlin meeting should also help in this regard.

Output Title	Tax authorities able to tackle profit shifting by multinational enterprises by effective implementation of international standards for transfer pricing and related compliance controls
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Number of countries agreeing and implementing action plans for legislative changes (where required) and administrative improvements for transfer pricing and related controls	Milestone 1 - 4 countries	Moderately exceeded. Cambodia, Ethiopia, Rwanda, Jamaica, Peru and Zambia have all agreed and are implementing action plans for legislative changes and administrative improvements for TP and related controls.

Key Points

Following OECD and WBG technical assistance, tax authorities have agreed and are implementing action plans for legislative changes (where required) and administrative improvements for transfer pricing and related controls in Cambodia, Ethiopia and Zambia (all joint OECD/WBG), Jamaica, Peru (OECD only). WBG have also provided TP support to Georgia, Azerbaijan, Armenia, Bangladesh and Liberia. Colombia, Kenya, Vietnam and Ghana (which previously received technical assistance under DFID’s funding of the pilot that preceded this programme) have continued to receive ongoing advice under this programme to assist them in introducing legislation and applying it through TP cases. Scoping missions have been conducted in Nigeria (both) and Myanmar (WBG).

The legislation introduced as a result of technical assistance is closely aligned with international standards to assist tax administrations in improving transfer pricing compliance. Technical assistance increases the ability of tax authorities to carry out TP audits, increases revenues and increases the awareness of TP rules among taxpayers. Colombia introduced secondary legislation on transfer pricing in late December 2013 following OECD/WBG support, and it is anticipated that Cambodia, Ethiopia, Jamaica and Zambia will introduce transfer pricing legislative changes in either 2014 or 2015.

These programmes are not just limited to addressing transfer pricing but also address related multi-national taxation issues such as thin capitalisation, tax treaty abuse and Permanent Establishment issues, so that a holistic approach is taken to improving tax collection.

The OECD has this year responded to a commission from the G20 Development Working Group on the effects of Base Erosion and Profit Shifting (BEPS) in low income countries, setting out recommendations for how best to tackle BEPS. This work progressed UK/DFID objectives to tackle tax avoidance in developing countries through the G20. The technical knowledge used to draft the report was gained through technical assistance delivered through DFID funding.

The programme includes funding for a project on how to address the difficulties that developing countries experience in obtaining suitable data on “comparable transactions” for use in transfer pricing, which was commissioned by the G8 under the UK’s Presidency in 2013. The OECD published a paper in March setting out approaches to address the issue, seeking comments. The WBG is also conducting a study on comparability in a draft paper. Both papers will inform the work of the OECD/WBG under the G20 mandate to produce a toolkit on Comparability.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendations

Of the five countries that are delivering on actions plans, three are DFID tier 1 priority countries (Ethiopia, Rwanda and Zambia). Though work has also been carried out in tier 1 countries Bangladesh and Liberia (both WBG) action plans have not yet been completed. For the funding to continue to deliver to DFID priorities, work should continue to be directed at, and deliver in, DFID tier 1 priority countries. It is nevertheless recognised that support is demand-led and so OECD, WBG and DFID (as well as HMT and HMRC) will need to work together to generate demand.

Output Title	Tax Inspectors Without Borders (TIWB) secretariat established and facilitates expert deployments to developing countries
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Progress with TIWB secretariat plan implementation, including establishment of databases of experts, standardised deployment processes and toolkits for experts, receiving organisations and donors	Completion by end 2013.	Part met. The action plan is essentially complete though further work does need to be advanced on four of the actions. Work was not complete by milestone of end 2013.
Number of country deployments of experts facilitated by TIWB	Milestone 1 – 3 countries	Met. TIWB deployments have taken place in Ghana, Rwanda (HMRC adviser) and Albania

Key Points

A small-scale TIWB Secretariat has been established within the OECD Task Force on Tax and Development. The TIWB feasibility study outlined 10 actions for the Secretariat to complete by end-2013. Good progress has been made on all 10 actions, though work needs to be advanced on four of them:

- The database of retired tax audit experts has been established, but with low numbers of high quality experts.
- There is an initial published version of the TIWB website but the extended version is yet to go “live”. OECD report that it will do so shortly.
- OECD have established a network of contact points in partner administrations, to act as a liaison to request secondment of serving audit experts but the network is not yet complete as not all potential partner administrations have responded yet.
- TIWB pilots are underway but still ongoing.

The action plan was not complete by the milestone completion date of end 2013, an ambitious target given it was only two months from the start date of the programme (though six months from the approval of the business case).

The following deployments are in place:
- Ghana - 2 short term visits for audit assistance on transfer pricing
- Rwanda - 2 short term visits for audit assistance on transfer pricing. Tax expert provided by UK (HMRC). DFID supplied additional funding to meet cost through iFUSE.
- Albania – Audit assistance on transfer pricing. Programme prepared and deployment agreement in place and signed by parties, will start 1 January 2015.

The OECD report that other donors have not been as forthcoming as expected in providing assistance for TIWB missions and this is hindering the progress of some missions. In order to provide an extra source of funding we recommend that up to 10% (£20,000) of DFID funding be allocated to meet travel and subsistence costs for HMRC to fulfil TIWB missions. This will be disbursed by DFID. It is not expected that this would impact current outputs.

Summary of responses to issues raised in previous annual reviews (where relevant)

N/A

Recommendation

In order to provide an extra source of funding for TIWB missions we recommend that up to 10% (£20,000) of DFID funding be allocated to meet travel and subsistence costs for HMRC to fulfil TIWB missions. This will be disbursed by DFID. It is not expected that this would impact current outputs.

Output Title	Partner country governments able to assess VFM and governance of investment tax incentive regimes
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of countries receiving investment reviews and agreeing action plans for changes to investment tax regimes	3 countries	Met – Nigeria, Swaziland and Southern African Development Community (SADC) all received investment reviews, which they are implementing.

Key Points
Three countries have received reviews of their tax incentives for investment and agreed action plans to implement changes to their tax incentives frameworks. They include:

Nigeria: Analysis of Nigeria’s tax incentives was conducted as part of the OECD Investment Policy Review (IPR) for Nigeria and recommendations on tax incentives were made as part of the IPR implementation plan. Discussion is underway on how the OECD can assist the Nigerian government in implementing the IPR recommendations, including measures to simplify the tax system and broaden the tax base through elimination of wasteful tax incentives.

Swaziland: Tax incentives for investment have been evaluated for their effectiveness and cost-efficiency through an analysis of Swazi corporate tax data designed to evaluate alternative tax policy scenarios that could generate revenue at least equivalent to the one mobilised by the current system, while still being investment-attractive. The study recommended policy choices aimed at removing preferential corporate tax rates, repealing tax allowances and ironing out tax rate differentials to improve the neutrality and equity of the tax system. Further, a cost-benefit analysis of the textile industry was conducted to compare and contrast the costs sustained by the government due to fiscal tax incentives against the beneficiary impacts of the sector. The analysis showed that the government costs to incentivise the textile industry are twice as high as the realized “benefits”. The Swazi government has been acting upon the OECD recommendations. The suggested policy changes were submitted by the Ministry of Finance to the Cabinet and are currently under discussion and consideration for implementation.

Southern African Development Community (SADC) Regional Investment Policy Framework (IPF): OECD worked with SADC on the development of their Regional Investment Policy Framework (IPF) and conducted in-depth analysis of the tax incentives regimes of the 14 individual SADC Member Countries, including Angola, Botswana, Democratic Republic of Congo, Lesotho, Malawi, Mauritius, Mozambique, Namibia, Seychelles, South Africa, Swaziland, Tanzania, Zambia, Zimbabwe. The work revealed the challenges that individual SADC member countries face when offering tax incentives and the long-term costs from regional tax competition. Working through the SADC presents a rare opportunity to forge regional cooperation on tax incentives. As part of this work an implementation roadmap of the regional investment reform agenda will be developed, focusing on actionable and practical steps to improve the investment climate across the SADC area. SADC is committed to implement the recommendations identified in the Regional Guidance and to integrate them into national development plans and strategies. This will be done with involvement of the SADC Finance Ministries, in addition to the SADC member state officials delegated to the SADC Sub-Committee on Investment.
Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
None
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers remain the same. Identified in the business case they remain salaries of technical experts, plus overheads, travel expenses and trust fund expenses. Salaries are set according to the relevant scales of the organisations in question.

VfM performance compared to the original VfM proposition in the business case

The business case identified directly attributable increases in tax revenue as the primary assessment of the VFM for the intervention. It estimated the directly attributable tax revenue increase from the programme to be $160m (£106m) against costs of £6m, implying a direct cost/benefit ratio of approximately 17x. This is however based on an extrapolation from a very small number of cases and it is likely that benefits from individual interventions will vary widely and the estimate of total benefits across the programme should be regarded as having a wide confidence interval.

In 2013, technical assistance was provided to the Philippines to prepare for the peer review process and to build an EOI Unit. In 2014 the country reported a recovery of more than US$1 million from just two cases as a result of exchange of information from treaty partners. However, EOI takes time to be effective and is unlikely in most cases to lead to major increases in revenue over the short term.

The examples given in the business case of revenue accrued from transfer pricing legislative changes (Colombia increasing revenues from US$3.3m in 2011 to US$5.83m in 2012 and Kenya increasing tax revenue by an additional US$12.9m) offer a guide, albeit at the high end, of the likely revenue returns from the transfer pricing technical assistance programme though no further revenue returns are yet attributable from the last year of the programme.

Assessment of whether the programme continues to represent value for money

Although some returns of revenue attributable have been recorded, including $1 million from the EOI technical assistance in the Philippines and the TP gains delivered during the pilot phase, many of the reforms implemented as a result of transfer pricing work are yet to bear fruit.

Direct results from programmes delivered to date will take time to be realised as reforms in country are implemented and revenue returns accrue. In many cases the full impact of support will only be measurable after the lifetime of the programme (eg impact on revenues of improvement in exchange of information and continued transfer pricing administration).

Quality of financial management

Funding for the work by the OECD and Global Forum is via the Tax and Development Programme, which is a standing part of the OECD’s regular Programme of Work and Budget (PWB). The OECD/GF will report to the OECD Development Assistance Committee (DAC) and the Committee on Fiscal Affairs (CFA) on their financial arrangements in January, after which they will report to DFID. WBG have also arranged to submit a financial report on their programme spend to coincide with the OECD/GF in January, at which point we will be able to assess the quality of financial management for the programme.

The OECD and Global Forum’s annual accounts are certified by auditors. The 2013 accounts have been closed and certified by the auditors. The 2014 accounts will be certified in 2015.

WBG will undergo a formal audit at the end of the programme cycle, which is 2016.

Date of last narrative financial report	OECD/GF/WBG - Expected in January 2015
Date of last audited annual statement	OECD/GF/WBG - Expected in January 2015

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

Risk: Tax authorities in partner countries receiving assistance have insufficient capacity or technical skills to implement recommendations, or that the necessary senior management support is absent.
Impact: Medium,
Likelihood: Medium.
Mitigation: These risks can largely be mitigated by ensuring that support is only given to tax authorities where senior backing has been given and by proceeding with technical assistance in a properly diagnosed, planned and sequenced manner on a case-by-case basis to maximise impact.

Comment:
The OECD reports that to ensure there is an adequate commitment to provide resources and capacity before starting assistance, they agree a customised ‘framework document’, which specifies the commitments programme countries are expected to make, including ensuring that they commit resources to reform and to implement that reform. Support has been scaled-down to a country where it was considered that the requisite political commitment to reform is lacking (Rwanda), and support to another country has explicitly been made conditional on demonstrating commitment to making requisite legislative change (Cambodia, which has demonstrated that commitment).

The Global Forum report that they recognise the risk as a challenge and many of the countries they work in lack adequate numbers of trained and experienced staff. They try to support countries in ensuring that they have the right people and tools through their ongoing training activities, and help them develop tools such as work manuals and in drafting and reviewing legislation.

Risk: Political interference in the provision of assistance or the implementation of action plans, driven by the potential impacts on vested interest.
Impact: High,
Likelihood: Low,
Mitigation: This risk can largely be mitigated by ensuring that appropriate senior/political support exists for reform before proceeding with any intervention.

Comment:
The OECD report that they have not yet encountered senior resistance to implementation. Resistance has instead been encountered at an administrative level (for example, turf-wars between head office and local offices). Their programmes include assistance in designing administrative structures to address such issues. As mentioned above, actions are taken to ensure that the requisite support and buy-in is in place, and that commitment to implementation is made.

Although the Global Forum does not come across cases of political interference they do recognise that making a commitment to and subsequent implementation of the Transparency and EOI standards is a political issue which calls for political leadership. This is one of the reasons why the “Africa Initiative” was launched in October 2014 This has an overarching aim of engaging political leaders and opinion leaders in Africa to involve them in the transparency and exchange of information agenda.

Risk: Shortage of technical experts/difficulty in recruiting experts to carry out the programme in full.
Impact: Medium,
Likelihood: Low,
Mitigation: This risk can be mitigated by ensuring appropriate advertising of the posts and if necessary mobilising existing tax expert networks in the OECD and elsewhere to ensure relevant experts are made available.

Comment:
Difficulties in engaging sufficiently experienced expertise in a very competitive market represents a real obstacle to achieving expansion of the programme. This has been mitigated to an extent by the close working between WBG and OECD which has provided a wider pool of expertise to contribute to each programme. Co-ordination with TIWB also ensures an effective use of resources. But for TIWB, a challenge remains in finding a high quality standard of experts for TIWB missions as not all donors have been forthcoming in providing tax experts and complications have arisen in sourcing retired experts. OECD is rethinking how tax experts can be sourced.

Outstanding actions from risk assessment

No outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme has delivered to the planned timeframe, which is measured through the Logframe with the exception of the TIWB element, which has delivered its workplan but not to the end of 2013 milestone.

Performance of partnership (s)

DFID partners’ expertise gained through technical assistance work has been helpful this year in making policy through the G20. The OECD, Global Forum and WBG have all delivered and contributed to reports on BEPS in Low Income Countries and AEOI roadmaps which DFID have supported as co-facilitator of the DRM workstream of the G20 DWG. Their expertise will continue to be valuable in delivering the G20 agenda over the course of the programme.

Asset monitoring and control

DFID hosted an annual review meeting with all three partners to discuss their work over the last year of the programme and their plans for next year. DFID officials are also in regular contact with partners about this programme and other work and also sit on the TIWB steering committee.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The survey for outcome indicator 3, was not itself part of the programme but was expected to have been carried out by WBG as part of its wider activities but made available for use. This has not taken place, with the WBG reporting that the cost to obtain statistically significant survey results is high and that it is not cost-effective or an efficient use of funds to conduct private sector surveys for every project country. Non-programme specific surveys for Kenya and South-East Europe are underway that will assess the effects of transfer pricing reform, but results will not be available until 2015/16 and only Kenya is a project country. For these reasons we have recommended that outcome indicator 3 should be discontinued and deleted from the logframe. WBG will continue to gather anecdotal evidence on private sector perceptions of transfer pricing reforms and feedback results of Kenya and south east Europe surveys to provide evidence of the link between improved transfer pricing and improved investment climate.

There is a clear time lag for some of the indicators, notably output indicator 1.1, 1.2 and 2.1 where the full impact of the assistance is not realised in the same reporting year as the assistance itself.

Monitoring progress throughout the review period

All partners submitted a report of activities in advance of the annual review. DFID then hosted an annual review meeting with partners to discuss their work over the last year and plans for next year and question them on the reports. There has been follow up since the meeting to gain additional information and to make clarifications.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process