Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Business in the Community: Private Sector Engagement Programme
Programme Value: £750,000		Review Date: 15 July 2014
Programme Code: 203417	Start Date: 15 July 2013	End Date: 15 June 2018

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	Low

Summary of progress and lessons learnt since last review
During its first year, the partnership with BITC has shown itself to be an effective mechanism for increasing insight and understanding for business on how they can best assist during humanitarian emergencies across the world:

The Minister of State presented UPS with the inaugural BITC International Disaster Relief Award at the BITC Responsible Business Awards in July. BITC International and Communications Teams produced case studies on the shortlisted businesses for the International Disaster Relief Award which have been circulated across the business community using BITC networks.

During April and May, the BITC International Team, working with an independent research consultant, sent out the online surveys for business and NGOs to help produce a 2014 baseline of business engagement in international disaster relief. The qualitative one to one surveys also took place in April, May and June. 44 businesses and 23 NGOs participated in the surveys (with a target of 50 businesses and 25 NGOs).

The panel discussion on Private Sector Engagement in Humanitarian Aid on 23rd April 2014, highlighted the BITC/DFID programme and opportunities. Over 100 people were in the room and over 200 people attended online. This event holds the ODI record for number of people engaged online for the full length of the event (180 online).

Summary of recommendations for the next year

The Business Case and logframe will be reviewed after year one, in line with feedback from businesses as to the challenges they face engaging with the humanitarian community. This should be completed by end October 2014.

DFID should investigate whether there are priority organisations which they would like to target through this mechanism, increasing engagement internally to private sector department and economic development teams to ensure DFID maximises the strategic value of the programme. This should be completed by end October 2014.

- BITC and DFID should investigate opportunities to align development of its matching tool with OCHA’s work in the same area. This should be completed by end September 2014.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	203417
DevTracker Link to Log frame:	203417

Outline of the programme

The UK will provide up to £755,000 over a 5 year period to Business in the Community to help improve the coordination and effectiveness of the UK private sector when they respond to humanitarian emergencies.

The UK Government’s humanitarian policy ‘Saving lives, preventing suffering and building resilience’ recognised that humanitarian need is likely to continue to grow. The systematic use of the private sector in partnership with humanitarian actors will go a long way to help meet these challenges.

One of the seven goals the UK Government set itself for improving the effectiveness of UK humanitarian support was making themselves a network enabler that supports greater partnerships within the humanitarian sector, including with businesses. In so doing, it recognised the invaluable role that the private sector has to play as a donor of both resources and expertise, and how it can operate in partnership with humanitarian actors to save lives.

There has however been a growing sense within the humanitarian sector that, beyond monetary donations, there is insufficient guidance, support, and regulation to guarantee quality humanitarian support from businesses. Moreover, a lack of mutual understanding and communication between humanitarian and commercial actors means that access to the opportunities which humanitarian-business partnerships represent has been severely inhibited. The commercial sector therefore remains, for the most past, an ad hoc responder to major emergencies.

To address this problem work needs to be undertaken to build and disseminate guidance and best practice to businesses on how to respond, and to generate the mutual respect and trust between the private sector and humanitarians necessary to establish collaborative partnerships that can be activated during emergencies.

This programme with Business in the Community (BITC) seeks to address this problem. The Programme entails:
- Producing and disseminating guidance for business on developing their approach to disaster relief.
- Building a matching tool to identify and link businesses’ actual, and potential, contributions and engagement on this agenda with non-government organisations (NGOs).
- Support to BITC in the development of a Disaster Award Category in their Annual Responsible Business Awards.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment A
The BITC Private Sector Engagement Programme widens and improves interest and engagement from the business community in humanitarian emergency response. While still at an early stage the interest and participation by business in the events supporting the programme has been at least as anticipated. When the full feedback is available we hope that this will exceed expections in this first year.

Overall output score and description: A

Initial reporting and feedback from the private sector indicate that BITC have so far successfully fulfilled their objectives in terms of speed of raising the understanding and profile of private sector enagement with humanitarian emergency response. As the winner of the International Disaster Relief award was only announced on 8 July we are still awaiting feedback from the event.

Key lessons

These include:
- One of the biggest obstacles for business in engaging with the humanitarian community is knowlegedge of how to gain access at the right level to the right people in the right organisation. The private sector sees a role for DFID (and BITC) to assist here.
- Many business are keen to use their skills rather than donate cash. To do this they need to build long term relationships with the charitable sector which anticipates emergencies rather than just responds to them. The business community is in need of an honest broker.
- DFID should to maximise the strategic partnership by working alongside BITC with other traditional partners such as UN agencies and NGO’s. Bringing BITC in to talk at DFID led engagement events could bring greater partnership gains in the long run.

Key actions

1. Increase engagement internally within DFID to maximise strategic value of BITC partnership.
2. The business case and logframe will be reviewed and updated one the project has been active for 12 months

Has the logframe been updated since the last review?

No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increased insight and understanding for business on how they can best assist during humanitarian emergencies
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Development and delivery of annual BITC International Disaster Relief Award (Award) as part of the BITC International Disaster Relief programme (IDRP). Milestones 2 and 3 will be repeated annually.	IDRP launch, supported by senior DIFD representative. Announcement of Award at launch: December 2013 / Webinar for business on engagement in programme and Award application process: January 2014 / Webinar for businesses on engagement in programme and Award application process: February 2014 / International Disaster Award winners announced: June 2014	Completed. The Minister of State presented UPS with the inaugural BITC International Disaster Relief Award at the BITC Responsible Business Awards on July 8
Numbers of best practice case studies identified	First set of case studies announced: May 2014	Completed
Online guidance for business on engagement with humanitarian community on BITC website	Develop new IDRP web pages and add new guidance material: March 2014 / Refresh and populate BITC website with Award winners and case studies: May 2014	Completed

Key Points

BITC have successfully established the International Disaster Relief Awards into its well respected Awards programme (independently assured by AD Little). The BITC Awards are the UK's longest running and most respected awards programme championing responsible business. The Awards are rigorously assessed by business peers from all sectors and the IDR award panel was chaired by Lindy Cameron.
This award has allowed DFID to spread the message about the need for the private sector to engage in humanitarian emergencies amongst the private sector. The Awards programme initiates an average of 35,000 unique website users during the Awards season, over 400 senior business leaders and delegates attend the launch of the awards and workshops and over 4,000 senior business representatives attend the gala regional and national gala awards evenings. Our Financial Times partnership ensures separate supplements and national media coverage of the Awards (2013 the Advertising Value Equivalent of the Awards print coverage was £360,000).
The quality of the applicants for the award, and hence also the case studies, have been of a mixed standard but this was to be anticipated with this being the first year of the award and businesses being unsure of what to expect. The case studies of business best practice from this year are expected to provide inspiration for a larger number of applicants next year.
The events and meetings surrounding the awards provided networking opportunities for business, government and NGOs, to increase knowledge, inspire and develop or maintain relationships. The International Disaster Relief Award and the Responsible Business Week event marketed to 20,000 businesses and relevant stakeholders. Over 120 representatives from business, government and NGOs were engaged in discussions around the role of business in international disaster relief via the BITC International Disaster Relief programme. Initial feedback from business indicates they appreciate this opportunity to engage outside the private sector.

As the winner of the International Disaster Relief award was only announced on 8 July we are still awaiting feedback from the event. A survey has been sent to all particpants and we await details of the feedback.

Summary of responses to issues raised in previous annual reviews (where relevant)
n/a

Recommendations

DFID and BITC to look to strengthen the best practice case studies from next years award by starting to target businesses early and using cross DFID knowledge to encourage firms already involved in humanitarian response to apply and share their experiences.

DFID and BITC to review logframe to ensure the programme addresses the emerging challenges businesses face engaging with the humanitarian community.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Formal partnerships between NGOs and businesses are created
Output number per LF		2	Output Score	N/A
Risk:		Medium	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of new partnerships between NGOs and business established which can be attributed to the "Matching Tool"	Working group identified to develop "Matching Tool": May 2014	During the scoping process it has been discovered that OCHA are also working on a matching tool. BITC and DFID are in discussions with OCHA on how to align these programs.

Key Points

Due to the focus, of both DFID and BITC, on Typhoon Haiyan in year one of the grant, BITC has only been able to do minimal preliminary research on the ‘matching tool’ element for the International Disaster Relief programme. Due to the need for substantial demand led research on what the ‘matching tool’ should look like and how it can work to maximise its effectiveness and success DFID agreed to move action and spend under Output 2 to year 2.

During preliminary research for the matching tool BITC discovered that OCHA are also working on a similar type matching tool. BITC and DFID are now in discussions with OCHA on how to align these programs to maximise results.

Summary of responses to issues raised in previous annual reviews (where relevant)
n/a

Recommendations

BITC and DFID should investigate opportunities to align development of its matching tool with OCHA’s work in the same area.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Raised awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response
Output number per LF		3	Output Score	A
Risk:		Low	Impact weighting (%):	40
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Online guidance for business on engagement with humanitarian community on BITC website. Milestone 2 will be repeated annually	Develop new IDRP web pages and add new guidance material: March 2014 / Refresh and populate BITC website: May 2014	Completed
Number of face to face meetings with business targets	First milestone: 20 Meetings by September 2014	Work ongoing and on target
Number of forums and increase in dialogue around importance of engagement and partnerships between NGOs and business. Milestones 2 and 3 will be repeated annually	IDRP launch, supported by senior DFID representative: December 2013 / An event with NGOs on engaging with business : January 2014 / Workshop and Webinar for businesses on engagement in programme and Award application process: February 2014	Completed
Number of businesses showcasing their International Disaster Relief programme in their corporate communications. Milestone 1 will be repeated annually	Factsheet on effective communications for business around international disaster relief programmes completed: September 2014	Work ongoing and on target

Key Points

Throughout the year the BITC Programme Manager and International Director have had one to one meetings or calls with businesses including, but not limited to: Accenture, Alliance Boots, Allen & Overy, APCO, BHP Billiton, Bouygues, BT, Deloitte, DHL, GE, GSK, IBM, IHG, Met Office, Shell and Unilever. BITC has also engaged extensively with NGOs or institutions such as OCHA, ODI, Oxfam, Save the Children, START, Red Cross, World Food Program and UNHCR to raise awareness of how business can assist with humanitarian relief.

On 1 April 2014, the BITC International Team held a two hour workshop as part of the BITC Responsible Business Week taking place 31 March - 4 April 2014. The BITC International Team researched and organised the event which was entitled: International Disaster Relief: How can we move from a reactive to proactive business response. The event took place with maximum numbers (over 60 participants). The audience was a mixture of NGOs, government and business and included: Avios, Bain & Company, BNY Mellon, British Red Cross, DHL, Experian, Foster & Partners, Freshfields, Bruckhaus, Deringer, DFID, Freud Communications G4S, GlobalChain, Grant Thornton, Hogan Lovells, ODI, Impact International, Jaguar Land Rover, Lifesaver Systems, Linklaters, Lloyds Banking Group, London School of Economics, Mabey Bridge, Marsh & McLennan Companies, Novus Property Solutions, PwC, Skanska, UNHCR, ValueCSR and Weber Shandwick. The event had six tables and each discussion had a table leader namely; Jay Aldous, Director, Private Sector Partnerships, UN World Food Program; Dr Jane Cocking, Humanitarian Director, Oxfam; Bob Gibbons, Humanitarian Programme Manager, CHASE, DFID; Kate Gibson, Vice President Corporate Responsibility, IHG; Claire Hitchcock, Director, Community Partnerships Europe & EMAP, GSK and Celia Moore, Corporate Citizenship, Europe, Middle East & Africa, IBM.

Many of the businesses who attended the event went on to participate in the surveys and we hope will consider providing submissions for the 2015 International Disaster Relief Award. Several one to one conversations have taken place with those businesses who are looking to develop their international disaster relief programme. An article based on the output of discussions was written and communicated to attendees and published on the BITC and on Business Fights Poverty websites.

George Gibson the DFID programme lead took part in two well attended BITC webinars.

Summary of responses to issues raised in previous annual reviews (where relevant)
n/a

Recommendations

DFID to continue to work with BITC, their business partners and NGOs/UN agencies to raise awareness amongst business and NGOs of the importance and effectiveness of the private sector in humanitarian response.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The main cost driver is salary costs. Charge out rates and levels of engagement were agreed with partners in advance.

VfM performance compared to the original VfM proposition in the business case

BITC has a broad range of experience in:

- Identifying, articulating and driving the business case responsible and sustainable business action.
- Providing fora to share expertise, information, research and best practice
- Capacity building and partnership brokering, whether in the UK or internationally.

Given its wide network of members and experience of working with a number of other UK Government departments, partnering with BITC has offered DFID the opportunity to effect sector wide change in humanitarian response.

Though difficult to quantify in absolute terms, improving the private sector’s coordination during humanitarian emergencies offers the potential to improve the quality and effectiveness of their responses by ensuring that it is only those resources which are both appropriate and needed which are used. While still early days in the programme it should eventually help make both funding agencies and NGO more aware of the sorts of resources at their disposal, enabling smarter funding decisions.

BITC has unique experience and expertise in convening business which means that their relationship with business are already established, reducing research and business development time and costs for DFID.

Assessment of whether the programme continues to represent value for money

This programme continues to offer value for money, as it capitalises on BITC’s strategic position as a central source of advice and guidance for the private sector and their existing experience of partnering with the public sector to leverage business to address social challenges. In addition to the programme outputs DFID has been able to leverage its relationships to gain valuable advice from BITC in engaging business on wider issues than just humanitarian emergencies.

BITC has delivered all products required against the logframe to date (with the exception of the matching tool where agreement was reached on delayed delivery).

Quality of financial management

The original budget and forecasting profile remain accurate, with the exception of £35,000 for the development of the matching tool moved from year one to year two of the project.

The Accountable Grants has been established. A narrative and financial reporting schedule has been agreed and is being adhered to.

Date of last narrative financial report	May 2014
Date of last audited annual statement	Due September 2014

E: RISK (½ page)

Overall risk rating: Low

Overview of programme risk
The risk is low that the evidence to support further engagement with the UK private sector in this agenda is weak. Initial evidence shows that there is a strong desire amongst business and NGOs to pursue this agenda.

DFID engagement in key events including Ministerial and senior management participation in the International Disaster Relief award has assisted in engaging key stakeholders and all signs point to little difficulty in further engaging the private sector.

Outstanding actions from risk assessment
There are no outstanding actions.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
All relevant timeframes have been met. Due to additional support and advice the BITC International Team gave business in the wake of Typhoon Haiyan, and the DFID resource taken by our response, it was agreed with DFID to move the research and development of the matching tool to year two of the grant. This will not affect the programme meeting its overall timeframe.

Performance of partnership (s)
DFID’s arrangement with BITC is a new partnership and developing mutual undertstanding of working methods has been a key part of the first phase of this programme. Arrangements now appear to be clearly understood by all on both sides.
The level of performance related and financial risk is appropriate. DFID’s partnership with BITC is working well and their access into both private sector partners and NGO’s is excellent.

Asset monitoring and control

The main “assets” are the best practice guidelines and case studies. These are all open source and hosted on the BITC website. The remain available for DFID to use as it wishes.
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The project does not use partner Government systems, so DFID’s Partnership Principles do not directly apply.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
No change in the evidence base. Evaluation planned for later in project.

Monitoring progress throughout the review period

Reporting and monitoring arrangements are included in the Accountable Grant arrangements. BITC has to date provided three quarterly reports. DFID has been engaged with BITC throughout the project.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against VfM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process