Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Yemen Social Fund for Development
Programme Value: £100,000,000		Review Date: January 2015
Programme Code: 201427	Start Date: 10/05/2010	End Date: 31/12/2015

Summary of Programme Performance
Year	2011	2012	2013	2014	2015
Programme Score	n/a	A	A	A	A
Risk Rating	High	High	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

This review was completed on the 31st January as required by DFID’s programme management rules. As such it is published in the midst of a major political and security crisis in Yemen following the resignation of President Hadi, Prime Minister Bahah and the Cabinet on 22nd January, and one which has seen a significant further deterioration in the already challenging environment that SFD operates in. There is also significant risk of a further deterioration including the potential for violent conflict.

This review is based primarily on SFD’s reporting of their progress during 2014, which was discussed at a Joint Donor Review in early December, prior to the current crisis, and primarily reflects their performance up to that date. More recently, SFD have reported that they continue to operate largely as planned despite the current crisis but we are continuing to monitor progress closely. Should we receive information that raises concerns about SFD’s performance, this will be addressed in subsequent reviews.

SFD has made good progress since the last review under exceptionally difficult economic, political and security circumstances. They have exceeded the milestones against all of output 1 (which carries a 70% weighting against DFID commitment), and met most of their milestones against other outputs.

The two most significant challenges faced by SFD over the reporting period were a shortfall in funding and an increasingly difficult security situation. Firstly, of the full planned budget of $1.126 billion, only $780 million has been pledged leaving a funding gap of $346 million. In addition, of the $780 million funds pledged, SFD have so far only received $447 million. A number of donors are failing to disburse as planned: of these, the Saudi Fund for Development is the most significant ($10 million disbursed out of $100 million promised). For the Government of Yemen’s (GoY) contribution, of the $101 million pledged, approximately 75% has been disbursed as of September 2014. We are concerned about the GoY’s ability to deliver the remaining funds given the current political and economic situation. Despite SFD’s proven track record in delivery, the funding gap has frustrated their ability to maintain progress. Overall SFD assess that they were unable to deliver 18% of projects due to the financial shortage, with the highest pro rata rate of non completion in the water and sanitation sectors. Secondly, a deteriorating security situation has caused 4% of SFD projects to be put on hold. SFD are also currently only operating in 300 of 333 districts.

Despite this, SFD has remained resilient and adaptable. They have manged security concerns by continuing to work with locally employed consultants who are well known in communities and understand the local political contexts. They have continued to build on their track record in supporting and influencing government policy and have played an important role in influencing the outcome of the National Dialogue Conference (NDC). SFD report that the Chair of their board, the Prime Minister, remains actively supportive of SFD’s role in delivering development interventions that support poor communities.

At a management level, SFD have continued to demonstate their effectiveness by successfully delivering against a number of additional World Bank grants. SFD maintain a risk management matrix that is included in their annual reporting to donors and they actively monitor and manage risk.

SFD have adapted their reporting style to include more visual evidence of delivery, and now routinely produce films to document their impact. They have begun to use “smart” devices to record progress, embedding within photographic material the timing and GPS coordinates of projects delivered.

Overall reporting remains focused on output and quantitative scores, but we welcome the introduction of more qualitative information and use of case studies. The latter contributes overall to a better understanding of the impact and outcomes of interventions. SFD sex-disaggregates data collection across the majority of interventions. We urge them to continue, and broaden the range of indicators that they disaggregrate wherever possible.

2015 will be an important year for SFD, not only in delivering the remainder of commitments for Phase IV, but also in preparing their vision and plans for Phase V and beyond. SFD’s funding shortfall poses a major risk to its ability to meet planned targets by the end of this phase. DFID will need to consider options for managing this (see summary of recommendations).

Summary of recommendations for the next year

For SFD	For DFID
Financing Gap
Continue lobbying donors for funding and to provide an update on the latest financial position and progress on securing new donor funding at next Joint Donor Review meeting.	Lobby GoY and donors to either ensure release of existing pledged funds or to re-prioritise other pledges to support SFD.
Programmatic Issues
SFD to explore urgently whether it can start multi-year labour-intensive public works (“workfare”) assistance in rural areas	Work with SFD Small and Microenterprise Development programme (SMED) and the World Bank to identify measures for promoting greater financial inclusion.
Sustainability of education infrastructure remains a longer term challenge. Although many of the issues are outside of SFD’s direct control, SFD should continue to take additional measures at the design and implementation stage to mitigate these problems. This applies in particular to maintenance of buildings and equipment, and to the issues of non-functioning water supply and/or badly maintained or unusable toilets. More attention should be given to the design of water supply and toilet facilities to reduce maintenance issues. This will be an area of focus for an Independent Monitoring study.	Monitor progress carefully for remainder of Phase IV
Speedily finalise the recruitment of the specialist who will help develop policy and procedures to ensure female inclusion in water projects
Preparations for SFD Phase V
Progress Vision for Phase V and development of concrete proposal	Provide consolidated set of comments on Vision document to SFD. Identify key design issues and expertise required to deliver these
SFD to set out in its Phase V vision its proposed approach, plans and budget for evaluation of Phase V as a whole and for individual sector evaluations.	As per SFD’s request during the JDR, explore options to provide TA to support the detailed planning for Phase V, possibly within the context of a longer term vision (25-30 year horizon). This might include but not be limited to: / Stronger integration of human development objectives across SFD’s work / Synergy between interventions in water, food security, social protection and employment / Research on links between SFD interventions and conflict. / Support for organisational change to ensure SFD remains ‘fit for purpose’ going into Phase V. / Options for balancing delivery of core Phase V commitments with ‘off-phase’ demands and grant allocations of donors. / Other issues that may need TA include: i) Linkages between micro-finance and other areas of SFD’s work; and, promoting gender equity across the whole of SFD’s work
	Explore possibility of accessing International Climate Fund (ICF) funding.
	Support the World Bank’s recommendation that SFD considers developing 2-scenarios within the Phase V vision: a best case scenario (if Yemen’s security situation improves and the decentralisation process proceeds) and a worst case scenario (if the current political unrest and security situation continues or deteriorates further). The Review team believes SFD would still be a key player in both scenarios but its role in each would be different in objectives, scope and approach.
Monitoring and Evaluation
SFD to continue to engage with DFID’s Independent Monitoring programme and use the findings to inform the remainder of Phase IV as well as the design of Phase V.	Keep a watching brief on evaluations being planned and/or implemented by SFD and ensure that SFD plans include an evaluation the Empowerment for Local Development (ELD) Programme. This should include qualitative data on whether the programme has succeeded in strengthening relations between local authorities and communities, initiating genuinely participatory planning and to what extent it has influenced budget allocation and programming by local authorities.
Agree an approach to the evaluation of SFD IV with DFID and the World Bank, including a greater focus on qualitative dimensions and the synthesis of existing impact studies.	Amend the logframe to reflect DFID’s real results attribution (currently calculated on basis of 14% of original budget)
With DFID, SFD should establish metrics to measure VFM (e.g. through the ‘3E’ (economy, efficiency and effectiveness) methodology)	Continue to improve communications with SFD management and other donors in order to address programme risks (eg competing donor demands and grant funding vs core funding shortfalls) by establishing a regular monthly tele/video conference with SFD.
	DFID team to discuss the findings of the World Bank’s review of SFD’s procurement systems with Procurement and Commercial Department to ensure that the approach and findings are in line with internal requirements.The review findings are expected in February 2015.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Log frame

Outline of the programme
In 2010, DFID committed to provide £100 million over five years between January 2011 and December 2015 to Phase IV of the Yemeni Social Fund for Development (SFD) to improve access to basic services, enhance economic opportunities and reduce vulnerability for the poor.

DFID support will enable SFD to meet their overall aim to improve the lives of the Yemeni poor. The main objectives of our support are:
- Improve access to basic services, such as education and health facilities
- Create economic opportunities and improve the business environment
- Create employment opportunities for the poor
- Increase the ability of local authorities, NGOs, and communities to manage, monitor and evaluate development programmes.

In total, the programme will:
- Enable the construction and/or rehabilitation of 9,000 classrooms and 80 health centres
- Provide access to credit and savings for 100,000 clients
- Provide employment opportunities for 300,000 poor people
- Train 7,720 individuals and organisations in project planning

This is a multi-donor supported project and DFID’s contribution equates to 14% of the planned total budget. This percentage attribution to DFID will change if the contribution from others differs from original commitments. Key results currently attributable to DFID therefore include:
- Over 50,000 pupils enrolled in SFD-supported schools
- 6,720 households provided with new/improved drinking water
- 90,440 people provided with access to improved water sources (within 30 mins walking distance or less)
- 3,360,000 employment days created

SFD will be entering their 5th Phase at the beginning of 2016 and 2015 will be an important year in which to plan for the transitions from Phase IV to V.

Context

SFD’s 4th phase has been conducted in a particularly challenging Yemeni political, economic and security context. This started with the popular protests in 2011 as part of the ‘Arab Spring’ that led to the resignation of Yemen’s President and started a period of political transition. 2014 initially proceded relatively positively with the conclusion of Yemen’s National Dialogue Conference (NDC) setting out a new political settlement and initiating a period of constitutional drafting. However, in September 2014, the Al Houthi rebel movement, involved in a decade-long conflict with the government in the country’s northern Sa’ada Region, took control of the capital Sana’a. Following this, a Peace and National Partnership Agreement (PNPA) was concluded by all parties on September 21 calling for renewed commitment to the implementation of the outcomes of the National Dialogue, to be led by a new Prime Minister and a new technocratic government. [1] This, and the political transition process, subsequently broke down with the resignation of the President and Government on the 22nd January and the Al Houthi movement formally seizing power on the 9th February. It is unclear how the situation will develop from here but there remains significant risks of violent conflict and/or insecurity, political instability (including the potential for Southern Yemen seccession) and economic collapse.
[1] World Bank, Yemen Overview. Last updated October 2014.
The current political crisis provides the backdrop for Yemen’s status as one of the poorest countries in the Middle East. Poverty is widespread with 37% of the population living on less than $2 a day. Remote, widely scattered villages and poor road conditions make access to health and other social services extremely difficult. Yemen is the eighth most food insecure country in the world, ranking 69 out of 76 countries in the 2014 Global Hunger Index. It is also bottom of the 2014 Global Gender Gap Report. According to the most recent Humanitarian Needs Overview in 2015, 15.9 million people (61% of the population) are in need of humanitarian assistance, 10.6 million are food insecure (unable to buy or produce the food they need), and 850,000 children under the age of 5 are acutely malnourished. Furthermore, approximately 13.4 million lack access to clean drinking water, 12 million lack proper sanitation facilities and 8.4 million cannot access basic health services. Yemen imports over 90% of its wheat, making it particularly vulnerable to fluctuations and volatility in global food prices.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
SFD continue to deliver against their outputs in ways that gives us a high level of confidence that they will by the end of 2015 (Phase IV) deliver important outcomes for those that they have been able to reach. Evidence (qualitative and quantitative) presented to donors at the December Joint Donor Review in Amman suggests that SFD have delivered high quality interventions for their target groups, that they have made a signficant contribution to rehabilitation of infrastructure, better access to water sources, put additional cash in the pockets of the poor, and continued to deliver interventions in ways that contribute to empowering communities and local authorities to take greater ownership and responsibility for decision making and delivery.

Overall output score and description A – Outputs met expectation
The explanation for SFD’s shortfall in meeting milestones is essentially due to the lack of donor funding, both a shortage of committed funds and delays in donor disbursement. The quality of SFD interventions, and the manner in which they are delivered, is generally high though there is potential for improvement in the areas of gender sensitivity and sustainability.

Key lessons
- Understanding the impact of SFD requires paying greater attention to the quality of what they deliver in addition to the quantity. Often it is the linkages between interventions that will have the greatest impact on quality. Rooftop rainwater harvesting, for example, provides improved access to a valued resource, but will also enable more girls to go to school due to reduced time spent in domestic labour.
- SFD appear to still face difficulties in managing the demands of the World Bank to take on more ‘off-phase’ grants. We will continue discussions on this with the World Bank and SFD.
- Although a highly capable organisation, regular technical and management engagement between DFID and SFD will ensure we are able to address critical challenges early and jointly.

Key actions
- Agree a strategic plan and dedicated financing for technical assistance for SFD V
- Identify key design issues and expertise required to deliver those

Has the logframe been updated since the last review? Yes. The logframe for support to the Yemen Social Fund for Development (SFD) required amendment in order to align it with the broader Results Framework (RF) developed by the World Bank and agreed between SFD, DFID and other donors contributing to Phase IV. The logframe was also revised to better reflect outcome performance following recommendations from Internal Audit Department. Despite a number of changes, there was no fundamental revision of the scope of SFD IV’s activities and both the Outcome and Impact statements remain the same. The revised RF was finalised by SFD and donors at the joint donor review in November 2013 and refined in subsequent meetings.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Community and Local Development Programme: Basic Services Improved
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	70%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2014 Milestone[2]	Cumulative achievements[3]	Cumulative achievements attributable to DFID[4]
Number of classrooms constructed or rehabilitated	6,800	7,996	1,119
Number of formal teachers trained	80 (male) / 80 (female)	189 (male) / 218 (female)	26 (male) / 30 (female)
Total km of rural roads built or upgraded	880	914	128
Number of people provided with access to improved water sources (within 30 mins)	516,000	530,834	74,317
Number of Primary Health Care workers qualified (3 year qualification) (sex disaggregated)	240 (male) / 240 (female)	206 (male) / 168 (female)	29 (male) / 24 (male)
Number of people provided with access to improved sanitation facilities	200,000	192,230	26,912
[2] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2014.
[3] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 20134.
[4] DFID attribution rate is calculated as 14% of the overall achievements

Key Points
SFD have made good progress under the Community and Local Development (CLD) Programme since the last annual review, exceeding milestones for the 2014 period against all but two indicators. The funding constraints experienced by SFD and poor security have impacted all CLD interventions. By way of example, SFD report that during 2014, the Project Approval Committee was not able to approve any new sanitation projects.

SFD’s response to the crisis has been measured, but they have been able to deliver beyond the 2014 milestones because they have an effective approach to developing a project pipeline enabling them to rapidly disburse funds.

Beyond the poor security and shortfalls in funding, SFD have also been affected by increases in fuel prices and power outages. SFD have managed these appropriately, dealing with insecurity through contracting local consultants; with power outages and fuel shortages (diesel and petrol) by maintaining reserves and through compensating consultants for additional fuel costs. Security concerns have mostly affected projects in Amran, Lahj, Saada’a and Dhali’I.

As SFD look forward to their next phase (Phase V), they will continue to focus on sector and community projects, shifting over time to a delivery approach that will be more closely integrated with decentralised District level development planning. Since SFD have demonstrated their capability in supporting better delivery of services in education, health, water and sanitation, they will continue to lead this work in areas where District Authorities do not have the capacity to mange finances, and design, deliver and monitor projects. Over SFD V, a greater number of projects will be included within district level plans.

Education
The education sector represents the vast proportion of SFD’s interventions in the CLD programme. During 2011-2014, close to 8,000 classrooms have been built and rehabilitated, and the newly constructed classroom space is expected to accommodate an estimated number of 117,000 boys (compared to the end 2014 target of 152,000) and 96,000 girls (against a target of 119,000). This was confirmed by an SFD implemented utilisation survey which found that 94% of the education projects are delivering the intended service.

856 projects were completed and handed over to the Ministry of Education with a total of 5,329 new classrooms built, 2,674 rehabilitated and 4,117 still under implementation. Additionally, 96 capacity building projects have been developed, aiming to train 1,968 administrative staff and supervisors,4,154 formal education teachers, life skills trainers, community and literacy class facilitators.

Health
During the period from January 2011 to September 2014, SFD developed 431 projects at an estimated cost of $47.6 million in partnership with the Ministry of Public Health and Population (MoPHP) and its governorate offices. Of these projects, 301 were completed and 130 projects are under implementation. These projects support the construction and/or equipping of: health units, health centers, district hospitals, childhood and motherhood centers, Basic Emergency Obstetric Care (BEmOC) centers and Comprehensive Emergency Obstetric Care (CEmOC) centers. As of the reporting date, 93 health facilities have been constructed or rehabilitated (compared to a target of 120), and 255 community midwifes and 2,116 primary health care workers (PHW) have been trained (exceeding the targets of 240 and 1,875 midwives and PHWs respectively). Of these, SFD’s work in the health sector enabled a total of 374 PHW (206 male and 186 female) to achieve formal qualification during the reporting period. DFID is also funding UNICEF to train both community midwives and health facility staff in Yemen. SFD continues to coordinate with UNICEF in this area.

Water and Environment
Although no new projects have been approved during this period, currently there are 106 projects with the Projects Approval Committee (PAC) worth $22.4 million and whose approval is on hold due to lack of funds. Cumulative achievements of the sector have exceeded 2014 targets, by 2.6%, 10.9% and 5.2% for the three water indicators: water access, storage capacity for improved water, and storage capacity for unimproved water respectively. SFD reviewed the trend in the annual average cost per capita for projects that provide access to improved water (i.e. excluding training and awareness activities and projects that provide access to unimproved water), and found an increase of about 50% in the per capita cost between 2011 and 2014. The increase is believed to be attributed to increase in fuel and labour prices, and deteriorating security situation.

SFD has adopted the community contracting approach in areas where contractors are not willing to operate due to the security situation (e.g. Mareb, Aljawf, Amran, Albaidha, and Abyan). Hiring consultants from within the area working under the supervision of SFD branch offices is helping to keep operations going in insecure areas, with the odd few exceptions. In an effort to compensate for both the increase in price and shortage of fuel, SFD are making use of renewable energy sources for projects where energy is needed to operate the system.

Roads
The completed rural roads projects have created 914 km of rural roads since January 2011 (exceeding the end 2014 target of 880 km), generated 1,303,748 workdays and provided better access to the nearest village/market for 447,119 people. Additionally, rural roads projects under implementation have generated 1,333,038 workdays so far. For the street pavement projects (Rural Labor-Intensive Works activities) 1,121,555 workdays have been generated as of September 2014 from both completed and on-going projects.

Summary of responses to issues raised in previous annual reviews (where relevant)
In the education sector, sustainability and maintenance of infrastructure remains a longer term challenge. Although many of the issues are outside of SFD’s direct control, SFD should continue to take additional measures at the design and implementation stage to mitigate these problems. This applies in particular to maintenance of buildings and equipment, and especially the prevalent issues of non-functioning water supply and/or badly maintained or unusable toilets. More attention should be given to the design of water supply and toilet facilities to reduce maintenance issues.

Despite the funding issues, SFD have continued to coordinate with the Ministries of Education and Health at central and sub-national levels to strengthen partnership and reaffirm areas of responsibility.

Recommendations
The CLD component has been hit hardest by shortfalls in funding. DFID should work with SFD and the World Bank to to press all donors to honour their commitments, to seek additional funding and/or to persuade donors to re-allocate undisbursed pledges towards SFD given SFD’s proven ability to deliver at scale and current funding shortfall.

As part of the planning and design of Phase V, it will be important for SFD to consider how they continue to integrate interventions in Human Development with a proposed increased focus on national priorities in improving food security, dealing with water scarcity and job creation. Increasing female enrolment in education requires integrated interventions with multi-disciplinary actors and complementary strategies (eg linking water and sanitation projects at home and in schools to infrastructure developments). SFD should include these issues in their strategic plan for technical assistance.

Ensuring womens’ right to participate in all stages of water projects is an onging challenge. SFD’s Water and Environment Unit (WEU) is planning to develop policy and procedures to ensure female inclusion and are in the process of hiring a specialist to help with this. DFID should monitor progress carefully for the remainder of Phase IV and offer support as part of an overall contribution to technical assistance

Output Title	Small and micro enterprise development programme: Economic Opportunities Created
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2014 Milestone[5]	Cumulative achievements[6]	Cumulative achievements attributable to DFID[7]
Number of active borrowers / % female / Number of additional branches in rural areas	90,000 / 60% female / 4 rural	118,223 / 54% - (62% if counting only those loans from MFIs directly supported by SFD) / 6	16,551 / 0.8
Enabling Environment: Credit bureau legislation / regulation submitted to the government	Code of conduct adopted	Workshop and awareness about credit bureau – 1st draft sent to all MFIs and Yemen Micro-Finance Network to provide consumer protection guidelines to MFIs	n/a
Enabling Environment: Code of conduct regarding consumer protection adopted by Yemeni Microfinance network (YMN)	Draft adopted by MFIs and YMN	Completed. Signed and agreed by all MFIs, and displayed in the various branches	n/a
Financial Sustainability: Number of MFIs that are financially sustainable	7	1	n/a
[5] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2014.
[6] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 2014.
[7] DFID attribution rate is calculated as 14% of the overall achievements

Key Points
On balance we have scored this output an A – Outputs met expectations. SFD has exceeded expectations for the number of borrowers (by 30%) and for the number of rural branches. This has however been offset by the percentage of female borrowers coming in below target and the reduction in the number of MFIs that are financially sustainable. Both, and the latter in particular, are due to factors beyond SFD’s control.

The SMED Programme has exceeded its end of Phase IV target by 18,000 active borrowers. The percentage of female borrowers was 54%, a little below the target of 60%. This was mainly due to the private sector banks and micro-finance banks (MFBs) that are included within this target, which SFD indirectly supports, who focus on perceived lower risk customers such as small businessmen. For those micro-finance institutions and banks that are directly supported by SFD through SMED with loan funds (and/or equity) the percentage of female borrowers is 62% (two of which failed to meet the target but the others far surpassing it). SFD also exceeded the target for the number of additional rural branches (6 vs a target of 4). SFD say they will work actively to promote greater levels of lending to women.

Because of the deterioration in the security situation there was an increase in the portfolio at risk in most of the MFIs with many clients not able to repay their loan instalments on time. This, in turn, has led to a drop in the number of MFIs that are financialy sustainable from 5 out of 12 this time last year to 1 out of 12. SFD and the World Bank, however, assess that a number of these will rapidly return to sustainability, should the security situation stabilise. A further significant achievement this year was the approval by the Central Bank of Yemen of new regulations governing mobile banking. These had been developed and driven through by SMED. SMED report huge commercial interest in rapidly rolling out mobile banking services. SFD, the Central Statistical Organization (CSO), and the International Labor Organization (ILO) also his year funded the “Yemen Labor Force and Microfinance Survey (2013/2014)”. This survey will give a reliable estimate of the market size for microfinance services as well as its demographical and sector segmentation and will enable a realistic estimate of the targets for continued expansion in the micro finances sector.

he Business Development Services represented by SMEPS was financially supported with an amount totaled 1.8 million U
Summary of responses to issues raised in previous annual reviews (where relevant)

1. Links to other DFID Yemen financing programmes (IFC) on results reporting, and value of providing support through both channels still needs rationalising. DFID economic advisor should look in detail at any potential overlaps. This has not been done since the last review but is a priority going forward.
2. SFD has begun to collect data on rural active borrowers, directly addressing this recommendation in the 2013 AR.
3. Findings of the Evaluation of the Ultra Poor Graduation Pilot Project in Yemen: DFID had stepped in to fund this to ensure a proper evaluation of the graduation pilot. The evaluation was completed by Innovations for Poverty Action (IPA) and the draft report shared with SFD. SFD and DFID have now provided comments to IPA and work is underway towards finalising the report and agreeing on the dissemination of its findings.

Recommendations

SFD should consider whether the indicator on financial sustainability remains realistic given the current environment.

DFID Yemen should explore the specialist expertise that exists in-house on microfinance and co-ordinate with the WB and SFD to explore if, and how, we might further support the development of SFD Phase V work in this area (over and above the existing WB support), including on supporting linkages between micro-finance and other areas of SFD’s work.

DFID should work with SFD and the World Bank to identify how SMED might promote greater financial inclusion.

Output Title	Labour Intensive Works Programme: Reduced Vulnerability for the Poor
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2014 Milestone[8]	Cumulative achievements[9]	Cumulative achievements attributable to DFID[10]
Number of people directly benefitting from multi-year workfare[11] assistance in rural areas	90,000	0 (Start of multi-year assistance delayed)
Number of people directly benefitting from short term workfare assistance in: / Rural areas / Urban areas	Rural 768,000 / Urban 331,600	566,892 / 255,570	79,365 / 35,780
Indirect beneficiaries: Number of days employment created under workfare assistance programme for multi-year activities in rural areas	1,312, 000	0 (Start of multi-year assistance delayed)
Number of days employment created under workfare assistance programme for short term activities in: / rural areas / Urban areas	Rural – 9,500,000 / Urban – 2,100,000	7,800,000 / 1,600,000	1,092,000 / 224,000
Indirect beneficiaries: Number of households benefitting from community livelihood assets	240,000	205,615	28,786
Land: Total area of rehabilitated terraces and land (Hectares)	3,735	3,635	509
[8] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2014.
[9] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 20134.
[10] DFID attribution rate is calculated as 14% of the overall achievements
[11] Labour Internsive Public Works

Key Points
Progress under this component is behind schedule with, in particular, the multi-year workfare assistance in rural areas still to commence operations. Both are due primarily to shortfalls in funding. While annual disbursement under this component was $51.1 million in 2013, up from $30.7 million in 2012 as the programme caught up following delays in 2011, in 2014 this has fallen to $21.4 million with a significant number of projects developed but unable to proceed pending SFD receiving further funds. SFD report that they currently have 63 projects with a combined value of $16 million that are suspended due to a lack of funds and have a further $50 million of projects for 2015 prepared but currently unfunded.

Notwithstanding the funding shortfall, good progess has been made under the short-term rural and urban workfare assistance component (and in line with the positive findings from the 2013 Randomised Control Trial). Given funding shortfalls and keen to provide benefits to the greatest number, SFD have prioritised the short-term assistance at the expense of the multi-year assistance. Preparation work for the multi-year assistance has continued with 252 areas in Yemen identified for interventions and field verification visits conducted by programme officers to 193 of these. Work on the multi-year workfare assistance will start during 2015 but with projects, lasting 3-5 years, straddling phases IV and V.

Summary of responses to issues raised in previous annual reviews (where relevant)

A comprehensive Operational Manual (OM) for the LIWP has been updated and finalised. DFID will review this OM and share comments with SFD.

Further discussion with SFD regarding delayed progress on their longer-term workfare assistance is still needed. What will this mean in terms of the overall resources required going forward and specifically shifting the longer term workfare assistance programme to 2015/16 and into SFD V?

Recommendations

As SFD develops its vision and plans for Phase V, DFID should support SFD to ensure there are clear linkages between the LIWP and other interventions focused on delivering NDC recommendations relating to food security, and water scarcity and employment. Any substantive shift in focus should continue to ensure and support partnership with communities and local authorities, as well as the participation of women to ensure they also benefit.

LIWP interventions have the potential to address longer term environmental degradation, water scarity and climate change adaptation. However, the LIWP cannot do this alone. Other programmes would need to be carefully integrated to explore synergies and complementarities – notably the agricultural and livelihoods programmes. A mix of interventions at the level of water catchments could offer advantage. It is recommended that DFID support SFD to review the synergies between sector interventions and consider how best to adapt the LIWP programme to move towards a more intergrated model for phase V. Such an approach will also need to carefully consider the need to balance short term safety nets and the role of LIWP in smoothing consumption, with the longer term benefits.

Output Title	Capacity Building: Stakeholders capable and empowered
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	2014 Milestone[12]	Cumulative achievements[13]	Cumulative achievements attributable to DFID[14]
Number of people trained in M&E, participatory methods, planning or other strategic information management (disagregated by male, female and Local Authority (LA) members trained on Empowerment and Local Development programme	Male: 2,000 / Female: 1,200 / LA: 1,200	777 / 681 / 4,868	109 / 95 / 682
Number of village councils in pilot areas which are functioning effectively: / - meeting regularly / - wide participation (sex disaggregated) / - initiate self-help initiatives	1,200	3,806	533
Organisation supported / - Number of NGOs supported / - Number of local authorities supported / - Number of Community-Based Organisations formed	NGOs: 75 / LAs: 70 / CBOs: 2,200	55 / 50 / 1,805	8 / 7 / 253
[12] This represents the total cumulative milestone since the start of Phase IV, January 2011 through to September 2014.
[13] These figures represent total cumulative results since the start of Phase IV, January 2011 through September 20134.
[14] DFID attribution rate is calculated as 14% of the overall achievements

Key Points
The lower than expected figures for the numbers of people trained is largely due to a lack of funding. Where milestones have been exceeded, this can be explained by an underestimation of the number of members of the 40 local authorities available for training and the number of village council in each District at the beginning of phase IV.

For Phase IV, SFD planned to target support to 80 District Councils. The approach aimed to calibrate support according to the stage a District Authority was at in terms of their ability to implement development projects funded by SFD (and receive certification). In the first stage, SFD implements basic services and subprojects; in the second stage, Local Authorities (LAs) and SFD jointly implement subprojects that may serve more than one village; and, in the third stage, LAs implement and manage subprojects, leaving SFD to supervise and monitor the overall activities.The intention for SFD is to take a longer term view and to ensure that over time the balance of SFD sector interventions could be designed, implemented, monitored and financed through the District Authorities. Currently of 80 District Authorities, 54 have well developed plans with $90 million worth of projects on plan (but unfinanced). Of these 54 District Authorities, 20 are currently implementing projects wholly led and managed by the District Authorities themselves. It was reported during the Joint Donor Review that an increasing number of SFD interventions are being identified through the 54 District Authorities who have plans in place.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

Recommendations
Although it is too late in the current project cycle to revise the logframe further (given the need to amend the Results Framework jointly with other donors), it is clear that what should be measured is not the outputs related to number of people or authorities trained but rather the number of district level project plans that exist; and the number of overall SFD interventions and self help initiatives that have been identified and are being supported through District planning processes. This should be addressed in the development of the Phase V Results Framework and logframe.

SFD’s initial vision for Phase V planned to build on the successes of this component making it a core pillar of SFD’s work and significantly expanding it. SFD saw this work as supporting the National Dialogue commitments to greater decentralisation and contributing to building the Yemeni state from the bottom up through linking communities with district authorities. There had also been significant support for this from the GoY and in particular the Ministry of Local Adminstration. Given the current political instability and uncertainty it is unclear if a scale up of SFD’s work in this area would be appropriate or realistic. DFID should work with SFD to develop a revised vision for this component and one that is flexible to adapt to a range of potential political scenarios.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The rise in prices of fuel and labour in addition to the deteriorating security situation have increased the overall unit cost of some SFD project activities. However, to keep its unit costs low, SFD has been continuously modifying the standard design of its infrastructure projects in order to come up with low cost designs. Its procurement process follows transparent and competitive bidding in order to achieve maximum value for money. Additional measures include cutting unnecessary administrative procedures and speeding up the transfer of the contractors’ and suppliers’ payment requests. SFD’s operation costs are likely to increase due to the reduction of disbursements. If cost increases reach an unsustainable level due to the overall funding gap of this project, SFD may be forced to reduce its labour force or to re-orient programming to new areas of intervention that will receive funding. SFD’s project programming may have to be more conservative.
Cost/Cap. $
Cost/Cap. $
Year
Figure 1: Increase of cost/capita with time with time

The annual average cost per capita was calculated for projects that provide access to better water (i.e. excluding training and awareness activities and projects that provide access to unimproved water). Figure 1 shows that between 2011 and 2014, the cost/capita has increased by almost 50% (our view is that this does not change the initial economic appraisal). To compensate for the increased costs, SFD are exploring the use of solar/renewable energy sources in this sector.

VfM performance compared to the original VfM proposition in the business case
SFD performance in terms of value for money is considered satisfactory in comparison to the original VfM proposition in the business case. SFD is inherently a long term development programme – the original cost/benefit analysis suggested that most of the net benefits will not accrue for some years after the initial investments. A key indicator of SFD’s achievement of VfM is their continued ability to deliver despite a shortage of funds.

When considering the VfM of DFID’s contribution to SFD, it is sensible to apply the ‘3E’ principles: Economy, Efficiency, and Effectiveness:
- On Economy, the operating costs associated with managing the Fund were originally set at 6.4% of total costs ($72 million), which is broadly comparable with other internationally coordinated mechanisms such as some Humanitarian Trust Funds. The actual allocation under phase IV to date ($41.4m) actually represents 5.3% of total allocated funds to non-special projects. This suggests that operational costs remain broadly on track or indeed under those originally planned.
- On Efficiency, DFID’s contribution represents one of 25 donor contribution agreements to date with SFD IV. This suggests that substantial opportunities for efficiency have already been realised, as SFD is able to apply more consistent mechanisms to its programmes, rather than have a number of different donor-designed mechanisms to manage. This helps make our funds go further whilst also harmonising the inputs. This also supports the broader level of efficiency associated with DFID management of a single programme which covers a range of interventions. The risk to this degree of flexibility is that SFD may be spreading itself too thinly across its various activities. This is discussed regularly with SFD who assure us that they have sufficient capacity to manage the current workload. More pressing is the effect of the funding gap which limits SFD’s ability to progress implementation.
- Effectiveness can be measured by assessing progress against targets. For the purposes of this analysis we concentrate on the original economic appraisal which focused on the roads, water, education, and labour intensive works components of the SFD project, as the major areas of DFID support. The table below sets out the expected output values and actual performance. As can be seen from the table below, targets were exceeded in three of the four areas. This suggests that the project remains broadly effective and demonstrates SFD’s resilience and ability to continue operating despite the rapidly deterioriating security situation.

	Number of pupils enrolled in SFD supported schools	Kilometres of road built	Cubic metres of water storage	People benefiting from labour intensive works
2014 Estimate	152,320	880	1,790,000	723,606
2014 Actual	117,710	914	1,985,653	822,462

Assessment of whether the programme continues to represent value for money
SFD has delivered value for money since the outset of its phase IV programme. The synergies between SFD’s interventions contribute to this. For example, providing better sanitation in schools has been found to contribute to girls’ enrolment, thereby increasing the value of constructing and rehabilitating classrooms.

SFD uses established benchmarks to determine costs of suppliers. Procurement specialists are responsible for ensuring cost controls are in place and that consultants are delivering the required level and quality of services contracted.

SFD also demonstrate a strong awareness of VFM through their decisions to stop certain interventions when appropriate. For example, rural sanitation that involves sewerage networks and wastewater management will be stopped in the next phase of operation due to the inability to maintain them. There will be exceptions for cases where local communities can confirm that they are able to provide operational and maintenance support for the interventions but otherwise, funds will be directed to more sustainable measures.

Quality of financial management
SFD’s financial management procedures are considered to be satisfactory. They are transparent, verifiable and are designed to ensure cost effectiveness and good value for money of SFD operations. SFD uses an automated Oracle multicurrency/multi-donor financial management system across all branch offices to track and control the flow of disbursements. Stringent internal control procedures are applied to all financial transactions and reports are produced for each grant or loan in the donor disbursement system to track the movement of funds. The World Bank assessed SFD’s financial management procedures during the December review mission and concluded that SFD continues to maintain satisfactory financial management arrangements.

The Finance and Administration Unit uses a Financial Manual which sets out the organisational structure, disbursement and payment procedures, and job descriptions. A chart of accounts has also been developed specifying the different codes per category of project expenditures. This manual was approved by SFD’s Board of Directors and is considered to be an effective financial management tool by donors.
SFD has a qualified Internal Audit Department (IAD) led by the Internal Audit Manager, who reports directly to the Managing Director. The department is responsible for conducting regular audits for the branches, departments, and units within SFD. The internal auditor follows up on any actions agreed upon with the concerned branches, departments or units. It also coordinates and cooperates with the external auditors.
SFD also has a dedicated Contracts and Procurement Unit which is responsible for the overall management of procurement. SFD’s procurement procedures are standardised in a detailed manual and aim to ensure that all invested funds are used for their developmental purposes, with due attention to considerations of economy and efficiency and without regard to political or other non-economic influences or considerations.

The World Bank Procurement Team is also currently carrying out a review of SFD’s contracting procedures. The post review findings are expected in February 2015 and will be shared with SFD and its Development Partners. Once received, it is recommended that the DFID team discuss the findings with Procurement and Commercial Department to ensure that the approach and findings are in line with internal requirements.

Date of last narrative financial report	23/07/2014
Date of last audited annual statement	06/07/2014

E: RISK (½ page)

Overall risk rating: Medium
SFD’s shortage of funding remains the highest risk to SFD achieving its phase IV objectives and in contributing to Yemen’s development challenges. The funding gap of $346 million is impacting SFD’s capacity to implement pipeline projects and develop new initiatives. However, SFD regularly communicates with the government and lead donors to mobilise more funding.

In an effort to manage limited funding in 2014/15, SFD is doing the following:

- Giving priority to districts that have not used their allocations
- Within these districts, giving priority to districts affected by the conflict
- Giving priority to projects with higher labour intensity (and hence more direct financing to the poor)
- Utilising 2nd additional financing from the World Bank which is earmarked for CLD
- Focussing on areas of expertise and comparative advantage. E.g. less focus on nutrition because others can add more value

SFD is facing a challenge in the management of unearmarked versus earmarked funds. All unearmarked funds have been utilised.

SFD also faces significant risks from the current political instability and associated risk of conflict that could either threaten SFD’s autonomy and/or lead to significant insecurity and conflict that prevents SFD delivering projects across Yemen.

Overview of programme risk

A comprehensive risk assessment is detailed below. Key changes to note include:
- Recognition of the current breakdown in the political transition and risk of a deterioration in the security and economic context
- Absence of GoY ownership results in decreased ability to sustain SFD constructed infrastructure
- Increase in conflict and insecurity temporarily limiting SFD’s ability to operate in some areas
- Increase in price and availability of fuel
- The risk of SFD’s inability to raise total amount of funds for Phase IV operations and consequently an inability to implement pipeline projects and/or develop new initiatives is being realised

No.	Description	Probability	Impact	Mitigating Action
1. Country Risks
1.1	Transition to an inclusive political settlement stalls, co-ordinated international pressure for transition runs out of steam	High	Medium	DFID is working closely with the FCO to deliver strong messaging to key political actors to encourage swift agreement and initiation of political transition/settlement.resolution of the current inpasse Use FoY and/or other lobbying opportunities process to raise isses with GoY.
1.2	Conflict & security deteriorates with consequences for SFD staff duty of care and effective programme delivery	High	Medium	SFD hires consultants who are local to project sites and therefore able to access sites safely. SFD work closely with communities and local councils to maintain the security of SFD staff/consultants/contractors Where the project site is considered too dangerous, SFD staff are instructed to wait until the situation becomes stable. It is estimated (based on SFD reporting system) that about 4% of projects are currently halted/delayed due to security situation. Usually SFD resumes the work once the situation allows. SFD works through 9 Branch Offices in addition to its Sana'a Headquarters. They are able to decentralise operations if staff are prevented from accessing the main office in Sana'a
1.3	Increasing inflation, including essential commodity prices, risks exacerbating poverty and humanitarian situation and create tensions	High	Low	SFD's Labour Intensive Works Programme aimed at “reducing vulnerability for the poor” has been developed specifically as a reaction to rising food price rises and their wider impact on the poor. SFD will consider scale up of LIWP to address emergency needs.
1.4	Fuel scarcity impedes movement and access and exacerbates conflict	High	Medium	SFD maintains strategic stocks of diesel. SFD pools transport for staff and increases consultants’ transport allowances.
1.5	Lack of functioning Government in Yemen	High	High	Continue influencing and direct support to protect SFD’s autonomy and capacity.
1.6	Lack of Government of Yemen commitment to poverty reduction	Medium	Medium	Maintaining effective communication with SFD and key Government Ministries (Ministry of Social Affairs and Labour; Ministry of Planning and Ministry of Finance). / Incorporate discussion of policy issues into 6 monthly reviews to ensure policy direction is maintained in agreement with both parties.
2. Programme Risks - SFD Management and Governance
2.1	Change in SFD Leadership leads to reduction of SFD's autonomy. This could result in an increase in Government coercion and misuse of SFD funds	Medium	Medium	SFD board of directors (government, the private sector and CSO’s; chaired by the PM) limits the executive powers of any SFD Director. SFD has robust financial controls which limits the risk of misappropriation of funds. Joint donor messaging about the importance of SFD independence, neutrality and impartiality. Continued dialogue with high level Yemeni interlocutors.
2.2	Social, political or military interference in locally managed projects	High	High	SFD applies objective targeting criteria and continues to strengthen these for geographic selection. SFD relies on participatory methods for targeting local communities and households to ensure community oversight/ownership. SFD have agreed to raise any incidents of political pressure with donors immediated.
2.3	SFD capacity and professionalism deteriorate including poor reporting, financial management and, weak human resource management	Low	Medium	SFD has a robust operations manual and a strong Project and Policy Approvals Committee. Reporting: DFID continue to provide support and have begun independent monitoring of SFD in December 2014 Financial: SFD have stringent internal accounting systems and regular external audits. HR: SFD to strengthen its HR strategy, including a staffing needs assessment and review of procedures to ensure retention of quality staff.
2.4	Extremely vulnerable families will not be reached by the programme	Low	Medium	SFD carry out geographic targeting based on the 2004 census and 2005 Household Budget Survey data to identify villages for community targeting. The 2014/15 Census and 2013/14 HBS (supported by DFID, WB and others) will provide SFD with more accurate and up to date statistics to refine their targeting to a greater extent. Donor partners carried out a review of SFD’s targeting methodology to ensure the poorest families receive assistance. [SIMON to add something on deprovation index]
2.5	Absence of GoY ownership results in decreased ability to sustain SFD constructed infrastructure	High	High	In spite of a dysfunctional central Government structure, SFD are still able to work closely with local Government counterparts and local communities to ensure sustainability at district/Governorate level SFD projects rely on community ownership including in-kind contributions and user fees to cover operational costs DFID will have the ability to assess this through our Independent Monitoring programme.
2.6	Community sustainability: Community based operations and management break down	Medium	Medium	SFD visit completed projects regularly to monitor the situation. Before and after photos are recorded for all interventions. These are publically available on Picasa. Support will be given to capacity building even after completion of projects. SFD withhold a percentage of all consultancy funds to ensure all projects are completed and handed over to communities. Village level management committees set up to oversee operations.
2.7	District sustainability: Districts supported by SFD are not able to implement projects	Medium	Medium	District capacity building is a small part of the overall programme. The methodology sets out clear criteria and incentives to gradually move towards districts implementing their own projects through a four-phased approach..
3. SFD Implementation Risks
3.1	Inability to raise total amount of funds for Phase IV operations: Inability of SFD to implement the pipeline projects and/or develop new initiatives. Underuse of SFD's absorptive capacity and associated increase of SFD's overhead cost	High	High	Continuous communication with the government and lead donors to mobilise more funding to SFD. Take further action (such as adjusting SFD's staff levels) Specifically for the delayed GoY contribution - SFD have put live projects on hold and are not signing any new commitments or contracts from a government source. SFD regularly communicate with the government to honor its commitments once government fiscal situation improves. Use any positive findings from DFID's Independent Monitoring to reassure donors of satisfactory progress where required. Subject to agreement with SFD.
3.2	Donor funding is suspended	High	High	SFD have prepared contingency plans including scenario-based reprioritisation of activities in order to meet the urgent needs of the Yemeni poor, and re-orientate work plans towards greater investment in cash for work and humanitarian programming DFID continue to lobby donor partners on the importance of working with SFD
4. Reputational Risk
4.1	SFD Funds not used as intended	Medium	High	Use of Independent Montoring to verify use of funds and collect beneficiary feedback SFD Senior management aware of DFID's zero-tolerance approach to fraud and corruption Ability to suspend transfer of funds if concerns are raised.

Outstanding actions from risk assessment

1. Insert clause in future MoU concerning SFD’s responsibility to raise any incidents of political pressure with donors immediately.
2. Explore alternative options to expand financial services at local levels and communicate innovative international examples to SFD.
3. Maintain regular communication with SFD on their ability to operate in the current security situation.
4. Investigate the resilience of SFD’s Headquarters including: staff’s ability to access the building, contingency plans if the building is occupied, the extent to which data is backed up on servers etc.
5. SFD to continue to demonstrate and emphasise their neutrality and autonomy to reassure donors.
6. Consider reducing the size and increasing the frequency of payments to SFD to mitigate the risk of funds being misused or diverted. Payments should also be made in arrears if possible.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
SFD is broadly on track to achieve its targets by December 2015. 20/31 or 65% of milestones were met or exceeded during the last reporting period demonstrating SFD’s impressive absorptive capacity and ability to deliver. Despite its strong performance to date, SFD faces two key obstacles to the achievement of final tagets. The first, and most significant issue, is related to the gap in SFD’s phase IV budget which stood at $346 million as of September 2014. SFD’s shortage of funding is impacting SFD’s capacity to implement pipeline projects or develop new initiatives. SFD had to halt projects under implementation funded by the government contribution, (only 25% of the 2014 commitment has been disbursed to date) and also become more conservative with the planned use of external funding to prevent any over-commitments. As such, SFD had to suspend several projects that were still under preparation and already assigned to donors until there is more clarity and predictability of the government contribution. Such action delays the utilisation of donor funding and risks SFD not being able to achieve its planned targets. SFD is continually in the process of communicating with the government and lead donors to mobilise more funding.

The second issue is related to the deterioriating security situation. While still active in 300 districts, SFD has had to develop new mitigation measures to secure access to the most difficult areas and manage the increasing risk. SFD’s policy to hire local consultants remains an important approach to manage security concerns in areas with sporadic conflicts or where there is political mobilisation and tension. Communication with local communities and councils is also initiated and intensified to secure SFD staff and consultants. In worst case scenarios, implementation is delayed until the project site becomes more stable.

Currently, delayed/halted projects due to security and funding shortages represent 22% of the total SFD-supported projects that are under implementation. 18% of these halted projects had been mainly due to shortages of funds. Security concerns were found to be an issue among 4% of halted projects and are distributed over 15 governorates.

Cause of delay/halting	Halted/halted UI Projects	% Halted/halted UI Projects	Total number of projects under implementation

Funding shortages	436	18%	2,406
Security issues	102	4%

Performance of partnership (s)
SFD is a high performing, resilient and reliable partner with a strong track record for delivery in the most challenging contexts. In addition to its headquarters in Sana’a, SFD operates through 9 branch offices across the country which are responsible for recruiting local technical experts or consultants to assist with the implementation of project activities. All aspects of procurement and project management are managed by SFD field staff. To be a more effective partner, DFID will seek to improve its coordination with other donors to reduce the burden on SFD. This will be particularly relevant during the completion of the Business Case for future support to SFD’s next phase.

Asset monitoring and control
Due to multi-donor support to SFD, DFID do not claim ownership of assets.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Given the current political instability and uncertainty following the occupation of Sana’a by Houthi militants and subsequent signing of the Peace and National Partnership Agreement (PNPA) on 21 September, there is a high degree of uncertainty around any assessment of the Government of Yemen’s (GoY) commitment to, and the direction of travel against, all of the partnership principles. We continue to assess this regularly, particularly concerning our support to SFD which despite being financially and operationally independent of GoY is a quasi-Governmental body set up under Yemeni law with GoY board-level representation.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Evaluation

DFID’s core funding includes support to SFD’s Monitoring and Evaluation Unit. SFD are monitoring service provision and the associated benefits to provide more specific conclusions. SFD researched and now uses Open Data Kit technology to support its monitoring and evaluation. SFD HQ are now able to track enumerators through GPS, providing increased assurance that enumerators are where they claim to be. This will be supported by the World Bank’s Third Party Monitoring and UK Independent Monitoring programmes. We recognise that SFD is a priority for evaluation and support SFD’s central commissioning of large scale evaluations. These will focus on new initiatives and certain sectors that focus on the household level where smaller evaluations are not feasible.

National data being collected

New data from 3 important national statistical exercises will be crucial in helping SFD to update its geographical targeting. These are the National Demographic and Health Survey (data available March 2015); the Household Budget Survey (data available July 2015) and the Census which will progress if the security situation allows.The World Bank has worked closely with consultants at the Central Statistical Organisation (CSO) in Sana’a to finalise the HBS questionnaire including designing a module on social protection/assistance.

Impact evaluations of SFD’s new initiatives in the nutrition sector

The roll-out of two nutrition sector ‘special programmes’ (outside the scope of Phase IV) is due to commence shortly: the Conditional Cash Transfer (CCT) and the Integrated Nutrition Interventions (INI) programmes. The design of an impact evaluation of the two programmes was produced by an external consultant in March and fieldwork started in December 2014. SFD have linked the consulting firm with UNICEF and MoPHP in addition to setting up a technical steering committee. DFID and other donors will follow this closely and input as required. In addition to nutrition interventions being a departure from SFD’s original areas of focus, it will be important for lessons learned to be applied to the Long-term Labor Intensive Works Program (LIWP) which plans to integrate nutritional education and awareness training during the second year of programme implementation.

Evaluation of Empowerment for Local Development (ELD) Program
Discussions are ongoing between SFD’s M&E Unit and a professor of Political Science at the Massachusetts Institute of Technology (MIT) about the evaluation of the ELD program. Though both CLD and ELD projects work with the local communities and offer support, ELD entails a stronger institutional treatment as it mandates the election of a council and only gives matching grants to villages that prove to have enough capacity to implement something on their own. CLD, on the other hand, has more of a monetary emphasis, as the programme works briefly with the community committees that are elected/selected during the process of project identification and implementation. Given these differences, and the added complexity and expense of taking the ELD approach, comparing the effects of ELD to that of CLD (both against control groups getting no assistance) could be fruitful. However, as a result of SFD’s shortage of funds and the lack of capacity to complete the implementation of the interventions, the evaluation has not proceeded. DFID will explore supporting this evaluation with future funding.
DFID should engage with all SFD evaluations. At a minimum, the project team will keep a watching brief on which eveluations are being planned and implemented.
Monitoring Funds Distribution
SFD carried out an analysis of funds distribution to assess the share of investments that go to poorer villages. The analysis covered 655 projects of community and local development (CLD) and the labour-intensive works (LIWP) located in rural areas that have been approved and completed during the period from 1 January 2011to 1 September 2014. The findings show that 82.7% of the investments benefited the highest deprived 50% villages (in accordance to SFD’s national ranking of villages using HBS and Census data).
Monitoring progress throughout the review period

SFD’s main internal area of focus for M&E is the improvement of the Management Information System (MIS). The M&E Unit is working towards various inprovements in the quality of data including clarifying definitions of key reporting indicators and enhancing SFD’s field consultants’ reporting format to ensure that the source of data entered is clearly collected and verified. This will be supported by SFD’s bi-annual data entry audit and ongoing support and training of SFD staff at the branch level on MIS use and data entry.

Joint Donor Reviews, held twice a year, provide an opportity to discuss progress, constraints, risks and challenges with SFD in an open forum. Updates on key project output indicators, accompanied by a financial narrative report are also provided on a quarterly basis along with requests for funds. Audited financial statements are provided annually and reviewed by a financial analyst.

Independent Monitoring

The high risk security situation makes it extremely challenging for DFID and other donors and partners to effectively monitor and evaluate the delivery and impact of their projects across their complete range of operation in Yemen. To mitigate the risks that this poses, DFID Yemen have recently established an Indepedent Monitoring programme to provide independent verification of DFID supported projects in the field, in addition to a range of information from beneficiaries and from the wider population. The programme also gives DFID an ability to focus on specific areas of concern if required. A verification study of SFD’s water and education projects is taking place between November 2014 and February 2015.

Utilisation Survey
SFD’s M&E Unit has completed a Utilisation Survey covering four governorates: Mareb, Al-Jouf, Sana’a and Al-Mahweet as well as the capital city of Sana’a. The survey investigated the operational status of 118 infrastructure projects in sectors completed within the framework of phase IV. The survey found that 94% of the education projects are delivering the intended service, 77% of the water projects are fully operational and the four health projects visited operating and receiving patients. The M&E unit is preparing to extend this study to other governorates and the training for the enumerators is due to start in December 2014.
Monitoring and Evaluation Operational Manual Update
SFD hired a consultant in late January 2014 to update the M&E operational manual however the final output was unsatisfactory. As a result SFD is investigating the option of revising the operational manual internally and seeking external consultants with previous experience working with SFD who have a background in impact evaluation strategies, reporting, and data verification to help in the process.

Project Completion Screen (MIS)
SFD’s Management and Information System (MIS) is the main source of data for the preparation of reports submitted to the government and donors. The data that used to be inputted into the MIS were planned outputs/components and not the actual implemented components, which follow project execution. Projects may undergo changes during the period of implementation that result in outputs that may not match the planned and expected outputs, which used to present a challenge in terms of accurate reporting. A Project Screen has been developed and is now integrated into the MIS to address the previous limitation. The screen requires project officers to input all project components required to complete the project in one screen before converting projects to completed status. This improvement in the MIS will help project officers and the M&E Unit to verify data and rely on accurate project outputs for reporting. The SFD M&E Unit carried out training in how to input the data from the supporting documents in seven branches, and will complete the training in the remaining two braches before the end of this year. The M&E unit is also recruiting data auditors to check the data inputted in the system with the supported documents including the completion report prepared by the consultant.
Review Process

This Annual Review was completed by a Senior Social Development Adviser outside of the DFID Yemen team to provide an element of independence and the DFID Yemen Deputy Programme Manager through a desk-based review and meetings with SFD staff and other donors. The data for the review is based largely on narrative and financial reports provided by SFD as well as data and reports provided during the joint-donor reviews held in June and December 2014. Further supplementary emails containing information on progress were also reviewed.

In addition, discussions were held with key SFD staff including the Managing Director, Head of Monitoring and Evaluation and various Unit Heads.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C