Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Accelerating the Rise in Contraceptive Prevalence in Uganda (ARC)
Programme Value: £35m		Review Date: 24/07/2014
Programme Code: 202420	Start Date: Oct 2011	End Date: May 2015

Summary of Programme Performance
Year	2012	2013	2014	2015
Programme Score	A	A	A
Risk Rating	Low	Low	Medium

Summary of progress and lessons learnt since last review
ARC continued to make good progress against set milestones until this review was carried out in July. A number of changes have happened as a result of last year’s review. In particular, Uganda Health Marketing Group (UHMG) has developed quality checks to ensure services delivered under the network are of an approved standard. However this focus on quality improvement and miscommunication on the availability of funds has meant that some activities slowed down or made less progress than was expected.
Both implementers have increased their work with community health workers in terms of distributing vouchers and encouraging people to attend clinics but also with regards to distribution of short term methods of family planning. Marie Stopes Uganda (MSU) has started to deploy dedicated providers to areas with challenging access to family planning and is using them to help train local health care workers particularly in remote areas in the north of the country.
Uptake of long-acting methods continues to increase, however demand remains passive (with providers reaching out to communities to deliver services and create demand) rather than active (where communities directly demand for services) and uptake of permanent methods of contraception by men remains low. Questions about the reliability of the results reported by one implementing partner on long-acting and permanent methods, especially permanent methods, means that we have removed our appraisal of permanent methods from the review and have adjusted scores accordingly and are recording the possibility that there may be change in results around long-acting methods delivered through outreach. We do not consider that these changes, once clarified, are likely to be sufficient to alter the overall review score but we will revisit this following further investigation.
There remain challenges with data collection, particularly with regards to value for money (VfM), service delivery numbers on permanent methods in particular and outreach services in general due to an allegation of falsification of results by staff within one implementing partner, and socioeconomic disaggregation. The latter is particularly important given some of the changes in delivery model being adopted by UHMG to try to increase their cash client base. Further work needs to be done by both agencies to improve understanding of the impact of fees on client behaviour.
Discussions on VfM have led to changes in the logframe however there needs to be further discussion around this. In particular there needs to be some discussion on unit cost and an overall summary of cost per couple-year of protection (CYP – a standard outcome measure in family planning programmes). UHMG in particular needs to further consider how they will capture VfM not just in terms of reporting for this programme but also in terms of business sustainability.
Since this review was completed in July allegations against one implementing partner regarding falsification of results from permanent methods in particular and outreach services more generally have led to a suspension of funds and questions over the quality of results reported, particularly for permanent methods. The suspension will impact on the project’s ability to meet the remaining results in the logframe over the period July 2014 to May 2015 (planned project end date), and the concerns about results on permanent methods for the period up to July 2015 have been fully reflected in this report. This incident has called into question the current arrangements under delegated cooperation arrangements with USAID and identified the need for closer working with USAID on DCAs in future, alongside a strategic review of the value add of DCAs given that this one does not appear to be cutting down on transaction costs for DFID Uganda.
Summary of recommendations for the next year
1. Continue to improve data collection, particularly with regards to socio economic profile of clients, willingness to pay, VfM, and outreach. UHMG to consider how they will build data management capacity to facilitate reporting on socioeconomic status and VfM. This will help with their business sustainability work too.
2. MSU and UHMG to improve how they work with men to improve uptake of family planning.
3. DFID to arrange more regular meetings with USAID to monitor progress of the programme and address/ understand challenges e.g. financing early.
4. Work with USAID on the project evaluation: consider looking at a few key areas such as the voucher programme, impact of the dedicated provider model, beneficiary understanding and behaviour, value for money, socio economics and sustainability of supply chains, subject to outcome of funding suspension to one implementing partner.
5. MSU to consider ways of improving the financial sustainability of the Blue Star Clinics. Consider working with UHMG to understand some of the models they are using.
6. Start to consider options for and increase dialogue on maintaining progress gained by ARC once the programme draws to a close.
7. With immediate effect, review DFID Uganda’s oversight arrangements under the delegated cooperation arrangement, including strict adherence to quarterly financial and physical progress reporting and joint review.
DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202420/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202420/documents/

A. Introduction and Context (1 page)

Uganda’s fertility and population growth rates are among the highest in the world. Only 26% of women are using modern contraception; 34% of women express an unmet need for family planning. About 44% of all pregnancies are unintended, and these account for the deaths of around 3,000 women every year. The burden of unwanted pregnancy and its consequences disproportionately falls on poor women and adolescents. High fertility is undermining the potential for per capita income growth, and creating additional costs for public service provision.
Half of contraceptive users in Uganda get their contraceptive supplies from the non-state sector; condoms and pills from shops and pharmacies, and injections and intra-uterine devices (IUDs) from NGOs / for-profit providers. A large percentage of sterilisations and implants are administered in public health facilities. Therefore, partnerships between the state and the non-state actors are important for increasing uptake of family planning services in Uganda.
The Government of Uganda recognises the importance of family planning and the need to collaborate with non-state actors to provide family planning services. It has established an alternative mechanism / distribution channel through UHMG to make available family planning commodities to the private sector and NGOs.
ARC aims to increase the availability and use of the most cost-effective modern family planning services through partnership between state and non-state actors. The programme focuses on improving the access to and quality of a range of modern contraceptive methods and ensuring that the poorest groups benefit the most from UK support. The programme is funded jointly by USAID and DFID (DFID as majority funder) and complements the DFID-funded Government of Uganda / UN Joint Programme on Population (GoU-UNJPP) and the USAID-funded reproductive health programme. Whilst the GoU-UNJPP focuses on service delivery through the public sector, ARC complements this by working through the non-state sector to increase access to quality family planning services.
ARC funds MSU and UHMG to expand their existing operations. MSU focuses on social franchising and the provision of sexual and reproductive health services particularly family planning. UHMG focuses on social marketing of long-acting family planning products and demand creation including through the Good Life network of primary health care clinics. DFID is directly procuring family planning commodities for these organisations to ensure best value for UK funds. It uses all proven private sector family planning service delivery channels such as outreach, social marketing and social franchising with and without vouchers. ARC aims to prevent an estimated 650,000 unwanted pregnancies between 2011 and 2015 in Uganda. DFID support will enable at least 300,000 additional women to voluntarily use modern family planning methods of their choice. DFID-attributable planned outputs between October 2011 and September 2015 as stated at the start of the programme were:
i.	Better information about family planning choices.
a.	300 community health workers to be trained to provide information and referral.
b.	Targeted radio campaigns to reach rural communities in 45 more districts, double the number reached prior to October 2011.
ii.	Fewer barriers to accessing family planning services.
a.	200,000 more women to redeem vouchers at accredited family planning service providers.
b.	5 types of family planning products to be available through subsidised social marketing compared to 3 types prior to October 2011.
iii.	A better supply of quality family planning services.
a.	370 more family planning providers to be accredited to MSU and Marie Stopes International’s global standards,
b.	The number of MSU outreach teams working in Uganda to increase from 8 to 20.
c.	500 shops and clinics will provide socially marketed family planning products through the expansion of activities of UHMG.
iv.	More choice of family planning methods. DFID-funded services to provide over:
a.	130,000 IUDs.
b.	260,000 Implants.
These results would contribute to a broader, transformative impact on the Ugandan economy, given the risks to economic and social development posed by the current rate of population growth and the opportunity of social sector savings from lower demands on public services. Following allegations about the quality of results reported from outreach, these results will be revisited.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment:
It is expected that ARC will meet some project objectives by the end of the programme. It would have been on track to meet most project objectives, but suspension of funding and accordingly, activities, for one implementing partner since June has meant that some objectives are now unlikely to be met.

Overall output score and description
The programme has made good progress over the last year. UHMG has focused on improving the quality of services provided by the network of clinics they support. MSU has focused on improving links with the community and public sector and using community health workers to increase awareness of family planning. The supply chain is working well and uptake of long-acting methods is increasing although it is questionable whether this would be maintained without donor input. The results included in this report reflect achievements up to 31st July 2014.

Whilst there has been good progress, there remain some challenges around data from outreach camps, assessment of reach by socioeconomic status, and measurement of value for money, all of which are critical if we are to truly understand the impact of the project.

Key lessons
A number of lessons have been learnt over the course of the ARC project.
1. The ability for social marketing to scale up demand for family planning.
2. The ability to design approaches that can offer services to all quintiles of the population through subsidisation of commodities and free distribution.
3. The potential role of the private sector in providing services to rural populations.

Have assumptions changed since design? No

What would you do differently if re-designing this programme? Encourage greater dialogue between DFID and USAID. Include quality and disaggregation measures from the beginning. Review incentives in place in implementing partners to report results.

How will you and your partners share the lessons learned more widely in your team, across DFID and externally? Documentation and dissemination of the results of the program and the lessons learnt will be carried out at technical meetings with the Ministry of Health and reproductive health stakeholders. A debrief will be organised to share the lessons learnt within the team and the annual review saved on Quest for access across DFID externally. Learning from this programme will be used in the design of the next phase of DFID’s support to the health sector.

Key actions
1. Work with USAID on the design of the independent evaluation. Consider an independent assessment of quality as part of this.
2. Consider ways of assessing willingness to pay and assessing knowledge gained through social marketing tools
3. Work on data collection in particular VfM measures, outreach services and data disaggregation by income quintile. Encourage MSU and UHMG to work together on this.
4. Need to look at ways of ensuring sustainability of finance models and ways of maintaining the supply chain.

Has the logframe been updated since the last review? Yes. An additional outcome on Value for Money was added.

Output 1: Following the 2012 annual review indicator 1 was amended as MSU had already exceeded the target. Instead a new target was introduced, measuring the number of new private facilities supplying family planning services. The review last flagged concerns that some of the new clinics were not delivering quality services and that the focus on numbers should be changed to one on quality. This indicator was changed to a measure of service quality and is included under Output 3. In addition an indicator has been added to Output 1 on reach by different population groups (quintile, age etc). This was included following recommendations from the 2013 annual review to improve community reach through greater interpersonal communication by community health workers.

Output 2, Indicator 2 was removed and replaced by a quality measurement indicator as the indicator on number of subsidised family planning products offered through UHMG through social marketing was achieved in 2013.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Women and men have better information to make healthy reproductive choices
Output number per LF	1	Output Score	B
Risk:	Low	Impact weighting (%):	20
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1. Number of people reached with Family planning messages through DFID supported interpersonal communication and community mobilisation activities disaggregated by age	700,000 (15-24yrs: 70,000), (25 yrs & above: 630,000)	Total = 553,43 / (15-25 yrs: 157,548), (25yrs & above: 395,882)
2. Include indicator that reflects communication funding through the Communication for Healthy Communities (CHC) project implemented by FHI 360.	This is for a component that is just commencing. Milestones and results will be reported next yr.
3. Number of family planning radio spots and talk shows on local radio in social marketing project area (attributable to DFID)	Radio spots: 15000 / Radio talk shows: 120	Radio spots: 12,719 / Radio talks shows: 47
4. Percentage of the population reached nationally with DFID supported messages on family planning	75%	Message reach; radio 62.8%

Key Points
Output 1 focuses on increasing the population’s knowledge and awareness of family planning options and services. It does this through a variety of different activities including use of village health teams (VHTs) in communities to increase knowledge to services and methods and behaviour change communication and social marketing through the media, in particular radio.

This year has seen an increased focus on community health workers as a means of reaching people and increasing awareness of family planning methods and services in response to last year’s comments (further detail below).

Indicator 1 was replaced with one that disaggregated data on reach, and the old indicator was amended to measure service quality rather than numbers of clinics and moved to output 3. Whilst MSU is on track to meet the overall milestone they have reached far more under 25s and fewer over 25s than expected. MSU was able to reach more people below 25 years than planned because of the toll free hotline and Marie-text services, popular among this age-group, that were expanded in 2014. With Uganda’s current age structure, there is a large population under 25 with increased access through these modern communication modes. The population over 25 is mostly reached through VHTs and service delivery points. Poor data capturing and verification at the community level affects the numbers over 25 reached. We regard this as a reasonable trade-off. Reaching adolescents, who are at highest risk for unplanned pregnancies, pregnancies with adverse outcomes and sexually transmitted infections, with messages about family planning and contraception, safe sex and HIV, before or around the same time that they become sexually active, is arguably a better buy than reaching older groups.

MSU is planning to report on additional disaggregated components at the end of the project. They are collecting data over the lifetime of the project.

Indicator 2 has been added to reflect a new communication component recently been agreed with USAID and implemented by FHI 360. It will be reported on next year.

UHMG faced a number of challenges this year in terms of financing and staff turnover that have affected progress against indicators 3 and 4. Delays and confusion over funding due to miscommunication about level of funds available meant that activities commenced in April and were temporarily stopped in June. The results above reflect three months’ worth of work. Conversations with USAID have clarified the funding situation and activities will resume soon.

Summary of responses to issues raised in previous annual reviews (where relevant)

Enhance capacity of community health workers to effectively give advice on family planning:
MSU has trained 300 community health workers in 10 districts to provide access to short term methods of family planning in the community. 180 of these have been trained to also administer the Depo-Provera injection (a hormonal method) in particularly challenging parts of the country in the north. In addition, MSU has set up the dedicated provider scheme where they place an MSU member of staff in public health facilities, either district hospitals or health centre IVs each with the responsibility to train staff in that facility as well as train and supervise health workers in 3 health centre IIIs over an 18 month period.
UHMG is working with BRAC on the training of community health providers to further increase uptake and understanding of family planning. The providers sell some subsidised short term commodities at predetermined prices and keep some of the profits as compensation for services delivered and incentive as they do not receive formal remuneration as VHTs.

Recommendations
1. The indicator on disaggregation of data needs to be further developed by both MSU and UHMG to understand better who is being reached. Consider disaggregation by gender and by income quintile.
2. Consider ways of collecting beneficiary feedback to assess understanding of information provided. This could either be done by the partners or independently as part of the project evaluation.
3. UHMG to look at ways of collecting data on socioeconomic status and willingness to pay, particularly with the move from outreach to clinic days.
4. DFID and USAID to meet quarterly to discuss the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Women and men face fewer barriers to accessing family planning services
Output number per LF	2	Output Score	A+
Risk:	Medium	Impact weighting (%):	20
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of long-acting and permanent methods vouchers redeemed through accredited service delivery points (attributable to DFID)	79,000	92,547

Key Points
Output 2 focuses on increasing access, especially by the poor, to long-acting methods of family planning through a voucher scheme implemented by MSU. The vouchers are sold by community based distributors to members of the community that meet poverty criteria. This is assessed by using a poverty grading tool. The vouchers cover comprehensive family planning services (including insertion, review visits for complications and removal of long-acting methods or for permanent methods) and can be used at any of the MSU Blue Star Clinic franchise clinics. Concerns about the quality of reporting on outreach do not extend to services delivered using vouchers.

There continues to be good progress with the number of long-acting and permanent methods vouchers redeemed through accredited service delivery points. MSU has applied different approaches to try and increase redemption. This includes more engagement with community health workers, use of media, developing a mobilisation strategy and providing business training for providers on how to manage risk and cash flow (since services are only reimbursed after they have been provided and checked).

Summary of responses to issues raised in previous annual reviews (where relevant)

Strategy to increase cash client base and increase synergy between Blue Star (MSU) and Good Life Clinics (UHMG). UHMG is exploring different ways of increasing their cash client base. This includes partnerships with industry to subsidise delivery of services for their staff (eg. Coca Cola and DFCU Bank), and a move from outreach to clinic days. This encourages communities to attend clinics for services, allowing them to access a wider variety of services, some of which they pay for. They are also working with Good Life Clinic owners to see if fees can be levied from other services and are trying to learn from other service delivery areas such as HIV testing. UHMG is also starting to sell a wider variety of commercial products through their warehouses. In the longer term they would like to consider implementation of voucher schemes.

MSU has struggled more to identify ways of improving financial sustainability. They have opened some clinics in peri-urban and urban areas that levy a fee for services from those who can afford it and they are using this to cross subsidise clinics in poorer areas where people are less able to pay. The fees set are based on data from annual surveys and are lower than standard market rates depending on location. Saying this, they never turn anyone away if they can’t pay.

Links between MSU and UHMG have increased. MSU shared quality improvement tools with UHMG for the Good Life Clinics and they have started to have quarterly meetings and joint field visits. In addition they are working together to minimise overlap.

Improvement of Blue Star uptake: addressed above. In order to increase Blue Star uptake MSU is increasing community mobilisation through interpersonal communication using the VHT and satisfied users. The free hotline also provides information on availability of services at these clinics. There is a need for MSU to consider more strategic opportunities to improve their financial sustainability.

Systematic collection on socio-economic profile and ability to pay of clients accessing services through the Blue Star Clinics and other service delivery channels: UHMG is exploring the potential to link with an organisation conducting population surveys that will be conducted in the next year and include questions on willingness to pay. They are measuring SE status according to the geographic regions they operate in. MSU is collecting information on SE status from the poverty grading tool they use when issuing vouchers however collecting data on cash clients is challenging.

Recommendations
1. Good Life Clinics to measure the impact of clinic days versus outreach on the access to services by people of different socio-economic status.
2. MSU and UHMG to continue to look at ways of measuring socio-economic profile and ability to pay.
3. MSU to consider additional ways of improving financial sustainability of the Blue Star Clinics. Consider working with UHMG to understand some of the models they are using.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	The supply of quality family planning services and products in Uganda is expanded
Output number per LF	3	Output Score	B
Risk:	Medium	Impact weighting (%):	40
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of long-acting and permanent methods services provided by outreach at public sector facilities (attributable to DFID)	83,600	Unable to report due to concerns about reporting of permanent methods. However, permanent methods represent a small proportion of services delivered (around 15%, historically) and we judge that this milestone has been fully met or exceeded without it. If we are to completely exclude permanent methods reported from the total, the number of services delivered sums to 84,065, which exceeds the target.
Percentage increment in Quality Treatment Assessment score among public health workers after the training and mentoring process.	10%	Assessment will only be carried out in 2015
Percent of Good Life Clinics that meet 80% of quality standards on 2 successive quality improvement visit	75% of all Good Life Clinics	88%
The number of short term hormonal family planning methods sold through social marketing (attributable to DFID)	1,181,250 injectables and 698,775 pills	755,908 (inj) 635,237 (pills) (only results up to 30th June 2014 available)

Key Points
Output 3 focuses on increasing the supply of quality family planning goods and services available in Uganda. Key activities include increasing the quantity of quality long-acting family planning commodities available through bulk purchasing and distribution by UHMG warehouses, improving the quality of clinics by objectively assessing services provided using a scoring tool and using social franchising to improve availability and uptake of family planning in primary health care centres.

UHMG has taken on board recommendations to improve the quality of Good Life Clinics and has worked with MSU, MoH and WHO to develop tools for assessing quality of clinics. Uptake of long-acting methods of contraception continues to increase. The number of pills sold through social marketing is likely to meet this year’s milestone. However fewer injectables were sold over the past year and the milestone may not be met. Part of this may be due to confusion over DFID funding which delayed social marketing work till April 2014. In addition, concerns about the quality of reporting of services delivered by outreach teams calls into question the data on the number of long-acting and permanent methods delivered using the outreach model.

Summary of responses to issues raised in previous annual reviews (where relevant)
There is need to consider a quality related indicator relevant to the Good Life Clinics to provide assurance on services provided through these clinics: UHMG took on board this recommendation and worked closely with MSU to develop tools to assess and improve quality of Good Life Clinics. It would be useful to independently assess these instruments to get a picture of the level of quality being delivered by Good Life Clinics.

There is need to review the current marketing strategy for the socially marketed short term methods particularly information on market segmentation that profiles the clients ability to pay. This may provide useful data that will inform the marketing approach: UHMG has looked at ways of measuring willingness to pay and are considering including some questions in a population survey that will be implemented next year by another agency.

Innovative capacity building efforts, with a big focus on follow up supervision and mentoring as opposed to training alone, should be implemented to strengthen the role of public health workers in routine provision of family planning services. This has not been reported against, however MSU’s dedicated provider programme places trained MSU staff in public health facilities i.e district hospitals and health centre IVs where they each mentor and train government health workers including staff in three health centre IIIs to deliver family planning services.

Recommendations
1. Consider independent quality checks of clinics or review quality tools used as part of the evaluation.
2. Continue to look for ways to improve measurement of willingness to pay data and information on socioeconomic profile of clients and follow up with UHMG on recommendation 2 from the 2013 AR.
3. Consider sustainability of the dedicated provider model of training. Discuss other methods of mentoring and capacity building with USAID and partners.
4. Ensure implementation of recommendations following the review of results reporting from outreach.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	A better choice of family planning methods is available and being used
Output number per LF	4	Output Score	A
Risk:	Low	Impact weighting (%):	20
Risk revised since last AR?	N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of implants and IUDs provided by MSU programmes (attributable to DFID)	57,000 (IUD) / 117,000 (Implants)	47,934 (IUDs) / 115,179 (Implants)
Number of implants and IUDs provided through UHMG social marketing activities (attributable to DFID)	1,500 (IUDs) / 3,000 (implants)	2,591 IUDs and / 11,829 implants
Numbers of tubal ligations / vasectomies performed by MSU programmes (attributable to DFID)	3,420(V) / 31,200 (TL)	755 (V) / TLs not reported due to concerns raised about quality of results reporting

Key Points
Output 4 focuses on improving the availability of a range of different family planning methods (including long-acting methods) and improving uptake. Key activities include increasing the long-acting methods available through UHMG’s network of Good Life Clinics and MSU’s Blue Star franchise clinics and training staff to offer permanent methods of family planning in MSU clinics.

Against this output, one indicator has exceeded expectation, one has roughly met expectation, and one has fallen short, justifying an overall score of A – met expectations. Field visit discussions with both health workers and women attending clinics show that there is awareness of long-acting and permanent methods. Despite this, when both partners were questioned on whether uptake of long-acting and permanent methods was sustainable now without the programme, they both felt that demand was still passive and required providers to reach out to communities to deliver services and create demand. In terms of permanent methods, demand for vasectomies remains low.

Summary of responses to issues raised in previous annual reviews (where relevant)
There is need for continued efforts to increase uptake of IUDs. DFID support through the GoU-UNJPP should be synergised with the ARC programme to enhance achievement of results: There continues to be push to increase uptake of IUDs and it is increasing. However work to align with the UNJPP programme has not moved ahead and with only three months left of support to UN-JPP we do not recommend taking this recommendation forward.

Recommendations
1. Consider ways of working with men to increase uptake of permanent methods of contraception.
2. There needs to be some thought given to the sustainability of this programme particularly if it were to end next year. There has obviously been progress increasing availability of family planning methods etc but it may be too early to completely discontinue funding this programme and expect the impacts to continue. There needs to be some discussion with the Government and development partners on how to maintain the supply chain and continue to encourage uptake.
3. Ensure implementation of recommendations following the review of results reporting from outreach.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The key cost drivers are the cost of commodities, transport and personnel.
VfM performance compared to the original VfM proposition in the business case
There is evidence of VfM in the programme. There was a 55% decrease in cost of Jadelle and Implanon as a result of negotiations between the manufacturers and an initiative by a group of private and public sector partners to subsidise prices for these products in response to the July 2012 London Summit on Family Planning and the UN Commission on Life-saving Commodities’ call to improve access to family planning commodities. In addition, the cost per CYP especially through social marketing has been maintained significantly lower than projected in the business case. However assessment needs to be carried out in terms of the efficiency of the programme.
Assessment of whether the programme continues to represent value for money
Economy: This concerns the process of turning DFID money into inputs.
Procurement of commodities: This is managed by the International Procurement Agency (IPA) through a direct contract with DFID. IPA uses a competitive process to procure the commodities. Given the importance of implants in the methods provided under the programme, the recent agreement to reduce the price of both Jadelle and Implanon by over 50% has generated significant savings. These savings enabled increase in quantities of implants procured for the programme
Efficiency: This concerns the transformation of money into outputs. The key efficiency measures are costs of delivering service through the different channels.
Similar to last year it is to be expected that costs per long-acting and permanent method service through outreach would be the highest since service to more remote communities is included and MSU bears the cost of staff, vehicles and fuel. The unit costs for Good Life Clinics would be expected to be much lower since: (i) the non-commodity costs are not subsidised by DFID but paid by clients; and, (ii) the services delivered are overwhelmingly for short-term methods for which the price of both commodity and underlying service costs are much lower. Neither MSU nor UHMG has measured the cost per long-acting and permanent method through the different channels.
Effectiveness: This concerns whether the interventions chosen are the right ones to maximise the impact on the desired outcome. A good proxy for this is the cost per CYP. The economic appraisal in the Business Case suggested that the cost per CYP across the whole programme would be £11. A provisional average cost per CYP has been calculated but not published in this review due to concerns about the quality of data relating to permanent methods delivered through outreach. It also did not include some of the costs incurred during the provision of services e.g. costs to government facilities at which outreaches are conducted – these costs may include a small amount of staff time and a small attribution for infrastructure.
Recommendations:
1. MSU and UHMG need to conduct further work to establish and monitor the unit cost of services delivered. MSU and UHMG to work together on calculating VfM. UHMG may need to hire technical support to do this.
2. Monitor the unit cost of commodities procured.
3. Consider including VfM as a component of the final project evaluation.
4. Ensure implementation of recommendations following the review of results reporting from outreach.

Quality of financial management
Date of last narrative financial report	31/07/2014
Date of last audited annual statement	28/02/2014 (UHMG); 10/12/2012 (MSU)

USAID provides quarterly reports that indicate good financial management and good financial procedures. The last narrative financial report was received on 31 July 2014. Both UHMG and MSU shared their annual progress reporting with DFID during the 2014 Annual Review meetings held with them on 21st and 22nd July respectively. During the year, USAID conducted a financial review of MSU. The report of this review had not yet been shared by USAID when the suspension due to misreporting of results begun. USAID has now agreed to share this report before the end of the calendar year. The external audits for UHMG and MSU have been done and were forwarded to the USAID Regional Inspector General in Pretoria for review and issuance. Once these have been issued, they will be shared with DFID by USAID. Going forward, DFID and USAID will hold regular quarterly meetings to discuss quarterly reports and performance.

E: RISK (½ page)

Overall risk rating: Medium – revised up since last year due to increased attention to commodity distribution and risk perceived in the reproductive health services voucher scheme.

Overview of programme risk
Description of risk	Probability	Impact	Comments (August 2014)
Lack of national political support. Ugandan government policy is supportive of family planning, but there is a strong pro-natalist sentiment in the statements of some politicians. There is also some religious opposition to family planning in general, and to MSU in particular because of its association with abortion.	Medium	Medium	Given increasing domestic budget allocations towards family planning exceeding Uganda’s commitments at the FP2020 Summit in July 2012 ($6.9m compared with a $5m commitment), the probability attached to this risk is judged to remain low. However, the reputation of family planning will be significantly damaged if the communications around the alleged problems with results reporting by one implementing partner are not handled well. We are working with USAID to address this.
Government of Uganda engagement. In particular, MSU’s outreach services are delivered mainly in MoH facilities, so the outreach programme is heavily dependent on MSU achieving and maintaining a good working relationship with the MoH.	Medium	Medium	MSU continues to collaborate well with MoH particularly at the district level. Government of Uganda capacity – including at the MoH remains weak and this remains a risk for long-term coherence and effectiveness of family planning service delivery. In addition, there are challenges with the capacity of health workers to deliver particularly long term family planning methods through routine care particularly in the north of the country. However, the relationship will be significantly damaged if the communications around the alleged problems with results reporting by one implementing partner are not handled well. We are working with USAID to address this.
Impact of the voucher programme. MSU has experience of vouchers in Uganda and MSU has experience elsewhere, but such a large voucher scheme may have unpredictable effects on demand and supply in the overall market.	Medium	Low	These questions remain important and will be revisited with USAID to decide on the best approach to evaluating the question. The government are working with the WB to develop a larger voucher scheme for maternal and new-born health.
Changes in US legislation.	Medium	High	Reduced following the 2012 US election, but rising again due to results from the mid-term elections and the forthcoming Presidential election in 2016.
Implementation management capacity. The ability of MSU to achieve the rapid scale-up proposed in this programme has not been proven. UHMG is a relatively new organisation still in the process of developing full management capabilities.	Medium	Medium	MSU has been able to set up the Blue Star franchise. They continue to increase the number of clinics accredited. MSU has also been able to provide outreach services in all the districts in Uganda achieving national coverage. While UHMG has demonstrated strength in social marketing, it is a priority for them to strengthen their social franchising capacity – particularly on quality of care. As part of this they have reduced the number of clinics in their network to allow a focus on quality. UHMG has capacity constraints with regards to data management. In addition, MSU needs to enhance their efforts to manage clients from their large outreach operations that may experience side effects and complications.
Fraud in voucher scheme or commodity distribution	Medium	Medium	This has been reviewed and assurance provided to Head of Office.

Outstanding actions from risk assessment
1. Assessment of voucher schemes impact on supply and demand to be discussed with USAID.
2. Handling of communications around outreach services results reporting and funding suspension to be discussed with USAID and a way forward implemented.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The budget for the ARC programme was re-profiled. £1,500,000 was reallocated from 2014/15s budget to 2015/16 at the start of the financial year. This budget re-profiling affected MSU funding for this year as all UHMG allocations at the time had already been disbursed and CHC activities not yet commenced. Subsequently, a proposed £4,250,000 disbursement this month has been suspended due to the investigation into results falsification, and a large component of the £4,000,000 disbursed in July may be returned to DFID.

Below is the programme expenditure analysis against component expenditure.

	Total Budget £	Total Expenditure £	% spend	Comments
Delivery through USAID for UHMG, MSU and CHC	27,950,000	18,200,000	65%	Out of the £5,750,000 remaining balance; £1,500,000 was allocated to FY 15/16 in line with DFID’s budget approval.
Procurement of commodities through IPA	4,259,060	3,556,330	84%	There was no procurement of Implanon in 2014 following overstocking of the commodity; however total budget was not affected.
Procurement of services and monitoring and evaluation	1,049,886	9,624	1%	There has been little spend on this component as the original impact evaluation approach was put on hold due to capacity constraints in the DFID office and advice from the senior evaluation adviser that a full impact evaluation would not be possible.

Performance of partnership(s)

MSU will remain an important player in the family planning landscape in Uganda in coming years, but sustainability is a concern.

UHMG has also performed strongly in its areas of strength namely social marketing and communications/behaviour change. Last year there were concerns over its level of competence as a social franchiser particularly around its capacity for effective training, accreditation, reporting and quality assurance of clinical services in the Good Life Clinic network. They have focused on these aspects over the last year working closely with the MoH and MSU to address this. There needs to be an in depth assessment of quality but this does seem to have improved. There remain capacity gaps around data capture and monitoring which is essential to improve business viability. They have done well in terms of warehousing and storage expanding their operations beyond traditional medical commodities thus increasing their profits.

USAID has worked effectively to manage and implement DFID resources in this programme. Results are being delivered on DFID’s behalf through the social marketing and outreach services. The ‘delegated authority’ arrangement represented an effective model when the programme was launched in 2011. Although a greater role is by DFID is recommended by Internal Audit Department now that DFID has significantly increased its in country technical capacity on health and is playing a leadership role in policy dialogue with government, implementers and other stakeholders, the current model at times dampens that function for DFID and can result in confusion for partners. There needs to be closer dialogue between USAID and DFID on the programme now and on family planning once the programme ends.

Asset monitoring and control including commodity stock levels

USAID monitor and control assets involved in the project. USAID maintains a list of assets for MSU and this has been shared with DFID. DFID is also aware of commodity stock status as UHMG regularly submits warehouse stock reports and DFID also participates in the monthly Family Planning and Reproductive Health Commodity supply meetings. DFID obtains forecasts from MSU and UHMG and forwards these to IPA for placement of orders.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant): Not relevant

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

We will revisit plans for an impact evaluation with USAID.

Monitoring progress throughout the review period

The programme is managed by USAID through a delegation cooperation agreement. This limits the amount of direct monitoring done by DFID during the reporting period. DFID conducts annual joint field visits with USAID and the implementing partners. In 2014 a joint USAID/DFID field visit was not possible due to various departmental commitments, however DFID carried out the field visits with the partners and DFID plans to meet USAID quarterly going forward.

As part of this review field visits were conducted and meetings held with MSU, UHMG, the MoH, and USAID.
Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process