Annual Review – post April 2018

Title: Support to Displaced People and Migrants
Programme Value £ (full life): £36,000,000		Review Date: 26th April 2019
Programme Code: 300404	Start Date: 1st June 2017	End Date: 31st May 2020

Summary of Programme Performance
Year	2018	2019
Programme Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	Business Case and Summary 300404
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Description of programme (1/2 page)

Over the last year the humanitarian outlook for refugees, migrants and displaced persons in Yemen has continued to deteriorate. Over 93,000 migrants arrived in Yemen in 2018, despite the protracted conflict and grave risks. By the end of 2018 there were an estimated 422,000 refugees, asylum-seekers and migrants living in Yemen. Over 90% of asylum-seekers, refugees and migrants originate from Ethiopia, with the rest coming from Somalia. More than 30% are unaccompanied minors, and the most vulnerable are pregnant and lactating mothers (4%) and children under 5 (4%). Trafficking remains a serious protection risk, alongside a lack of social safety nets, discrimination, stigma, lack of documentation to access basic services, and the ever-present threat of detention and deportation. This has been compounded by the suspension of registration of asylum-seekers and renewal of refugee documentation in the North in August 2016. Registration resumed in November 2018, but many remain undocumented, increasing the risk of arrest and deportation.

The number of internally displaced persons (IDPs) and returnees in Yemen increased by more than 1m over the course of 2018, to a total of 4.3 million since the start of the conflict. IDPs alone account for 11% of the Yemeni population.[1] More than half of the IDPs are living in Amanat Al Asimah, Hajjah, Taizz, Al Hodeidah and Sa’ada governorates, and about 60% have been displaced since the start of the conflict. Significant new displacement occurred in 2018 with the escalation of conflict along the West coast. Approximately 685,000 people were displaced from Hodeidah (511,310) and Hajjah (157,120). Other conflict-affected areas, such as Sa’ada, saw temporary displacement and further displacement of existing IDPs, as people moved out of areas experiencing violence for a period of days or weeks. The majority of IDPs live in rented accommodation or with host families, but 26% live in open sites such as public buildings, collective centres or spontaneous settlements where services are extremely limited and living conditions are dire.
[1] The 2019 Humanitarian Needs Overview estimates the total population of Yemen to be 30.5 million. They estimate that there are currently 3.34 million IDPs, 1.01 million IDP returnees and 420,000 refugees and migrants in Yemen. https://reliefweb.int/sites/reliefweb.int/files/resources/2019_Yemen_HNO_FINAL.pdf

Throughout the past year IOM and UNHCR have worked to meet the protection needs of refugees, migrants and IDPs despite the high levels of need and operational challenges, delivering:
- Humanitarian assistance including water, sanitation and hygiene services (WASH), food, non-food items (NFIs)[2], temporary shelter, cash assistance to meet basic needs and healthcare.
  [2] NFI kits include personal hygiene products, clothing materials, soap, footwear, mattresses and blankets.
- Specialist protection services including (Sexual) Gender-Based Violence ((S)GBV) prevention and response, legal assistance, mental health and psychosocial support (MHPSS).
- Monitoring flows of migrants into Yemen, and displacement tracking within Yemen, helping to determine where migrants and IDPs are located, what their needs are and informing the humanitarian response.
- Strengthened coordination of protection activities through UNHCR’s leadership of the Protection Cluster.
- Life-saving cholera treatment for over 22,000 individuals.

Over the last financial year (April 2018 – March 2019), DFID contributed £7.8 million to IOM and £3.5 million to UNHCR. Both programme components have results attributable to DFID funding as detailed in each output below.

Summary supporting narrative for the overall score in this review

The overall output score for 2019 is an A as most outputs have met or exceeded expectations and the programme continues to achieve its intended outcomes and impact. Only Output 1 scored a B, accounting for 20% of the total programme. All others (80% of the programme) scored an A or A+.

Consistency
Output 4, UNHCR’s support to Community Based Protection Networks, and 5, Protection Cluster coordination, remained at an A+, overachieving against all measurable indicators.

Improvements
Output 1, IOM’s humanitarian and protection support to migrants, improved from a B in 2018 to an A this year, with 7 indicators significantly overachieving, 2 indicators underachieving, two reporting insufficient data and one yet to be implemented but on track to meet targets by the end of the programme.
- Output 2, UNHCR’s support to refugees and asylum-seekers, increased from an A to an A+.
- Output 3, measuring support for IDPs delivered by both IOM and UNHCR, improved from a B to an A as IOM made progress on the provision of legal assistance services.
- Output 6, IOM’s displacement tracking matrix (DTM), improved dramatically, moving from a C to an A, as nation-wide data collection began.

In August 2017, IOM was granted an additional £2 million to support their cholera response, followed by a no-cost extension to extend this support to 31st July 2018. IOM delivered against the majority of their targets, achieving an A for Output 7. Due to the addition of this Output, the impact weightings for all other Outputs have been proportionately reduced.

Both UNHCR and IOM have improved their performance this year. IOM in particular has made significant improvements to certain activities, such as the DTM, and has made considerable efforts to strengthen the coordination of the consortium. IOM’s consortium partners have implemented innovative, adaptive programming, and have established a strong, cooperative relationship with DFID colleagues.

However, reporting from both UNHCR and IOM remains quite descriptive, and the level of analysis provided can make it challenging to assess the reasons for over or under achievement of targets. Reporting against the outputs below reflects this challenge, with clear recommendations on the importance of improving the level of analysis in reporting to ensure that quality and impact of activities is much clearer. Several outputs also include recommendations to strengthen beneficiary accountability under this programme which remains an underreported area.

Recommendations for the year ahead

Recommendation	Responsible	Deadline
Output 1
IOM and consortium partners to thoroughly assess their ability to deliver Indicator 1.5 (beneficiaries supported through protection referrals, including victims of trafficking and GBV) and propose alternative use of funding if appropriate.	IOM	Y3 Q2
If IOM is unable to train any health consultants by the end of Y2, they should propose alternatives.	IOM	Y3 Q1
DFID and IOM to discuss increasing support for host communities.	DFID, IOM	Y3 Q1
Output 2
UNHCR to provide data on beneficiary satisfaction, as required in the logframe.	UNHCR	Y3 Q1
UNHCR to include greater detail in narrative reporting to indicate the quality and impact of activities	UNHCR	Y3 Q1
Output 3
IOM’s to better explain overachievement of targets and revise where appropriate.	DFID, IOM	Y3 Q1
IOM and consortium partners to thoroughly assess ability to deliver Indicator 3.7 (cases referred for specialised services) and propose alternative use of funding if appropriate.	IOM	Y3 Q1
UNHCR to clarify the effectiveness of one-off cash transfers.	DFID, UNHCR	Y3 Q1
DFID to explore effectiveness of SMS communication with UNHCR	DFID, UNHCR	Y3 Q1
DFID to look for opportunities to strengthen support for women and girls through this programme.	DFID, IOM, UNHCR	Y3 Q2
Output 4
UNHCR to improve the effectiveness of Community Based Protection Networks	DFID, UNHCR	Ongoing
Output 5
DFID to work with CIMP to improve the quality and accuracy of data and analysis.	DFID, UNHCR	Ongoing
Output 6
IOM DTM team to improve the quality and accuracy of data	DFID, IOM	Ongoing
IOM to work towards an interactive, real-time platform for DTM information	IOM	Ongoing
IOM to improve IDP and migrant intentions data	IOM	Ongoing
Output 7
DFID and partners to ensure all potential obstacles and delays are considered if implementing future surge responses.	DFID	Ongoing
IOM to ensure lessons learnt from cholera project are mapped out and considered for any future interventions.	IOM	Ongoing
Logframe
UNHCR and IOM to revise logframe targets	UNHCR, IOM	Y3 Q1
IOM and UNHCR to include beneficiary satisfaction indicators that can be reported against each quarter.	IOM, UNHCR	Y3 Q1
IOM to ensure % of host communities receiving services and % of beneficiaries receiving two or more services are reported.	IOM	Y3 Q1
DFID and partners to review overarching logframe, attempting to streamline results where possible.	DFID, IOM, UNHCR	Y3 Q1
Value for Money
DFID to better understand cost pressures faced by UNHCR and IOM under this programme	DFID, UNHCR, IOM	Y3 Q1
DFID to work with partners to improve reporting on efficiency and effectiveness of activities.	DFID, IOM, UNHCR	Ongoing
Risk, delivery, commercial and financial performance
UNHCR to provide comprehensive written risk updates on a quarterly basis	UNHCR	Y3 Q1
UNHCR to brief DFID on their results allocation and targeting	UNHCR	Y3 Q1
UNHCR to improve the quality of narrative reporting by providing examples of successes, challenges, and impacts of interventions	UNHCR	Y3 Q1
IOM to prioritise the recruitment of a dedicated Consortium Coordinator	IOM	Y3 Q1
IOM and DFID to ensure monthly meetings are held regularly and, where possible, attended by the same people	IOM, DFID	Ongoing
IOM to provide a verbal update on spend at monthly meetings	IOM	Ongoing
IOM to ensure reports are delivered on time	IOM	Y3 Q1
IOM and UNHCR to provide updated asset registers	IOM	Y3 Q1
Monitoring, evaluation and learning
IOM to take on board recommendations from the Independent Monitoring report and provide updates to DFID on a quarterly basis	IOM	Ongoing
IOM and consortium partners to continue improving beneficiary feedback systems, particularly for migrants	IOM	Ongoing
UNHCR to prioritise travelling out of country for at least one quarterly meeting per year.	UNHCR	Y3 Q1
DFID to explore use of Catapult satellite imagery to strengthen IOM programming e.g. IDP settlement mapping.	DFID	Y3 Q1

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Conflict affected migrants have improved access to humanitarian and protection services.(IOM)
Output number per LF		1	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicators		Implementing partner	Milestone[3]	Progress
1.1	Number of migrants registered.[4]	IOM, DRC, Intersos	29,532	76,873	260%
1.2	Number of migrants receiving WASH, food, NFIs, ICLA, temporary shelter or transportation services.[5] % of migrants receiving two or more services.	IOM, DRC, Intersos	16,500	76,487	464%
1.3	Number of migrants benefiting from life-saving health care.[6] % of beneficiaries reporting satisfaction with service received.	IOM	7,800	25,957	333%
1.4	Number of migrants benefiting from MHPSS and PSS.	IOM, Intersos	3,992	21,418	537%
1.5	Number of beneficiaries supported through protection referrals, including victims of trafficking and GBV.	IOM, NRC, DRC	2,172	1,108	51%
1.6	Number of migrants receiving legal counselling. % of beneficiaries reporting satisfaction with service received.	NRC, DRC	4,840	16,362	338%
1.7	Number of community members receiving awareness sessions on migrants' rights. % of beneficiaries reporting improved knowledge.	IOM, Intersos	3,600	2,409	67%
1.8	Number of migrants receiving awareness sessions on migrants' rights and humanitarian assistance. % of beneficiaries reporting satisfaction with information received.	IOM, Intersos. NRC	29,668	61,678	208%
1.9	Number of individuals receiving training in mainstreaming cross-cutting issues such as inclusion, PSS and MRE. % of beneficiaries reporting improved knowledge.	NRC, HI	292	458	157%
1.10	Number of government health consultants trained by IOM on healthcare.	IOM	90	0	0%
1.11	% of surveyed beneficiaries reporting that they have received the project through safety, dignity and relevant to their needs.	IOM, NRC, DRC, HI, Intersos	80%	Insufficient data reported
1.12	# of awareness sessions on the existence and use of feedback mechanisms	IOM, NRC, DRC, HI, Intersos	16	Insufficient data reported
[3] Milestones reflect logframe targets since those recorded in last year’s Annual Review.
[4] Identifying vulnerabilities and human rights abuses suffered.
[5] Prioritizing the most vulnerable including women, children, persons with disability and the elderly.
[6] Including medical consultations, reproductive health care, health awareness, vaccinations and paramedic assistance.

Briefly describe the output and provide supporting narrative for the score

Of the indicators there were able to implement, IOM significant overachieved against 7 and underachieved against 2. Overall, this output has met expectations and therefore scores an A.

This output provides migrants with protection services including health care, psychosocial support, legal support, basic services and awareness sessions. These services are provided through IOM and consortium partners Norwegian Refugee Council (NRC), Danish Refugee Council (DRC) and Intersos. Handicap International (HI) is also a member of the consortium, providing training to partners on cross-cutting issues such as inclusion and mine risk education (MRE).

In 2018, 93,091 migrants arrived in Yemen, 80,679 of whom were Ethiopian, and 12,412 of whom were Somali. 75% were men, 16% were women, 7% were boys and 2% were girls. Of the 8,618 children who arrived in 2018, 21% (1,828) were unaccompanied and 114 were under 5 years of age. Of the 93,091 total, 8 were pregnant or lactating women and 8 had a physical disability.[7]
[7] This data was collected at Flow Monitoring Points in the governorates of Shabwah, Hadramut and Lahj. https://www.iom.int/sites/default/files/dtm/yemen_dtm_201801-12.pdf

IOM have exceeded their targets for indicators 1.1, 1.2, 1.3, 1.4, 1.6, 1.8 and 1.9 by a minimum of 57%. Since the last Annual Review, the consortium has registered 39,289 migrants; provided 62,284 with WASH, food, NFIs, temporary shelter or transportation; assisted 18,392 with emergency health care and 13,584 with mental health and psychosocial support; and provided legal counselling to 11,622. IOM and consortium partners faced delays in implementing several components at the beginning of this programme due to delays in signing agreements across the country, and therefore have increased activity over the past year once these issues were resolved.

However, the following indicators underachieved against their targets:

Indicator 1.5
IOM provides referrals to mental health and psychosocial support (MHPSS), health, legal and protection services for victims of trafficking (VoT) and GBV. Partners aim to follow all referrals until beneficiaries receive the intended services, although DRC have highlighted that this has been difficult due to the mobile nature of migrants and lack of communication channels as many don’t have phones.

1,108 migrants have received protection referrals since the last Annual Review. 70% of these were men, 21% were boys, 7% were women, and 2% were girls. Only 51% of the target has been reached, owing largely to external constraints. Access constraints along the Western Coast have prevented IOM from identifying VoTs there, NRC has found it difficult to target migrants on the move, and DRC has had issues confirming their sub-agreement in the North, limiting their capacity to refer cases there.

Partners have begun to tackle these issues; for example, NRC has engaged volunteers in Aden to alert them to new arrivals and IOM is improving screening measures to better identify cases of concern. Partners should continue to monitor these barriers, assessing their realistic ability to deliver against existing targets in the current operating environment and reprogramming as appropriate.

Indicator 1.7
Since June 2018, Intersos has reached 1,928 host community members through 101 awareness sessions on migrants’ rights in Lahj and Hadramout. Due to delays in signing sub-agreements, these activities did not begin until Q3 of the first year of the programme, impacting Intersos’ ability to meet their cumulative targets in following quarters. However, activity has picked up significantly over the last 6 months as Intersos expanded the trainings to Hadramout and aim to continue along this trajectory to ensure the overall programme target is met.

Indicator 1.10
IOM has been unable to train any government health consultants due to heavy restrictions and censorship of training imposed by authorities, particularly in the North. So far, IOM has been refused permission to organise any training, but the team remains optimistic that they will be able to achieve the full target within the lifetime of the programme. Should restrictions continue into the final quarter of Year 2, IOM should explore alternatives, such as delivering training only in the South, or redistributing funds elsewhere to support other programme activities.

Indicators 1.11 and 1.12
Insufficient data has been provided to report against these indicators. IOM and consortium partners are exploring alternative ways to collect feedback from migrants and the logframe should be updated to address this.

The consortium has seen improvements over the past year, and has demonstrated several instances of innovative, flexible programming, which should be commended. For example, DRC added a paramedic to the migrant response team, who was able to provide life-saving first aid to 375 people in the last quarter. NRC have also placed a volunteer representative within the migrant community to notify them of new waves of arrivals, enabling them to target arrival locations with greater accuracy. Consortium management and cooperation has also improved, owing largely to the allocation of a Consortium Coordinator and the introduction of monthly meetings with DFID and partners. However, improvements to working relationships could still be made, and this should remain a priority for IOM throughout the lifetime of the programme.

Lessons identified this year, and recommendations for the year ahead linked to this output

Partners have reported increasing instances of migrant detentions over the past year. In Q6, DRC reported that only 71% of recipients were able to redeem their food vouchers. This may be due to some migrants being detained before they were able to get a meal. The consortium is making attempts to better understand this issue and it remains an important concern.

Consortium partners have also raised the lack of support for host communities as a cause for concern over the past year. It is recommended that DFID and the IOM consortium explore how best this programme could incorporate support to host communities.

Additionally, the original logframe included measures of beneficiary satisfaction across 5 indicators (highlighted in blue in the table above), which have not been possible to report against. IOM and consortium partners have notified DFID of the difficulties with recording feedback from migrants, who often don’t have phones and are regularly on the move. DRC have made various attempts to tackle this issue, for example by placing monitors in locations where food vouchers can be redeemed but this did not have the level of success envisaged. IOM also deployed staff to facilities to gather feedback and have designed a database to collect findings of community feedback. They have also shared a video explaining feedback mechanisms on social media. The consortium has a dedicated Information Management and Monitoring and Evaluation (IM & ME) working group which is currently developing a standardised survey tool to be used by all partners. This should be reflected in the logframe through a stand-alone beneficiary satisfaction indicator, disaggregated by service where possible.

IOM have also never reported the number of beneficiaries receiving two or more services. This information should be provided in all future reports.

Indicators that have overachieved against their targets have done so significantly, by up to 537%. Therefore, it is recommended that IOM and consortium members conduct a thorough analysis of the logframe targets to ensure they reflect current ambition levels and anticipated operational ability for the remainder of the programme.

Output Title	Refugees and asylum-seekers have improved access to protection services. (UNHCR)
Output number per LF		2	Output Score	A+
Impact weighting (%):		20	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicator(s)		Implementing partner	Milestone	Progress
2.1	Number of individuals supported with SGBV prevention and response activities[8]	UNHCR, Intersos	1,237	1,680	135%
2.2	Percentage of assisted refugees (disaggregated by age, gender and nationality), reporting that some of their immediate protection needs were fulfilled	UNHCR	80%	Not reported	N/A
2.3	Number of gender specific community-based committees/ groups working on SGBV prevention and response	UNHCR, Intersos	12	12	100%
2.4	Number of children supported with child protection activities[9]	UNHCR, Intersos, SDF	1,956	2,648	135%
2.5	Number of Best Interest Determination (BID) assessments conducted[10]	UNHCR	87	91	105%
[8] SGBV survivors receive medical support, legal services and psychosocial counselling.
[9] These activities are specifically implemented in Sana'a, Aden, Kharaz, camp and Lahj.
[10] A BID assessment is the formal process designed to determine a child’s best interest for particularly important decisions affecting the child, the require stricter procedural safeguards. https://www.unhcr.org/uk/protection/children/4566b16b2/unhcr-guidelines-determining-best-interests-child.html

Briefly describe the output and provide supporting narrative for the score

This output has exceeded expectations and scores an A+.

This output provides refugees and asylum seekers with SGBV prevention and response and child protection activities. These services are provided though UNHCR and downstream partners Intersos (in Lahj, Aden and Sana’a) and SDF (in Sana’a).

UNHCR reports that as of March 2019, there are 274,162 refugees and asylum seekers in Yemen.[11] However, only 5,854 individuals were registered with UNHCR in 2018. Refugees and asylum-seekers continue to face challenges such as smuggling, trafficking, detention and restricted freedom of movement. Kharaz camp, located in Lahj governorate, is the only refugee camp in Yemen, hosting roughly 8,000 people, 98% of whom are Somali. The majority of refugees live in informal settlements and urban areas. Resettlement opportunities remain scarce and local formal integration has been unattainable for the overwhelming majority of refugees.
[11] UNHCR operational update, 15th March 2019 https://reliefweb.int/sites/reliefweb.int/files/resources/Yemen%20EXTERNAL%20Operational%20Update%2015%20March.pdf

In October 2018, alterations were made to some of UNHCR’s targets to reflect the barriers they have faced in operating as planned. Targets for indicators 2.1 and 2.5 were reduced as a result. For Output 2.5 – to conduct a BID assessment with a child – UNHCR must first register the child as an asylum seeker. However, due to restrictions imposed by authorities in the North of Yemen, asylum seeker registration rates have been lower than anticipated, preventing UNHCR from conducting the number of BID assessments planned. Therefore, the overall programme target was reduced from 765 to 190. However, child refugees who should have received BID assessments continue to benefit from other child protection activities implemented by UNHCR, such as psychosocial support and child-friendly spaces, for which the over target number of beneficiaries has increased from 975 to 3,400.

For Output 2.1, the number of SGBV community committees supporting refugees was initially set to grow throughout the lifetime of the programme. However, UNHCR only implements this particular activity in Kharaz camp, where 12 SGBV committees have now been established. The population of Kharaz camp has since reduced due to people moving to urban areas or spontaneously returning to their country of origin. UNHCR anticipate that the Kharaz camp population will now remain at a similar level throughout the remainder of the programme and that the 12 SGBV committees will sufficiently cover the needs; the overall target has therefore been reduced from 48 to 12. SGBV support for refugees and asylum seekers is also offered through UNHCR’s other prevention and response activities, which have reached 1,680 people in the last year.

Lessons identified this year, and recommendations for the year ahead linked to this output

UNHCR has met or exceeded the majority of indicators under this output, demonstrating reliable service delivery throughout the lifetime of the programme. However, it has been difficult to measure the quality of these activities, due to lack of reporting against Indicator 2.2, and lack of detail included in quarterly reports. It is recommended that UNHCR provide data on beneficiary feedback and endeavour to include a greater level of analysis within the narrative reports submitted to DFID by providing more specific examples of how interventions have benefitted recipients or achieved their intended outputs, outcomes and impact.

Output Title	Internally Displaced People (IDPs) have improved access to humanitarian and protection services. (IOM and UNHCR)
Output number per LF		3	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicator(s)		Implementing partner	Milestone	Progress
3.1	Number of IDPs receiving unconditional cash grants	UNHCR, ADRA, YRC	3,600	3,849	107%
3.2	Number of IDPs receiving legal assistance	UNHCR, Intersos	2,250	4,653	167%
3.3	Number of IDPs receiving psychosocial support	UNHCR	12,750	12,952	102%
3.4	Percentage of assisted IDPs (disaggregated by age, gender, geography, disability), reporting that some of their immediate protection needs were fulfilled	UNHCR	80%	93%	116%
3.5	Number of IDPs and % host community members benefiting from life-saving health care % of beneficiaries reporting satisfaction with service received.	IOM	19,500	18,271	94%
3.6	Number of IDPs benefiting from MHPSS and PSS. % of beneficiaries reporting satisfaction with service received.	IOM	4,000	10,268	257%
3.7	Number of cases referred for specialised services[12]	IOM, NRC	1,275	305	24%
3.8	Number of beneficiaries of legal counselling	NRC	842	5,185	615%
3.9	Number of beneficiaries of legal assistance % of beneficiaries reporting satisfaction with service received.	NRC	433	3,888	897%
3.10	Number of child protection cases identified and assisted with reintegration support.	IOM	75	78	104%
3.11	Number of IDPs receiving awareness sessions on rights and humanitarian assistance. % of beneficiaries reporting satisfaction with information received.	IOM	1,688	10,810	640%
3.12	Number of health facilities provided with operational support.	IOM	2	0	0%
3.13	Number of government health consultants trained	IOM	120	0	0%
[12] Including victims of trafficking and GBV.

Briefly describe the output and provide supporting narrative for the score

Of the indicators they were able to implement, IOM significantly overachieved against 5 indicators, overachieved against 4 and underachieved against 2. Overall, this output has met expectations and therefore scores an A.
Through this output, IOM, UNHCR and partners provide protection services to Internally Displaced Persons (IDPs) in Yemen, including legal assistance, health care and psychosocial support, cash grants and awareness sessions.

It is estimated that there are currently 3.3 million IDPs in Yemen. More than half of all IDPs are living in Amanat Al Asimah, Hajjah, Taizz, Al Hudaydah and Sa’ada governorates, and roughly 60% have been displaced since the conflict began. 26% of IDPs live in hosted sites such as public buildings, collective shelters, or settlements. Services at these locations are often limited, and residents face significant protection risks, including exploitation, harassment and GBV. 74% of those outside these sites live in rented accommodation or with host communities. IDP households are facing the most extreme hunger levels resulting in the adoption of negative coping strategies such as begging as a means of income, child labour or child marriage, which further exacerbates protection risks.[13] Food assistance is provided through DFID’s programme with WFP, who have reached 175,967 IDP households (estimated 1,055,802 people) with immediate response rations between June and December 2018, complementing the protection activities under this programme.
[13] 2019 Humanitarian Needs Overview https://reliefweb.int/sites/reliefweb.int/files/resources/2019_Yemen_HNO_FINAL.pdf

UNHCR

Over the past year, UNHCR scaled-up its cash programming, which has been assessed as the most effective and efficient way for people to meet their most immediate needs. UNHCR targets people with immediate protection needs such as medical concerns, domestic violence, or psychosocial needs due to war trauma. Recipients are identified through UNHCR’s unified Protection Monitoring Tool (PMT), which is completed during a household visit and contains detailed questions on the protection situation of potential beneficiaries. Vulnerability scoring based on UNHCR’s cash criteria is then applied to identify the most in need. UNHCR’s overachievement against Indicator 3.1 can largely be attributed to a favourable exchange rate between the YER and US Dollar, allowing them to provide a further 3,849 cash distributions since the last Annual Review.

Legal assistance provided by UNHCR mainly includes issuance of essential documentation such as civil status documentation and birth registration documents, including for children born outside marriage. However, they also provide representation in courts for conflict mediation relating to marriage, divorce and alimony, and legal advice to resolve Housing, Land and Property disputes. UNHCR have provided legal assistance to 4,653 in the last year, of which roughly 85% of cases related to civil documentation.

UNHCR have reached 12,952 IDPs with psychosocial support since the last Annual Review, just overachieving against their target. This includes individual and group therapy sessions at community centres and through mobile teams. Those requiring psychiatric assistance are referred to hospital or a specialised mental health centre.

UNHCR has overachieved against all targets and should revise future targets to accurately represent ambition and capacity levels.

IOM

IOM and consortium members have significantly overachieved against targets for Indicators 3.6, 3.8, 3.9, and 3.11, by a minimum of 157%. DFID and IOM should explore why these services were able to be implemented at such a greater rate than planned, applying relevant lessons learnt where possible to other underperforming indicators.

IOM reached 94% of the intended beneficiaries with health care assistance (3.5), including emergency primary health care, child health, reproductive health services and health awareness sessions. This is provided through fixed and mobile health clinics operating in IDP concentrated areas, where host community members also have access to services. IOM has achieved between 88 and 104% against this indicator on a quarterly basis throughout the second year of the programme. However, concerns were raised through the Independent Monitoring report about the quality of data collected under this indicator, calling into question the validity of this achievement. This issue is addressed further in Section G.

IOM supported 78 children this year (19 boys and 59 girls) with reintegration support, all of whom were identified as victims of trafficking. This includes focused psychosocial support and reintegration grants. IOM is currently working to tailor livelihood activities for these children or their parents/guardians.

However, targets for indicators 3.7, 3.12 and 3.13 were significantly underachieved.

Indicator 3.7

Since June 2017, IOM has only referred 254 cases for specialised protection services, including victims of trafficking and GBV. Of the 254, 20% were men, 23% were women, 35% were boys and 22% were girls. The consortium struggled to process referrals in the North as authorities asked to see confidential data they could not provide.

Last year’s Annual Review also referenced a poorly resourced referral network and recommended that IOM consider supplementing referrals with more direct service delivery. Poor availability of services continues to be an issue faced by the Protection Cluster as a whole and has been flagged by other donors as an area for improvement. The upcoming Protection Roundtable scheduled for May 2019 will present an opportunity to discuss this in more detail with the Protection Cluster and other donors, and identify actions to be followed up bilaterally with IOM and UNHCR. In the meantime, IOM has made improvements to the consortium referral pathway and recently had a standardised referral form finalised and endorsed by all consortium partners. HI has also concluded their mapping of MHPSS services, which they now plan to integrate into the referrals system.

Following these discussions, IOM and consortium partners should assess their ability to deliver against this indicator, identifying challenges and areas for improvement to ensure protection referrals are provided at an adequate scale for the need.

Indicators 3.12 and 3.13

As noted under Output 1, IOM have been unable to implement activities under Indicator 3.13 due to restrictions from authorities but should be able to begin implementation from Year 3 onwards. Indicator 3.12, however, has been delayed due to IOM prioritising the allocation of other donor funding. Overall targets are still expected to be met within the lifetime of the programme. IOM has been adequately informed of DFID’s spending expectations and should not be utilising other donor funds to cover activities allocated to this programme. Alternatively, DFID should consider funding alternative activities if there is appetite from others to fund health facilities.

Lessons identified this year, and recommendations for the year ahead linked to this output

As is the case with Output 1, IOM have not reported against the four beneficiary satisfaction indicators marked above in blue. The consortium has set up an Information Management and Monitoring and Evaluation (IM & ME) working group to tackle issues with beneficiary feedback, and it is recommended that logframe changes are made accordingly to capture changes.

IOM have also not been able to provide information on the percentage of host community members receiving health care. It is also currently unclear which other services host communities benefit from through this Output. As noted under Output 1, this is an area DFID should explore further with IOM, and IOM should provide data on the number of host community members also receiving services through this programme.

UNHCR’s cash assistance is provided as a one-off payment of 100,000 YER. UNHCR showed good adaptive programming when they increased the one-off cash payment amount to 150,000 in the latter half of 2018 and lowered it again in early 2019 to ensure beneficiaries retained appropriate purchasing power in response to the currency fluctuation. They also ensured this change was communicated to beneficiaries via text message and by members of the Community Based Protection Networks and community centres. However, the effectiveness of these one-off cash distributions of set amounts as opposed to longer-term cash assistance is unclear and DFID should explore this issue further with UNHCR. DFID should also work with UNHCR to understand the potential to apply SMS-based communication systems to gather beneficiary feedback and improve accountability to affected populations.

Women and children account for roughly 75% of those displaced by the war and there has been an increasing trend of female-headed households across the country. Women and girls are disproportionately affected by the conflict and face grave protection risks. In particular, conflict and economic pressures are increasing the risks of GBV, with 3 million Yemeni women and girls currently at risk of GBV, and 60,000 women at risk of sexual violence.[14] DFID should look to strengthen protection support for women and girls through this programme, particularly relating to the provision of SGBV services.
[14] IRC report: Protection, participation and potential: Women and girls in Yemen’s war https://www.rescue.org/report/protection-participation-and-potential-women-and-girls-yemens-war

Output Title	Strengthened protection monitoring and support to Community Based Protection Networks (UNHCR)
Output number per LF		4	Output Score	A+
Impact weighting (%):		8	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicator(s)		Implementing partner	Cumulative Q6 milestone	Progress
4.1	Number of active Community Based Protection Network members trained/engaged	UNHCR	140	141	100%
4.2	Number of PoC identified through protection monitoring	UNHCR	145,000	189,729	130%

Briefly describe the output and provide supporting narrative for the score

This output has exceeded expectations and therefore scores an A+.

This output relates to UNHCR’s support to community-based protection networks (CBPNs) for IDPs. UNHCR partners with Intersos, ADRA, Yemen Development Foundation, Yemen Red Crescent Society, Yemen Women’s Union, Hodeidah Girls’ Foundation and Yemen Alkair for Relief and Development to deliver this intervention. The core activity of the CBPNs is to conduct protection monitoring to identify persons of concern (PoCs) to UNHCR who require specialist protection support. Over the course of 2018 UNHCR trained 141 CBPN members to carry out these activities. UNHCR also worked to standardise the protection monitoring tool used by the members to ensure a consistent approach to identifying protection risks and concerns. The tool includes individual assessments, household assessments and focus group discussions. Through this UNHCR has reached 189,279 individuals, exceeding their target by 30%.

The expansion of the CBPNs has enhanced community participation and engagement in the identification of protection risks and strengthened IDPs’ own capacity to address these risks as well as helped to develop the common protection service directory to facilitate referrals. CBPN members refer persons with specific protection needs to other services, such as (S)GBV response, psychosocial support, healthcare services and legal assistance. The common protection service directory has gone a long way to supporting consistency and quality in the referral pathway, but it remains a challenge to track individual cases through referrals to ensure needs are ultimately met in a timely way and to a high standard. The next stage to develop the CBPNs would be to try and move towards a case management approach for referrals.

Lessons identified this year, and recommendations for the year ahead linked to this output

UNHCR to improve the effectiveness of CBPN interventions, particularly to strengthen referral pathways.

Output Title	Strengthened coordination through Protection Cluster support (UNHCR)
Output number per LF		5	Output Score	A+
Impact weighting (%):		4	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicator(s)		Implementing partner	Cumulative Q6 milestone	Progress
5.1	Number of partner staff members and government authorities trained	UNHCR	438	1,252	286%
5.2	Number of information products produced and disseminated	UNHCR	90	157	174%
5.3	Number of protection cluster meetings held each quarter	UNHCR	3	3	100%

Briefly describe the output and provide supporting narrative for the score

UNHCR has overachieved against all of the indicators for this output and therefore scores an A+.

UNHCR is the lead agency for the Protection Cluster in Yemen, providing overall coordination of protection activities including the GBV, child protection and mine action sub-clusters/working groups. Protection Cluster meetings were held monthly throughout 2018 at national and hub level.

The number of partner staff and government partners trained on protection and coordination significantly exceeded targets in 2018 due to a larger number of training sessions conducted towards the end of the year and the increased interest in training provided by the Cluster, reaching a cumulative total of 1,252 persons trained.
In August 2018 the Civilian Impact Monitoring Project (CIMP), which records conflict incidents affecting civilians and civilian infrastructure, expanded its coverage to national level, using complementary funds from other donors alongside funds provided by DFID to expand the scope of the intervention significantly. CIMP now has five operational hubs (Aden, Ibb, Sana’a, Sa’ada and Hodeidah) covering all Governorates, providing critical information on the impact on civilians of real time conflict events, based on open source information together with reports from partners.
In addition to daily alerts and flash alerts for significant events, CIMP shared weekly and monthly analytical highlights, presented its analysis at the monthly Protection Cluster meetings and produced written trend analysis on a quarterly basis. These reports were crucial to monitor the impact of incidents on civilians, both directly and indirectly affecting their lives and livelihoods. CIMP data was used directly to support programming, for example helping to determine the location of community centres according to where protection needs are highest.
Lessons identified this year, and recommendations for the year ahead linked to this output

DFID to continue working with CIMP to improve the quality of CIMP data and analysis.

Output Title	Yemeni population displacement and migrant monitoring (IOM)
Output number per LF		6	Output Score	A
Impact weighting (%):		8	Impact weighting % revised since last AR?	Reduced due to addition of Output 7

Indicator(s)		Implementing partner	Cumulative Q6 milestone	Progress
6.1	Number of Displacement Tracking Matrix (DTM) reports developed and shared with humanitarian actors in Yemen	IOM	12	34	283%
6.2	Number of Migrant flow monitoring reports on migrant trends shared with humanitarian actors in Yemen	IOM	12	10	83%
6.3	Number of training sessions conducted on new/enhanced DTM tools, methodologies, and quality control procedures to ensure the accurate and comprehensive data collection	IOM	3	45	1500%

Briefly describe the output and provide supporting narrative for the score

Although fewer migrant flow monitoring reports were published in the last year than intended, IOM published almost triple the number of DTM reports planned and held 42 additional training sessions. This output has therefore met expectations and scores an A.

This output relates to the IOM-led Displacement Tracking Mechanism (DTM), which records the flow of IDPs within Yemen, and IOM’s migrant flow monitoring which monitors the movement of migrants into Yemen as well as returns from Saudi Arabia.

Over the past year IOM has significantly expanded the DTM, which now encompasses area assessments and the emergency tracking tool. After a one-year hiatus in data collection due to access constraints, DTM reinitiated its area assessment in November 2018.

The area assessment is the main tool in the DTM to track population movement. The primary purpose of the area assessment is to track and monitor population movements at the district and sub-district level in Yemen to collate, analyse and share comprehensive baseline information on IDP and returnee populations; including numbers, locations, demographics, locations of origin, time of displacement, shelter types accommodated per location, sex and age disaggregated data, and movement patterns. Data for the area assessments was collected in November and December 2018, covering 95% of sub-districts in all 22 Governorates of Yemen. The area assessments were slightly delayed due to IOM enumerators being used to support the response-wide Multi-Cluster Location Assessment (MCLA). Without this the MCLA would not have been possible and is critical in forming the basis of the annual Humanitarian Needs Overview (HNO). This helps to explain the partial underachievement of output 6.1. The data is due to be released in full in early 2019. The area assessments provide important baseline data about IDP populations. Given that the majority of IDPs have been displaced for several years these assessments will help to identify what core needs are, identify gaps in responding to them and help to inform whether and how the humanitarian response to protracted IDPs should differ from those who have been newly displaced.

Beyond the area assessment IOM also used the Emergency Tracking Tool (ETT) to compile daily information from IOM and various partners including local and international NGOs and local and national authorities. According to the ETT between 1 June and 10 December 2018, 114,158 households (684,948 individuals, assuming an average household size of 6) were displaced due to an escalation in armed clashes across Yemen mostly from Hodeidah Governorate. These IDPs are living within host communities with family and friends, and some within IDP sites managed by authorities and NGOs. The ETT information helped agencies to identify the number and location of IDPs fleeing Hodeidah enabling agencies to preposition stocks in the right place and ensure they could reach IDPs to provide timely assistance.

IOM’s flow monitoring is an exercise through which DTM monitors trends in mobility into, out of, and within a country or region. Enumerators are deployed to seven pre-identified entry, exit and transit locations into and out of Yemen, referred to as Flow Monitoring Points (FMPs), where enumerators observe groups passing through the point and collect basic information, such as the number of people per group, nationality, point of departure, intended destination, sex and age disaggregation and visible vulnerabilities. Flow monitoring helps to identify the number of migrants from other countries entering Yemen, which helps agencies to provide a more targeted response to those with acute vulnerabilities. For example, flow monitoring has helped IOM to identify migrant patterns to know where to target assistance most effectively under this programme. It has also helped to show the number of Yemeni returns from KSA which is important to help understand where people are planning to return to so agencies can ensure response activities are in place.

IOM’s ETT and flow monitoring could be improved by developing an interactive, real-time web platform to enable humanitarian actors to see movements of people in a timely manner and respond more effectively.

Lessons identified this year, and recommendations for the year ahead linked to this output

- The quality and accuracy of DTM products has improved significantly over the reporting period, but remains a challenge due to difficulties in accessing IDP populations in certain areas and triangulating information. The IOM DTM team should work to improve the quality and accuracy of DTM data.
- In order to make use of DTM information in the most timely way to enable IOM should assess whether or no an interactive, real-time platform for DTM information is viable and will improve IDP and migrant intentions data.

Output Title	Cholera response (IOM)
Output number per LF		7	Output Score	A
Impact weighting (%):		20	Impact weighting % revised since last AR?	New output

Indicator(s)		Milestone (Sep 17 – Aug 18)	Progress
7.1	Number of cholera cases receiving health care at supported facilities	20,000	22,472	112%
7.2	Number of individuals reached through the health awareness activities (HH and awareness sessions)	65,600	60,600	92%
7.3	Number of people benefiting from water chlorination activities	80,000	400,000	500%
7.4	Number of individuals benefiting from water trucking	30,000	14,658	48%
7.5	Number of individuals benefitting from the rehabilitation of water networks	30,000	56,987	189%
7.6	Number of individuals benefiting from cholera hygiene kit provision	70,000	56,000	80%
7.7	Number of individuals benefiting from solid and liquid waste management activities	80,000	111,102	138%

Briefly describe the output and provide supporting narrative for the score

Although some activities have underachieved against their targets, overall IOM were able to treat 2,472 additional cases of cholera than planned and reach almost double the intended beneficiaries with water and sanitation hygiene (WASH) activities. This output is therefore assessed to have met expectations and scores an A.

During the last year, DFID extended its support to IOM’s cholera response, funding £2 million for cholera-related activities between 1st September 2017 and 31st August 2018. During this period, IOM targeted 14 districts in Hajjah, Hodeidah, Taizz, Ibb and Amran, working mostly through the Yemen Family Care Association and Yemen Red Crescent Society.

In total, IOM were able to treat 22,472 cases of cholera and acute watery diarrhoea (AWD) through 8 AWD treatment centres and 36 oral rehydration points. 19% were men, 18% were women, 35% were boys and 28% were girls. These facilities were supported by the provision of incentives for staff, medicines and medical supplies, equipment and WASH support. Minor rehabilitation was also provided when necessary.

IOM also conducted health promotion activities including training community health workers and conducting health awareness activities and visits. 206 health workers were trained on cholera case definition, diagnosis and treatment. 414 health care staff received training on infection prevention and control. 100 volunteers were trained on hygiene and health awareness, who in turn visited 8,000 households and conducted 300 infection prevention awareness sessions in communities. In total, 60,600 people were reached with hygiene and disease prevention messages.

400,000 people benefitted from water chlorination activities, 56,000 from cholera kits and 111,102 from waste management activities. IOM also supported the rehabilitation of 30 WASH facilities at health care centres and 7 water sites/networks in Ibb, Amran and Hajjah.

Lessons identified this year, and recommendations for the year ahead linked to this output

This project was originally intended to last from 1st September 2017 to 1st March 2018. However, IOM faced delays in rolling out some project activities due to bureaucratic hurdles presented by local authorities and security concerns and so was granted a no-cost extension to 31st August 2018. If DFID is to fund a similar surge project with IOM in the future, these obstacles should be taken into consideration and factored into response times.

These delays meant IOM was required to initially implement most activities through its downstream partners, which required continual support to guide them through financial and reporting procedures. IOM’s restricted movements also minimised their ability to monitor activities delivered by these partners. However, working through implementing partners did facilitate access and enabled them to begin the response sooner. IOM should ensure lessons learnt through this process are captured and used to enhance future activities and partner relationships.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The overall Theory of Change (ToC) underpinning this and other DFID humanitarian interventions in Yemen is shown below, with the inputs, processes and outputs relevant to this programme highlighted in red. This has been updated to reflect current assumptions, however the inputs, outputs, outcome and impact remain the same.
Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
ASSUMPTIONS

- Security allows for ongoing humanitarian operations
- Humanitarian access into and within Yemen is maintained
- Civilians can access humanitarian assistance
- Humanitarian agencies maintain permission to operate in Yemen
- Economy does not deteriorate to the extent that operations cannot continue

The expected impact of this programme is that the vulnerabilities of people affected by the conflict in Yemen are identified and reduced, prioritising the most vulnerable. The expected outcome is that the urgent humanitarian protection needs of migrants, refugees, asylum seekers and IDPs in Yemen are identified and met. Based on the assessment of this Annual Review, we continue to expect these to be met.

The assumptions noted above continue to hold, although have been challenged to differing degrees over the last year. For example, the economic situation has fluctuated over the last year, but this has not yet had any major impact on IOM or UNHCR’s ability to deliver humanitarian assistance inside Yemen and UNHCR in fact benefited from the exchange rate fluctuation which enabled them to overachieve on their cash assistance targets. Security and access challenges continue to affect humanitarian organisations present in Yemen and remain a major risk to programming.

Overall, this programme has improved since the last Annual Review, with all outputs scoring an A or A+. IOM and UNHCR are currently on track to meet planned targets by the end of the programme.

Explain major changes to the logframe in the past year

In October 2018, alterations were made to UNHCR’s targets to reflect their operational capacity. From June 2018 (Y2 Q1) onwards, targets were increased for nine indicators[15] and reduced for two. The reduced targets related to indicators measuring the number of children receiving Best Interest Determination (BID) assessments, and the number of SGBV community committees supporting refugees. Justification for this has been provided under Output 3.
[15] From UNHCR stand along logframe: Impact 2, Outcome 1&2, Output 2.1, 2.2, 3.1, 4.2, 5.1 and 5.4

Effort was also made to clarify the language used in particular indicators, for example, clarifying that the SGBV community committees are gender specific. No indicators were added or removed, and none of these changes affected the overall aim or budget of the programme.

Describe any planned changes to the logframe as a result of this review

UNHCR has continued to overachieve against a number of targets, which will be increased again following this Annual Review. Whilst consistent overachievement may be commended, it may also be indicative of an initial lack of ambition, uneven application of resources, or inadequate targeting. DFID should gain a more in-depth understanding of UNHCR’s results allocation and targeting to better understand their consistent overachievement.

Conversations with IOM and the consortium regarding logframe amendments are ongoing. Based on the recommendations of this Annual Review, revisions will be made to clarify the language used in particular indicators, establish a stand-alone indicator to measure beneficiary satisfaction under each output, and amend targets to reflect IOM’s capability to deliver. It is recommended that DFID and IOM confirm all logframe amendments within a month of this Annual Review.

The quality of IOM’s logframe reporting has also been poor over the last year, and concerns over the accuracy of data were highlighted in the latest Independent Monitoring (IM) assessment. Logframe submissions are sometimes missing data or duplicate figures in catch-all indicators. IOM should address this by ensuring logframe submissions undergo a thorough quality assurance check before submission, and should take action on the IM recommendations, explored further below in Section G.

The overarching logframe for this programme is measuring a very large number of indicators. It is recommended that DFID and partners review logframe indicators in an attempt to streamline results where possible and reduce reporting requirements.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Economy

Both IOM and UNHCR procure goods such as NFIs and food items in large quantities at a global level to ensure cost savings and value for money. IOM and UNHCR should work to better understand the specific cost pressures faced through this programme to identify possible opportunities to reduce costs and improve Value for Money.

Efficiency

From Y2 Q1, several of UNHCR’s targets were increased. For example, the overall target for individuals supported with SGBV prevention and response activities doubled from 1,650 to 3,300. This was due to UNHCR consistently overachieving against the existing targets. UNHCR continue to achieve 100% or more on almost all of their indicators, showing that they are able to efficiently implement programmes, reaching more beneficiaries with the same budget.

IOM’s consortium continues to strive for the most efficient approach to delivery. This can be seen in their efforts to streamline working groups across the consortium and cooperatively strengthen the referrals system.

Effectiveness

In September 2018, the SRO approved the following programme adjustments for the IOM consortium:
- In the South, DRC expanded their Protection Patrolling Team, procured Emergency Medical Supplies and began do-no-harm activities to mitigate tensions between migrants and host communities.
- NRC added multi-purpose cash assistance for protection cases and reprogrammed activities in the North to target IDPs rather than migrants following continuous refusal from MoFA for any activities supporting migrants.
- In Lahj, Intersos increased the number of awareness sessions for migrants and community members and the number of collective PSEA sessions. Intersos also expanded the Migrant Response Team to Hadramout and expanded the procurement and distribution of emergency food rations.
- IOM added protection activities to migrants in the coastal areas of Shabwa and Hadramout.
- Handicap International cancelled their planned assessments of partners PSS approach.

These changes did not affect the overall programme budget and have allowed IOM and consortium partners to deliver a more effective response. Since these revisions, DRC have also added a paramedic to their coastal patrolling team to provide emergency medical support to migrant arrivals. In November 2018, 66 medical cases were identified, of which 38 were given first aid and 28 were stabilised and referred to IOM’s mobile clinic or health centre for onward assistance. The paramedic has subsequently briefed doctors on the types of cases seen on the coast to anticipate future needs at the hospital, saving time and improving the efficiency of the response.

Due to the depreciation of the Riyal, UNHCR were able to distribute more one-off emergency cash grants to IDPs this year, even though the amount increased from 100,000 YER to 150,000 YER when the economic crisis was at its peak. They have reached 6,714 beneficiaries with cash assistance through this programme since June 2017, 1,914 more than the target. These are one-off distributions given in response to emergency situations, such as medical emergencies, or to someone fleeing domestic violence. However, there remains a question on the effectiveness of one-off cash distributions to a larger number of people versus repeat distributions to those who are the most acutely vulnerable. DFID should work with UNHCR to assess the effectiveness of one-off versus repeat cash distributions in addressing protection needs.

Equity

The groups targeted through this programme, IDPs, refugees, asylum-seekers and migrants, are amongst the most vulnerable in Yemen. A large proportion of IDPs are also women and children, and all groups include people with specific needs. IOM’s Independent Monitoring report found that assistance was being delivered to the targeted communities, providing assurance that the most vulnerable are being benefitting from this programme as intended.

Both UNHCR and IOM disaggregate their data by gender, with IOM also reporting number of child beneficiaries. Handicap International, who provide a technical advisory role in the consortium to support inclusion mainstreaming, has recommended that data also be disaggregated by disability using the Washington Group questions.[16] The consortium is currently taking this forward and DFID should follow up on a regular basis to ensure disability reporting is included in submissions whenever possible. HI are also collecting information on access of persons with disabilities to different services and will feed the findings back to the consortium.
[16] The Washington Group Questions are a set of questions designed to identify people with a disability.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

Through this programme, DFID supports four of the five most vulnerable groups identified in the 2019 HNO: 1) IDPs and returnees, 2) children, 3) women and girls, and 4) refugees, migrants and asylum-seekers. Thus, DFID funds are reaching the most in need in Yemen, and therefore provide VfM from an equity perspective.

IOM and consortium members have improved both their delivery and cooperation over the last year, leading a more efficient response. They have also improved the efficacy of their programme by making small but impactful changes, such as the addition of a paramedic to the Migrant Response Team.

UNHCR have provided VfM by overachieving against all their measurable targets and enabling DFID funds to reach more people with assistance. However, it has been difficult to measure the quality, and therefore effectiveness of their response due to the lower level of detail provided in reports.

As a whole, the programme has shown significant process from last year and should continue from a VfM perspective.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Risk / category	Risks	Mitigation measures	Residual risk
Delivery	1. DFID has a reduced monitoring capacity without staff present in country. / 2. Hostile environment creates high staff turnover and risks low capacity of staff to deliver / 3. Reliance on downstream partners for delivery / 4. Poor financial management leading to significant underspend (IOM) / 5. Weak consortium management and cooperation (IOM)	- IOM and UNHCR have both participated in DFID’s Independent Monitoring programme. / - IOM have several members of staff covering finances in country and regularly meet with consortium partners to monitor financial reporting. / - IOM has a dedicated Consortium Coordinator and facilitates regular meetings with all consortium members to discuss common issues and challenges. DFID holds quarterly meetings with the consortium which has increased over the reporting period to monthly meetings with all consortium members to more closely monitor implementation and financial management. / - DFID has increased the percentage of time the Programme Manager spends on financial monitoring of IOM reports, including conducting thorough reviews of financial reports and forecasts and setting out expectations clearly at monthly meetings and in written communication. The Programme Manager and SRO have also worked closely with the Senior Programme Manager and Humanitarian Team Leader to ensure they are aware of any financial challenges and can provide appropriate support.	Major
Fiduciary	1. Aid diversion through loss or damage / 2. Risk of fraud and corruption taking place. / 3. DFID funds are diverted to terrorist organisations.	- DFID regularly communicates the importance of preventing and reporting fraud and corruption to all partners. Both IOM and UNHCR have reported any suspicions of fraud or aid diversion to DFID in a timely manner. / - There is minimal procurement through this programme. / - Both submit deconfliction requests and keep on top of security updates to minimise risk. / - Appropriate precautions and controls such as security guards, bars, CCTV, stock logs etc. are in place in facilities. / - Both have beneficiary feedback mechanisms through which beneficiaries can report instances of fraud or aid diversion and are working to strengthen these systems. / - MoUs confirm partners obligation to comply with UK counter-terrorism legislation. / - Mitigation measure for Delivery risks also apply. / - IOM’s most recent independent monitoring report found no reports of fraud or aid diversion in the programme.	Major
External context	1. Conflict situation deteriorates, reducing the ability of partners to deliver / 2. Increasing insecurity poses risks to staff safety / 3. Bureaucratic impediments, such as procurement delays, visa refusals, restricted movement, or air space regulations, prevent programme delivery / 4. Restraints on commercial imports prevent programme delivery / 5. Exchange rate fluctuation negatively impacts programming	- DFID works advocates with all parties to the conflict on humanitarian access; and HMG supports the work of Special Envoy to work towards a political solution. / - DFID work with all major donors to lobby on the importance of keeping ports open to help tackle humanitarian crisis and maintains high level of communication with all partners to monitor the situation. / - UNHCR and IOM have operational hubs throughout Yemen to strengthen the capacity of the humanitarian response system to operate. / - UNHCR and IOM work closely with local partners who have better access and networks across the country. / - UNHCR and IOM are in regular contact with government and defacto authorities to establish their mandate and activities and regularly meet with local authorities to improve access. / - OCHA’s Access Monitoring Working Group works to lobby on access constraints and support negotiation processes. / - UNHCR and IOM regularly monitor the security situation and use the EHOC deconfliction notification system to deconflict field missions.	Major
Safe / guarding	1. Beneficiaries and/or staff harmed by programme activities. / 2. Incidences of sexual exploitation and abuse (SEA) occur.	- DFID is in the process of conducting an enhanced due diligence assessment on UNHCR and IOM centrally and DFID Yemen will implement recommendations. / - Both IOM and UNHCR strive for a conflict sensitive approach to implementation, for example by also supporting host communities	Major
Operational	1. DFID is unable to fulfil its duty of care towards staff. / 2. Low internal staff capacity due to heavy workloads, lack of monitoring capability and risk of PM/Adviser gap.	- DFID staff are not currently able to travel to Yemen. DFID instead prioritises travel to the region to enable regular monitoring of programming and establish strong relationships with partners. / - Programme Manager ensures all programme documents (delivery plan, delivery chain, programme summary) and Vault folders are kept up to date so key information can be easily accessed and passed on. / - DFID has appropriate recruitment processes in place for timely recruitment.	Moderate
Reputational	1. Largescale aid diversion or fraud case / 2. Mass casualty or damage incident affecting DFID programmes / 3. Safeguarding risks are realised	- DFID encourages clear, open, honest conversations about these risks with partners, aiming to identify and mitigate against them early. / - Safeguarding and fiduciary mitigation measures cover reputations risk mitigation.	Major

The overall risk of this project remains major as it involves operations in an active conflict where access remains a challenge.

IOM provides updates on risk in their quarterly narrative reports and in quarterly meetings, and proactively share allegations of fraud, loss and aid diversion with DFID.

UNHCR reports that risks have not substantially changed since the beginning of the programme. Whilst the overall contextual risks may not have changed, the dynamic operating environment means it is unlikely no change to risk has been observed in the past year. UNHCR should provide DFID with risk analysis on a quarterly basis.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

As was the case in the last Annual Review, IOM have continued to experience staffing issues over the past year. However, at the end of 2018, a new Senior Management Team consisting of an experienced Chief of Mission, Deputy Chief of Mission, Senior Resource Management Office and Head of Programmes Support joined and have prioritised the recruitment of a full team. As of February 2019, IOM has 18 international staff in country with 30 other positions at various stages of recruitment, only 14 of which IOM have yet to identify a suitable candidate for. IOM HQ has committed to move successful recruits immediately from their current posts into Yemen to support this initiative. IOM currently employs 400 national staff across the whole of Yemen, with an additional 141 providing roving support. The distribution of staff across the country can be found in Annex A.

Over the last year, there has not been a dedicated DFID-funded Consortium Coordinator or Consortium Coordinator Assistant, as was outlined in the original budget. A new member of staff was recruited in the latter half of 2018 to act as Coordinator, but only with 50% of their time. Whilst significant improvements have been seen a result, such as the consolidation of four working groups into two and a newly agreed approach to referrals, these achievements should highlight the necessity of consortium leadership and it is recommended that IOM prioritise the recruitment of a specific DFID-funded Consortium Coordinator, as was agreed in the budget. To further support consortium coordination, DFID has moved to hosting monthly meetings with IOM and consortium partners. These meetings have facilitated open, insightful discussions about the situation on the ground and have been incredibly beneficial to programming as consortium members have been extending the meeting to discuss common issues and ways of working. It is recommended that the monthly meetings continue, noting the added value of the same attendees coming each month.

IOM has inconsistently spent against their forecast throughout the lifetime of the programme, in particular facing challenges with underspending. Expenditure since the beginning of the programme is shown below:

Despite the trend of increasing spend, IOM only managed to spend 64% of their total budget for the first year of the programme. This underspend is largely attributable to the delay in implementing DTM activities and access constraints faced by partners, many of which were beyond IOM’s control, but should have been considered as likely risks when forecasts were initially determined. IOM failed to take the necessary action to inform DFID of anticipated underspend, which could have had serious consequences for the Yemen portfolio. DFID and IOM finance colleagues met in late 2018 to outline the importance of accurate spending against forecasts, IOM’s responsibility to inform DFID of any alterations, and the rigidity of yearly budgets. DFID has also requested that IOM provide a verbal update at monthly meetings on spend from the previous month so any deviances from forecasts can be identified and dealt with promptly.

IOM continues to provide quarterly narrative and financial reports, although sometimes behind schedule. It is recommended that IOM deliver reports on time to enable DFID to adequately review before quarterly meetings.

UNHCR continue to spend accurately and provide timely reports. However the level of detail provided in reports is insufficient to judge the quality of services delivered. It is recommended that UNHCR brief DFID on how their results are calculated and improve the quality of their narrative reporting.

UNHCR reports that there have been no significant change to risks since the beginning of the programme. Given the volatile context they are operating within and the information we receive from other partners DFID would anticipate more detailed analysis. UNHCR should provide a comprehensive written update on risk each quarter, using the DFID risk matrix as a tool to do so if helpful.

It is also recommended that IOM and UNHCR provide updated asset registers.

Date of last narrative financial report(s)	UNHCR: 21/02/2019 / IOM: 21/02/2019
Date of last audited annual statement (s)	UNHCR: 12/07/2018 / IOM: 29/05/2019

G: MONITORING, EVIDENCE & LEARNING

Monitoring

IOM

Due to the security situation in Yemen, DFID staff are unable to conduct field visits to directly monitor programmes. Instead, DFID commissions Independent Monitoring, which IOM was part of last year. This exercise looked at the quantitative accuracy of data, quality of service and adherence to targeting criteria for two indicators: 1.2) Number of migrants receiving WASH, food, NFIs, ICLA and temporary shelter and; 2.1) Number of medical consultations conducted for IDPs and other conflict affected populations. The findings were as follows:

The most significant finding was that there were inconsistencies in the data reported on beneficiary numbers across both outputs. Indicator 1.2 had an overall inaccuracy of 22% and Indicator 2.1 had an overall inaccuracy of 52%, both of overreporting. IOM responded that the logframe seen by monitors contained incomplete datasets and noted the challenges with electronic data collection in Yemen.

Other significant findings related to poor beneficiary satisfaction, lack of knowledge of feedback mechanisms, insufficient operating hours of hospitals and lack of equipment and staff. Positive findings included staff speaking to beneficiaries in their own language, no evidence of informal payments, and that all beneficiaries were from the intended target populations.

The recommendations from the IM report were as follows:

1. Improve database accuracy on beneficiary numbers and services rendered.
2. Improve adherence to gender standards.
3. Improve risk categorisation of beneficiaries and tracking of quality and type of service delivery received.
4. Ensure all beneficiaries receive at least the three basic services (food, NFIs, awareness raising).
5. Review and improve health services.

DFID and IOM have agreed to follow up on progress towards these recommendations via roadmap on a quarterly basis. IOM have already taken some action, for example, by revising data collection formats to avoid duplication and capture all required detail. With limited monitoring opportunities for DFID staff, logframe inaccuracies are a cause for concern, which was also reflected in the findings of the independent monitoring report, and IOM should ensure they are addressing this issue as a priority.

HI has been providing technical support to the IOM consortium on inclusive data collection and monitoring and has drafted a monitoring tool to be used across the consortium. However, as mentioned in Output 1, consortium partners face challenges with systematically tracking migrants as they are frequently on the move. Hotlines are available, but migrants often do not have phones. The consortium recognises this as a key issue and is working through their IM & ME working group to address it. However, when complaints have been received, they have been acted on accordingly. For example, Intersos was informed that they were not providing migrants with enough water and so procured additional supplies to be included in the food rations.

UNHCR

In late 2018, UNHCR undertook a Participatory Assessment to gather information on the specific protection risks faced by women, men, boys, girls and diverse groups. 160 focus groups discussions were held with refugees and IDPs in eight community centres in the North, and 86 discussions were held in the South. These assessments were the only data collection tool. Children, adolescents, youths, adults and older persons were all involved and separate discussions were held for men, women, boys and girls. UNHCR have used this assessment to shape 2019 programming and are due to share a summary of the findings with DFID.

UNHCR field, protection and programme staff conduct monitoring through field visits to check the delivery modality of partners. Multi-functional teams monitor the project through unannounced spot-checks, site visits, age, gender and diversity assessments and focus group discussions. UNHCR also contracted a third party to conduct regular Post Distribution Monitoring (PDM) for its cash and NFI programme in 2018. Two rounds of beneficiary interviews have been conducted and UNHCR is due to share a summary of the findings with DFID soon. UNHCR is also working with OCHA to conduct a PDM pilot for the Yemen Humanitarian Response Plan.

In their latest report, UNHCR recorded that 93% of assisted IDPs reported that some of their immediate protection needs were met. However, they were unable to provide data on feedback from refugee recipients of assistance. As part of the next logframe submission, UNHCR should suggest new indicators to DFID to measure beneficiary satisfaction and ensure it is possible to report against them regularly.

Both partners engage in quarterly meetings with DFID. IOM have travelled to Amman and Djibouti to meet with DFID colleagues, but it has not yet been possible to conduct a quarterly review with UNHCR in person. Meeting in person has had an incredibly positive impact on the working relationship between IOM and DFID and it is recommended that UNHCR prioritise travelling out of country for at least one quarterly meeting each year.

This Annual Review has been written by the Programme Manager and SRO (who is also the Humanitarian Adviser) of this programme. An Economic Adviser, Conflict Adviser, Evaluation Adviser and additional Humanitarian Adviser have provided assurance on the quality of the analysis. IOM and UNHCR have also fed in to ensure this review is factually correct and representative of current activity. The full review has been assessed by both the Head of Programmes and the Head of Humanitarian Team before receiving approval from the Head of Department.

Evidence

Both the Civilian Impact Monitoring Project, supported by the Protection Cluster to monitor the civilian impact of armed violence, and IOM’s Displacement Tracking Matrix expanded to national level last year, which has been a difficult process and should be commended. Both provide vital data and are used across the humanitarian response.

IOM and UNHCR both provide data disaggregated by sex, with IOM disaggregating by age to some degree also by reporting numbers of men, women, boys and girls. UNHCR and IOM also often provide the geographical locations of activities in narrative reports.

DFID also should consider how the Catapult satellite project can best support this programme, for example in the identification and assessment of IDP sites to enable a timely and effective response, particularly in areas that may be hard to access.

Learning

In July 2018, DFID provided IOM with 2,500 NFI kits and 3,000 tents to IOM to distribute in response to increased displacement from Hodeidah. The distribution of these NFIs was controlled by the Shelter Cluster, who later produced an extensive ‘lessons learnt’ report on the whole process. Some examples of lessons were:
- The Cluster should pre-identify partners with logistical capacity to undertake this kind of activity and engage with the Logistics Cluster for support.
- A more extensive exploration of transportation options should be carried out to ensure the most cost effective option is chosen.
- Ensure all kits are complete with no missing items.
- The tents contained instructions in English, which then had to be translated into Arabic during training. Partners should be provided with translated instructions ahead of time to minimise time required setting up tents.

DFID partnered with Palladium to fly the NFIs from Palladium’s warehouse in Dubai, into Aden. However, it was agreed that DFID would be invoiced for the goods as they were replenished in the warehouse, not when they were flown. Following the distribution, Palladium changed its procurement strategy and downscaled the Dubai warehouse, which meant they did not replenish the stocks that DFID had sent to Aden and therefore that DFID could not be invoiced for them. This caused some issues with DFID Yemen’s internal financial management and could have caused DFID Yemen to significantly underspend against their budget for this financial year. If this process is to be repeated again in future, requirements regarding invoicing should be made clear in the contract.

Consortium coordination has significantly improved since the last Annual Review, and the appointment of a Consortium Coordinator has been important in facilitating this. The consortium has set up technical working groups, agreed on a referral mechanism, conducted service mapping, and meets regularly to discuss common issues. However, the Consortium Coordinator is not filled on a full-time basis. IOM should arrange the appointment of a dedicated full-time Consortium Coordinator, as was agreed in the original budget.

Progress on recommendations from previous reviews (1/2 page)

Recommendation	Responsible Org	Comments
DFID should focus on strengthening relationships with IOM and UNCHR, ensuring that partner information sharing is substantive and proactive. At times, these relationships should be extended to downstream partners, to ensure comprehensive feedback on implementation and its challenges	DFID	Relationships with both organisations have improved over the last year. DFID now hosts monthly meetings with IOM and consortium partners, which have been incredibly beneficial owing to partners willingness to share detailed information on programme delivery and challenges. IOM and partners have also travelled out of country twice to met with DFID colleagues. Communication with UNHCR is more limited, and DFID should attempt to strengthen this relationship further, particularly with technical coordinators.
With ongoing delays to programme delivery DFID Yemen will strengthen oversight of the programme including regular updates on access constraints and actions taken; progress reports on delivery; and enhanced scrutiny of report quality including finances. If access constraints for the Displacement Tracking Mechanism continue beyond May, this programme component should be redesigned or funding should be reassigned.	DFID, IOM, UNHCR	As above, DFID has moved to hosting monthly meetings with IOM and consortium members. DFID has also worked closely with IOM to improve their financial management and logframe reporting. DFID will continue to closely monitor progress of delivery.
Significant revisions are required to the logframe in order to clarify, simplify and ensure it is accurately reflecting progress in the intended areas. There are indicators from the original logframe that the IOM consortium is currently not reporting against. UNHCR have significantly overachieved against a number of indicators. DFID should review targets going in to year two to ensure appropriate levels of ambition and ensure overachievement is not at the expense of other indicators. All partners should disaggregate results by gender, age and disability. Partners should also collect and act on data on the percentage of beneficiaries satisfied with services Any proposed changes to the logframe are to be discussed and agreed with DFID, with sufficient consideration of potential impacts on VfM, theory of change and risk. DFID will consider agreeing individual weightings for output indicators.	DFID, IOM, UNHCR	UNHCR’s logframe targets were revised this year to reflect delivery capability. DFID discussions with IOM on logframe revisions are ongoing, and new targets will be used from next quarter based on the recommendations of this Annual Review. Both partners are also working on providing a better measure of beneficiary satisfaction and programme quality.
Given significant new funding from Saudi Arabia (KSA) and the United Arab Emirates (UAE) for IDP programming, DFID should consider focusing support towards refugees and migrants. Host communities are often as vulnerable and resource starved as the displaced communities they host. Expanded programming for the host community should also be considered, particularly on building/rebuilding community infrastructure. This “humanitarian+” programming would improve sustainability of the response, ease community tension, and support vulnerable displaced and host communities.	DFID	With a changeover of both PM and SRO for this programme in the latter half of 2018, and no clear request for this support from programme partners, this recommendation has not yet been implemented and continues to next year. It is recommended that DFID assess this recommendation with partners following the Annual Review to determine whether it remains relevant to the context, taking into account KSA and UAE funding in 2019.
The system for referring migrants to response points needs to focus on building the capacity of service providers for beneficiaries and establishing clear responsibilities in referral pathways for complex cases. IOM should consider more direct service delivery if referral services are non-functional.	IOM	IOM has expanded service provision to support public secondary and tertiary health services over the last year. IOM reports improved quality of available referrals services in both public and private sectors.
In line with humanitarian best practice, partners should be encouraged to reduce in-kind distributions and instead deliver cash, as appropriate. This will enable to most vulnerable to prioritise their needs, whether that be food, shelter, or medical care. We recognised there are certain circumstances where cash distribution is not feasible or appropriate.	DFID, IOM, UNHCR	UNHCR has increased their cash distributions this year, and NRC began implementing multi-purpose cash for protection cases.
The Civilian Impact Monitoring Project (CIMP) should be reviewed to understand if it is achieving its goals. If not, the CIMP should be adapted to be more effective or funds re-aligned and spent on more effective programming.	DFID, UNHCR	CIMP has improved this year as coverage expanded to national level. Daily, weekly and flash reports are issued and utilised by the humanitarian community.

Annex A – IOM Yemen Human Resources