Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Africa Enterprise Challenge Fund Research Into Business (AECF Rib)
Programme Value: £5.2m		Review Date: 19 December 2012
Programme Code: 201500	Start Date: 22/12/2009	End Date: 31/12/2015

Summary of Programme Performance
Year	2013	2014
Programme Score	A	B
Risk Rating	Low	Medium

Summary of progress and lessons learnt since last review
The AECF Research into Business (RIB) window has completed two rounds (RIB1 ad RIB2) of funding and the fund manager (FM) is looking to support more projects in a further round should funds be available.
RIB1 projects funded by DFID are nearly three years into addressing the challenges of getting agricultural technology products and services to users in a profitable and sustainable manner. Progress against milestones as set out in the logframe covering, among other measures, innovation, access and reach to beneficiaries.
AECF was originally established with relatively light touch monitoring and support from the Financial Manager to businesses. This has proven inadequate for measuring milestones on impact particularly for gender and poverty effects. Over the past year extra effort was made by AECF management to assess and improve the quality of the commercial and impact data presented by the RIB1 businesses. Results chains and beneficiary models were prepared for all projects and project managers were tasked to be particularly thorough in checking these, validating the impact data and talking to beneficiaries. Further emphasis is required on monitoring and evaluation of the projects whilst continuing to provide them with some business support.

The nine projects funded through RIB1 can be broadly placed in three groups.
1. Group 1 contains most (7) of the nine RIB1 projects. These seven projects are starting to show increased sales, profitability and impact on small farmers. Most of the companies in this group are more than 20% off the targets set at contracting. This has necessitated contract renegotiations and submission of revised business plans from some of them. These RIB projects have been challenged by the slow pace of policy and regulatory change in Africa for novel technologies and their own relatively weak marketing systems, however these challenges were identified when the original targets were met. Despite this the majority of the seven projects are now increasing sales and improving their marketing. As with any range of projects some are performing better than others and progress is generally well captured by the FM’s traffic light assessment of risk.
2. Group 2 contains projects forced to cease operations due to circumstances beyond the reasonable control of the business. Luckily only one company is in this group. Toguna Agro Industries ceased operations in northern Mali due to civil conflict. Toguna’s turnover dropped from over six hundred thousand dollars in 2013 to zero in 2013.
3. Group 3 contains media and communications companies. Just one such company was funded in RIB1, the Mediae Trust. This company is distinct in that it does not focus on profitability through commercial sponsorship of the new technologies it informs farmers about. Commercial sponsorship has the potential to limit the range of technology information disseminated to farmers. Mediae therefore attempts to maintain its independence through donor funding of its core business. How important this independence is in terms of impact has not been tested.
   Results from Mediae’s work has, to date, driven achievement of many of the RIB1 milestones and requires special assessment. Mass media reaches high numbers of households and this has significantly boosted the number of beneficiaries reached by RIB1. Assessment of Mediae’s impact on those beneficiaries has demonstrated increased income per household, notably small dairy farmers. The reach and impact results of the seven projects in group 1 are relatively modest in comparison. A 5 month intensive assessment of Mediae’s work was completed in 2014, funded by AECF, and carried out by a consortium led by the University of Reading. Independent review of this assessment, again funded by AECF, showed that generally the methodology was sound and the quantitative information robust. The same assessment showed that the main beneficiaries were not the poorest but those households that had cash to invest in those new technologies the TV programmes produced by Mediae informed them of. For example, the mean impact on 40,000 small scale dairy farmers was a statistically significant US$602 per household from the dairy interventions featured on the Mediae programmes.
4. The main learning from RIB1 is that it takes some significant time for businesses to understand the commercial realities of successfully commercializing new technologies. The challenges start with getting regulatory approvals. In all cases this has taken longer than expected. Finding an appropriate route to market has been another challenge and a many of the RIB1 firms have gone through one or two changes in strategy. Across the portfolio these two challenges have taken anything from one to three years to sort out. Meanwhile large upfront capital investments need to be funded, procured and installed, while payroll and other running costs must be covered even as sales are non-existent or minimal. Once all those issues are covered there are the logistical challenges of getting a US$5-20 product out to 10,000 plus people. Taken together these challenges show that, while there is demand for the outputs of agricultural research, patient capital and plenty of time is needed before a sustainable business can be built around commercializing the outputs of agricultural research.

Summary of recommendations for the next year
RED should continue to engage and collaborate with ARD on the management of AECF on:-
- Proposed logframe revisions recently submitted by AECF for assessment by DFID. The revisions proposed for the RIB log frame appear appropriate but work needs to be done on quantifying the milestones and ensuring they are in line with other windows.
- Strengthening the monitoring and evaluation of AECF to ensure that RIB1 projects are effectively assessed and disaggregated data derived.
Promote the dissemination of information about RIB1 projects particularly case studies and exposure of the research community to some of the lessons generated on the commercialisation of new agricultural technologies in Africa.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:	2217858

Outline of the programme
Research into Business (RIB) is a window of the African Enterprise Challenge Fund (AECF). RIB funds companies that turn the outputs of research into businesses. DFID contributed (£5.2 million) US$8.01m into Round 1 (RIB1) launched in 2010. Australia's Department of Foreign Affairs and Trade (DFAT) put US$10.33m into Round 2 (RIB2) launched in 2012. This annual review only assesses progress of the nine companies funded through RIB1 but comments on RIB2 as necessary.
The RIB window offers an opportunity to see if funding for commercial companies could increase the uptake of the outputs of agricultural research through commercialization of agricultural research products by AECF grantees. The ideas presented in RIB are very innovative and are not ‘agribusiness as usual’ with many of the companies implementing novel technologies and targeting new customers with products and services they have never seen or heard of before, selling inputs ranging from seeds and plantlets, to vaccines and semen, and to fertilizer and aflatoxin free groundnuts. One company is selling a new type of soil testing service and another is providing agricultural information through an educational drama TV series. Five of the 9 business are start-ups, 5 are small with turnover of less than US$1m. Summaries of the 9 businesses are provided in annex 1.
RIB is managed by the AECF Fund Manager (FM)[1] for the Alliance for a Green Revolution in Africa (AGRA). RIB provides businesses with a mix of grants and non-recourse loans (repayable grants). RIB1 provides slightly more repayable loan than grant, with an average of 52% of total funding provided as repayable grants. Loans are not yet due for repayment.
[1] The Fund Manager of the AECF is KPMG International Development Advisory Services (KPMG IDAS).
This report covers the period July 2013 to June 2014. Progress against milestones is based on the grantees reports submitted in February 2014 and verified between March and June 2014 by the FM.
The RIB programme provides a unique forum for researchers, communication companies and agri-businesses to meet and exchange ideas on what the market demands and how to meet that demand.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
RIB has 1 indicator for impact and 3 indicators against its outcome statement of “Agribusiness market systems have high development impact by working better for the poor in rural areas of selected African countries”.

Impact Indicator	Milestones	Progress
Impact Indicator 1: / No of households[2] who benefit from AECF RIB projects of which: / i) 60% of whom are living on less than $2 per day; and, / ii) 50% women	No actual milestone for 2014 / 2012 milestones = 200,000 households of which i/120,000 ii/100,000. / 2016 milestone = = 750,000 i/450,000 ii/ 500,000	2013 actual = 154,954 households with i/ 63,987 and ii/ tbd. / No accurate disaggregation by gender is yet possible.
[2] The original log frame stated “people”. This was presumably a typing error and has been assumed to mean households and changed to households in RIB reports.

Key Points
The number of households benefiting from RIB is estimated to be 154,954 households. This total is dominated by 108,774 households benefitting from one RIB1 grantee, the Mediae Trust. This company produces education/entertainment TV series [Shamba Shape up (SSU)] on small-scale agriculture in Kenya. 108,774 is the number of SSU viewing households who made changes in maize, dairy or both enterprises and that were influenced by SSU (there was no double counting of households). . The executive summary of the draft report is attached as annex 2[3]. The impact figures given in the report are probably an underestimate given that survey questions were limited to 3 of 30 plus technologies promoted by SSU and did not cover urban viewers with links to farms. Households benefiting from other RIB projects are far more modest, varying from 2,872 (FAIM Africa Ltd) to 21,580 (Brentec Investments Limited). Dissapointedly, four of the nine projects had no beneficiaries documented up to June 2014. Explanation for the lack of beneficiaries relate to implementation delays and poor market access. For example, FAIM has not built laboratory facilities which funding was provided for and failed to meet sales targets. Similarly Super Sires has fallen behind on their semen marketing efforts whilst focusing on a longer-term project of building an in vitro fertilization facility. This facility has also run into difficulties as operating cash reduces from lack of sales.
[3] Data in the report appears acceptable. An independent quality assessment of the draft report funded by AECF does suggest restructuring the report and strengthening cirtain sections eg. methodology and evaluation criteria.
The AECF fund manager is still not in a position to accurately calculate the number of poor households or gender benefits from RIB1. The AECF was designed, as many challenge funds were, with a light touch approach to monitoring and results measurement. Despite concerns being raised around this in the early stages of RIB 1, it is only now recognised tthat the monitoring and results measurement process should track the day-to-day activities to inform short-term improvements to delivery including tracking the business performance, development impact and wider systemic impacts. This light touch approach for RIB1 monitoring has not produced the level and quality of results that are needed by the Fund Manager, donors and key stakeholders. This is being addressed as AECF M&E systems are strengthened following the 2014 M&E study by Coffey International and an ongoing staff recruitment and restructuring within AECF. Despite highlighting our concerns erification studies of RIB1 projects are only now being planned for 2015 and 2016.
The poverty focus of the RIB1 projects does need to be monitored closely. The SSU study carried out by Reading University assessed the poverty status of SSU viewers. SSU viewers were considered to be less likely to be below a $2.50 per day Purchasing Power Parity poverty line. Those benefiting from the programme tended to be those with sufficient cash to invest in new technologies, e.g. dairy farmers. The Mediae study did report gender disaggregated findings related to monetary benefits but not at the household level.

Outcome Indicators	Milestones	Progress
Outcome Indicator 1: / Agricultural growth of agribusiness sector in selected African countries where AECF projects are operational	Baseline 3.5% / 2012 milestone = 4% / 2012 actual 4.11%[4] / 2014 no milestone / 2016 Milestone = 4.5%	Figure presented in 2012 was from 2011 data. Attribution of change in agricultural growth to AECF is too tenuous to be meaningful.
Outcome Indicator 2: / % of AECF projects contributing to one or more of the impact areas that contribute to market system[5] improvements	2012 milestone = 10% / 2012 actual = 50% / 2013 milestone = 50%	Milestone Achieved 2013-4 actual 80% / In 2014, RIB businesses continued to contribute to all impact areas
Outcome Indicator 3: / Data on increased incomes for AECF’s RIB Window Average amount of benefit per year received per person - disaggregate d by gender	2012 milestone = £15 (US$25) / 2012 actual = $40 / No milestone for 2014 / 2016 milestone £30 ($45)	Milestone achieved 2013 actual = $184 / The FM states that they do not have the resources to disaggregate by gender.
[4] Data taken from Burundi, Kenya, Uganda, Mali, Malawi, Mozambique, Nigeria, Rwanda, South Africa. 2011 figures used as 2012 not available.
[5] AECF recognizes six categories of systemic change: - Copying of the business model. - Crowding in of other businesses into the space created by the AECF project. - Copying successful practices by e.g. growers who are not directly involved with the AECF project. - Legal and regulatory changes brought about as a result of the project. - Changes in factor markets – land, labour, access to or the price of capital. - Innovation.

Key points
RIB has exceeded the target for the percentage of projects impacting on market systems. It was always expected that the real impact of AECF RIB would not be through direct beneficiaries, but through indirect beneficiaries reached as a result of market system improvements that might not have happened without the AECF RIB project. There are several examples of RIB1 companies impacting market systems. BLGG is engaging with government on innovations that could significantly improve soil testing and fertility management on smallholder farms. Leldet advocated for the formation of an umbrella organization of seed companies in Kenya, the Seed Trade Association of Kenya (STAK), for a regulatory environment that is supportive of private sector firms. They subsequently quit STAK due to frustration that the drive for change seemed not to be working. Super Sires are engaging the Kenya government to come up with an improved regulatory framework for embryo transfer. Brentec in Uganda is working with government to introduce standards for vaccines to reduce the entry of substandard products into the country. Mediae has influenced the way agricultural information is disseminated and a number of TV and radio stations, as well as the print media, including the largest selling daily newspaper have now dedicated space to agricultural information. This is an example of the AECF project crowding in other businesses. There are also examples of banks being encouraged to develop financial products as a result of the AECF project, for example, Super Sires, and FAIM.

Figures for RIB1’s average amount of benefit per year received per person is dominated by the figure obtained through the Mediae Trust SSU Reading University study. Other RIB1 projects have more modest figures of monetary benefit per person. The SSU study estimated generated benefits of US$24.7m or US$227.3 per benefitting household. The impact on small scale dairy farmers was particularly impressive with a statistically significant benefit for 40,000 households each of whom benefitted by an average US$602 per household from the dairy interventions featured on the SSU series.

Overall output score and description B
Whilst results from RIB1 have been slightly skewed by the dominance of the media and communications project (Mediae Trust) the majority of RIB1 projects are now starting to perform. One project has been disrupted by force majeure but is part of a very large company and could recover if the conflict abates. Achievement of milestones against outputs are generally on track and as expected.

Key lessons
A key lesson from the period under review relates to the need to simplify the overall AECF structure and its form of operation. Progress has been made on improving the governance of the AECF following the recommendations of the Nathan due diligence report. A task force has been established to set up a Kenyan company limited by guarantee, which may assume the responsibilities of overseeing the AECF by late 2015. DFID is a key member of the task force.
Turning research products into viable businesses takes time. RIB businesses have been faced with regulatory hurdles and high start up and running costs and challenged to make enough sales to turn a profit. For the year under review the portfolio is showing US$1.2m in turnover and US$1.4m of losses. These are covered in part by disbursements of US$ 1.0m of AECF grants. Some encouraging signs of companies moving into profitability are starting to show. For RIB companies, like any other companies, this is driven by growth of commercial sales. Public funding can help companies get through the difficult early years. But soft money, from AECF or other sources, should never be a substitute for the commercial discipline of growing sales.
The Fund Manager tasks have had to evolve from a 'monitoring and evaluation' function to more of a 'Knowledge Management' role. Knowledge management incorporates project monitoring and results measurement as well as evaluation and in-depth learning from the portfolio, and the analysis and dissemination of that collective learning to different audiences. In the RIB Window, this has required extending to become communicators and advocates for policy positions in order for the FM to contribute to wider impacts on the market systems the RIB companies are engaged in
There are a few scientists willing to venture into businesses related to the research they have spent their lives undertaking. Business is difficult for researchers as the skills needed to raise funds, keep teams paid and motivated, reaching commercially oriented clients and dealing with uncertainty and slow moving regulatory agencies are very different from those required in the comfort zone of the average scientist. RIB has continued to engage with research organisations, such as ILRI and ICIPE, and the fund manager reports that only recently has progress been made in terms of awareness and engagement on issues. One particularly powerful tool found to be useful in this area, is exposure of researchers to the managers and entrepreneurs supported by AECF / RIB.
Measuring and attributing impact of RIB has proved to be a challenge. Most firms do not know their clients well enough to self-report development impact. This has led the FM to have had to develop the skills, and invest in the human resources and time, to get this information from beneficiaries. Typically this is being done through interviews with a small number of beneficiaries. The FM is now developing the skills to identify, procure, and manage studies of hundreds or thousands of households. This requires developing results chains, beneficiary models, baseline and verification studies for reporting of impact.
RIB’s goal includes taking outputs of science and making them available to farmers around Africa. One tool that was to assist in making this happen was the Virtual Market Place (VMP). The VMP no longer exists on the AECF website and is no longer promoted. The FM sought US$200,000 of support from DFAT to make more of the VMP for RIB2 but the proposal was been turned down. The VMP never managed to prove its worth at the formative stages of RIB and lessons from this still need to be captured.

Has the logframe been updated since the last review?

Yes, a revised log frame has been developed by AECF and was submitted to DFID for review in Nov. 2014. The revised logframe draws upon lessons to date and harmonises indicators across the funding windows.
Summary of responses to issues raised in previous annual reviews (where relevant)
A number of general recommendations were made in the 2013 RIB annual review and the overall 2014 AECF review.
1. DFID RED and ARD, as the lead contact for AECF, to contribute to strengthening the AECF monitoring and evaluation system.

   RED attends AECF meetings convened by ARD. From Sept. 2015, the annual review is to be coordinated across DFID. In 2014 Coffey International were commissioned to assess the AECF M&E system (the MRM report). The MRM recommendations of May 2014 have largely been accepted by the AECF board and recruitment for new staff is expected to be completed in early 2015. The Fund Manager has piloted a Donor Committee for Enterprise Development (DCED) Standard for Results Measurement. With the agreement and funding of DFAT DCED will be applied to all RIB2 projects. The FM has been asked to measure RIB2 impacts separately from RIB1 so that the former can be attributed to DFAT Australia. Verification studies similar to the Reading University SSU study will only be carried out on those RIB1 projects demonstrating significant impact. Brentec and Klein Karoo are the most likely candidates for this in 2015/16.
2. RED and ARD to contribute to AGRA to strengthen its approach to loan repayments

   The fund manager has produced an analysis of AECF loans. This was presented to the AECF board and discussed. The 2014 AECF AR recommended that a clear process and definition of responsibilities regarding the monitoring of loans, loan repayments, netting off loans and grants. The development of this is not due till March 2015.
3. DFID RED to discuss the revision of the logframe with DFID Africa Regional Department as the lead DFID Department on AECF

   RED attends AECF meetings convened by ARD. The FM has submitted a draft revised logframe for the whole of AECF including RIB window to DFID ARD in Nov. 2014. RIB indicators and milestones appear to have been significantly improved to reflect strengthened M&E capacity. Revised milestones still need to be finalised.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Mechanisms in place to identify, select, support and monitor Research into Business (RIB) projects to ensure they achieve improvements in market systems in ways that benefit poor
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Output Indicator 1.1: / No of projects in RIB window by the end of each milestone year: (a) No. of applications received / (b) No. of projects with signed / contracts and operational (c) No. of projects that have a positive impact on gender equity (d) No. of applications generated by the virtual platform / (e) No. of projects taking up technologies that specifically benefit the environment and contribute to increased adaptive capacity	No actual milestone for 2014 / 2012 milestones = a/200 b/10 c/8 d/40 e/5. / 2013 actual = a/549 b/10 c/4 d/40 e/5. / 2015 milestone = a/400 b/25 c/18 d/100 e/13.	Milestone achieved / 2013- 2014 = a/549 b/15 c/12 d/40 e/14. / The original RIB logframe envisioned three rounds of funding. Subsequently DFID decided to only fund round 1 or RIB1. The figures presented against milestones includes RIB2 funded by DFAT. The FM is seeking funds for a RIB3.
Output Indicator 1.2: / Capitalisation of fund (US$): / a) Total donor funds committed to projects by year end / b) Repayments to AECF RIB Window / c) Total funds invested in projects	2012 Milestones a/ £5m b/0 c/£5m m / 2012 actual a/ US$ 5.97m b/0 c/US$ 8.2m / 2014 milestone a/ £10m b/0 c/£10m	Milestone achieved / 2013-2014 actual a/ US$10.08m b/0 c/US$ 21.2m[6]
[6] This fugure is 2013-14 RIB2.

Key Points
The FM states that RIB is behind on the 2015 gender indicator[7] but explains that a number of projects have not yet reached enough people for any impact to be measurable. The FM is confident that the portfolio of projects selected has technologies that do specifically benefit the environment and contribute to the capacity of their clients to adapt to climate change e.g. the seeds of Leldet, FAIM’s tissue culture plantlets for banana and passion fruit, BLGG’s soil tests and advice, Super Sires improved dairy genetics, Brentec’s poultry vaccine.
[7] No. of projects that have a positive impact on gender equity
Despite the long delays in getting RIB1 and RIB2 projects contracted, US$21.2m of AECF and other matching funds have been committed in the reporting period for RIB2. Since its inception US$5.97m of RIB1 funds have been granted or loaned to the 9 companies (see matrix annex 3). $16.2 million of matching funds have been contributed by these 9 companies, a leverage of 2.6 times the AECF RIB1 investment.

Recommendations
A balance of RIB1 DFID funds is currently held by AECF. These funds should be allocated to monitoring and evaluation of RIB1 projects including verification studies of RIB1 projects by June 2015
RED will work with ARD to do a streategic review of the prospects for achieving delivery of the outcomes from AECF RIB from RED contributions. By June 2015.

The fund manager has to produce an analysis of AECF loans by March 2015

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Projects and business ideas selected and funded by the AECF under the RIB Window are innovative and demonstrate that new business models are replicable and can benefit the poor
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Output Indicator 2.1: / % of projects in AECF’s RIB portfolio of approved projects that are marked 3 or above on the AECF innovation scale and thus judged to be innovative and demonstrating new business models that are replicable and can benefit the poor	2012 milestone = 50% / 2012 actual = 88% / 2014 milestone = 60%	Milestone moderately did not meet expectations / 2013 - 2014 actual = 100%

Key Points
The nature of RIB suggests that all projects must be innovative as they are commercialising new technologies. It is logical that 100% of projects will score higher than the target level of 3 on the AECF innovation scale. All the projects are replicable if companies can develop similar skill sets to take advantage of the new technologies. Questions do remain about the capacity of the grantees to benefit the poorest farmers who may not be able to afford new technologies. The most detailed study to date (Mediae Trust’s SSU) suggested that SSU viewers and households benefiting from SSU were less likely to be below the $2.50 per day Purchasing Power Parity poverty line. Hopefully the Mediae Trust project is an anomaly but other projects in the RIB1 portfolio should be closely monitored for poverty impact.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations
AECF have changed this indicator in their draft revised log frame to “Ongoing projects that are marked 3 or above on the AECF innovation scale: (a) total number; and (b) percentage”. The actual 2014 percentage figure is 87% for RIB projects. The indicator is complemented with a second stating “Ongoing projects where innovation is 'recognised': (a) total number; and (b) percentage. The new indicators provide a more accurate assessment of overall innovation and should be adopted.

The revised logframe also suggests the output be changed to “AECF identifies and supports business initiatives with high potential to generate sustained and significant positive development impacts and which are innovative” and adds two further output indicators. All of these are appropriate to RIB1.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Projects and business ideas selected and funded by the AECF Research into Business (RIB) Window that utilise existing, or near complete, technologies resulting in benefits for the poor
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Output 3.1: / % of projects in AECF’s RIB Window portfolio of approved projects that are judged to have used or have the potential for using, existing, or near complete, technologies that have or are likely to benefit the poor / a) Potential to use new tech to benefit poor HH / b) Actually use new tech to benefit poor HH / c) Failed to get new tech to poor HH	2012 milestone a/ 90% b/10% c/ 0% / 2016 milestone a/50% b/ 40% c/ 10% / 2017 milestone a/10% b/ 60% c/ 30%	Milestone achieved 2013- 2014 actual a/100% b/100% c/0%
Output 3.2: / % projects in AECF’s RIB Window where the new technologies are recognised and disseminated through the / a) the media, / b) conferences, case studies, or published documents	2012 milestone a/ 10% b/ 25% / 2012 actual a/56% b/44% / 2016 milestone a/30% b/60%	No milestone for 2014 / On track to achieve 2016 milestone / 2013- 2014 actual a/50% b/53%

Key Points
RIB is ahead of target on the number of projects that have been disseminating messages through the media. A few RIB1 firms have made media appearances on radio, newspaper and television. Some are active on social media as well as in engaging with governments and other stakeholders in their sectors. RIB grantees have primarily used conferences to make people more aware about their products. The number of case studies and published documents are predicted to grow next year.
These indicators are to be revised in the proposed new logframe.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations
More accurate indicators in the draft revised log frame that measure progress toward “Business initiatives supported by the AECF generate development benefits which with high outreach, in particular to: those in rural areas; very poor; women; and youth” (Output 4) should be accepted.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Projects and business ideas selected under the AECF’s RIB Window are commercially viable
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Output 4.1 / % of / AECF’s RIB projects/business ideas that are profitable 36 months after / receiving AECF funding	2012 milestone 0% / Milestone for 2016 40% / Milestone for 2017 70%	No milestone for 2014 / Actual for 2013 27%.
Output 4.2 / % of repayable grants that are repaid to AECF. / Repayable grants (GBP) expressed as a %	Milestone for 2012 0% / No milestone for 2014 / Milestone for 2016 60%	Not yet relevant to RIB1

Key Points
The FM does not specifically report on the “profitability after 3 years” indicator as all projects are just reaching their third year. Despite this it is noted that most of the RIB1 companies are more than 20% off the targets set at contracting. This has necessitated contract renegotiations and submission of revised business plans for some companies such as BLGG and Brentec. Brentec has completed the process. BLGG is yet to finalise due to delays on their side.
The traffic light system used by the FM to assess risk includes assessment of the business model (BM) (post contracting) and cash flow (CF). Review of this data suggests that 2 of the 9 RIB1 projects are likely to fail to become profitable and may not repay loans (FAIM and BLGG). See annex 4. Much of the engagement by the FM with RIB companies has revolved around promoting more of a commercial orientation. Several RIB companies have found maintaining and managing a direct sales forces difficult and costly, but appear to increasingly appreciate that they will do better if they convince users unfamiliar with a product or service to buy it. The DFID AECF annual review 2014 noted that grantees that were interviewed during the course of the review were very pleased with the role of the AECF, with most reporting that funding has been additional and instrumental for the project to take place.
RIB projects are beginning to show indications of profitability with improvements in turnover. For example, local maize producers are now increasingly seeking disease resistant maize seed (as is being offered by Leldet Ltd) to improve their grain yield over the next harvest season. Others have suffered from force majeure in the form of conflict in northern Mali (Toguna Agro Industries). Toguna has reduced turnover from over $600,000 per year in 2012 to zero in 2013-14.
Although no RIB1 loans are yet due for repayment, grantees are struggling to achieve the results they originally proposed and their planned timeframes... Loans account for 53% of the RIB1 commitments. Challenges relating to the legal definition of the loans issued and incentives for the collection of these loans are currently being addressed by the AECF committee, as a large proportion of the loan portfolio is set to mature in the coming 3 years.

Summary of responses to issues raised in previous annual reviews (where relevant)
The 2013 AR recommended RED to review whether the output 4 risk should be changed from ‘Low’ to ‘Medium, and if so, to update the logframe. This recommendation still applies. In the proposed draft revised log frame issues of profitability are found in a changed output 3 “The business initiatives supported by AECF (and the products and services resulting from them), are sufficiently commercially viable that the associated development impacts are sustainable”. Bearing in mind the particular challenges to commercialising new technology projects, this output should be rated medium risk for RIB.

Recommendations
The FM has found turning research products into viable businesses takes time. RIB businesses have been faced with particular regulatory hurdles and high start up and running costs and struggled to make enough sales to turn a profit. A revised output on “The business initiatives supported by AECF (and the products and services resulting from them), are sufficiently commercially viable that the associated development impacts are sustainable” (new output 3) should be rated medium risk for RIB.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Projects and business ideas selected under the AECF’s RIB window have a high development impact in terms of increased incomes and job creation for poor people living in rural areas
Output number per LF		5	Output Score	B
Risk:		Low	Impact weighting (%):	20
Risk revised since last AR?		Y/N	Impact weighting % revised since last AR?	Y/N

Indicator(s)	Milestones	Progress
Output 5.1 / Data for AECF’s RIB / Window: / a) annual impact ratio / (benefit per GBP invested / (commitment) by AECF RIB) / b) cumulative impact ratio / (benefit per GBP invested/ committed by AECF's RIB window (to date)	2012 milestone a/ 0.3 b/ 0.3 / 2012 actual a/2.35 b/2.64 / 2013 milestone a/1.5 b/ 2.15 / 2017 milestone a/ 6 b/11	Milestone moderately did not meet axpectations / 2013-2014 actual a/6.4 b/ 8.17
Output 5.2 / Job creation / a) Number of new jobs (FTEs) created in a year acquired by men and women / b) Job creation ratio (cumulative no of jobs created per GBP 10,000 invested in projects by AECF). / c) AECF cost per job created / (GBP)	2012 milestone a/200 men 100 women b/0.6 c/16,667 / 2014 milestone a/700 men 300 women b/1.8 c/555 / 2017 milestone a/1300 men 700 women b/2.87 c/232	Milestone moderately did not meet expectations / 2013 - 2014 actual a/272 b/0.61 c/16,373

Key Points
The FM has now begun the process of improving the validity of the key performance indicator data, this includes measurement of development impact. The bulk of impact from AECF projects is anticipated to come from changes to market systems rather than directly from the activities of grantees and their clients.
The investment committed to Dec 31 2013 was US$4.5m from RIB1 and RIB2. RIB is therefore generating US$6.4 of benefit per dollar committed thus far. 272 jobs have been created against a target of 300. Jobs per US dollar invested and disbursed are still very low and each job created cost US$16,373. This is well above the target for 2017 ($232). Whilst it is still a little early to predict success but RIB projects, the FM predicts that they will, with time, exceed the log frame targets.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations: AECF have proposed that impact related indicators be folded into a new output “Business initiatives supported by the AECF generate development benefits which with high outreach, in particular to: those in rural areas; very poor; women; and youth” (output 4). The five indicators measuring this output appear more accurate for RIB and should be accepted. For example the changed output 4.5 states “Cumulative number of additional jobs created (FTE) through/in enterprises supported by AECF: (a) men; (b) women; and (c) youth (18-35 years).
The strengthened monitoring systems and verification studies proposed for RIB1 need to be put in place to measure these new indicators and associated milestones. The balance of RIB1 funds held by AECF should be utilised for this purpose.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
The competition nature of the AECF ensures funds are provided to the most commercially viable ideas, that offer a large development impact. Management fees of the fund are fixed at 20% of the funds allocated for businesses, whilst this is less than many other Challenge Funds, the RIB programme has paid a disproportionate % of it’s funding in the past and RIB funding has been used to subsidise other AECF windows which may not relate to research. For this reason, RED made a decision to fund only one round of RIB funding rather than three and reduced our funding from £12.5m to £5.2m.

The management fees (20%) are currently split: 4% to AGRA who manage all fiduciary and legal matters; and 16% to the Fund Manager, KPMG, who conduct the day-to-day operations of the fund. The Fund Manager’s contract includes a 10% annual performance fee, paid 12 months in arrears and which is part of the 16%, based on implementation of the annual workplan, its performance against the indicators related to output 1 of the log frame, the quality of proposals brought to the Investment Committee and the quality of the annual monitoring report.

Date of last narrative financial report
Date of last audited annual statement	3545854

E: RISK (½ page)

Overall risk rating: Medium
There is no major change to the risks envisaged in the original risk assessment register. These risks have been envisaged in the original risk assessment register.
The AECF continues to use the RAG system (red, amber, green) ([8]). As of June 2014, the AECF has rated six projects as amber and three projects as red. The reasons for red ratings include:-
[8] Green – within target range (+/-5%) or substantially above target; Amber – below target 9frequently due to delayed start or over-optimistic targets) but no major concerns at this stage; Red – doubts about business viability to make targets
- BLGG Kenya - still submit new business plan and targets.
- Super sires Ltd - Lack of semen sales threatening the viability of the business. Management seems more focussed on the big project of constructing and equipping the embryo transfer lab. But there are concerns that cash may run out before the facility is ready and generating sales
- FAIM Africa - The company has failed for another year to reach annual sales targets. Impact targets originally stipulated have therefore been missed

The AECF assesses risks individually for each project and reports them internally within AECF on a quarterly basis. For the purpose of simplification, the overall traffic light system should continue to be used.
RED continues to collaborate with DFID Africa Regional Department as the DFID’s lead on AECF to harmonise input. RED assesses any potential risks to the RIB-1 programme through meetings with AECF, or as any risks are reported by the AECF, by either by e-mail, semi- and annual reports, or through any such reports to the AECF Governing Council.

Overview of programme risk
A risk assessment was included in the project design of the overall AECF. The original assessment has been reviewed and updated each year.

One new risk has been added relating to financial management in AGRA. There are significant concerns about their capacity. The probability of this risk is identified as high because there have been a number of staffing changes and unfilled vacancies within AGRA and the impact assessed also as medium because donors can only disburse funds for the AECF if they can be confident the systems are in place to manage those funds. Grantees have already raised delays in receiving funds as an issue, in one case receiving them too late for the project to happen. This is the key risk currently facing the programme. Under R11 above a financial due dillience of the AECF will be undertaken.

For all other risks the mitigating measures identified in the 2013 annual review still stand. In addition, the FM has updated their own risk strategy for monitoring grantees. They have included two new elements to assess grantees: compliance (projects not adhering to all the stipulations of the funding contract) and character. Risk assessments are reviewed for each project twice a year. They are also developing project ‘one pagers’ for the Investment Committee which will provide all key information on a project including their risk assessments and financial and development impact.

Recommendations

None – the overall AECF risk matrix has been updated to reflect the risk regarding weak financial control in AGRA.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
The AECF is well ahead of schedule regarding commitments to projects, funds committed and funds raised (Output 1). The grantees that AECF fund are mostly behind schedule when compared to the timeframes submitted. This is expected due to the difficult nature and ambitious targets that grantees set. The Log frame should be adjusted – using experience from the programme over recent years – to develop more accurate targets and indicators.

Performance of partnership (s)

The partnership is performing adequately. However more work needs to be done to institutionalise AECF knowledge and experience beyond high level management, to increase longevity of AECF beyond current partners.

Asset monitoring and control
Reporting by the Fund Manager on DFID’s capital is deemed as adequate in the ARD annual review.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

During 2013 enhanced monitoring for the overall AECF portfolio was implemented for 2 windows (Zimbabwe and Tanzania) which saw the implementation of the DCED standard for results measurement. This has involved conducting baselines and subsequent verification studies of the development benefit of projects. The experience from this implementation has contributed to the recommendations of a Monitoring Review Mission in April 2014 to apply a limited form of the DCED standard to all windows including the RIB programme.

During 2013, a detailed verification study of the development impact of the RIB 1 funded Mediae project was conducted by University of Reading in the UK with Wageningen in Holland and Kenyan universities. It confirmed the significant development benefits that have been claimed for the net development impact of the project but it reduced the overall number of households that are affected from 156,000 to 109,000.

An independent evaluation of the AECF has been commissioned by AGRA and has begun its work. The $2.7m evaluation will seek to confirm the development impact of the programme and address questions of additionality and systemic change.

Monitoring progress throughout the review period

It is proposed that a set of common indicators across all windows is agreed by the fund manager and the AECF Committee. These are currently being prepared by the fund manager based on an agreed set of indicators for the new AAW logframe. All Windows will report on indicators in the following four output areas:
- Fund management process – including number of contracts signed, capitalisation of the fund etc
- Business innovation
- Commercial sustainability of businesses
- Development benefits – including increased incomes and jobs

Additional output indicators will be set for RIB. In this way, the results of individual Windows can be reported and aggregated into a revised log frame for the overall portfolio.

Annual Review Process:

Independent Animal Health consultant Tim Leyland undertook the review with support from Lesley Hamill Research Manager.  The review was undertaken with inputs from ARD and Aus Aid and discussions with the AECF team.

- The Project Memorandum approved on 23 September 2009 (Quest number 3305359, 2972399, 2490321 and 2587909).
- The AECF logframe (Quest number  2217858)
- AECF RIB1 Annual report (Quest number 3704436)
- Terms of Reference (Quest Number 3705446)
- Annual review score sheet (Quest Number 4784694)
- 2014 report from AECF (Quest Number 4786884)
- Annual review 2013 (Quest Number 4121580)
- Annual Audited Accounts (Quest Number  3545854)

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process