Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performances performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	4 December 2014

Title: African Development Bank Technical Cooperation Arrangement
Programme Code: 201359	Start Date: 01/09/2007	End Date: 30/09/2014

Summary of Programme Performance

Year	2011	2012	2013	2014
Programme Score	75.5	B	B	A
Risk Rating	Medium	Medium	Medium	Medium

Financial Position

Original Programme Value	£13 million
Extensions/ amendments	Extension in December 2009 (to September 2012) / Extension in August 2012 (to March 2014) / Extension in February 2014 (to September 2014).
Log-frame revisions (with dates)	December 2009 / October 2012
Total programme spend	Total DFID contribution of £10,480,410 of which £10,241,712 has been spent to 30/09/2014. AfDB will submit a final expenditure statement in February 2015. Any unspent balances will be returned to DFID.

Follow up actions required following closure

AfDB has told us that they will provide us with a final financial statement in February 2015, once final payments have completed. This is consistent with FCPD guidance which states that “the financial end date of a project is six months after the operational end date to allow for any final financial activity (e.g. paying invoices or retrieving unspent funds), even after the project has been officially closed in ARIES.” We will write to the AfDB in mid-February to ensure that this financial statement is received. The project will then be closed under ARIES workflow 40.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	N/A (Pre-Business Case)
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4710686.xls

Outline of programme and what it has achieved

Through the African Development Bank (AfDB) Technical Cooperation Arrangement (TCA) DFID provided a total of £10,480,410 to the AfDB from project inception in 2007 to completion in 2014. Of this amount, £10,241,712 has been spent to 30/09/2014. The objective of the TCA was to support improvements in the AfDB’s organisational effectiveness through the provision of training, technical assistance, capacity building and institutional support. The TCA focused its support on sectors and themes prioritised as strategically important by the AfDB and African member countries. During the implementation of the TCA those sectors that were prioritised were infrastructure and regional integration; private sector development; governance; institutional capacity; and climate change adaption and clean energy.
The TCA project design built on the critical role that the AfDB has for Africa’s future. It is uniquely positioned to achieve its mission of stimulating economic growth and social progress within its Regional Member Countries (RMCs). As the continent’s leading development financing organisation, the AfDB is well positioned to coordinate cross-border investments into sectors of strategic priority – these include developing the private sector, building infrastructure and achieving regional integration. In addition, the AfDB’s African nature and ownership provides it with unparalleled legitimacy from which to encourage and assist RMCs to consider cross-cutting issues relating to economic and financial governance, gender, climate change and organisational management.
Prior to project completion the AfDB commissioned an evaluation of the TCA. The objectives of the evaluation were to (a) test critical assumptions underpinning the TCA approach, (b) evaluate the performance of the TCA in delivering anticipated results, and (c) draw lessons for future management of AfDB Trust Funds. Overall, the evaluation found that the TCA organisational strengthening activities had been relevant to achievement of AfDB strategic goals and that this relevance had been optimised by the flexible nature of the TCA and its ability to respond to emerging priorities. Evidence gathered during the evaluation also indicated that TCA activities had supported the AfDB to achieve results in its strategic priority areas identified above. The evaluation concluded that the TCA had its greatest impact in the policy domain, contributing to the evolution of AfDB policy, in particular in the areas of climate change, private sector development and governance.

The evaluation also observed that the management arrangements for the TCA had evolved over time, to one of functional management, and that these arrangements had had implications for the overall effectiveness (and measurement of effectiveness) of the TCA as a whole. In this regard a series of recommendations were made around Trust Fund management at the AfDB as well as specific recommendations in respect of the future Framework Agreement for capacity building support between DFID and the AfDB.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The expected outcome of the TCA was that “the AfDB is a more effective, results orientated and responsive development institution”. This programme has met expectations. Both the 2013 Multilateral Aid Review (MAR) Update and the Multilateral Organisation Performance Assessment Network (MOPAN) survey provide analysis which indicates that the AfDB has progressed in the areas anticipated during the operation of the TCA. Most notably, stakeholder perceptions elicited during the 2012 MOPAN survey identified improving effectiveness and a stronger focus on results.

The ongoing alignment of the TCA to AfDB to Bank Strategy, as well as to MAR and MOPAN findings served to sustain the TCA as relevant to achievement of its outcome objectives. The partial contribution of the TCA to these changes was validated by the evaluation, but it was beyond the scope of that work to consider the extent of change or how far that could be attributed to the TCA as opposed to other initiatives or environmental changes.

Output Score and Description

Output Score: A

Lessons and how these have been shared

The independent evaluation of the TCA drew a number of lessons. These lessons were primarily of relevance for broader trust fund management at the AfDB, including in its future collaboration with DFID, but also for wider capacity development activities. The evaluation and the corresponding joint management response have been shared within the AfDB and DFID.

Some of the key lessons can be summarised as follows:

the TCA affirmed the value of Trust Funds to the AfDB. They enable the Bank to reach out to new partners, test new approaches, address capacity gaps and enable new initiatives to become bankable;

organisational strengthening initiatives need to be based on periodic and structured internal capacity needs assessment. The absence of such assessments, linked to AfDB strategic priorities, at the outset of the project might have reduced the ability of the AfDB and DFID to prioritise optimally between potential TCA activities. This may have effected TCA effectiveness, but not its validity. For flexible organisational strengthening initiatives such as the TCA to be effective, there also needs to be broad awareness of the objectives and management arrangements for the fund across an organisation.

Trust Fund results frameworks need to be realistic with results set at the right level and allowing sufficient time for results to be achieved and demonstrated. Where possible for Funds supporting organisational effectiveness, expectations should be linked to existing organisation wide objectives rather than developed for the Trust Fund in isolation. For the Trust Fund arrangements like the TCA which cover multiple and varied activities there should also be individual results frameworks for each intervention. This approach was adopted as the TCA evolved, leading to better formulated and evidenced proposals and clearer articulation of expected results.

clear roles and responsibilities for the implementation phase of Trust Funds should be agreed at the outset and as activities are approved and these should be incorporated into relevant AfDB staff objectives. Activities under the TCA as a whole have been characterised by implementation delays. This has been in part owing to excessive optimism at the outset, but also on occasion a lack of prioritisation within the AfDB, in particular under the infrastructure component. Management arrangements for the TCA have evolved over time and strengthened as lessons were learned both by the AfDB and DFID. There remains a risk though that organisational strengthening activities, such as those under the TCA, are not prioritised once approved where they are not adequately incorporated into AfDB management arrangements.

This Trust Fund has helped to identify areas where DFID assistance continues to strengthen the AfDB’s capacity to deliver. More detailed capacity assessments are now in place for future organisational strengthening activities. A good example is continued investment in the Bank’s results management system, which has led to results frameworks being established for all recent activities. This will make the Bank’s impact easier to measure and track. A new Technical Cooperation Framework Arrangement between DFID and the AfDB is also being established. This will feed into more effective and efficient management of future Trust Fund management.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Enhanced capacity of AfDB to deliver higher quality and high priority infrastructure investment.
Output number per LF		1	Output Score	C
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (reduced from 25% to reflect lower expenditure under this component).

Indicator(s)	Target 2014	Progress
The value of national infrastructure investment approvals (millions of Units of Account).	3150	2051
Regional infrastructure investment approvals (millions of Units of Account).	550	425
Time lapse between approval and first disbursement (months) for infrastructure projects.	12	11 (for all Bank operations)

Key Points
A decision was taken to wind up all substantive activities under this output in 2013. This decision followed an extended period of slow implementation. No new activities have been since been approved. The slow implementation rates were largely attributable to the lack of priority and corresponding ownership given to these activities, in part because of transitions within AfDB leadership in this sector. The detail of individual activities and their reason for termination is explored in earlier annual reviews.
The logframe indicators for this output have also not been a useful measure of performance. The output level indicators look to AfDB performance in the infrastructure sector generally, including total disbursement levels. These indicators do not reflect that TCA-funded projects in this sector are a small component, among many, contributing to the achievement of the AfDB in this sector. Since activities have now been wound up, a decision was taken not to amend the logframe indicators for this output. Instead, for the purposes of this PCR, the impact weighting for this output has been amended to reflect the actual weighting (and funding) applied to this output during the duration of the TCA as a whole.

Summary of responses to issues raised in previous annual reviews (where relevant)

As noted above, following identification of poor performance in consecutive annual reviews, activities under this output were ceased in 2013. The most recent annual review further recommended that the Transport and Information and Communication Technology department should ensure that any future capacity development proposals (developed outside of the TCA) should build on more detailed internal assessments of capacity needs. This is reiterated in the recent project evaluation.

Recommendations for future programmes

Future organisational strengthening activities in the infrastructure sector should respond to the recommendations of the evaluation and (i) build on internal capacity assessment, (ii) be clearly integrated with organisational objectives and deliverables, and (iii) have clear and realistic results frameworks at the outset.

Output Title	Improved AfDB capacity to define and pursue its governance agenda effectively.
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target 2014	Progress
AfDB partners’ and donors’ ratings of AfDB strategic focus on good governance.	Strong (MOPAN assessment).	4.09 (adequate) in 2012 – MOPAN assessment
Progress in effectively implementing AfDB strategy to support good economic governance.	Governance Strategic Framework and Action Plan (GAPII) being effectively implemented.	GAPII was approved by the Bank in May 2014 with implementation taken forward in context of the Bank’s Ten Year Strategy 2013-2022.

Key Points

Activities under this output were successfully completed, although in some instances implementation delays were experienced, which was typical for the TCA as a whole.

The most significant activity under this output was the review of implementation of the AfDB’s Governance Strategic Direction and Action Plan (GAP). This concluded that, at the country level, AfDB performance under the GAP had been very strong. At the sector level, the review indicated that GAP’s objective of mainstreaming governance had been partially met. However, the review also noted that the AfDB remained committed to mainstreaming governance across sectors and had produced studies and guidance notes.

The review findings and lessons learned have been used to inform the development of GAPII which was approved by the Board in May 2014. This really draws attention to the need to address incentives for governance across the sectors, bringing it more into sector strategies, objectives and performance frameworks. As a result of GAPII, the AfDB’s governance work will also increasingly focus on supporting economic transformation of the continent to ensure more inclusive and green growth. The development of the GAPII represents an increase in the scope of the AfDB’s governance priorities in areas that align well with DFID priorities.

Summary of responses to issues raised in previous annual reviews (where relevant)

The most recent annual review recommended that the AfDB ensure the lessons of the review of GAP were reflected fully in the development of GAPII. This has been achieved, in particular in terms of developing the AfDB’s internal approaches to implementation and the need to be clear on roles, responsibilities and integration with the AfDB’s broader results management frameworks.

Recommendations for future programmes

The AfDB should periodically reflect on how its new internal systems for implementing GAPII are operating in practice. This should determine what future organisational strengthening efforts are required in this sector before these are considered under future Trust Fund arrangements (either with DFID or other partners).

Output Title	Enhanced capability to support climate change adaptation and exploitation of low carbon growth opportunities.
Output number per LF		3	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target 2014	Progress
Percentage of new projects classified as climate sensitive which become climate proofed.	100%	70% (new AfDB projects with climate-informed design) / 80% (new ADF projects with climate-informed design)
Percentage of energy investment that is clean energy.	Increased by 60% from 2009 baseline.	The AfDB invested in 978 MW of new power, of which 324 MW come from renewable sources during 2011-2013, representing 33% of the total installed generation capacity

Key Points

Over the lifetime of the TCA, the AfDB has made real progress under its climate change workstream, most notably with the finalisation of a Climate Change Action Plan (CCAP) which includes more clearly defined objectives and is supported by increasing capacity within the AfDB. This progress was noted in particular in the 2013 DFID Multilateral Aid Review (MAR) update. As at the time of this review, 70% of all new AfDB projects and 80% of all new ADF projects have been through a climate assessment and proofing process, which is consistent with the project objective of all climate sensitive projects being proofed.

TCA activities have contributed to this radical repositioning of the AfDB through finalisation of the monitoring and evaluation framework for the CCAP and development and roll-out of an integrated training programme for senior executives. Training has been very positively received, although it is too early to assess the results of understanding in terms of sustained achievements under the CCAP.

The TCA has also successfully contributed to actions with AfDB RMCs through mapping of country Nationally Appropriate Mitigations Actions (NAMAs) and development of a toolkit to support RMCs to better understand concepts and support development of NAMAs.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review noted that the AfDB was slightly off track against some of its very ambitious climate change targets. The AfDB is continuing to make progress, but future monitoring and evaluation of the CCAP should explore, if targets remain off track, whether this is owing to the speed of ambition, the nature of AfDB instruments, or capacity weaknesses and, if necessary, consider opportunities for addressing these through alternative Trust Fund arrangements.

Recommendations for future programmes

See general lessons learned in section B of this Project Completion Report.

Output Title	Improved AfDB human resources and procurement capacity.
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes (increased from 10% to reflect actual balance of expenditure across components).

Indicator(s)	Target 2014	Progress
Perceptions of the AfDB’s donors and partners of its effectiveness in managing human resources.	Adequate (MOPAN assessment).	Adequate (the most recent MOPAN survey was from 2012).
Gender Balance Index (percentage of professional staff that are female).	35%	27%
Time elapsed from project approval to first disbursement (months).	11	11

Key Points

The 2013 Mulatilateral Aid Review update identified progress against some specific institutional weaknesses previously identified by the AfDB, including in the areas of results management, project management and procurement. As acknowledged in the evaluation, TCA activities have contributed to addressing some of these institutional weaknesses, in particular in the area of procurement. Efforts have focussed in three areas, (i) refining process, (ii) use of information technology, and (iii) training. For many of the most recent activities under the TCA, it is too early to say what the impact has been, but we have already seen a reduction in the time elapsed from project approval to first disbursement in line with project expectations.

The TCA has also contributed to progress made in strengthening the AfDB’s approach to human resource management, with a reduction in professional staff vacancy rates from 15% to 6%. Progress is also being made in decentralisation with a steady increase in the percentage of operational staff based in the field (40% in 2013 up from 29% in 2011) and 50% of projects managed from the field (up from 25% in 2011). Weaker progress has been made, however, in the area of attracting and supporting female staff at the professional level. This remains an important objective for the AfDB and should be prioritised. It should be noted, however, that activities under the TCA to support this objective have been limited. Achieving the target set out in the project logframe is also largely dependent on factors which could not have been influenced by the TCA.

Summary of responses to issues raised in previous annual reviews (where relevant)

Earlier annual reviews noted concern with progress in reducing procurement timelines. Reform activities now appear to be delivering results and the AfDB is back on track against its objectives. A number of procurement reform activities remain ongoing, however, and these should continue to be prioritised (using AfDB resources) once the TCA has concluded.

Recommendations for future programmes

As noted in the evaluation, institutional strengthening activities may take considerable time to deliver visible results. For this reason it is important that separate components have their own individual realistic results frameworks. This will mitigate the risk that activities are closed down prematurely thereby undermining the value for money of funds invested to date.

Output Title	Infrastructure, social sector and governance operations contribute to development of dynamic private sectors.
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Target 2014	Progress
Share of public and private operations having private sector development impact.	70%	>70% (of operations contributing to one of the AfDB’s PSD strategic objectives according to internal AfDB assessment).

Key Points

This output has seen the most considerable activity during the last year of implementation of the TCA. Activities contributed to the approval in 2013 of a Private Sector Development (PSD) Policy and Strategy which now recognised PSD as an AfDB-wide priority to which all operations, across sectors, can contribute. As evidenced in recent AfDB Annual Development Effectiveness Reviews, the AfDB now places PSD at the core of its mandate.

The TCA has also contributed to the implementation of the PSD Policy and Strategy. Through TCA support 30 Country Strategy Papers (CSPs) have been supported to operationalise the Strategy (which represents 75% of all AfDB CSPs undertaken during the TCA lifespan). This has contributed to 90% of CSPs now adopting a primarily PSD approach. The TCA has also contributed to development of a number of AfDB thematic advisory services through which tools and training have been delivered on specific topics, including value chains, public private partnerships, and financial intermediaries. Wider training to sensitise AfDB to a range of general and specific PSD themes, in part linked to the development of CSPs.

Most activities intended under this output have been delivered as expected, although a number were the subject of small delays, which were the primary reason for the no-cost extension of this project from March 2014 to September 2014. These delays were typical for the TCA as a whole, although it should be noted that substantive activities under this output were only added to the TCA in 2012, which was significantly later than for other components of the TCA. It is too early to assess the results of much of this work, which will most appropriately be considered as part of ongoing monitoring and evaluation of the AfDB’s PSD Policy and Strategy and wider implementation of CSPs.

Summary of responses to issues raised in previous annual reviews (where relevant)

The last annual review recommended that the AfDB should monitor that its new organisational mechanisms for strengthening PSD impact, including the PSD Steering Committee, are working effectively. Capturing new sector operations mainstreaming PSD will be particularly challenging. As the new approach to PSD remains in its relative infancy this recommendation is still valid and should continue to be considered by the AfDB.

Recommendations for future programmes

See general lessons learned in section B of this Project Completion Report.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key project costs are the professional fees for technical advice and training. These services have been procured in accordance with AfDB procurement policy and procedures which periodically review the remuneration of consultants and fix thresholds according to experience to ensure the Bank received value from its suppliers. In this regard the independent evaluation noted that AfDB rates paid are comparable to those of other International Financial Institutions and Multilateral Development Agencies.

VfM performance compared to the original VfM proposition in the business case

The original project memorandum did not include a specific value for money assessment or improvement measures to be adopted during programme implementation. Instead, value for money has been considered on an iterative basis during programme implementation. As noted above, the key cost driver has been the sourcing of professional services, the economy of which has been driven through competitive procurement and as part of the review and strengthening of AfDB procurement policies and procedures as a whole. In this respect, the 2013 MAR update noted that the AfDB has effective procurement systems with transparent publication of data.

The independent evaluation did explore the efficiency and effectiveness of the TCA in more detail and drew the following conclusions:

- where there were weaknesses in the efficiency of the TCA these stemmed primarily from the delays (sometimes significant) in the start of activities. This was both in terms of preparation and approval of proposals and progression to procurement of expertise. This may have resulted in inefficient use of both AfDB and DFID staff, rather than of external procured expertise once mobilised. Although delays may have resulted in some inefficient use of internal resources, the evaluation noted that strong supervision did contribute to greater effectiveness of those activities that were undertaken;
- the number of individual sub-projects submitted for approval also appeared to undermine the efficiency of the approval process. Where departments submitted packages of inter-linked activities, with clearer results frameworks, this appears to have positively affected efficiency in use of both AfDB and project resources. The same was true of training events, whereby a greater number of staff could have been targetted in one event rather than running multiple consecutive events;
- based on an overarching review of all 48 sub-projects, only 4 did not meet quality expectations (equating to 3.1% of project spend) with a further 2 being cancelled before disbursement because of revised prioritisation;
- the absence of a more structured capacity needs assessment in the priority areas of the TCA prior to submission and approval of activities reduced the opportunity to prioritise organisational development opportunities and ensure alignment to wider strategic objectives. This is likely to have reduced the overall effectiveness of the TCA in meeting the AfDB’s strategic objectives, but did not affect the validity of the TCA approach.

Each of these areas identified in the evaluation was progressively addressed through the iteration of management arrangements for the TCA. More detailed capacity assessments are now in place for future organisational strengthening activities to respond to and the AfDB has considerably strengthened its approach to results management with frameworks having been put in place for all recent activities. These lessons are also being incorporated fully into the design of a new Technical Cooperation Framework Arrangement between DFID and the AfDB as well as into the AfDB’s wider approach to Trust Fund Management.

Assessment of whether the programme represented value for money
The end of programme independent evaluation concluded that the TCA did offer value for money. Although it found that the efficiency and effectiveness of TCA delivery could have been strengthened, it concluded that the vast majority of activities delivered were effective in delivering their intended results and that the TCA management arrangements responded and evolved over time to promote greater effectiveness in the use of programme resources.

Quality of financial management during programme

Financial management and reporting information during the programme has largely been very strong. The AfDB has developed systems to enable it to report frequently and accurately on funds approved for disbursement and actual disbursement rates. The only weakness has been in the area of forecasting. This has meant that it has, on occasion, been difficult to assess what the future financial needs of the TCA were. This stems mainly from the large number of projects which have been managed under the TCA by diverse staff across the organisation.

Date of last financial report	19 August 2014. Final financial report due in February 2015.
Date of last audited annual statement	19 August 2014

E: RISK (½ page)

Quality of risk management over the life of the programme

Risk has been rated as ‘Medium’ throughout the lifetime of the programme, although risk has overall been reducing as both the quality and breadth of management of these risks has steadily improved. Broadly risks have fallen into three categories, (i) overall programme management risks stemming from the large number of activities, diverse AfDB internal incentives for delivering these, and the resources available within the AfDB to oversee and coordinate these, (ii) risks affecting the delivery of individual projects within the TCA, and (ii) risks relating to the achievement of expected programme results, in particular the relevance and effectiveness of interventions for sustainably strengthening the organisational capacity of the AfDB.

Programme management processes were gradually adapted over the lifetime of the programme. This iterative process was identified in the evaluation as leading ultimately to an effective ‘functional management’. In particular, a new approach was adopted for the inception of TCA activities that ensured articulation of clear objectives and expected results. The AfDB’s Partnership and Coordination Unit (currently the Resource Mobilisation and External Finance Department) also invested considerably in strengthening approaches for securing feedback on steps to implement approved activities. Conversely, risk management at the individual project level varied considerably depending on the value and complexity of the project. For those larger project, risks were identified and management approaches undertaken. For smaller activities, of which there were many, explicit risk assessment was not routinely undertaken and where it was often managed through design rather than actively throughout implementation. This may have been appropriate given the scale and value of some of these interventions, but it would have been useful to have an agreed TCA approach to risk management which set out what was required for each type of intervention.

For the third group of risks, the evaluation concluded that the TCA had been relevant and had contributed to strengthening the AfDB as an organisation in areas where it had been active. It noted, though, that the effectiveness, although not the credibility, of the TCA approach as a whole may have been undermined by the absence at the outset of clear internal capacity assessments to form the basis for prioritising organisational strengthening activities. The AfDB (and, as necessary, DFID) are responding to this in future capacity building initiatives through ensuring that such linkages are made.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Through the TCA a diverse number of organisational strengthening activities have been undertaken over a seven year period. Activity design has been led by the individual teams within the AfDB and coordinated by the AfDB’s Partnership and Coordination Unit (currently the Resource Mobilisation and External Finance Department). Implementation of activities under the TCA has been characterised by delays, in particular under output 1. Delays stemmed from a mixture of optimism bias in terms of timelines, competing demands on task team leaders time and, on occasion, protracted procurement. As a result, the TCA has been extended on a number of occasions to enable existing activities to be completed. This flexible approach has, however, also been used to introduce new activities in themes of emerging and strategic importance to the AfDB and DFID, including private sector development and approaches for working in fragile states. In this regard, the recent evaluation confirmed that this flexibility has contributed to enhancing the delivery of results from the programme. These lessons will be taken forward post programme completion into the design of future trust fund arrangements to ensure the right balance between robust results management and flexibility to respond to emerging priorities.

Performance of partnership(s)

The 2014 evaluation of the TCA paid close consideration to the evolution of the relationship between the AfDB and DFID and the effect that this had had on programme delivery. Overall it found that the AfDB and DFID had invested considerable time in their partnership and refining the management arrangements for the TCA and that this has contributed to the performance of the TCA. Transaction costs had initially been very high, but this had served to clarify joint objectives, set the parameters for support and promote coherence among projects. In this respect, the evaluation found that the TCA was highly appreciated within the Bank and that the association with DFID, combined with the flexible and responsive approach, were key to this appreciation. The AfDB and DFID produced a joint response to the evaluation and will work collectively to respond to the recommendations of the evaluation in the development and implementation of any future Trust Fund arrangements.

Asset disposal and value obtained by DFID

No assets were acquired under the TCA.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An evaluation of the TCA was completed in 2014. It focussed on a set of 11 questions which were designed to test assumptions, assess efficiency and effectiveness and draw lessons. Data was drawn from a variety of sources, including (i) an extensive document review, (ii) interviews and group discussions with AfDB and DFID staff, (iii) online perceptions and outcomes surveys targeted at AfDB, DFID and member country stakeholders, and (iv) a project expenditure review.

Overall, the evaluation found that the TCA was relevant to achievement of AfDB strategic goals and that this relevance was increased by the flexible nature of the TCA and its ability to respond to emerging priorities. Activities were largely delivered as expected, with disbursement rates being relatively high when compared to those of other AfDB trust funds. Evidence gathered during the evaluation also indicated that TCA activities had supported the AfDB to achieve results in its strategic priority areas.

Monitoring progress throughout the programme

Monitoring of the TCA was undertaken at two levels: (i) by Task Leaders within the AfDB, and (ii) at the aggregate level by the AfDB Partnership and Coordination Unit (currently the Resource Mobilisation and External Finance Department). Progress was reported back to DFID at both of these levels on a regular basis; by Task Leaders back to DFID technical advisers in the relevant thematic area and by the Resource Mobilisation and External Finance Department to Africa Regional Department. In this way, DFID received feedback from both the AfDB both as the implementer and as the beneficiary, at both the organisational and individual level. Given the scale of activities, feedback from RMCs was not routinely sought as part of ongoing monitoring of TCA activities, but was incorporated into larger projects funded under the TCA. RMC views were also considered as part of the evaluation.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process