Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Assets to Adolescent Girl’s Programme
Programme Value: £16,289,239		Review Date: 12/12/2014
Programme Code: 203375	Start Date: 17/12/2013	End Date: 31/03/2020

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	High

Summary of progress and lessons learnt since last review

This is the first Annual Review of SPRING. It is a review of the progress of the inception phase in preparing the programme for launch and implemention activities in the coming year. This review assesses performance on procurement and contracting the implementing and evaluation teams, progress of the management agent in setting up programme management systems and milestones during the inception phase.

The programme was approved in December 2013. The business case set out a plan for the approval of terms of reference and procurement of a management agent and a monitoring and evaluation provider.

Programme delivery arrangements, including the signature of a delegated cooperation agreement between the three SPRING donor organisations (Nike Foundation, USAID and DFID) and the completion of contracting for the SPRING management agent and implementing team have been successfully completed. The implementing team have established in-country presence and completed field research to identify potential applicants and to better understand girls’ needs in the cohort 1 SPRING countries. The first cohort of SPRING businesses is expected to start receiving support from the programme in June 2015, and the programme is broadly on track to deliver against this expected timeline.
Summary of recommendations for the next year

  - Strengthen project management by refining the existing project plan and consolidating programme leadership in the headquarters in Kenya.

  - Ensure strong communications resource is available with prioritised objectives and develop a coherent approach for fundraising and partnerships going forward.

  - Ensure arrangements for working with the donor management team provide for a good balance between keeping DFID, Nike Foundation and USAID informed and participating in key decision points, while allowing implementing team to focus on programme activities

  - Continue researching strategies for reaching girls with limited purchasing power and building and promoting the business case for enterprises to increase focus on providing assets to girls

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

Outline of the programme

The SPRING programme works as a business accelerator. It will identify early-stage ventures with products that can improve the lives of girls and provide support to these businesses to enable them to reach girls at scale. The support provided will include funding but also access to mentors, expertise and peer-to-peer learning to help drive their business models forward. The businesses supported by SPRING will have products that help girls to safely learn, earn, save and invest. SPRING is a five year programme that will start in Kenya, Uganda and Rwanda, before rolling out to five more countries across Africa and Asia.

Expected Results

The programme will catalyse innovative product development that, with a supportive enabling environment, helps girls to safely stay in school, return to school, and/or earn, and enable them to break the cycle of poverty. It will reach 200,000 girls directly with economic assets by 2019 (output). It will identify cost effective, sustainable and scalable products, services and distribution methods for economically empowering girls by 2019 (outcome). And it will attract large scale investment through effective communications that demonstrate the opportunities to others; contributing to lifting 50 million girls out of poverty by 2030 (impact).

The more detailed programme logframe and theory of change is being developed by the implementing team drawing on research during the inception phase. This will be submitted as part of the final programme inception report at the end of January 2015.

Contribution to DFID’s objectives:

Economic assets are the building blocks of economic and social progress. An asset can generate
income, enhance productivity, facilitate access to capital and credit, and store wealth. It strengthens the owner’s capacity to cope with and respond to shocks by enabling them to diversify income and smooth consumption. Assets can also contribute directly to girls’ economic empowerment by reducing their time-poverty and enabling them to stay in school. Products, in the SPRING context, are assets.

The economic empowerment of girls and women, and their ownership of assets is a strategic priority for DFID. DFID’s Business Plan (2011-15) highlights the critical role of wealth creation and gender equality in poverty reduction. DFID’s Strategic Vision for Girls and Women highlights economic empowerment, and especially access to assets. The Economic Development Strategic Framework emphasises improved access to markets, finance, property and employment opportunities for girls and women.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

An outcome assessment is not possible at the time of this review, because the programme is still in inception phase. SPRING’s expected outcomes include significant additional investment in products targeted at girls and improved economic and learning outcomes for girls. Programme activities with the first round of business ventures are expected to begin in June 2015.

The implementing team contracted at the end of July 2014 are currently in their inception phase, which will be completed by 27th January 2015. Based on progress so far, there is no reason to expect that the programme outputs in the logframe will not be achieved. There are emerging risks, as will be detailed later in this document. However, at this point there is insufficient evidence to assess whether the outputs are likely to exceed or fall below expectations.

Overall output score and description

The output score for programme activities at this stage is “meets expectations” (A).

The results and milestones expected to have been achieved by December 2014 are as follows:

1. Complete arrangements for multiple donors to work together on the programme
2. Complete procurement of an implementing team with a diverse range of skills including programme management, experience of working with enterprises, human-centred design and communications.
3. Implementing team complete an inception phase to set up the programme and be on track to lauch the programme Bootcamp with the first cohort of entrepreneurs by June 2015.
4. Complete procurement of an M&E team for the programme by end of December.

Programme achievements and developments since programme funds were approved in December 2013 include:

- The addition of USAID to the SPRING donor team (May 2014).
- Signing of Delegated Cooperation Agreement between the three SPRING donor organisations (completed August 2014)
- The completion of contracting for the SPRING implementing consortium (July 2014)
- The Inception Phase Milestones for the implementing team were to launch the website splash page by October 9th, launch entrepreneur outreach activities in country by 21st November, provide a draft inception report by 15th December and a final inception report by 27th January. The first two milestones have been met and the others are on track.
- Announcement of the SPRING programme and launch of website splash-page (October 2014)
- Inaugural SPRING Steering Committee meeting (November 2014)
- The completion of the procurement process for a Monitoring and Evaluation team, with contracting expected to be complete in January 2015.

The implementing team have been in place since the end of July 2014. They have established in-country presence and completed field research to identify potential applicants and to better understand girl’s needs. The entrepreneur fieldwork has informed the design of the selection process and application form, which are now finalised. The fieldwork on girls provided ideas for the types of products girls would find most useful and insights into the constraints and behaviours of girls, which will be used during the selection process and to shape the bootcamp curriculum for entrepreneurs. Some challenging activities during the inception phase are around communications and outreach.

Key lessons

- The post-tender clarification PTC negotiations for the SPRING implementing contract were lengthy and detailed and resulted in a number of revisions to the budget. A contract amendment will be required at the end of the inception phase to reflect some of the budget changes. The inception phase was an important opportunity to revisit and further develop detailed budget plans for the programme.
- Conducting research consultations with adolescent girls living in poverty and with entrepreneurs who could be potential applicants during the inception period has been valuable and has influenced proved programme design and selection criteria, for example:
  - The field research findings informed the decision to extend the programme to include businesses selling a product from which girls benefit (an expansion from the initially narrow inclusion criteria of businesses with products sold directly to girls).
  - Products were also further defined to include services that could contribute to girls’ economic empowerment , an expansion from the initial definition of products as goods.
  - Understanding more about key challenges around desireabily, affordability, and accessibility has informed the design of the application process to ensure that entrepreneurs are thinking about how to meet girls’ needs from the beginning.
- Convening core members of the consortium for a kick-off meeting was a challenge for the implementing team to organise very early on in their contract, but they successfully mobilised a geographically scattered team to meet in person. The kick-off meeting accelerated establishment of effective working relationships among all consortium and donor stakeholders.

Has the logframe been updated since the last review?

The logframe has been updated to include inception phase milestones, in accordance with the new SMART rules guidance. These milestones will only be reported on for this Annual Review. All future reviews will assess progress on implementation phase milestones.

The logframe for the implementation phase will be completed over the next year. It is currently being revised by the Results Director of the implementing team based on insights from the field research the team have been conducting on entrepreneurs and girls. It is likely to be further refined by the M&E partner.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective arrangements for multiple donors in the programme
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	25%
Risk revised since last AR?		Not applicable	Impact weighting % revised since last AR?	Not applicable

Indicator(s)	Milestones	Progress
1.1 Signature of Delegated Cooperation Agreement between DFID, Nike Foundation and USAID	Complete signature by July 2014	Agreement signed in August 2014
1.2 Setting up of Crown Agents account to manage finances	Set up account by July 2014	Account activated August 2014

Key Points

This output has been scored an A because donor arrangements were successfully completed prior to programme implementation activities starting.

USAID were a welcome addition to the SPRING donor team in May 2014. Their participation was not anticipated in the business case but they have joined the programme in its earliest stage and are contributing valuable funding and expertise.

In order to allow for pooled funding of the SPRING donors, a Delegated Cooperation Agreement (DCA) has been signed between DFID, Nike Foundation and USAID to enable the setting up of a dedicated bank account for the SPRING programme. Agreeing the content of the Agreement and the process of getting signatures took longer than was originally envisioned. However, the payments account was successfully set up with disbursements from the donors taking place before the first invoice for payment from the implementing team was received. The governance terms of reference annexed to the DCA that sets out clear donor working arrangements will be an important document for the lifetime of the programme.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

None

Output Title	Successful procurement and contracting of implementing team
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
2.1 Completion of competitive tendering process for implementing team	Successful bidder identified by March 2014	Successful bidder identified in May 2014
2.2 Signing of contract with implementing team	Contracting completed in May 2014	Contract signed 27th July 2014

Key Points

This output has been scored an A because, despite delays in the process, an implementing team has been contracted successfully and there are no further recommendations on this output.

There were substantial delays with procurement and contracting, because of interviewing the bidders and the post-tender clarifications stage, which took almost eight weeks to complete. However, the interviews and PTC were very valuable in making the decision on which supplier to choose and providing greater confidence in the chosen supplier’s ability to deliver. The innovative nature of the programme required a more in-depth review to understand programme design and qualifications of consortium members during the PTC stage to ensure accurate understanding of the proposal Given the number of changes that took place during PTC, more time spent on collating and consolidating these changes would have been valuable, but this needed to be balanced out against causing further delays to contracting.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

None

Output Title	Successful completion of inception phase
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
3.1 Field research and in-country presence of implementing team set up	Implementing team appoint country managers for each Year 1 country and complete fieldwork required for design of application process by November 2014	Completed
3.2 Communications and Outreach activities launched	Launch events and information sessions take place in cohort 1 countries to build a pipeline of interested applicants, raise interest among potential sponsors, investors and mentors	Ongoing – entrepreneur outreach strategy finalised Oct 2014, website splash page launched. Social media presence launched and in-country information sessions for entrepreneurs have started, with the first one taking place in Kenya on 26 November, with high attendance. Mixed progress on developing strategy for fundraising and mentors.
3.3 Confidence in programme systems for launch of Year 1 activities	Implementing team on track to start programme activities with Cohort 1 in May 2015	The team have made impressive progress during the inception phase and and are on-track to start activities with Cohort 1 in May. However, there are concerns around inefficient processes that have led to intensive use of staff time and emerging risks for planning and resourcing programme activities beyond May 2015.

Key Points

This output has been scored an A because the programme team have made rapid progress and are on-track to successfully complete an inception phase and open for applications in early January. However, as detailed below, there are emerging risks around the sustainability of the current approach to programme activities and the team will need to maintain strong programme direction and leadership.

The implementing team have been in place since the end of July 2014 and have made impressive progress in a very short time period. Significant achievements of the inception period, as outlined in the draft inception report include:

- Regional office set up in Nairobi with all key programme staff recruited
- SPRING was formally announced by the Secretary of State on 9th October, and the website splash page also went live on this date.
- The implementing consortium have completed field research in all three Year 1 countries in SPRING, on entrepreneurs and on girls’ needs. The entrepreneur fieldwork has informed the design of the selection process and application form, which are now finalised.
- The fieldwork on girls provided ideas for the types of products girls would find most useful and insights into the constraints and behaviours of girls, which will be used during the selection process and to shape the bootcamp curriculum for entrepreneurs.
- Entrepreneur outreach activities have started in-country – the SPRING social media accounts were activated in late November and the first information session for potential applicants was in Nairobi on 26th November.
- The application window and full website launch are on track for early January 2015.

Programme activities that have proved challenging during the inception phase are activities around communications and outreach. Developing a communications strategy for the programme has required more staff time and resource than planned for, both from the donor team and the implementing consortium. Staff resources have at times been diverted away from other activities to communications. The website development process has been particularly time-intensive and would have benefited from greater structure in the process. Further action on communications includes sub-contracting a local communications agency in Kenya, in place in December 2014, to ensure that the required level of expertise is used to develop a communications and social media presence strategy.

Reporting requirements have been burdensome and there has been some lack of clarity on decision-making roles between the donor and implementing teams, which has also led to inefficient use of staff resources.

The feedback from members of the donor management team and the implementing team also indicate a concern around the sustainability of the current approach to programme activities. Intensive inputs from team members at inception stage have raised concerns around planned staff inputs from key team members later in implementation. Leadership of the programme needs to successfully transfer from London to the permanent programme team now in place in Kenya. The intense level of effort required to ensure that the programme is on track to attract a good cohort of entrepreneurs for year 1 has meant that there has been little opportunity or effort to focus on detailed planning for beyond the bootcamp in June 2015. The limited budget and resources may also become more challenging as implementation progresses. The team have two members focused on fundraising, and are currently building up a network of organisations who have expressed interest. However, there is currently less clarity around what the additional funds would be directed towards or plans for outreach to sponsors, investors and mentors. The inception report sets out some of the key insights on the fundraising approach so far and flags that increasing efforts once Cohort 1 is announced may be a more successful and feasible approach, however there is then a risk of limited technical assistance for the first cohort.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable

Recommendations

  - Strengthen project management and leadership by (i) consolidating strategic planning activity and leadership of the programme to come from the headquarters in Kenya and (ii) defining clear roles and accountabilities for the project leadership and management team. It is recommended that a review meeting is scheduled between the Donor Management team and the Project Director to review progress in March 2015.

  - Review and share plans for programme activities to September 2015. A refined project plan should assess the project delivery model in light of learnings from the inception phase. Further details by category of programme activity should be included - key actions, staff responsible for action, milestones, risks to delivery and contingencies. This refined project plan should be delivered by February 2015.

  - Develop a coherent approach for fundraising and partnerships with potential sponsors, mentors or technical assistance providers. It is recommended that this is in place by February 2015.

  - Ensure strong communications expertise is available to implement a communications plan and deliver agreed objectives. The team should consider assigning expertise with local knowledge of social media, to ensure website traction is maximised. It is recommended that the implementing team report back on progress by February 2015.

  - The frequency of reporting to the Donor Management team should revert to monthly, as outlined in the SPRING Donor Governance Terms of Reference, with additional check-ins if required for key decisions. For written reports for internal use by the implementing/donor team, design and formatting should be kept to a minimum level required for clarity. The implementing team should provide clarity on when they are seeking advice and when they are seeking approvals from the Donor Management team, to ensure appropriate level of decision. These new working arrangements should be agreed by the end of the inception phase in January 2015.

Output Title	Completion of contracting for Monitoring and Evaluation Team
Output number per LF		4	Output Score	A
Risk:		Low	Impact weighting (%):	15%
Risk revised since last AR?		n/a	Impact weighting % revised since last AR?	n/a

Indicator(s)	Milestones	Progress
4.1 Completion of competitive tendering process for evaluation team	Identify successful bidder by Oct 2014	Successful bid chosen 14th Nov 2014
4.2 Signature of contract with successful bidder	Submission to ministers for approval before Christmas Recess and Signature of contract before end-January 2015	Submission to Private Office sent on 5th Dec 2014

Key Points

This output has been scored an A because a successful bidder has been identified and the submission requesting approval to contract has been sent to Ministers so we are on track to complete contracting by the end of January.

Developing the terms of reference for the SPRING evaluation was complex and required substantial input from evaluation department and two rounds of external quality assurance by evaluation experts, which resulted in a delay in advertising the Invitation to Tender (ITT). The ITT was advertised in early September, and two bids of high quality were received. The successful bidder has been informed and post-tender clarification (PTC) is now complete. There has not been an extensive PTC - the bid and the two rounds of questions asked have provided a sufficient level of confidence to proceed with contracting. The priority is to ensure that the evaluation team are in place and ready to start collecting data before the first round of programme activity starts, and we are currently on track for this.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable

Recommendations

None

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Key cost drivers will be the administrative costs of managing the programme. The most costly programme activities are likely to be recruitment of entrepreneurs and providing support to entrepreneurs in geographically diverse locations and running a two week residential bootcamp.

VfM performance compared to the original VfM proposition in the business case
Performance against vfm measures and any trigger points that were identified to track through the programme

The value for money assessment of the SPRING business case states that:
The initiative represents a potentially high value for money intervention, through its competitive and rigorous approach to identifying innovative ideas that will have undergone some level of initial testing, and will then be enhanced by quality tailored support. Selecting proposals that answer strategic research questions will enable us to both deliver assets to girls and to generate evidence. The unique offer to applicants, the range of approaches to attracting applicants and the range of geographies has been designed to attract the very best applicants and ideas.

Assessment of whether the programme continues to represent value for money
Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?

This original business case proposition on VfM continues to be valid. A fuller assessment of the programme’s value for money will be possible in next year’s Annual Review once the first cohort of entrepreneurs have been recruited and programme activities begin.

Quality of financial management
Consider our best estimate of future costs against the current approved budget and forecasting profile
Have narrative and financial reporting requirements been adhered to. Include details of last report
Have auditing requirements been met. Include details of last report

We have established a financial forecasting schedule with the implementing team. The initial forecasts for the inception phase were substantially revised. The accuracy of forecasting is improving over time.

The first set of audited accounts is expected in July 2015.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK (½ page)

Overall risk rating: Low/Medium/High

The overall risk rating of the outputs at inception phase is low.

However, it should be noted that SPRING is a high risk programme because it has been explicity designed to test assumptions and build evidence in an area where the evidence base is weak. The evidence on women’s ownership of assets is clear in terms of development benefits, but evidence on girls is not readily available. Moreover, using a private sector development approach to improve girls’ ownership of assets is a novel approach. Rigorous monitoring and evaluation, and continuous focus on research are critical to the success of this initiative, given the experimental nature of programme design and the weak evidence base on interventions that work at scale and sustainably to increase girls’ access to assets.

Overview of programme risk

Level	Risk	Likelihood	Mitigation
Programme Delivery	Inefficient use of programme resources, especially staff time, as a result of weak programme management	Medium	Recommendation to strengthen programme management and leadership communicated to implementing team. Continuous monitoring and a review of progress by March 2015
Programme Delivery	Activities to directly engage adolescent girls in the programme are not implemented in a safe and appropriate way	Medium	Application of GRM’s Child Protection Policy uniquely to SPRING should be documented and media consent forms strengthened. Implementing team staff should received training on GRM’s child protection policy and advice and guidance from the Technical Director on Girls should be incorporated into programme delivery.
Programme Output	Not enough applicants of sufficient quality, lack of interest from potentially attractive ventures that do not see themselves as playing a role in girls’ economic empowerment	Medium	Entrepreneur outreach effort ongoing in-country, building a network and increasing social media presence to attract local and global applicants. Pro-active outreach to identify and engage with local and global ventures whose business models could be adapted to include greater focus on girls.
Programme Output	Lack of technical assistance funding and mentors for cohort 1	High	Increased outreach to potential sponsors and mentors – recommendation to develop a more coherent approach to this outreach. Explore opportunities for large strategic partnerships.
Programme Output	Lack of adequate communication of SPRING at global level reduces effectiveness of fundraising, sponsorship and entrepreneur outreach	Medium	Develop a clear and measurable strategy to build awareness of SPRING within and beyond specific focus countries.
Programme Outcome	Entrepreneurs are unable to reach girls with low incomes in a commercially viable way	High	Implementing team are currently gathering evidence on girls’ earning and spending patterns to understand better what strategies entrepreneurs should use to reach low-income consumers. Entrepreneur application includes an explicit question on how they propose to reach girls living in poverty.
Programme Outcome	Girls shift away from education because of greater availability of income generating products	Medium	Develop guidelines to target income-generating products in an age-appropriate way. Include this risk and mitigation strategies in questions at selection stage and bootcamp stage for entrepreneurs.

Outstanding actions from risk assessment

Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix
Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand

The implementing consortium are led by GRM International, who are part of the Wealth Creation Framework Agreement and there are no outstanding actions from the Due Diligence Assessment that was carried out when they joined the Framework.

A Fiduciary Risk Assessment is not applicable for this programme.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Selection of the first cohort is unlikely to be finalised before May 2015, which means the bootcamp and programme activities will be delayed till June or July.

However, the overall programme timescale is on track and in fact may be shorter than originally envisioned because the total duration of accelerator activities per cohort have been shortened from 12 months to 9 months on advice from implementing team members with experience of other business incubators.

Performance of partnership (s)

The formal relationships that govern SPRING include the contract with the implementing team and the Delegated Cooperation Agreement between the donors. The DCA sets out the programme governance arrangements, which include a donor management committee responsible for the day-to-day oversight and a Steering Committee which meets every six months and provides strategic direction. There will be a contract amendment with the implementing team in January, reflecting agreed changes to the programme design and re-allocation of staff time that took place during the inception phase.

These formal arrangements are working well. The first Steering Committee meeting took place on 14th November and provided constructive comments and suggestions on the programme design, which are being incorporated e.g. advertising a specific category of products on increased girl safety. The arrangements for keeping in touch with the implementing team have also worked well during the inception phase, although concern has been raised about the proportion of time spent reporting and it is expected that the frequency of updates will be scaled down as the programme moves into implementation.

Asset monitoring and control
Not applicable

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The Results Director in the implementing team has been revising the logframe and revisiting the assumptions of the original programme Theory of Change, based on the results from fieldwork in the inception phase. A revised logframe and Theory of Change will be part of the final programme inception report.

Procurement and contracting for an independent evaluation team for SPRING is ongoing. A successful bidder has been identified and contracting is expected to be completed in January 2015.

Monitoring progress throughout the review period

Progress of the inception phase has been closely monitored, with weekly update reports from the implementing team and regular calls every two weeks for a general update and detailed discussions on specific aspects such as communications, implementation phase logframe, results of fieldwork, etc.
The Steering Committee meeting of SPRING provided a milestone at which progress so far was assessed and recommendations made for programme implementation.

This Annual Review process:

A desk-based review conducted by the DFID lead advisor on SPRING. It has included input and review from Girl Hub, Nike Foundation and USAID staff who are part of the donor management team of the programme and have been involved in the programme design, procurement and inception phase.

Evidence sources include project documents, including the draft inception report received on 10th December and evidence of the implementing team meeting inception phase milestones. Content from the first draft of the programme inception report from the implementing team has also been used.

A review meeting took place with the Project Director of the Implementing Consortium and the SRO for the programme. Feedback has also been received from members of the implementing consortium.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process