Annual Review - Summary Sheet

Title: Queen Elizabeth Diamond Jubilee Trust: UK Contribution
Programme Value: Up to £50 million		Review Date: January 2015
Programme Code: 203754	Start Date: 25.11.13	End Date: 30.06.19

Summary of Programme Performance
Year	2013/14
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review
This is the first review of support to the Queen Elizabeth Diamond Jubilee Trust (the Trust) to reduce levels of avoidable blindness in the Commonwealth. The programme addresses: trachoma in Africa and the Pacific; diabetic retinopathy in India, Pakistan, Bangladesh, Caribbean and the Pacific; retinopathy of pre-maturity in India, and; strengthening of knowledge, tools and people to improve eye health across the Commonwealth. The logframe sets year one targets for March 2015. This review assesses progress towards these targets against intermediate milestones agreed with the Trust in September 2014.

The Trust has established a scientific advisory board (SAB) to assist the board of trustees to review proposals. The SAB includes members that lead work funded by the Trust. Conflicts of interest are declared and minuted, although a more detailed conflicts of interest policy is advised. Lead organisations have been identified and proposals developed for each initiative. These have been reviewed by the SAB and approved by the Trust board. A review of selected proposals, and interviews with key informants, indicate that: they are ambitious and of high quality; are embedded within appropriate, country owned strategies; have due consideration for health system capacity building, and; have buy-in from government and other country stakeholders. However, DFID country offices report varying degrees of awareness of the Trust supported programmes.

Implementation is at different stages for the four initiatives. An internationally recognised approach for tackling trachoma already exists, and the Trust support ‘supercharges’ country level strategies for its implementation. Retinopathy initiatives have required more foundational work to gain agreement for approaches that embed detection, prevention and treatment within neonatal and diabetes services (for retinopathy of prematurity and diabetic retinopathy respectively). Implementation across multiple initiatives, countries and partners will be challenging. Encouragingly, implementing partners highlighted investment in robust data and reporting systems, which should provide the basis for active performance management. A portfolio approach to managing risks across the different initiatives could be considered, with flexibility to reallocate resources if needed to safeguard overall results. The planning and contract phase has progressed well, and good foundation laid for implementation.

All contract organisations interviewed (Sightsavers, London School of Hygiene and Tropical Medicines, Public Health Foundation of India) noted the professionalism of the Trust’s management, and pragmatic approach to working across multiple initiatives and countries. The Trust has been effective in using its brand to mobilise engagement of key international and country level partners. However, greater clarity is needed for how support for initiatives funded under this programme are branded at country level.

Summary of recommendations for the next year
- Agree a formal conflicts of interest policy for the SAB and board of trustees.
- Update logframe before March 2015 based on latest data.
- Align DFID and the Trust reporting cycles for future annual reviews.
- Develop a more detailed risk matrix that is reviewed quarterly by DFID and the Trust teams.
- The Trust management team to consider a focus on aggregated results across countries, with performance in any individual country allowed vary by an agreed margin. This would allow flexibility to re-allocate resources if needed and management of delivery risk across the portfolio.
- Clarify branding guidelines at country level, and communication with DFID country offices.

Further recommendations relating to specific outputs are detailed under Section C.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Link
DevTracker Link to Log frame:	Link

Outline of the programme

The Trust was formally established on 6 February 2012 under the chairmanship of the Rt Hon Sir John Major KG CH, former Prime Minister of the United Kingdom. Its purpose, with the contributions it has received, is to create and manage programmes that will bring life-changing benefit to people across the Commonwealth.

DFID will provide up to £50m in match funding to support the Trust’s avoidable blindness programme. International efforts are underway to eliminate the main causes of avoidable blindness worldwide, providing a unique moment to join and help progress the global Vision 2020 initiative.

The avoidable blindness programme comprises four initiatives. Three tackle main causes of avoidable blindness (blinding trachoma, diabetic retinopathy (DR) and retinopathy of prematurity (ROP)). The fourth supports the other three with fellowships, research and technology development.

The Trust funds work in 10 Commonwealth countries where trachoma is endemic, 4 of which experience very high levels of infection. In Africa, working with Sightsavers and the International Coalition for Trachoma Control (ICTC), the Trust will support the elimination in Malawi and Kenya, and significant reductions in the burden of trachoma in Mozambique, Nigeria and Uganda. In the Pacific, working with ICTC and the Fred Hollows Foundation, the Trust will support elimination in Fiji, the Solomon Islands, Vanuatu and Kiribati (the Trust also supports work in Australia, not with DFID funds).

Diabetes rates are predicted to increase 54% from 366m in 2011 to 552m globally by 2030. In the Commonwealth, an increase of 60% is predicted over the same period. Diabetes increases the risk of many eye health problems, with DR being the main cause of blindness. The Trust is supporting a partnership between to the Public Health Foundation (PHFI) of India and the London School of Hygiene and Tropical Medicines (LSHTM) to improve prevention, detection and treatment of DR in India, Bangladesh and Pakistan. The Trust is also supporting the Caribbean Council for the Blind to reduce rates of DR in the Caribbean, and the Fred Hollows Foundation to reduce rates of DR in the Pacific.

India is rolling out a programme to improve rates of survival for neonates. Premature babies are at risk of ROP, a cause of permanent blindness. With Trust support, PHFI and the LSHTM are working with federal and state governments to integrate services to prevent, detect and treat ROP within Special Newborn Care Units (SNCUs). These units are being rolled out at district level by the government of India and Unicef, with a target with 1000 units operational in 2017. The Trust is supporting strategy and guideline development, training, new patient record and management systems and the development and testing of more affordable equipment for ROP diagnosis.

The LSHTM is funded to host and manage the Commonwealth Eye Health Consortium (CEHC). The Consortium supports fellowships to increase eye care expertise in low income Commonwealth countries, provides a knowledge platform to facilitate learning and information exchange, and a technology programme to develop, validate and rollout low cost eye health diagnostic and management tools.

Outcomes
DFID support to the Trust will be measured by progress against two outcome indicators. Targets for each will be established or updated by March 2015 based on up to date data and national consultation:

Outcome Indicator 1: Percentage of trachoma endemic districts that have achieved criteria for stopping district level Mass Drug Administration (MDA);

Outcome Indicator 2: Survival to discharge (and without ROP) rates of infants <2000grams in Special New-born Care Units (SCNUs) in quality improvement programme area.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
It is too early in programme implementation to assess progress against outcome targets. Targets will be finalised as evidence gathered during the first year of the programme is reviewed, and country consultations and strategy development are completed. However, Ministries of Health and country stakeholders have been engaged actively in planning processes. Strategy development has embedded programmes within broader health systems, with a focus on sustainability (or exit for elimination goals). Robust planning and strong country and partner engagement have provided a good foundation for achieving outcomes and sustaining benefits as the programme progresses in the future.

Overall output score: Met Expectations (A)
In the programme logframe, most indicator year one milestones are set for March 2015 as the first initiative, Trachoma, commenced its implementation phase in April 2014. A number of milestones were also to be determined during the first year of the programme. For the purposes of this review, DFID agreed a set of intermediate milestones with the Trust in September against which to assess progress towards March 2015 milestones. Output 1 progress could also be assessed based on recent programme data against March 2015 targets. Achievements against milestones were assessed against documentary evidence (e.g. meeting minutes and reports), partner reporting, and key informant interviews with lead implementing agencies and in-country partners (India, Mozambique, Uganda and Kenya).

Implementing partners report to the Trust on a six-monthly basis. For future annual reviews, the Trust should revise the programme logframe, in consultation with DFID, to provide targets for each indicator that can be aligned with the DFID November to January Annual Review cycle for this programme.

Output 1: Effective implementation of selected elements of the SAFE strategy [for Trachoma]. Score: Moderately fell short of expectations (B)
The Trust’s board approved a grant of up to £42.8m to Sightsavers in September 2013, following a positive SAB proposal review. The Trust’s funding provides a significant financial boost to trachoma efforts. Feedback from sub-contractors, Ministry of Health (MoH) (Uganda) and DFID offices confirm that Sightsaver’s approach “supercharges” existing MoH strategies, with a focus on coordinating partners under national Trachoma Action Plans (TAPs) and MoH leadership. In particular, Sightsavers, the ICTC and country implementing partners support better use of epidemiological data, updated procedures, significantly increased clinician productivity and improved supply chain performance. TAP development took longer than anticipated in some countries, and progress in launch, training and implementation varies. In September 2014, Kenya and Uganda had made good progress towards March 2015 trachoma surgery targets (52% and 43% respectively); implementation had just begun in Malawi (2%), and was yet to begin in Nigeria, Tanzania and Mozambique. Sightsavers report that March 2015 targets may be slightly missed, but that implementation pace will accelerate to achieve targets for year 2. TAPs provide a coordination framework for different funding streams and activities across all elements of the SAFE (Surgery, Antibiotics, Face washing and Environmental interventions) approach to trachoma elimination. Buy-in from MoHs, existing donors and partners has been good, and Sightsavers has identified how the Trust funds can best contribute to TAP implementation. Engagement of WASH (Water, Sanitation and Hygiene) partners not previously supporting trachoma was specifically noted (e.g. adding face washing to hand washing campaigns). The priority given to trachoma and capacity of countries to deliver varies (e.g. Mozambique has fewer than 20 ophthalmic surgeons). A country by country balance will be needed to maintain stretching targets and strong programme management on the one hand, while ensuring continued MoH ownership on the other. Sightsavers HQ centrally procures some items (e.g. vehicles) to improve cost-effectiveness. Standard contracts (with Sightsavers HQ) are used for country implementing partners, with evidence of robust negotiations on cost, and some benchmarking across countries.

Output 2: Increase in the proportion of diabetic patients treated for diabetic retinopathy in targeted Commonwealth countries. Score: Met Expectations (A)
The Trust’s board approved grants in October 2014 to the Public Health Foundation of India (India, £3.5m), Fred Hollows Foundation (Fiji, Kiribati, Solomon Islands and Vanuatu - £0.5m; and Bangladesh and Pakistan - £0.5m) and Caribbean Council for the Blind (£1.5m) for work to reduce rates of diabetic retinopathy. In India a situation analysis (11 cities – DR prevalence is higher in urban areas) and two national DR summits have informed proposal development. The situation analysis shows diabetics present late with eye health complications, often with blindness. Increased awareness among diabetics and diabetes clinic staff is needed. PHFI works closely with federal and state ministries of health, working closely with both diabetic and eye care disciplines, both of which participate in a national DR taskforce. DR is included in the national non-communicable disease (NCD) strategy. Implementation will start in 6 – 7 states, with services tested first in one. Delivery planning will be focused at district level, with a variety of models available, including outreach (working with village health workers) and clinic based services. PHFI will collate detailed costing and output data to assess the cost effectiveness of approaches in different settings. PHFI showed good awareness of health systems reform in India. Diabetes care is already included in the benefits package for the new social health insurance scheme, and will include DR treatment. The programme will provide new evidence to inform standard treatment guidelines. PHFI is networking with international technical agencies and NGOs, and sharing learning with the Fred Hollows Foundation and The Caribbean Council for the Blind.

Output 3: Increase in the number of infants treated for ROP. Score: Met Expectations (A)
A proposal to address ROP in India was reviewed by the SAB in April 2014. The SAB requested additional detail on how initial targets states would be selected. An updated proposal was approved by the Trust’s board in November 2014, with grants made to the LSHTM and PHFI. A high-level ROP summit was held in November 2014, and a national taskforce has been established, along with a number of technical working groups that include members from across several medical and nursing disciplines. ROP has been included in the national child safety programme (RSBK). Services will be provided in Special Newborn Care Units (SNCUs), currently being rolled out nationally by the Government of India (GoI) and UNICEF. Detailed situation analyses will be undertaken in selected states to inform implementation. A real-time patient record database has been developed by LSHTM, and adopted by the GoI, that allows detailed collection and analysis of patient data. This includes performance and quality data for each clinic that will allow effective performance management, and assessment of how effectively protocols are rolled out and adopted and adhered to.

Output 4: Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools. Score: Met Expectations (A)
In September 2013, the Board approved a grant of £7.1m to International Consortium for Eye Health, hosted by the LSHTM to support: (a) academic scholarships, and clinical and research fellowships; (b) a knowledge platform for DR, and; (c) development and introduction of new technologies for use in developing country settings. The first 3 MSc students enrolled at the LSHTM in September 2014, a further 3 have been selected to start an MSc at the University of Cape Town in January 2015. A number of candidates have been selected for short and longer-term clinical fellowships, and candidates for research fellowships are being shortlisted. The Diabetic Retinopathy Vision 2020 Network has been established, and a first international workshop brought selected network members together in London in September 2014. Progress is being made to commercialise and rollout the PEEK mobile phone based eye health diagnostic tool, and with the development and piloting (in Tanzania) of the OpenEyes patient record system. The Trust also funded the World Health Organisation (WHO) to develop an eye care service assessment tool. The Trust supported participation by eye health experts in the Royal Society Commonwealth Science conference India (September 2014).

Output 5: A robust, responsive and supportive Trust. Score: Met Expectations (A)
The Annual Report, under the Charities Act 2011 and the Companies Act 2006, was approved by the Board of Trustees on 9 October 2014 and published later that month; this included the Trust’s audited Financial Statements and Accounts which received an unqualified audit. The Report contains narrative highlights on achievements and performance against the ‘main objectives’ for 2013/14 but does not present them within a results based reporting structure. Monitoring indicators were agreed with key implementing partners and the Trust should ensure as much as possible logframes for the various initiatives have common indicators to allow the aggregation of results at the outcome level. In future Annual Reports, the Trust should align results reporting to these common indicators to demonstrate progress towards achieving programme output and outcomes. Implementing partners interviewed for this review reported satisfaction with the management approach of the Trust. The 6-monthly reports submitted by grantees include a section asking for feedback on grantees relationship with the Trust, and if there is anything that the Trust should be doing differently. The Trust developed a draft monitoring and evaluation (M&E) strategy following the agreement of indicators with partners. DFID’s Specialist Evaluation and Quality Assurance Service (SEQAS) carried out an assessment of the evaluation element of the strategy and found that it sets out the Trust’s broad approach to M&E but would benefit from revision to provide a clearer, more structured and more integrated approach. The report’s full findings will be shared by DFID with the Trust.

Key lessons

The Trust and implementing partners have invested considerable effort in comprehensive and inclusive planning processes at country level, with strong government and stakeholder buy-in reported. However, as evidenced by varied progress across countries in the Africa Trachoma Initiative, implementation across countries and initiatives will require effective monitoring, responsive management and a continued focus on maintaining strong country engagement.

Key actions

Key actions are set out under the review of each output in Section C below, and in the programme summary above. Over the next twelve months DFID will focus engagement with the Trust in addressing these actions, which should be addressed in time for the next Annual Review from November 2015 to January 2016. Progress will be monitored by the DFID Commonwealth Programme Manager and Deputy Programme Manager and discussed regularly with the Trust throughout the coming year.

Has the logframe been updated since the last review?

Not applicable as this is first annual review.

## C: DETAILED OUTPUT SCORING
Output Title	Effective implementation of selected elements of the SAFE (Surgery, Antibiotics, Facial Cleanliness, Environmental Improvements) strategy
Output number per LF		1	Output Score	B
Risk:		Low/Medium	Impact weighting (%):	40%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target – / March 2015	Achieved – Sept 14	Progress (November 2014 milestones )
Number of people provided with trachomatous trichiasis (TT) surgery.	Total: 26,500 / Kenya - 9,000 / Malawi - 1,500 / Nigeria - 2,000 / Uganda - 13,000 / Mozambique - 1,000 / Pacific Islands – TBC	10,371 / 4,773 / 35 / 0 / 5,563 / 0 / 0	The Trust Board approval for Africa Trachoma Initiative (Sept 2013) (Sightsavers lead). / ICTC working groups formed to support scale up (01/14). / TAP consultations held in Kenya, Malawi, Mozambique and Uganda. Nigeria pending / Sightsavers Trachoma Action Plans (TAP). developed for Kenya, Malawi, Mozambique, Nigeria and Uganda (the Trust Scientific Advisory Board approved). / Face washing and environmental intervention workshops held in 5 countries – and findings consistent with TAPs. / TAPs launched in Kenya (10/14), Malawi (10/14), Mozambique (11/14), Uganda (11/14). Pending in Nigeria. / Pacific Trachoma Initiative approved by the Trust’s board (06/14) (Fred Hollows Foundation lead). / TAP workshops in Fiji (09/14), Kiribati (09/14), Solomon Islands (08/14). Vanuatu scheduled for early 2015.
Number of people treated with antibiotics in endemic target communities in Kenya, Malawi and Pacific Islands.	Total: 7.3m / Kenya - 3m / Malawi - 4.3m / Pacific Islands - TBC	1,241,259 / 1,241,259 / 0* / - / * planned for 4Q14
Number of endemic districts where Facial cleanliness is implemented through effective behaviour change programmes	Total - 35 / Kenya - 1 / Malawi - 17 / Uganda - 17 / Pacific Islands - tbc	Facial cleanliness activities due to start 1Q15
Number of endemic districts where environmental improvement is implemented	Total - 46 / Kenya - 12 / Malawi - 17 / Uganda - 17 / Pacific Islands - tbc	As above

Key Points
- Sightsavers report that planning process took longer than initially anticipated, but resulted in strong country buy-in and support. Although initial output targets will not be met for March 2015, they are confident that TAPs provide a strong foundation for accelerated implementation progress next year.
- TAPs ‘supercharge’ existing country Neglected Tropical Diseases/trachoma strategies - improve productivity, update protocols, MoH (ophthalmology and NTD departments) and partner coordination, management and reporting. The Trust complements funds from other sources (e.g. USG Envision), either geographically or in terms of SAFE component focus.
- DFID funded Global Trachoma Mapping Project (GTMP) provides new data on prevalence and informs TAP targeting. Combined epidemiological and service delivery assessments resulting in revised targets and more detailed costing information. Monitoring systems are being updated.
- Sightsavers have standardised 5 year contracts with implementing partners that provide for annual review of targets, costs and budgets. Standard approach allows benchmarking across suppliers and countries (although recognise some justifiable variance – e.g. high cost base in Mozambique).
- Additional technical work on face washing and environmental components of SAFE strategy undertaken and now being integrated with TAPs. Engagement of WASH sector partners starting.
- Malawi and Kenya have elimination goals. Mozambique, Uganda and Nigeria have intermediate targets – important to manage constrained capacity (e.g. only 20 ophthalmologist in Mozambique).
- Sightsavers/partners working to strengthen data recording and reporting, including testing digital systems.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as this is the first annual review.

Recommendations

- Logframe targets to be updated by the Trust based on TAPs and agreed with DFID.
- Sightsavers to report and the Trust to monitor degree to which implementation remains coordinated with national strategies, including potential impact on the provision of other health services (e.g. other eye health programmes).
- Sightsavers to report and the Trust to monitor degree to which FE components are appropriately integrated at country level.

Output Title	Increase in the proportion of diabetic patients treated for diabetic retinopathy in targeted Commonwealth countries
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target – Mid 2015	Progress (November 2014 milestones)
Number of diabetic patients screened for diabetic retinopathy	India – states identified and targets established / Pacific – targets identified	India DR Summit – 04/14. / India Situation Analysis – 04/14. / DR Taskforce established – 07/14. / India, Pakistan, Bangladesh, Pacific and Caribbean proposals reviewed by scientific advisory board (09/14) and approved by the Trust’s board 10/14. / Information sharing and lesson between PHFI and Fred Hollows Foundation – FHF Bangladesh participated in India DR summit.
Proportion of screened diabetic patients treated for diabetic retinopathy
Number of health professionals trained on prevention, detection and management of diabetic retinopathy

Key Points
- Work on diabetic retinopathy requires more foundational work in each country to identify how best to integrate DR prevention, detection and treatment within existing diabetes and ophthalmic services. This includes exploration of if and how best to introduce lower cost diagnostic technology, such as PEEK (development of which is also supported by the Trust).
- In India, a situation analysis has been completed. PHFI (with the Trust’s support) has been effective in engaging national and state level governments, leading professionals and professional bodies, including in well attended national symposia. A national taskforce has also been established that includes representatives from both diabetes and ophthalmology disciplines.
- DR proposals are well integrated as part of broader health financing and health reform processes, with DR services included in proposed benefits packages for social health insurance programmes.
- Proposals for Bangladesh, Pakistan and the Pacific have been approved by the board, and can build on existing work funded and supported by the Fred Hollows Foundation.
- A Caribbean proposal (£1.5m) was approved by the board in October 2014. Work to improve primary health care worker and public awareness of DR will be supported in 5 countries. The PEEK diagnostic technology and OpenEyes patient record system will be piloted in Antigua and Barbuda. Ministries of Health will be the implementing partners in 3 countries, with NGO implementation (with MoH approval) in the remaining two.
- The CEHC can facilitate capacity building and lesson learning across countries tackling DR through the Diabetic Retinopathy Vision 2020 Network, and scholarship/fellowship programmes.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as this is the first annual review.

Recommendations

- Based on national consultations and situation analyses undertaken, the Trust and implementing partners should agree geographical focus (India), and logframe baselines and appropriate milestones and targets for DR initiatives by mid-2015.
- Multi-country implementation and support for the DR Vision 2020 network provide opportunities to measure and compare the effectiveness and value for money of different delivery approaches for different populations across countries, including potential to provide services in more rural settings.
- Implementing partners should ensure that mechanisms are in place to monitor and report periodically to the Trust on the socio-economic status of patients accessing DR services.

Output Title	Increase in the number of infants treated for ROP
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target – Mid 2015	Progress (November 2014 milestones )
Number of infants screened for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area	States identified and baseline data collection underway to inform targets.	National ROP summit, Delhi, 4-5 October 2013. 43 delegates including government, NGOs, Unicef and DFID. / National ROP taskforce established and meeting regularly. / ROP proposal approved by the Trust’s board October 2014, including criteria for selection of target states. / Situation analysis to inform selection of states against criteria initiated. / Focused effort will be required to establish targets and begin implementation once intervention states are agreed (political commitment of state governments is a selection criteria).
Proportion of infants treated for ROP in Special New-born Care Units (SCNUs) in quality improvement programme area
Number of health professionals trained in screening and treatment of ROP

Key Points
- Government of India (GoI) commitment to improve quality of newborn care likely to increase prevalence of ROP due to increased survival rates of premature babies.
- The Trust programme well timed to integrate strategies to prevent, detect and treat ROP within newborn care services as GoI commitment is implemented. Focus on public sector (which provides majority of maternity services), but some components (such as inclusion of ROP into medical training curricula) will have spilt over into private sector maternity services.
- LSHTM and PHFI have well established links with policy makers and professional association leaders. Good work has been done to generate high-level government and partner buy-in to include ROP within newborn care packages.
- Multi-disciplinary national taskforce convened, along with technical working groups (e.g. standard treatment guidelines, curriculum development etc.)
- Strong focus on data systems that will be integrated into clinic reporting systems, and will allow real time tracking of cases, care and quality of care provided.
- Evidence that ROP programme is linking with initiative 4 to make use of research fellowship opportunities and technology development for lower cost diagnostic equipment that can be used at clinics (PEEK).
- State level situation analyses to be undertaken to identify initial pilots (including existing capacity, political commitment, potential for scale-up etc.). It would useful to use this as an opportunity to gather more information of which populations are most likely to access services initially.
- Less focus and capacity to look at costing and cost-effectiveness of services.

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as this is the first annual review.

Recommendations
- The Trust to agree appropriate logframe milestones with implementing partners for years 2 and 3 (e.g. state selection, completion of situation analyses and agreement on targets).
- The Trust and ROP implementing partners to agree approach to costing services and estimating cost-effectiveness of ROP programming (drawing on lessons from the DR initiative).
- State level situation analyses should include an assessment of which populations groups are utilising SCNUs and are most likely to benefit from ROP investments.

Output Title	Strengthened eye health systems in lower and middle income Commonwealth countries in three key areas of people, knowledge and tools
Output number per LF		4	Output Score	A
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target – May 2015	Progress (November 2014 milestones )
Number of health care professionals trained and working in eye health in their home country	Total 10 / Short-term Clinical Fellowships – 10	CEHC advisory board established and criteria agreed for selection of scholarship candidates (sex, country need, potential to influence in home country, academic merit etc.). / 3 MSc candidates (1 yr. course) selected and enrolled at LSHTM. / 3 MSc candidates (2 yr. course) selected to enrol at University of Cape Town in Jan 2015. / Candidates selected for 8 short-term (Sept 2014 – April 2015) and 12 long-term clinical fellowships (starting Jan 2015). / Data for applicants, short-lists and selected candidates tracked to ensure balanced reach and in-take. / 28 applications for research fellowships received, and shortlisting underway.
Number of countries with domestic institutions that have agreed and implemented national frameworks for DR screening and treatment	10 countries in DR network and 2 countries agree DR framework with their National Prevention of Blindness Committees (NPBCs)	Diabetic Retinopathy Vision 2020 Network established (DR-NET). / 81 participants (including MoH and clinicians) from 11 countries participated in the first DR-Net training workshop in London in November 2014. Each country team developed a 2 year action plan to develop DR services in their countries.
New eye care technologies developed	Development and studies underway	Preparation for OpenEyes pilot in Tanzania progressing, with launch planned 02/15. Discussions underway with Botswana. / PEEK crowdfunding campaign launched to support development and manufacture of PEEK retina adaptor - strong multi-platform media coverage (BBC WS, celebrity Twitter support etc.).

Key Points
- Good progress on academic scholarship/fellowship programme with clear attention to selection criteria to maximise future benefits to countries (not just candidate academic potential).
- Good linking of initiative 4 to other initiatives: PEEK diagnostic technology programme supporting service delivery for ROP etc; fellowships building capacity for countries or technology programmes to plan and deliver service (e.g. one fellowship will help field validate PEEK).
- DR network established. 81 participants (including clinicians, nurses, Ministry of Health staff) from 11 countries (Botswana, Fiji, Ghana, Indonesia, Jamaica, Kenya, Malawi, Nigeria, Tanzania, Uganda, and Zambia) participated in a training and planning workshop in London in November 2014. Each country team developed a 2 year action plan to advance DR services within their national contexts.
- The World Health Organisation is making good progress finalising an Eye Care Service Assessment tool (currently under final peer review).
- The Trust supported participation by eye health experts in the Royal Society Commonwealth Science conference India (agenda and conference presentations available).

Summary of responses to issues raised in previous annual reviews (where relevant)
Not applicable as this is the first annual review.

Recommendations

DR-Net should follow up with members by May 2015 to report on how action plans developed at London workshop have been integrated within national policies at country level.
Output Title	A robust, responsive and supportive Trust
Output number per LF		5	Output Score	A
Risk:		Low	Impact weighting (%):	10%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Target – November 2014	Progress
Annual report and financial accounts clearly detailing use of DFID funding	Compliant accounts and reporting. Clear lines of communication	Unqualified audit report for FY 2013-14 received in October 2014. / 2013-14 Annual Report and Accounts approved by Board of Trustees and published in October 2014.
Proportion of grantees satisfied by implementation and value added by the Trust	Grantee responses to satisfaction survey included in annual reporting to the Trust	Grantees interviewed by DFID for this annual review reported responsive and productive management relationship with the Trust. / Grantee satisfaction recorded as part of six-monthly reports.
Development of monitoring indicators and evaluation reports showing capacity building and lessons learned	M&E Strategy completed, key monitoring indicators agreed with implementation partners (ICTC, LSHTM, PHFI, FHF)	Draft M&E Strategy completed in October 2014. An assessment of the Strategy has been carried out by DFID’s SEQAS which concluded that it contains much useful information but would benefit from revision to set out a more structured and integrated approach to M&E. / Monitoring indicators agreed with LSHTM (for Fellowships, Research and Technology) ICTC (for African Trachoma) and PHFI (for ROP).

Key Points

- The Annual Report of the Trustees, under the Charities Act 2011 and the Companies Act 2006, was approved by the Board of Trustees on 9 October 2014 and published later that month. It included the Trust’s audited Financial Statements and Accounts which received an unqualified audit.
- The Annual Report contains narrative highlights on achievements and performance against the ‘main objectives’ for 2013/14 but does not present them within a results based reporting structure including indicators and targets.
- Grantees interviewed by DFID for this annual review reported a responsive and productive management relationship with the Trust. Grantees are required to provide information on their relationship with the Trust, and any suggested changes in practice, as part of the six-monthly reports.
- DFID’s Specialist Evaluation and Quality Assurance Service (SEQAS) carried out an assessment of the evaluation element of the Trust’s draft M&E Strategy. SEQAS found that the strategy sets out the Trust’s broad approach to monitoring and evaluation but would benefit from revision to provide a clearer, more structured and more integrated approach to M&E including; setting out at a high level the impacts, learning and added value that the Trust envisages as the outcome of its work; providing a clear understanding to donors and stakeholders of what the Trust wishes to monitor and evaluate and why and; stating the Trust’s intentions on how findings will be used including a communications strategy. Further findings from the report are highlighted below and the report’s full findings will be shared with the Trust by DFID.
- The Trust is developing the strategy to include an overarching Theory of Change with summary theories for each initiative. These must be sufficiently robust, clearly setting out inputs, outputs, outcomes and impact of the Trust’s work as well as the assumptions behind each initiative.
- The current strategy states the evaluation needs in relation to each of the initiatives but these would benefit from further clarity on the relationship between each initiative and the overall evaluation objectives, the type of evaluations proposed and the high level evidence gap it addresses.
- The Trust should include plans for evaluating added value and legacy. The draft strategy does not explicitly address VfM. The Trust intends that the legacy will be that interventions are sustained and funded and that scale up takes place. It will therefore be necessary to include an assessment of the costs of the interventions as well as their effectiveness to convince future funders of their value.
- Regular monitoring by the Trust is undertaken through detailed work plans for each region and country. There is a monitoring template which is completed by the Trust’s co-ordinating partners twice a year which illustrates the main issues the programme is dealing with, the activities, timeframe and link to logframe.
- The Monitoring Template is used as the format for the six monthly progress reports provided by the Trust’s co-ordinating partners. The second of these reports also includes a budget update and any changes to each Initiative’s log-frame or targets. In addition, the Trust also receives monthly updates from all co-ordinating partners on the status of the initiatives, which provides information on progress made and any challenges that may need addressing. This provides a monitoring framework which is regularly updated.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as this is the first Annual Review.

Recommendations

- The Trust should ensure as much as possible that logframes for the various initiatives have common indicators to allow the aggregation of results at the outcome level.
- In future Annual Reports, the Trust should align results reporting to these common indicators to demonstrate progress towards achieving programme output and outcomes.
- The Trust should provide in its annual report to DFID a summary of feedback on Trust performance received in routine reporting by suppliers.
- The Trust should develop its monitoring and evaluation strategy in line with the recommendations of the SEQAS report to ensure the strategy defines a clear, structured and integrated approach and can be built upon as the programme progresses. DFID will work with the Trust to support the development of a more robust strategy.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The main cost drivers for the programme are: human resource and logistics costs incurred through implementing partners. These vary by initiative and delivery channel (e.g. clinic based services or outreach teams). Pharmaceutical costs for prevention of trachoma are met by the International Coalition for Trachoma Control. Costs for surgical equipment, training materials, and diagnosis of RD and ROP vary by country programme.

VfM performance compared to the original VfM proposition in the business case

There is insufficient information available at this stage to assess actual costs and likely cost-effectiveness against those estimated in the business case.

There is evidence that management of the programme seeks to ensure value for money including:

- Expert assessment of proposals by a scientific advisory board to ensure results are realistic, and the selection of countries and intervention populations are appropriate;
- Robust approaches to contracting, including use of standard contracts that allow comparison of unit costs and productivity rates across suppliers;
- Initiatives focused on reducing cost of inputs – e.g. through the development of lower cost technologies, and updating of service provision protocols to comply with best practice;
- Development or strengthening of data systems to record quantity, quality and costs of outputs.

Assessment of whether the programme continues to represent value for money

The economic appraisal set out in the business case adopted different methodologies to assess VFM for each initiative. More detailed epidemiological and service model/cost was available for trachoma programming, which was found to be highly cost effective in terms on disability adjusted life years (DALYS) averted. Less information was available for both DR and ROP initiatives, and so cost-effectiveness thresholds were calculated for each, and found to be plausible for both. There has been no new evidence to suggest deterioration in the cost-effectiveness of the trachoma programme. Nor that DR and ROP programmes cannot be delivered within parameters deemed to be cost-effective.

More detailed epidemiological and programme implementation cost data, and information on outputs achieved, will be available at the next annual review and will allow a testing of VFM assumptions.

Equity

The Africa Trachoma Initiative (the largest Trust grant) focuses primarily on poor rural communities in 5 target countries. DR spending is primarily India focused, with smaller contributions to the Caribbean, Pakistan, Bangladesh, and the Pacific. ROP programming is focused on India. Both DR and ROP programming will initially have an urban focus, due to the availability of capacity and higher prevalence in urban areas. The business case risk assessment identifies a need to ensure that overall benefits are pro-poor. DR and ROP programming should include work to assess which populations benefit from services, and there should be active consideration for how service delivery models could be adapted if necessary for delivery (or case finding and referral) in lower resource settings.

Quality of financial management

The spend profile for 2014/15 has been as expected. DFID has paid 2014/15 funding to the Trust in two instalments in April and October 2014 to reduce the payment in advance of need.

The format of reporting to support each payment request is detailed in the Memorandum of Understanding. This requires the Trust to supply a certified letter with any payment request setting out the detailed actual expenditure to date (committed and spent), a forecast of funds to be disbursed or committed during the next 6 months, a statement supporting new funding raised to which DFID will be viewed as eligible to match and an explanation of the disparity between the forecast commitments and disbursements and funding already held by the Trust.

This reporting requirement has been made for both of the 2014/15 payments.

In addition the Annual Report published in October 2014 provides detailed financial reports, including confirmation that there has been no evidence of any financial risk or fraud. The Annual Report also includes the Trust’s audited Financial Statements and Accounts which received an unqualified audit.

Date of last narrative financial report	October 2014
Date of last audited annual statement	October 2014

## E: RISK

Overall risk rating: Medium

Overview of programme risk:

This is a complex multi-initiative, multi-country programme, with several lead contractors and multiple sub-contractors. Strategies for the elimination of trachoma are well established, but resources and capacity to implement at country level are highly variable. DR and ROP strategies are less well established, and need to be effectively integrated within diabetes and newborn health services. Initial engagement with countries suggests good progress in this respect, but implementation challenges are yet to be fully mapped.

All implementing partners reported a strong focus on strengthening data and reporting, with a strong emphasis on using data for routine programme management. The Trust should agree a reasonable schedule and reporting framework for field visits with lead implementing agencies. Theses should include a specific assessment of data collection procedures and practices (e.g. cross checking a sample of field records against aggregated returns).

Each programme has its own risk register created and maintained by the delivery partner. The six monthly reports include a section on risk where the delivery partner is required to report on risk and identify new risks which are then assessed, updated and reviewed.

The Trust has an overall Risk Register which the Executive Team reviews and updates monthly. The register is also included in the agenda for each Audit Committee meeting. In addition, a copy of the register is sent out along with the management accounts if there have been any major changes to it since the last Committee meeting. The top three risks are reviewed by the Trustee Board at their quarterly meetings and are included in a verbal report about the activities of the Audit Committee.

In addition, the management team ensures that the robust internal controls that exist are functional and complied with to mitigate risks to which the Trust is exposed in administering DFID’s contribution.

The Trust has Policies on Anti-Fraud and Corruption and the Bribery Act which are issued to all staff and are included in the staff handbook. All delivery partners are required to have their own policies on this which are included in their grant agreements. For example, the Trust have confirmed that Sightsavers have their own anti-fraud and corruption policy demonstrating that they require their own delivery partners to have their own policies and procedures.

Outstanding actions from risk assessment

The Business Case and Due Diligence identified a number of high level risk and mitigation actions. Of the initial risks identified four have been completed. The risks that remain outstanding or are ongoing have been incorporated into a Risk Matrix, with progress updates received from the Trust. Going forward the Risk Matrix will be used to summarise and monitor the main risks and mitigation measures across the programme. This will be reviewed and updated at the regular programme meetings between the Trust and DFID.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

Logframe targets have been established for March 2015. Intermediate milestones for November 2014 were agreed by the Trust and DFID in September 2014 against which progress towards March targets could be assessed. The latter largely focus on preparatory and planning activities, but suggest that good foundations have been laid for implementation. Implementation progress for the Africa Trachoma Initiative has varied by country, although Sightsavers report that they expect progress to accelerate in year 2.

Timelines and targets for DR (output 2) and ROP (output 3) initiatives were less defined due to an earlier stage of consultation required in countries to agree intervention models and geographical focus within India. Consultation processes secured government and partner commitment to action on ROP and DR. Situation analyses and technical work are now underway in India, and will inform geographic focus, detailed work planning and identification of appropriate milestones and targets.

Performance of partnership (s)
Feedback from central and country level implementing partners (including Ministry of Health staff), and reports from national symposia, taskforces and launches, suggest that good partnerships have been established across initiatives and countries.

Sightsavers (Africa Trachoma Initiative) has implemented standard contracts with 17 sub-contractors. Information on unit costs and budgeting are shared across partners in countries. Sightsavers note some initial resistance to information sharing, but report that sub-contractors have subsequently found the opportunity to share costs and assumptions useful.

Asset monitoring and control

Not applicable.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not applicable.

H: MONITORING & EVALUATION

Evidence and evaluation

The types of evidence assessed for this review are detailed under Section B. Performance and Conclusions. Programme implementation is generating new evidence in a number of ways, which is then actively informing programme focus and targets:

- Trachoma Action Plan consultation processes have provided vehicles for in-country review of epidemiological data, coordination of additional surveys (e.g. funded by the Global Trachoma Mapping Project or USAID’s Envsion programme) and prevention and treatment protocols. Review of new data has resulted in better targeting of services and revised milestones in some countries (e.g. Uganda). Programme implementation data will provide important insights on operational effectiveness and productivity that will inform milestones and targets.
- DR and ROP programmes include situation analyses to inform programme design and geographical focus. Programmes will generate operational evidence to inform understanding of the most cost-effective delivery modalities in different settings.
- With the Trust’s support, the World Health Organisation is developing an eye health services assessment tool that will allow more effective assessment of service delivery capacity.
- The CEHC initiative includes goals to generate and disseminate new evidence, including through: research fellowships, product development and testing, knowledge platforms and networking.

The Trustees approved an M&E strategy. As detailed under Output 5, SEQAS undertook an assessment of the strategy and concluded that the current document contains much useful information but would benefit from a clearer and systematic structure to aid clarity about purpose and enable a more systematic and integrated approach to M&E. DFID would like to see the Trust develop further its concepts of M&E to set out how the two activities relate to each other and how they can meet the Trust’s and stakeholders’ needs for information for management, learning and accountability.

DFID would like the Trust to address the recommendations made by SEQAS to support the development of overarching evaluation objectives and a robust Trust level Theory of Change, underpinned by summary theories for each initiative. This will help develop a clearer narrative around the use of evaluation and better enable analysis and comparison of cross cutting themes and methodologies.

Monitoring progress throughout the review period

DFID officials have monthly progress meetings with the Trust to discuss progress on the logframe and on financial management issues. In addition, DFID has representation on the SAB which meets twice a year, around March and September.

This desk-based review was carried out by a DFID Senior Health Adviser with inputs from the DFID Programme Manager and Deputy Programme Manager for the Commonwealth, relevant DFID Country Offices, the Trust and implementing partners (as detailed above). The main sources of evidence are detailed above.