Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Lablite: Moving DART (Developing Anti-Retroviral Treatment) implementation forwards into policy and practice in Africa
Programme Value: £2,302,366		Review Date: November 2014
Programme Code: 202037	Start Date: January 2011	End Date: March 2015

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	2	A+	A+	A+
Risk Rating	High	High	High	High

Summary of progress and lessons learnt since last review
The Lablite programme continues to make good progress in countries which represent a difficult working environment. Key messages and outputs have already been disseminated through high level policy discussions and the team will be planning additional events in each country before the end of the programme. The main issue is to persuade policy makers at national and international levels that the approach developed under Lablite can be effectively and safely implemented across a wide range of countries.

Summary of recommendations for the next year

The team to communicate the outcome of the meeting with Presidents Emergency Programme for AIDS relief (PEPFAR) at the Global Fund for AIDS, TB and Malaria (GAFTM) in Geneva to DFID, and depending on the outcome we will consider raising these issues at a higher level with PEPFAR and GFATM.

The team should provide some detail about the outcomes of the training, not just the processes followed.

The final report should contain details of how the messages from the research will continue to be communicated and disseminated when the programme comes to an end in March 2015.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202037/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202037/documents/

Outline of the programme

Lablite is an implementation research project, designed to demonstrate that the delivery of antiretroviral therapy using clinical monitoring, as developed in Developing Antiretroviral Therapy in Africa (DART), can be safely, equitably and cost-effectively decentralised in Africa and effectively rolled out.

One barrier to Antiretroviral Therapy (ART) roll-out in Africa is the perception that all patients on treatment need regular laboratory tests – to maximise the effectiveness of ART and minimise the potential side effects. This is a major obstacle, particularly in rural areas, because these laboratory tests need substantial infrastructure (e.g. machines, electricity, reagents, supply chain), and trained personnel, which are costly to set up and then maintain. In addition, patients who have to walk many miles to access treatment would greatly benefit from decentralised long-term care provision. The results of the earlier DFID funded DART trial showed conclusively that it was safe to deliver ART with clinical monitoring, but without the need for a large number of routine toxicity tests to be carried out.

The objectives of the project are to demonstrate how a decentralised Lablite monitoring package would work in lower level health centres, providing safe and effective care; and to assess the costs, coverage, and equity implications of decentralised Lablite patient monitoring for scale up of service delivery in Africa. Ultimately, a successful Lablite project will support health systems strengthening by providing decentralised Lablite ART delivery.

The outputs attributable to DFID’s support are:

- The clinical outcomes of a decentralised ART Lablite monitoring package used in representative health centres and their referral hubs by trained and supervised staff in Malawi, Uganda and Zimbabwe.
- Costs, coverage and equity implications established for the decentralised Lablite patient monitoring strategy and compared to standard approaches recommended in National ART Guidelines in Malawi, Uganda and Zimbabwe.
- Stronger capacity of African networks and key opinion makers to better engage in the process of getting research into policy and practice; and communicate new knowledge and data to relevant stakeholders and planners and policy makers.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: A+ – outcome moderately exceeds expectations

The outcome, to enable the use of effective approaches in the decentralisation of ART/HIV treatment programmes in Africa, is ambitious and the programme team are using a variety of evidence based approaches to persuade national and international policy makers that this approach can be safely and effectively implemented across Africa. This work is challenging because not all funding agencies are open to an approach which reduces the number of laboratory based tests to support ART roll out. The final results of Lablite will be available in early 2015, at which point it will be possible to see if the programme has met its objectives and outcomes.

Overall output score and description: A+ – outputs moderately exceed expectations

Key lessons
The team have excelled in developing communication and good working relationships with key stakeholders in each country. The wide-ranging scope of the project, both geographically and in terms of its cross-disciplinary nature, has been a challenge but there is evidence of good progress. The project coordination, by the UK team, has been central to maintaining coherence across the three countries. Early work to establish good working relationships at national level has now paid off with increasing local ownership of the outputs. Ministry of Health staff have been instrumental in ensuring that systems put in place work locally.

Key actions
As the programme comes towards a close it will be important to ensure that all the outputs and systems are effectively disseminated and the key approaches developed through this programme are made available to others in the UN, NGOs and National programmes.

Has the logframe been updated since the last review? Yes
The logframe has been updated to better reflect the key outputs of the programme. This has been done following the annual meeting of the programme and review meetings with DFID.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Effective Anti-Retroviral Treatment (ART) service packages tested.
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 Baseline survey completed	Survey carried out July 2012	Survey results analysed and reported August 2014
1.2 Training materials and tools developed and evaluated	July 2013	Training designed and implemented ahead of milestone
1.3 Population survey designed and implemented	May 2013	Phase 1 Survey carried out and analysed
1.4 Data from demonstration sites collected and analysed	March 2013	Bespoke data collection tools designed.

Key Points
Some study sites are now moving towards electronic data collection systems. The team are working to ensure the systems are compatible with other data also collected at the sites. The ‘hub and spoke’ system is now in place at the different centres. Ministry of Health colleagues have been instrumental in implementing Lablite, including overcoming the challenges associated with aligning data collection forms with existing tools.

An important step has been building confidence between researchers and national policy makers. This has been achieved by ensuring good communication between the two groups and training has been adapted nationally and regionally to increase opportunities for the groups to work effectively together.

Despite the best efforts of the research team there has been little progress in changing the policies adopted by International stakeholders including PEPFAR, although there is increasing interaction between the team and major players, such as GFATM, WHO and the Bill and Melinda Gates Foundation. There is a plan to meet with relevant decision makers in Geneva during a meeting hosted by the Global Fund for AIDS, TB and Malaria.

Summary of responses to issues raised in previous annual reviews (where relevant)
The team have developed a system to ensure that they document each step of the way and to prepare a report to share the lessons learned when the programme comes to an end.

Recommendations
The team to communicate the outcome of the meeting at GFATM in Geneva to DFID, and depending on the outcome we will consider raising these issues at a higher level with PEPFAR and GFATM

Output Title	Economic and qualitative results contribute to knowledge and inform debate around design of services
Output number per LF		2	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 Qualitative study informs debate around design of services	June and December 2013	Study designed and implemented in three countries. Results from Malawi, Uganda and Zimbabwe analysed
2.2 Equity study adds to existing information on the socio-economic aspects of decentralisation	September 2014	Initial data collection and analysis complete; further data collection and analysis ongoing
2.3 Young lives methods developed to estimate quality of life among young people in Africa	September 2013 – Development of methodology and tool / September 2014 – Quality of Life estimation in children in ARROW and in adults in Lablite	On track to meet final milestone in 2015, data collection completed and detailed analysis ongoing
2.4 Informal care and productivity costing techniques developed and applied in study countries	November 2014 – Data collection and analysis	On track to meet final milestone in 2015, data collection completed and detailed analysis ongoing
2.5 Effectiveness and cost-effectiveness modelling studies inform debates around national and international policy in HIV	July 2013 – Contact with key stakeholders in policy and modellers involved with informing debates around HIV policy	Important findings emerging which may influence policy decisions. The team have been invited to join international debates (WHO and other organisations) on HIV policy

Key Points
Equity data collection has been completed in Malawi, Zimbabwe and Central Uganda. Data collection is ongoing in Northern Uganda. Important information regarding out of pocket expenses and opportunity costs of having a family member under treatment have been collected. Since the introduction of services at remote location travel times and costs, for most patients have been significantly reduced. Anecdotally, there has been improved linkages with the community, through community health workers and relationships between patients and providers have improved, although health workers continue to complain about non-compliance of patients in taking medication.

Summary of responses to issues raised in previous annual reviews (where relevant)
The team have strengthened links with UNAIDS but have not been able to make substantive progress with PEPFAR, despite their best efforts.

The health economics methods being used are gaining traction and the team are preparing a detailed paper for wider dissemination during 2015.

Recommendations

Output Title	Build the capacity of African researchers to carry out research in Africa, participating in all steps including presentation of results and written outputs
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 The number of new and existing African researchers working on the programme. Capacity building of African researchers to carry out research in Africa.	January 2014 Lablite researchers present Project data nationally and internationally	African researchers working in programme (not including PI’s) / Project Coordinators: 2 x male; 1 x female / Health Economists: 2 x male / Statisticians: 2 x female / Training Coordinators: 2 x male

Key Points
The country teams are active in a range of training and capacity building activities, including mentorship, development of case study training materials, checklists and task-shifting. A cross-country training paper has been written, describing training tools developed following on from the needs assessment. In all 12 scientific papers are planned, the majority of which will have African first authors.

Summary of responses to issues raised in previous annual reviews (where relevant)
- African researchers have both undertaken formal training and received close mentorship in data analysis from Medical Research Council (MRC) Clinical Trials Unit (CTU) and York University (Centre for Health Economics), leading to national and international presentations and lead authorships
- African researchers are now involved in funding applications to continue research activities in their own countries
- Relationships developed with MOH in-country are increasing the capacity of partner organisations to engage in nationally relevant research

Recommendations

Output Title	Communication of new knowledge and data to relevant stakeholders, planners and policy makers.
Output number per LF		4	Output Score	A+
Risk:		High	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
4.1 Number of a) papers b) policy briefs c)other publications produced	November 2013 – a) 2, b)1 / September 2014 – a)1, b) 2	Exceeded milestone as the team have published a)7 (3 with female first author) b) 3 c) 3
4.2 Policy Analysis study informs debates around policy and guidelines processes nationally and internationally.	January 2014 – design of policy analysis study	On track, study designed and ongoing
4.3 Lablite results feed into and encourage dialogue, internationally around decentralisation of ART and implementation of new WHO guidelines.	September 2014 – invitations to meetings with key stakeholders	Achieved – e.g. Lablite staff were involved in the HIV Modelling Consortium, carrying out modelling work commissioned by WHO to inform the guidelines
4.4 Local researchers and wider Lablite team engage with policy makers and influencers.	Invitations to participate in national policy making activities and groups by February 2013	Teams in all three countries have been involved with a range of different national policy makers.

Key Points
The team have been invited to participate in policy dialogue meetings with UNAIDS, WHO and GFATM although there has been less progress with PEPFAR. In Malawi the team have continued to engage regularly with the Ministry of Health and Phalombe district. Discussions have centred on the use of video case studies in training of health workers. The Uganda team have been engaging frequently with the District Health Officers and other district staff in the areas in which different components of Lablite are taking place. The Zimbabwe Lablite team have focused their communications efforts this year on engaging with the Ministry of Health and Child Care (MOHCC), implementing partners, and the Zimbabwe offices of the WHO, in particular involvement with planning the national implementation of PMTCT option B+.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendations
The final report should contain details of how the messages from the research will continue to be communicated and disseminated when the programme comes to an end in March 2015.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers remain unchanged from previous years. The key cost drivers are staff and staff-related costs and transportation. Other costs drivers are incidental costs for surveys, data collection, monitoring and training costs.

Exchange rate fluctuations remain a risk in the context of the global economic downturn.

The overall costs of the programme are very competitive because participation of Ministry of Health staff in each country are largely covered by the individual countries.

VfM performance compared to the original VfM proposition in the business case

This programme is performing well and is designed to improve value for money for the delivery of ART, increasing the number of patients treated for the same finite amount of money. The results of DART suggest up to 33% more people can be treated safely and effectively using the same funding envelope, if expensive and potentially unnecessary laboratory costs are removed.

The focus is on the economic and practical difficulties experienced by patients seeking to access HIV care. The work includes studies with a focus on equity in Malawi, Zimbabwe, Central and Northern Uganda.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money. It is designed to improve value for money for the delivery of ART, increasing the number of patients treated for the same finite amount of money. The results of the earlier DART trial suggest up 33% more people can be treated safely and effectively using the same funding envelope, if expensive and potentially unnecessary laboratory costs are removed.

Quality of financial management

In previous years, the financial monitoring and invoicing were an area acknowledged to need improvement. Following CTU’s move to University College London claims have been received on a more regular basis. The programme continues to monitor cost-efficiency through close working between the programme administration, the university finance office and responsible staff in each of the three countries. Forecasting is accurate and the programme is on track to complete spending by March 2015.

Date of last narrative financial report	July 2014
Date of last audited annual statement	Not due until March 2015

Note: prior to the project moving to UCL annual audited statements were part of the overall MRC financial reporting.
## E: RISK (½ page)

Overall risk rating: High

Overview of programme risk
Although almost all of the field work has been completed, the programme remains at high risk because there are major challenges to overcome in the dissemination and uptake of the findings. The political situation in Zimbabwe remains stable but this may change. The continuing Global financial crisis has had a knock on effect of the budgets of Governments and some funding agencies. There is a demonstrable risk of interruption to ART supplies. This risk is relevant, not just to the research, but to ART provision for many countries in Sub Saharan African.

Outstanding actions from risk assessment
The team are continually monitoring and managing risk. They have not been able to make significant progress with PEPFAR and the opposition to the approach to ART roll-out could have a negative impact on long-term uptake of the findings. The team are actively seeking funding, from other sources, to underpin the future dissemination activities.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Lablite has made good progress, with monitoring against their revised logframe showing that they are meeting milestones for outputs. They are producing high quality research results that will help to meet the outcomes of the programme. The workplan has been ambitious and the team have achieved their outputs by March 2015 when the programme ends.

Performance of partnership (s)
The DFID-Lablite partnership is functioning well and has maintained strong relations and communications throughout the life of the programme. Lablite has developed and maintained strong working relationships with each of the participating countries and with the International agencies that are taking an interest in the outcomes of the programme (UNAIDS, WHO and GFATM).

The programme is managed by the MRC CTU, based at the University of London. All the partners meet each year to discuss progress and plans for the coming year. In addition the partners are involved in the discussions about what papers are to be published and to agree authorship. The programme has maintained high level relationships within the Ministries of Health in each country, despite high levels of staff turnover and changes in policies.

Asset monitoring and control
Lablite maintains an appropriate asset register that is monitored regularly during visits. In previous years DFID staff have monitored asset control during site visits.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
As Lablite does not provide support through government systems we do not use the partnership principles to inform the management and monitoring of the programme. There are no other specific conditions to the funding provided by DFID.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In early 2014 the team won the British Medical Journal Research Paper of the Year award, for the paper reporting the findings of their work on delivering ART to children (ARROW trial). The approaches used in ARROW, together with a similar trial delivering ART to adults (DART trial) were the basis for the work in Lablite. The awards was an external indication of the quality of the work of the team.

There are no major changes to the evidence base since the last review.

The economic evaluation approaches used by the Lablite team are innovative and many other teams are now considering adopting a similar approach.

Monitoring progress throughout the review period

The review was undertaken by members of the Human Development team of DFID’s Research and Evidence Division. DFID staff have had a number of meetings and discussions with members of the Lablite team throughout the year, including the health economics, statistics and administrative teams.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process