Annual Review – post April 2018

Title: Delivery of the 2018 Global Disability Summit
Programme Value £ (full life): £1,344,000		Review Date: 13 March 2019
Programme Code: 300530	Start Date: 22 February 2018	End Date: 31 December 2019

Summary of Programme Performance
Year	2019
Programme Score	A+
Risk Rating	Low

DevTracker Link to Business Case:	Found here
DevTracker Link to Log frame:	N/A

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)
This programme covers funding for delivery of the Global Disability Summit (GDS18), hosted by the UK Government, the Government of Kenya and the International Disability Alliance (IDA) from 23-24 July 2018. The Summit was designed to achieve three outcomes: (1) raise global attention on a neglected issue, (2) mobilise new global and national commitments, and (3) showcase best practice and evidence of disability inclusive development.

The Summit brought together more than 1200 high-level delegates from around the world and secured significant commitments in support of the UN Convention on the Rights of Persons with Disabilities (UN CRPD) and the Sustainable Development Goals. The Summit mobilised 171 sets of ambitious commitments and over 349 signatories to our collective action plan, the Charter for Change.

The programme also covers three other components, including: (i) the delivery of a public disability data tool, (ii) funding to ensure disabled people’s organisations were central to the planning, implementation and delivery of the Summit, and (iii) also a number of post-Summit activities, including the design of an accountability approach that is developed to maintain momentum since the Summit, and encourage full implementation of the Commitments made at the July Summit.

Summary supporting narrative for the overall score in this review (1/2 page)
The programme scored an A+ in this review period, with the vast majority of programme activities now completed and delivered successfully. The Global Disability Summit itself was a huge success, securing high-level attendance and significant commitments from actors around the world. Outstanding activities relate to the post-Summit accountability process which is still in progress.

Recommendations for the year ahead (1/2 page)
Disability Inclusion team to ensure successful delivery of the outstanding component of this programme on accountability by December 2019, with particular attention to:
- publishing a one-year on progress report by UNGA 2019;
- designing a long-term accountability approach for delivery of Summit commitments;
- continuing to disseminate and raise awareness of both (a) lessons learnt from the Summit across DFID for use in future events, and (b) commitments and successes from GDS18.
1. Disability Inclusion team work with Leonard Cheshire, and others, to develop a clear and sustainable roadmap for the global data portal by December 2019.
2. DFID’s Head of Events to continue to share learning from GDS18 with other Summit teams (including the lesson learnt document), particularly on delegate management, and working with a production company.

## B: DETAILED OUTPUT SCORING

Output Title	Successful delivery of the Global Disability Summit
Output number per LF		1.1	Output Score	A++
Impact weighting (%):		60%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Summit held with high level attendance from developing country governments, UN agencies, multilateral organisations, other donor agencies, civil society and private sector	Summit to be held in London in July 2018.	The Summit was attended by over 1200 delegates from around the world, including the President of Ecuador, the Vice-President of Argentina, five heads of UN agencies and over 40 government Ministers from around the world.
Number of governments and organisations signing the Charter for Change	The original target was 100 organisations signing the Charter.	Over 345 organisations from around the world signed the Charter.
Number of commitments made by governments and organisations	The original target was 100 organisations making commitments.	Over 170 governments and organisations made commitments, with a total of 968 individual commitments being made.
All sessions at the Summit to be fully accessible	The aim was for the Summit to follow best possible practice on accessibility.	All sessions were designed to be fully accessible, resulting in positive feedback from attendees.

Provide supporting narrative for the score

The Global Disability Summit in July 2018 (GDS18) raised global attention on a long-neglected issue, mobilised new global and national commitments on disability and showcased good practice, innovation and evidence from around the world. GDS18 was instrumental in building the recent global momentum around disability inclusive development and delivering ambitious new commitment to action. There were four indicators, which achieved an A++ score overall:

Indicator 1.1a required strong, high level attendance at the Summit, from across a variety of sectors. This was achieved with high level attendance from across the global community. 67 countries were represented overall, five heads of UN agencies and leading figures from across the global disability community. (Source: GDS18: Official Readout).

Indicator 1.1b related to the Charter for Change which was a collective call to action on disability inclusion. The Charter was the principal outcome document of the Summit, designed to bring about further implementation of the UN Convention on the Rights of Persons with Disabilities (CRPD) and Global Goals. It was signed by over 345 organisations including 47 national governments, 20 multilateral organisations and 226 civil society organisations. (Source: GDS website)

Indicator 1.1c focused on the number of commitments made. Over 170 ambitious sets of commitments were made at the Summit, comprising 968 individual commitments. This included 300 by national governments, 466 by CSOs and 125 by multilaterals. (Source: GDS18 Accountability Inception Report, draft). The commitments were wide-ranging, including:
- anti-discrimination laws to gender equality reforms and commitments on humanitarian assistance.
- Nine organisations and governments, including USAID, the World Health Organisation and UNICEF, along with the UK, joined the Global Partnership on Assistive Technology, aimed at transforming access to, and the affordability of assistive technology.
- Seven UN agencies committed to make their work more inclusive for people with disabilities in various ways, and at least 15 organisations, including the World Bank, committed to promoting the use of the Washington Group questions.
(Source: GDS18 Summary of Commitments)

Indicator 1.1d required sessions on the day to be fully accessible. All sessions were fully accessible including for those with mobility issues, use of sign language interpreters and on-screen captions, facilities for guide dogs, as well as the availability of braille and easy-read for related documentation. There were occasional issues with the functioning of the technology in some sessions, but overall feedback from attendees was that the accessibility was excellent.

Lessons identified this year, and recommendations for the year ahead linked to this output

GDS18 was successfully delivered in July 2018. The Disability Inclusion team has produced a ‘Lessons Learned’ document for future summits. The document sets out a number of recommendations regarding: planning, staffing and recruitment, governance, partner engagement, country and stakeholder engagement, cross-HMG working, comms work, policy and commitments, costs, delegate management and post-Summit accountability work.

The lessons learned document is now used by the Head of Events and will be shared with teams across DFID as a resource for future summits.

Output Title	Successful delivery of a public disability data portal
Output number per LF		2.1	Output Score	A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of countries for which disability disaggregated data have been collected	The original target was 40 countries, including the Summit countries.	Data have been collected for 40 countries across 16 separate indicators. (Source: Disability Data Review)
A website is developed, tested and launched that disseminates disability data	The aim was to launch the website at the Summit.	Website containing the data launched at the Global Disability Summit.

Provide supporting narrative for the score

Until recently there was no central online portal for data disaggregated by disability status. The Disability Data Portal was created to provide a snapshot of the data globally available on people with disabilities in 40 countries and identifies where there are gaps in the current body of data. The portal focusses on data relating to the four thematic areas of the Summit: inclusive education, stigma and discrimination, technology and innovation, and economic empowerment. The portal presents key development indicators relevant to the Summit themes, mostly drawn from the Sustainable Development Goals (SDGs), along with others relevant to the UN CRPD.

There were two key parts of this output. Indicator 2.1a required investigating what disability disaggregated data already exists across the world and collecting these figures into a central place. Indicator 2.1b then required a website which could be used to disseminate the data collected under indicator 2.1a.

Both of these tasks were completed in line with expectations and on time. The Data Portal had almost 13,000 unique users and over 30,000 page views in six months to the end of 20181. We have received positive feedback from users - for instance, it was highlighted as good practice by independent users at the Washington Group annual meeting in November 2018. It is regularly sourced on social media, and Leonard Cheshire continue to publicise it.

However, there are some suggestions which could result in improvements to the Portal. For instance, there is currently no way of downloading data from the Portal, making it harder for users to carry out analysis. There is also scope to link the site in with related and emerging data activities. For example, the Washington Group has a new analysis sub-group that is considering dissemination of data. The Data Portal could be used as a mechanism for sharing data collected using the Washington Group questions.

Lessons identified this year, and recommendations for the year ahead linked to this output
By December 2019, the Disability Inclusion Team should:
work with Leonard Cheshire Disability to cost a set of improvements including, but not limited to, creating a data download, adding more countries or indicators, or further validation of the underlying data.
- with Leonard Cheshire Disability to identify any potential funding to implement the recommended improvements. This will not necessarily be funded by DFID but we should consider whether programme funds could be used.
- discuss with the Washington Group (WG) whether there is scope for the WG to take ownership of the site and use it as a dissemination tool for WG data.

Output Title	Disabled People’s Organisations are central to the planning and delivery of the Global Disability Summit
Output number per LF		3.1	Output Score	A+
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of DPOs from developing countries participating in GDS18	The original target was for 50 DPOs from developing countries to attend the Summit.	IDA facilitated a reference group to ensure that CSOs contributed to design and planning of the summit. 450 applications were made in response to IDA's open call to DPOs to attend the Summit. 55 DPOs were selected to attend. (Source: IDA Report to DFID)
All sessions led by people with disabilities	The target was for all sessions at the Summit to be led by people with disabilities.	Successfully achieved, with all sessions led by people with disabilities. All panel sessions had at least two people with disabilities on the panel.

Provide supporting narrative for the score
The principle of “nothing about us without us” is central to the disability movement. It was therefore vital that the Summit reflected this and that people with disabilities were at the heart of the event. DFID and the Government of Kenya worked closely with the co-host, the International Disability Alliance, to ensure people with disabilities and their representative organisations were embedded in the planning and delivery of the Summit. More broadly, the success of the Summit was built around partnership, with civil society organisations actively working alongside governments, private sector and multilateral organisations to achieve a common goal to leave no one behind and bring disability front and centre of international development and humanitarian assistance.

This output was a key success of the Summit, and scored A+.

Indicator 3.1a was based on the number of DPOs from developing countries participating in the Summit. This was a huge success and critical to achieving the Summit’s objectives. This process was led by the International Disability Alliance (IDA), who undertook a set of actions ahead of the Summit, including:
The establishment of a Civil Society Reference Group to the Summit. This ensured that people with disabilities were involved in planning the summit and creating commitments from civil society.
- An open call to DPOs to attend and participate in the Summit. They received over 450 applications. 55 DPOs were selected to participate and supported, as necessary, to meaningfully engage in the Summit’s design and delivery.
- The Civil Society Forum was held on 23rd July 2018. Over 400 participants attended the forum. On average, 50% of each panel session were representatives of organisations of persons with disabilities.
(Source: IDA Report to DFID).

Indicator 3.1b required people with disabilities to lead the sessions at the Summit. This was achieved, with all sessions being led by people with disabilities. All panel sessions were also balanced, with at least two people with disabilities on each panel, and at least one woman.

Lessons identified this year, and recommendations for the year ahead linked to this output

The level of engagement, representation and leadership from people with disabilities, received significant praise across the international community. GDS18 was praised by high-level attendees as an important influence to change the way international conferences are designed and delivered. There are some lessons learnt on the process for selecting DPO attendees and ensuring the process for selection is as open and clear as possible. We also need to ensure that excluded groups within the international disability community, such as mental health groups, feature even more strongly.

Output Title	An accountability mechanism for the Global Disability Summit
Output number per LF		4.1	Output Score	B
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Number of commitments published online in an accessible way	The original target was to have all commitments on the DFID website immediately following the Summit, with an accessible commitment portal built on the IDA website by December 2018.	All commitments were made available on the DFID website immediately following the Summit. / An accessible portal on the IDA website has been developed which houses all the GDS18 commitments, although this was delayed by two months. It is not published.
First stage of accountability process put in place	Consultants contracted to undertake initial analysis and monitoring of commitments and deliver a one year on progress report.	Consultants are currently undertaking analysis of the commitments made, and on track to launch a process of self-reporting on commitments in April 2019. Initial findings will be published in a one year on progress report later in 2019.

Provide supporting narrative for the score

To help ensure the long-term success of GDS18, DFID is working to develop an accountability approach to encourage full implementation of the commitments, monitor progress and to maintain the momentum that GDS18 has generated.

This output is an ongoing process which has been subject to delay and has therefore scored a B. The delay was predominantly down to ensuring the IDA portal was as accessible as possible and technical issues in relation to the website. These issues have now been addressed and the portal is online.

Indicator 1.1a required the commitments to be published in an accessible format. This task has been completed, with the commitments available on the DFID website as well as a searchable portal on the IDA website, available at: www.internationaldisabilityalliance.org/commitments. The launch of the IDA portal was delayed by two months as the process for uploading, verifying and quality assuring commitments took longer than was previously anticipated.

Indicator 1.1b relates to the first stage of the accountability process being put in place. This work is on track and consultants have been contracted to undertake initial analysis and monitoring of commitments. Analysis is underway and a self-reporting process is due to be launched in April, alongside more detailed case studies in three focus countries. A one-year-on progress report summarising the findings is to submitted to DFID in July, and will be launched in September 2019, which will give an indication of how many commitments are on-track before the longer-term accountability process is launched. The underspend for this component (approximately 50%) relates to remaining activities planned under component 3.

Lessons identified this year, and recommendations for the year ahead linked to this output
Initial results of analysis and monitoring will be presented and discussed at a stakeholder engagement event at the UN Conference of States Parties in June 2019. The analysis is being undertaken by Equal International consultants, with the stakeholder event organised by the Disability Inclusion Team, with support from Equal International.

A one year on report will be published in September 2019, detailing progress against commitments. The report is to be compiled by Equal International consultants, with the Disability Inclusion Team providing sign off and organising the launch event at UNGA. The longer-term approach to accountability is intended to be launched at the end of 2019. The approach should link in with existing reporting mechanisms as far as possible, such as those associated with the UN CRPD and the 2030 Agenda. The approach is being designed by a Key Stakeholder Group (including representative organizations in the disability sector) in consultation with CRPD committee members.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

The Summit theory of change was designed in collaboration with stakeholders and co-hosts in the run-up to the Summit. The Summit theory of change provided a rationale for why the Global Disability Summit would make a difference and where it would fit in the overall process of transforming the lives of people with disabilities.

Impact Statement: The lives of people with disabilities are transformed and disability inclusive development is realised.

Outcome 1. Political will: Catalysing political and institutional will for inclusion in order to mobilise new global and national action. This includes creating opportunities to assess progress and promote accountability for the promises of the SDGs and UN CRPD processes, and to build on those with new commitments. The Global Disability Summit provided fora in which governments could make specific pledges and foster collective action for decision makers and global, national and local actors. The follow-up and accountability approach will be essential for success to hold leaders to account for their promises.

Outcome 2. Data and evidence: It is critical to raise awareness and the profile of issues faced by people with disabilities. The Global Disability Summit provided essential opportunities to share data and evidence to demonstrate ‘what works’ and presenting and furthering the imperative for disability disaggregated data.

Outcome 3. Leadership and representation: Providing high profile and diverse opportunities for leadership and representation of people with disabilities themselves to provide a global platform for people with disabilities to reduce stigma and discrimination. Leadership and representation is needed for effective change in challenging stigma and increasing voice and opportunities for partnership at a variety of levels; the global, national and local level, and the Global Disability Summit was a unique platform for ensuring this representation.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

The programme has already delivered on most of its intended outcomes: catalysing political will through high-level attendance and ambitious commitments, generating rigorous new disaggregated data for the Global Data Portal and sharing new emerging evidence, and also through providing essential leadership and representation opportunities on the global stage.

The only outstanding area is the follow-up of the Summit commitments through the broader accountability approach. This is ongoing and is on track to deliver its objectives by the end of 2019.

There are no other outstanding actions.

Explain major changes to the logframe in the past year (1/2 page)
There was no accompanying logframe for this programme.

Describe any planned changes to the logframe as a result of this review (1/2 page)
N/A.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Economy: A critical success criterion in design of the business case for GDS18 was securing private sector funding to offset the cost of the Summit. Through the development of partnerships with Microsoft and the Open Societies Foundation (OSF), the team secured £200,000 in funding from the private sector. This covered the following: travel, transport, accommodation for high-level attendees; catering and hospitality; moderator and VIP costs; and supporting technology on the day.

Several Summit outputs were purchased at the appropriate quantity and price. For example, the team negotiated robustly with the venue, event production company and other suppliers on costs. A number of these contracts were secured for reduced rates, and the venue was secured free of charge and for a number of extra days. The team drafted and agreed funding criteria for travel, accommodation and visa expenses in conjunction with the initial budgeting, modelling cost implications of different scenarios and principles for what could and could not be funded. Delegations from least developing countries and DPO representatives were identified as funding priorities.

One lesson learnt is that costs for Summits can be difficult to forecast given the evolving nature of delegate numbers. Teams should look to secure higher levels of funding than estimated to build contingency for this.

Efficiency: We monitored delivery of outputs by the production company and related sub-contractors through regular project-level meetings. We agreed delivery objectives, responsibilities and timelines with the production company and developed TOR between the co-hosts and the production company. We also worked closely with delivery partners and developed feedback loops, such as with Leonard Cheshire, on the global data portal, to ensure the outputs were to the highest possible quality and could have most impact.

Effectiveness: The Summit generated 171 sets of commitments from actors around the world – these have the potential for significant lasting impact for people with disabilities. Implementation of these commitments is now a priority, and therefore the continued development of a robust accountability approach and publication of the one-year on report will be central to ensuring the Summit delivers long-term impact. The funding to IDA to secure meaningful participation of people with disabilities and their representative organisations was extremely productive and was a particular success of the Summit – it set the tone for the Summit, and ensured GDS18 truly ‘lived’ the motto of ‘nothing about us, without us’.

Equity: The range and balance of attendees and country commitments was broad and equitable – and we paid particular attention to the involvement of women with disabilities. Every session was chaired by someone with a disability and each speaker panel included at least one person with a disability and one woman. There was more to do to ensure the involvement and participation of mental health groups and those with intellectual disabilities. The Summit was, however, cohosted by two people with intellectual disabilities which was groundbreaking for an event of this kind and strongly welcomed by civil society.

The global data portal will allow us to understand which developmental areas and regions show the greatest inequalities and help DFID and the wider sector reach and target the most vulnerable.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio (1 page)

The majority of the programme activities are now complete, but the remaining output should continue. The continued development of a robust accountability approach and publication of the one-year on report will be central to ensuring the Summit delivers long-term impact.

E: RISK (½ to 1 page)

Overview of programme risk (noting the rating from p.1) and mitigation

Reputational risks:
- Credibility – due to civil society criticism of domestic policy on disability inclusion there was a risk of protest at GDS18. Whilst there was a small protest outside the venue, the International Disability Alliance were on hand to meet with the protestors and hear their concerns. DFID have since met with the relevant organisations for further conversations.
- That criticism in the ICAI report on DFID’s approach to disability in development (published in May 2018) undermined DFID’s reputation and credibility on disability and therefore impacted on the Summit itself. A comprehensive fact check was undertaken on this review, and the review provided valuable recommendations for our future approach.

Delivery risks:
- Momentum post-Summit is not maintained – this is ongoing, but we have consulted widely on the approach. We have developed options through a collaborative approach – setting up a key stakeholder group and partnership forum to build partnership and momentum.
- Lack of ambitious commitments – this did not come into fruition and the Summit exceeded expectations.
- Data portal did not deliver a rigorous platform and insufficient data is collected – this was mitigated through strong engagement and collaboration with the delivery partner. There is a continued risk that the portal will not be fully utilised and developed, but this is a recommendation of the review.
- There was also a risk that some NGOs/PWDs did not support GDS18 because they felt it did not address a particular impairment type – to mitigate this, we consulted IDA/IDDC at every stage on tone and content and took policy advice on contentious issues to mitigate whilst advancing disability rights and ensuring visibility of different kinds of disability. We recognised the likelihood that despite efforts to represent all, some groups may have felt it was not enough.

Operational risks:
- Communications activities around the event, deliverables or high-profile figures do not get sufficient traction – we worked up a strong comms strategy and worked with a range of third-party actors to amplify our messages and GDS18 outcomes.
- Delegate management process is not efficient and has severe consequences on Summit outcomes – we appointed a senior member of staff with decision-making powers for and oversight of delegate management, and to dedicate sufficient resource and time to this area of work. VIPs needed tailored invitations much earlier to secure the date in diaries.
- Accessibility concerns and logistical issues – we ensured all hotel accommodation was fully disability inclusive/accessible and suitable for high level delegates e.g. close to venue, transport connections etc. It was important to manage expectations of delegates to avoid disappointment/misunderstanding e.g. unable to book top hotels due to finite budgets.
- Delayed or late-applicant visas prevents Delegates from attending, leading to poor representativeness of the Summit, especially from fragile states, with knock-on effect on reputation - we liaised closely with UKVA regional representatives and Home Office early to avoid visa delays. We escalated issues quickly to avoid reputational implications, and we drafted guidance for delegates to avoid delays.

The remaining residual risk of the programme is ensuring delivery of post-Summit accountability work. We judge this risk to be low, and it is being mitigated through dedicated focus and oversight from the A2 External engagement lead in the Disability Inclusion Team.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

The initial budget for the programme was based on a best assessment of likely costs, taking into account previous summit budgets, actual quotes received and consultation with procurement and commercial department. This also included consultation with disability experts on costs to ensure the Summit was fully accessible and costs of reasonable accommodations for people with disabilities were met.

The majority of the budget was disbursed via formal agreements with the following delivery partners:
- A contract with Calders Conferences and their downstream suppliers to manage direct Summit production costs;
- An accountable grant with Leonard Cheshire Disability to produce an Open Source Disability Data Portal and Data Analysis;
- An accountable grant with The International Disability Alliance (IDA) to manage the attendance, involvement and participation of Disabled People’s Organisations (DPOs) and delivery of the Civil Society Forum

The remaining budget is being disbursed through a contract with Equal International, who are designing and delivering the accountability approach, and drafting a Year One on report. This is still to be delivered.

To help reduce DFID costs, the team also secured co-financing for the Summit from the private sector. Travel and accommodation costs for government representatives from developing countries were covered by contributions by Microsoft and the Open Societies Foundation.

Calders Conferences were selected through a standing call-down contract to manage the production of the Global Disability Summit. Due to specific venue requirements and the value for money that the Here East venue offered, Calders were required to sub-contract SMART Live to deliver the majority of the works related to production of the event.

The team worked closely with delivery partners to ensure that delivery was consistently on track, on budget, delivered to a high standard and represented a high level of value for money. A budget lead was appointed, all budget items accounted for and regular meetings held both internally and with suppliers to review actual spend against projections. Where third party suppliers were necessary for delivery of specific services, these were sourced in consultation with the team to ensure that the services provided fulfilled the requirements and supported the delivery of Summit objectives.

Budget and Forecast
Component	Lifetime Budget	Current Spend	Current Forecast
Management of direct summit costs (300530-101)*	£786,145.42	£699,125.41	£734,125.41
Open Source Disability Data Portal and Data Analysis (300530-102)**	£105,838.00	£9,243.90	£105,838.00
Establishing an accountability mechanism (300530-103)***	£82,200.00	£40,964.00	£40,964.00
Representation of Disabled Peoples Organisations (300530-104)	£369,654.58	£369,654.58	£369,654.58
TOTAL	£1,343,838.00	£1,118,987.89	£1,153,987.89

*the remaining forecast (£35000) relates to outstanding GDS18 invoices. There is also a £52,020.01 underspend.
** the remaining forecast (£96594.10) relates to outstanding invoices from Leonard Cheshire.
*** the remaining forecast relates to remaining activities planned under component 3, which are on track and to be completed by December 2019.

Lessons and Recommendations
- There were some lessons learned in managing a contract with a production company on an event of this nature – where budgets regularly shift and adapt to meet emerging needs.
- VAT must be factored into all budget calculations – whilst most Summit costs will be VAT exempt there are elements which are not, for example spend on catering. These were not full considered at the initial budgeting of the programme which led to reallocations of funding.
- Also, clear rules and expectations on detailed financial reporting should be communicated to accountable grant delivery partners. Some payments were made later than expected due to delays in detailed financial reporting.

Date of last narrative financial report(s)	NA
Date of last audited annual statement (s)	NA

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring

There was light-touch monitoring processes in place throughout delivery of the Summit. The team met regularly to assess the efficiency and effectiveness of the team’s outputs, and to change and modify structures and systems accordingly. Feedback was received from Summit attendees, and GDS18 received substantial praise from across the disability community and from international actors.

The AR was undertaken through a collaborative process with contributions from different leads (policy, finance, logistics), building on the inputs received through the lesson learnt document.

Evidence

We are continuing to engage closely through our work under component 3: through a ‘key stakeholder group’ and a ‘partnership forum’ to generate evidence and input to shape the accountability approach.

Learning

A comprehensive lessons learned document was drafted through consultation with team members and feedback from GDS18 co-hosts.

## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided