Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: African Enterprise Challenge Fund (AECF) -South Sudan Window
Programme Value: £6M		Review Date: 24-28 November 2014
Programme Code:	Start Date: September 2011	End Date: / December 2014

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	B	A	B
Risk Rating	Med-High	Medium	Medium to High

Summary of progress and lessons learnt since last review

The outbreak of internal conflict in South Sudan in December 2013, and the failure to find a lasting resolution to this conflict, has had a negative impact across all sectors. Agricultural production, the business environment and the investment climate have been severely damaged. The events in December 2013 required DFID South Sudan to revise its programming portfolio to fit a significantly changed context. DFID South Sudan’s Interim Strategy, approved by Ministers in February 2014, responded to the emergence of conflict and the vast scale of humanitarian need, and recognised that funds had to be reallocated to emergency response. As a result, funds for several programmes were reprioritised and the Interim Strategy made it clear that no new investments would be made in businesses under AECF beyond the existing five already supported[1].
[1] Note however that even prior to the outbreak of conflict in Dec 2013, the AECF target of support being granted to 11 businesses was significantly off-track

Of the six contracts originally awarded by the AECF SSW, five of those contracts had been completed and signed before the end of 2013. One (Dryland Seeds) was subsequently withdrawn[2] in June 2014 leaving a total of five from an original target of eleven businesses to be supported by the AECF South Sudan Window (SSW).
[2] The contract for Dryland Seeds was withdrawn due to due to the company failing to meet all the requirements necessary for signing a funding agreement.

Of these five businesses, only one (Honey Care Africa) has made substantial progress, is operating on a strong business footing, and its manager is confident that the business will achieve profitability in the next year. Two more businesses have remained operational (South Farmers and Century Seeds), but have been operating below expectations and capacity, having been detrimentally impacted by the conflict in various ways. The two remaining businesses (Frontier Microfinance and Garden of Eden) have struggled to become operational and their business operations have made no significant progress in the last year. However it is too early to write these enterprises off as in effect they have only been operational for eighteen months and need more time, particularly in such a fragile state as South Sudan, to prove their viability.

The key lesson learned is that the risks to running a successful Small and Medium Enterprise (SME) in a new, very fragile state - characterised by a weak governance environment, poor regulation, minimal support for business development, very low skilled employees, and high risk of conflict - were underrated in the original programme design. Both the Executive Manager (EM), the Alliance for a Green Revolution in Africa (AGRA), and Fund Manager (FM), KPMG International Development Advisory Services, Africa, agree that in retrospect it was perhaps too early to launch a programme of this nature in such a new and fragile state and that with hindsight, waiting another year or two would have been a more sensible choice. In retrospect, a higher level of political economy analysis during programme design is recommended for a programme of this nature in South Sudan and in other fragile and conflict-affected states (FACAS) in order to identify the risks more quickly and accurately.

It is recommended that the AECF provides early business support such as mentoring, technical advisory services and training. Currently AECF does not operate this way, but this review finds that in the South Sudanese context there is a need to provide a higher degree of additional support if businesses are to be successful.

The review also finds that a great deal more needs to be invested in South Sudan in governance, infrastructure, skills and capacity and in building a solid business environment before it is likely that SMEs will be able to flourish and succeed. A simple hard-nosed ‘sink or swim’ approach to business development is more likely to result in more SMEs failing than succeeding under existing circumstances.

Summary of recommendations for the next year

A no-cost extension for at least another full reporting year should be granted in recognition of the fragility of the environment, the lack of time the businesses have had since signing contracts, the average time taken for SMEs to become profitable even in less fragile African states, and the negative impact of the outbreak of conflict upon the enterprises. Additionally, non-extension would likely mean that several of the businesses supported over the past two years would fail, representing poor value for money on the investment made so far. However, DFID South Sudan will need to take a view on whether the time-frame cited by the FM as necessary to enable the five businesses to absorb the full grant disbursements – which would extend the programme to September 2019 – is practical and feasible.

A no-cost extension should also enable greater flexibility in relation to achievement of targets and milestones. Milestones identified in the log-frame which currently have indicators for 2015 would then be able to be assessed accurately and fairly.

The review finds that DFID should also give itself more time to assess the impact and value for money of the AECF SSW programme in a fragile state context.

Grant disbursements which were delayed against the original schedule, have only reached the half-way point and this should be considered in determining the duration of any no-cost extension There also needs to be recognition that business partners may also require an extended time period to provide matched funding.

In-kind asset valuation is still not consistent. This was raised as an issue last year, and is a problem across the entire AECF portfolio, not just the South Sudan Window. The FM should continue to follow up on consistent valuation, addressing concerns from business partners who have been unable to complete this exercise, particularly when cash-flow has been problematic.

The FM and EM need to resolve the question on the use of the ring-fenced budget for dissemination of best practice. This is still an action pending from the recommendations of the last Annual Review.

The AECF innovation ratings system is based on an initial rating by the FM of the business model but is then fixed for the duration of the project. As new businesses develop they may become more innovative as they react to circumstances. The current innovation rating system therefore is too inflexible and should be amended to enable innovation ratings to be changed through the life of the programme[3].
[3] Note that the FM does report on changes in innovation in its ‘Site Reports’, written after every monitoring visit, however these do not currently influence the original innovation rating given at the point of business plan approval and used by DFID for monitoring purposes.

AECF should consider providing early business support including training, mentoring and technical advisory services to South Sudan businesses, and possibly those in other fragile states.

A. Introduction and Context

Outline of the programme

In September 2011, DFID committed £6m to the Africa Enterprise Challenge Fund South Sudan Window (AECF SSW) to provide support to selected enterprises in the agribusiness and agriculture sector that will have an impact on the rural areas of South Sudan[4]. An Accountable Grant of £6m was signed between DFID and the Alliance for a Green Revolution in Africa (AGRA) in Dec 2011[5], covering the period December 2011 to December 2014. AECF is a special partnership initiative of AGRA. The AECF SSW was formally launched in October 2011 through a series of well-attended events, attended by the Minister of Agriculture of the Government of South Sudan (GoSS) and DFID’s Secretary of State. The launch was accompanied by a promotion campaign in South Sudan as well as regionally, targeted at potential investors.
[4] See Quest No 3232664.
[5] See Quest No 3323668.

The Fund Manager (FM) is KPMG International Development Advisory Services Africa, based in Nairobi, Kenya. A dedicated adviser was recruited by the FM to lead the SSW and has been in place for the majority of this current reporting period[6]. The AECF SSW team is based in Nairobi.
[6] Aside from a period of maternity leave Sep 2013 to spring 2014, during which time an interim project manager was in place.

The second year of operations focused on finalising grant contracts with the agri-businesses whose business plans were selected for approval, transferring the first tranches of the approved grants and monitoring the businesses as their operations got underway. By the end of 2013, five of the six selected businesses had signed contracts and five of them had received funds from AECF. The sixth business signed a contract which then was subsequently cancelled and withdrawn by the Fund Manager, due to the company failing to meet all the requirements necessary for signing a funding agreement.

However all progress made in the second year has been overshadowed by the outbreak of the internal conflict. In mid-December 2013, shortly after the second AECF Annual Review mission, violence erupted in South Sudan, stemming from a political dispute within the ruling Sudan People’s Liberation movement. Fighting quickly spread beyond the capital to seven of South Sudan’s ten states, taking on dangerous ethnic dynamics. The worst affected regions include the Upper Nile, Unity and Jonglei states. Although these are not the regions in which DFID support to AECF is being implemented, the impact of the conflict is being felt in the implementation states (the Greater Equatorias), through major disruption to transport, infrastructure, markets and the national and local economies.

DFID, along with most other international donors and partners, evacuated most international staff and their families from South Sudan in December 2013. A temporary office was established in Kampala, with a small core of essential staff operating from Juba. There has been a gradual scaling back up of international DFID staff since February, sequenced with associated upgrades to security infrastructure and operations. The DFID Livelihoods and Food Security Adviser returned in April 2014. However, the final group of staff members did not return until December 2014, including the DFID Deputy Programme Manager for this programme.

The conflict is still unresolved and has had a detrimental impact on all sectors and caused a major humanitarian crisis. 1.91 million people have been displaced since December 2013, 1.44 million of these being displaced internally and the remainder being refugees in neighbouring countries. In response to the changed context, DFID South Sudan undertook a review of all programmes in consultation with delivery partners and prepared a 1 year Interim Strategy which was approved by Ministers in February 2014. The strategy prioritises support to the humanitarian response; strengthening resilience, particularly in the area of food security; protecting basic services and supporting the most vulnerable; and core work on governance and security where these support rather than undermine the political, peace-building, reconciliation and state-building processes. However, given the vast scale of the humanitarian needs, some funds had to be reallocated to the response and a decision was taken
that no new investments would be made in businesses beyond the existing five supported.

While in the second reporting year Fund Manager staff were able to travel extensively to and within South Sudan for marketing, relationship management, assessment of business plans, and monitoring of supported businesses, this year by contrast, there have been heavy restrictions on the travel of both the FM and DFID Livelihoods Advisor, due to evacuation and security concerns. DFID and the FM have therefore only been able to meet in person once.

The business environment:

The conflict has had particularly negative impacts on agricultural production and the business environment, affecting the progress of the enterprises supported by the AECF SSW. While rains were good in the last rainy season[7], the conflict has undermined business and investor confidence, as well as the ability of businesses to operate.
[7] Note that uneven rain distribution has been a problem in some areas where too much rain destroyed flowering maize heads, making mechanised cultivation difficult.

All participating business partners interviewed for this Annual Review have underperformed in relation to expectations and forecasts of twelve months ago. They all attribute this underperformance directly to the conflict which has caused insecurity in their areas of business operation.

The International Finance Corporation (IFC) of the World Bank was optimistic last year about an improving business environment, and a large-scale South Sudan Investment Conference took place just 10 days before the outbreak of the conflict in December 2013. Last year, the Government of the Republic of South Sudan (GRSS) announced that 1,201,600 South Sudanese Pounds (approximately US $250,000) would be reserved in the national budget to support SME development. The Government also removed roadblocks on the trunk road from Nimule which were causing delays on supply routes into the Equatorias and resulting in increased informal taxes on businesses.

However, in the current reporting period, deteriorating revenue from oil, exacerbated by a very weak formal tax regime and institutional framework and reported non-payment of salaries of the military and public sector workers, has resulted in an increase of all forms of taxes[8]. The IFC has agreed a programme of work on this area as a part of its Private Sector Development Strategy, subject to availability of funding, and the IFC reports a high level of demand from businesses for this support. Some businesses report that the financial sector is also nervous or unhelpful in providing support to SMEs, for example banks frequently refuse to extend loans to provide third party finance.
[8] Taxes affecting SMEs are both informal and formal. Multiple taxes are levied by the centre, state, local and payam government bodies. Each of these operate independently and there is currently no mechanism by which tax regimes are harmonised. Many taxes take the form of licences not intended at design point to be used for revenue generation.

At the time of writing (November 2014), the IFC is far less optimistic about the business environment, although reported some positive developments, including progress operationalising Business Registries in Juba and Wau. While Business Registries were established prior to the outbreak of conflict in December 2013[9], those in Juba and Wau were not significantly affected by the conflict and progress has been made during this reporting period in getting the two Registries functioning more efficiently. The Business Registry in Malakal however was looted. Registry upgrading has been a key factor in sixty additional foreign companies having registered in South Sudan in 2014.
[9] The Juba Registry was upgraded in 2012 and both Wau and Malakal Registries were established from scratch in 2013.

The South Sudan Business Forum has met several times since the outbreak of conflict and held a conference in August 2014 on mitigating the impact of conflict on the private sector in South Sudan. The main findings of this conference were that:

The conflict has increased negative perceptions about the quality of the business environment and investment climate in South Sudan;

Active, participatory and inclusive public private dialogue can significantly contribute to resolution of the conflict;

The conflict has resulted in loss of human life and property with major impact on Small and Medium Enterprises;

The agricultural sector has been severely affected by loss of ready to harvest crops, loss of implements and disruption of extension services;

Bank lending and access to insurance services has been adversely impacted by disruptions caused by conflict, asset losses and loss of funds. Government’s decision to stop payments of salaries through the banking system also had a negative impact.

The conference therefore recommended that the South Sudan Business Forum and the Government of the Republic of South Sudan:

Seek greater involvement and contribution of the private sector and other non-state actors in the search for peace and national reconciliation;

Address negative perceptions about the quality of the business environment and investment climate by providing policy guidance and information about the economy;

Implement interventions to mitigate direct impacts of conflict with particular focus on SMEs in the three most affected states;

Support the financial sector’s efforts to revive lending to businesses, especially SMEs;

Create opportunities for provision of political risk insurance in order to promote new investments;

Implement agreed strategy for development of the private sector and a supportive legal regulatory and institutional framework;

Implement measure to support revival of private health care.

The IFC is in the early stages of working with interested parties to establish Special Economic Zones (SEZs) in South Sudan, including one outside Juba. IFC is working on putting in place the legal framework for this and some investment companies have expressed an interest in setting up in the SEZ however the IFC notes a challenge of discerning speculators from investors. The ground designs have also been completed. Investments needed for SEZs will require a dramatic improvement in circumstances in the country though, particularly political stability and huge investment in energy and infrastructure. For the moment it is the opinion of this reviewer that such initiatives are likely to remain in the planning stage.

In the event that greater stability returns to the country, the IFC recommends that key investments in South Sudan able to have a transformative effect must be in extractives (other than oil), particularly gold and uranium, and in agriculture. Agricultural investments endorsed by the IFC include investments in commercial agriculture, in particular cereals including maize and rice, in livestock and in lowland coffee. However land registration and rights issues in South Sudan are no further progressed than they were a year ago, with this as an aspirational target for the Government. International processes such as the ‘RAI’ (Responsible Agricultural Investment) process appears to be largely unknown in South Sudan among stakeholders interviewed for this review.

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

This has been a very difficult year for South Sudan in all respects. The outbreak of conflict has been very damaging, not least in terms of lives lost but also in retarding any form of meaningful progress in relation to human and economic development in the country.

The agricultural and agribusiness sector has suffered from direct impact of the conflict on the productive areas and on the overall environment needed to support agriculture and agribusiness. Such an environment requires government investment and support services (extension, inputs, marketing), investment and improvements to be made to infrastructure, policies that could ease the entry and operations of businesses, and investor confidence, particularly from potential and existing foreign investors. From December 2013, there has been a decrease in efforts to support and build such an environment, and a necessary focus on life-saving response.

Unsurprisingly given this context, the businesses supported through AECF have underperformed. Only one business is performing to - indeed above - expectations. Fund-disbursal is far below target resulting in a substantial programme underspend which requires a no-cost extension to be negotiated between DFID and AGRA.

Some businesses are struggling to maintain a viable cash flow. They need a positive cash flow to be able to finance the next steps in their operation. South Farmers for example cannot afford an auditor to audit in-kind assets. They are requesting an upfront capital injection from AECF to help them through this cash flow crisis.

On a positive side, matched funding from the private sector has been close to agreed targets. The success of the Honey Care Africa honey collection programme has resulted in the achievement of an international award for creating economic and social value, from the Nestlé group (see page 14 for detail).

In effect, AECF-supported enterprises in South Sudan have only been operating for about eighteen months. Given the initial fragility of the economy and the exacerbated fragility due to the conflict, they need more time to become established, and although presently they may be under-performing, it is too early to conclude categorically that they have failed. Even in the best of times, growth of the SME sector is usually driven by a very small number of successful SMEs. In the SME sector in Kenya, for example, the time required for SMEs to break even in a number of different sectors ranges from 3-40 months, with the average being around seventeen months[10]. In the context of South Sudan, one would expect this process to take considerably longer. An SME intervention in this context should not therefore be necessarily viewed as failing if most firms have not yet made a profit. The best metric might not be the percentage of firms who turn a profit, but the average level of profit or growth.
[10] Time Required to Break-Even for Small and Medium Enterprises: Evidence from Kenya, Charles M. Rambo, University of Nairobi, Kenya , International Journal of Management and Marketing Research, Volume 6, Number 1, 2013.

Overall output score and description

Output one: Innovative Agri-business provided with finance and credit facilities required to get off the ground achieved a C rating

Output 2: Increase in commercial private sector investment in agriculture and agri-business achieved a qualified A rating

Output 3: New business models developed, achieved a qualified A rating

Overall therefore this programme gets an output Score of B for this year, Outputs moderately did not meet expectation

Key lessons

A thorough Political Economy Analysis is required, particularly for high risk fragile and conflict affected states (FACAS), to identify risks and constraints more accurately in the design process. Such an analysis may have recommended against programme implementation so soon after national independence in the particular circumstances of South Sudan.

Businesses need more time in fragile and conflict states to find their feet.

New businesses in FACASs such as South Sudan need a higher degree of mentoring and technical support, particularly during their early stages, than SMEs in a more stable environment. AECF needs to consider revising its operational modality in fragile states to enable such support to be given.

For agricultural production and agribusiness to succeed, an effective business and enabling environment is required. The difficulties encountered by programme partners this year have been due to a series of interrelated factors, starting from the outbreak of internal conflict in December 2013, but also overall lack of good governance, an unsupportive regulatory environment, a lack of supporting infrastructure (primarily all-weather roads) and a collapse of business and investor confidence in the country. All of those factors contribute to success or failure, and without addressing the wider risks and constraints in the country, individual initiatives such as this are at greater risk of failure.

Key actions

Agree no-cost extension for at least another full reporting year with EM and FM including duration, and reporting requirements of all parties.

- Clarify with DFID’s UK-based AECF Programme Manager that DFID South Sudan does not have unspent / under-utilised funds remaining from the original £6 million approved available for use by EM or FM. As approved by Ministers in February 2014 via DFID South Sudan’s Interim Strategy, unspent AECF-SSW funds have been reallocated, together with some originally allocated for other programmes, to humanitarian response, as the outbreak of crisis required urgent decisions to be made on appropriate use of resources given the dramatically changed context.
- DFID South Sudan to update overall programme budget on financial systems to reflect reduced total.

If a no-cost extension is granted, re-establish monitoring schedule for both the FM and DFID, security permitting.

As a part of the process of agreeing a no-cost extension, establish the next steps in the programme evaluation process.

FM to make decision on whether to release funds to partners struggling with cash flow issues.

Has the log-frame been updated since the last review?

No

## C: DETAILED OUTPUT SCORING

Output Title	Output 1: Innovative Agri-business provided with finance and credit facilities required to get off the ground
Output number per LF		1	Output Score	C
Risk:		High	Impact weighting (%):	35%
Risk revised since last AR?		Y	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 No of competitive rounds completed; No project concept notes received; no of business plans produced; no of business plans approved (cumulative data)	By 2014 / 2 rounds / 200 Concept notes / 20 Business plans / 11 Business plans approved	By 2014 / 1 competitive round / 200 concept notes / 20 Business plans / 6 Business plans approved / 5 contracts issued
1.3 No of contracts signed by AGRA by the end of each milestone year and their total value (US$) (cumulative numbers)	By 2014 11 projects US$ 7.7m committed to projects	By end 2014, US $3,380,000 committed to 5 businesses

Key Points

Innovative nature of businesses needs to be seen as relative to the South Sudanese context: Output 1 states clearly that the agri-businesses supported should be ‘innovative’. While in a global context none of the businesses supported would be regarded as particularly innovative, in the South Sudanese context, all businesses can be regarded as doing something new in a country where such enterprise is unusual[11].
[11] KPMG continues to emphasise this important point in their annual report and the Fund Manager’s definition of ‘innovation’ is described under Output Three.

Conflict has significantly and negatively impacted businesses: in the last Annual Review it was noted that it will take time for businesses to become established and profitable in such a fragile, emergent business climate. Investors were nervous and financial services and facilities to support businesses were few. The outbreak of conflict in December 2013 has further undermined the investment climate, and most businesses have struggled to maintain existing operations, let alone become profitable. The only enterprise which has got off the ground is the honey export business being run by Kenyan company, HoneyCare Africa[12]. Details on the negative impact on businesses is given below. Honey Care is fortunate to be operating in one of the most stable parts of the country (Central and Western Equatoria), which has so far been minimally directly affected by the conflict. It is also working with traditional honey producers who are able to access their product relatively easily using traditional techniques and do not require use or import of complex equipment or infrastructure to be able to operate. The supply of honey is less affected by weather extremes than are crops so the supply has been constant. They are also backed up by a strong, experienced parent company based in Kenya. For all of these reasons, and as a result or professional management in Juba, they have been commercially successful to date.
[12] Potential honey collectors/suppliers are able to more than satisfy demand from HoneyCare at the moment. A separate business enterprise has tried to replicate the HoneyCare model but instead decided that they would be better collecting the honey themselves but then have offered to collect honey for sale to HoneyCare to filter, package and export to Kenya

Detail on impact on business:

Two businesses express doubts over their capacity to absorb / qualify for next scheduled disbursals: in discussion with some business partners they had doubts about whether they would be requesting scheduled disbursals. Century Seeds felt that they were not in a financial position to manage the next disbursal which includes funds for a new seed treatment facility. South Farmers have been unable to satisfy two special conditions required by due process: provision of audited financial accounts, and the valuation of capital assets which enables release of further funds[13].
[13] South Farmers’ cash flow is seen as inadequate to support these costs and the business will therefore be unlikely to qualify for the next disbursal. Note however that a special facility to cover the costs of valuation of assets as well as improvement of financial management systems has been approved by the AECF governing committee and the amendment to the funding agreement is currently with AGRA.

One business is in a precarious condition: South Farmers established its chicken hatchery in Juba town. That this was achieved during the conflict period at the end of 2013 and beginning of 2014 is remarkable and the manager, James Nyikole is to be commended for his dedication, energy and commitment. The hatchery which finally went into production in March 2014 is currently producing about 8,000 chicks a week. However the original schedule was for 45,000 a week and the hatchery needs to produce at least 12,000 a week to break-even. The market for chicks has not yet been established and the demand has yet to be created[14]. Given that, and without a further injection of capital there was a strong possibility that the business may fail, an additional, un-matched USD$30,000 has been approved by the FM and EM for South Farmers to enable it to meet audit and valuation costs. Given the precarious business environment in South Sudan, special provisions have had to be made to pull promising businesses through a very difficult time and this review agrees with this decision.
[14] Supply of fertilised eggs from Europe, India and South Africa by air freight has proved very problematic. The government including the state Ministry of Agriculture and the Ministry of Defence are among their current major customers. Due to cash flow problems South Farmers has reduced its workforce from 25 to 10 full-time employees plus 5 casual labourers. It has also failed to retain recruited accountants and have fallen behind with financial reporting to AECF.

South Farmers also support contract farming of maize in Kajo Keji, although this operation appears to have been lower priority for the company in comparison with the chicken hatchery. In 2013, 800 MT of maize was harvested from a 200 acre nucleus scheme, and 150 MT from out-growers. In the current reporting period, this is now 250 acres of land on the nucleus farm, and 300 acres cultivated by out-growers (a doubling on 2013’s acreage). The entire production of maize is being purchased by the UN World Food Programme and South Farmers has no contract with other commercial buyers. While the humanitarian situation in South Sudan is likely to sustain this demand, in the medium term, this does not offer a sound commercial footing, and in the longer term the company should seek to diversify its customer base.

Declining security and roads maintenance hit one business: Century Seeds is continuing to produce improved seed for the South Sudan market, mainly maize seed but also producing limited quantities of sorghum, rice and groundnut seed. In 2013, total harvest was 93 tonnes, all sold. Approximately two-thirds of buyers were NGOs and the UN, but 30 tonnes of seed was sold over the counter to private buyers. In 2014, seasonal weather has been amenable to production but productivity reduced as a direct result of the conflict. There has been a deterioration in the security environment in Yei county with an increase in crime and banditry. Without any form of roads maintenance it has become extremely difficult to move around, especially during the rainy season, and this has limited business operations.

In 2014 only 50 of the planned 150 acres were cultivated by out-growers and the nucleus farm cultivated 30 acres. Presently there are 25 farmers working on the nucleus farm. However, there are only 6 out-growers supplying the enterprise this year, compared to 163 last year. Many have reverted to subsistence production although some are still linked into the ongoing USAID funded FARM project.

Problems with recruitment and matching funds hit one business: Frontier Microfinance has so far only received 10% of its contracted allocation. It has experienced challenges recruiting a business manager, however an appropriate person has now been identified and is in place at the time of writing (November 2014). Frontier Microfinance has also raised only a small amount of the required matching funds, due at least in part to the current difficulties in raising capital in South Sudan. Although AECF funding was designed to grow existing business, there is no evidence that after two years this has yet happened in this case. AECF are expecting a new business plan from Frontier Microfinance within six months but for the last year, the enterprise has made minimal progress in developing their business under AECF support.

Declining security and problems raising matching funds affect one business: Garden of Eden had planned to establish a new maize mill in Terekeka, Central Equatoria. However the December 2013 conflict seriously affected their planned operations and as result of this insecurity they have been unable to proceed with this planned operation. They are developing a new business plan which should be ready by the end of January 2015. In common with Frontier Micro-Finance, it has so far been unable to raise matching capital to fund operational costs from their parent company. The Fund Manager initially disbursed $80,000 as a down-payment but as yet this has not been utilised and this may require repayment to AECF if the business is not ultimately implemented.

One contract withdrawn due to failure to meet requirements for signing funding agreement: The contract with Dryland Seeds was withdrawn after twenty months due to the company failing to meet all the requirements necessary for signing a funding agreement. However, this company is also being separately funded under the AECF African Agribusiness Window for operations in Kenya.

Original allocations per company as per contracts

Funds committed Company	Grant Approved / USD$	Loan Approved / USD$	Total AECF Funds Approved / USD$	% of Loan	Matching funds USD$	Leverage
South Farmers Company Ltd	300,000[15]	500,000	800,000	63%	1,311,502	1.64
Honey Care Africa Ltd	500,000	750,000	1,250,000	60%	2,689,295	2.15
Garden of Eden Co. Ltd	75,000	225,000	300,000	75%	1,135,300	3.78
Dryland Seed Ltd	405,869	179,000	584,869	31%	590,000	1.01
Century Seed Co.Ltd	200,000	300,000	500,000	60%	500,000	1.00
Frontier Microfinance Ltd	249,600	250,400	500,000	50%	820,000	1.64
Total	1,730,469	2,204,400	3,934,869	56%	7,046,097	1.79
[15] Note that an additional, un-matched, US$ 30,000 has been approved this reporting period for South Farmers to enable it to meet audit and valuation costs.

Current disbursements and requests for disbursements

Company name	Total disbursements as at 26 November 2014 USD$	June 2014 disbursement requests under review USD$	Total disbursement plus requests under review USD$
South Farmers Company Ltd	$520,000.00	0	$520,000.00
Honey Care Africa Ltd	$581,202.00	$270,004.00	$851,206.00
Garden of Eden Co Ltd	$80,000.00	0	$80,000.00
Dryland Seed Ltd	0	0	0
Century Seed Co Ltd	$300,000.00	0	$300,000.00
Frontier Microfinance Ltd	$50,000.00	0	$50,000.00

Comparison of funds approved versus funds disbursed as of November 2014

Company name	Amount approved USD$	Disbursements to date (including requests to Dec 2014)	%age of overall approved funds used	Balance remaining USD$
South Farmers Company Ltd	$800,000.00	$520,000.00	65%	$280,000.00
Honey Care Africa Ltd	$1,250,000.00	$851,206.00	68%	$398,794.00
Garden of Eden Co Ltd	$300,000.00	$80,000.00	27%	$220,000.00
Dryland Seed Ltd	$584,869.00	0	0	$584,869.00
Century Seed Co Ltd	$500,000.00	$300,000	60%	$200,000
Frontier Microfinance Ltd	$500,000.00	$50,000.00	10%	$450,000.00
Totals	$3,934,869	$1,801,206	46%	$2,133,663

As of the 26th November 2014 the Fund Manager has disbursed $1,801,206 from a round one commitment of US$ 4.4 million. Note that disbursements were due to be made over three years. Due to the longer timeframe being required for SSW contracts to be finalised (compared to that required by other AECF windows) AECF SSW contracts were signed at least 18 months after the programme’s start date. In reality therefore, businesses have had little more than one year of disbursements, rather than the three years originally planned at this point. This accounts for a statistic where only 41% of the original planned disbursements have been made against the total target. However, if the disbursement figure is compared against the disbursement target planned for a single year, the percentage disbursed would look far more healthy. The very short time that businesses have actually been receiving disbursements is a strong argument for the programme extension recommended here.

As a result it is only possible to provide a C rating to the achievements under this output as disbursing 41% of funding to 5 out of a planned 11 businesses must only be described as substantially not meeting expectations.

Summary of responses to issues raised in previous annual reviews (where relevant)

The issues that were raised in last AR

Recommendations in the previous AR:
“A rapid decision is needed from the Fund Manager on completion of contracts with the remaining selected company (Dryland Seeds) and if this will not be completed, a revised budgetary forecast will need to be produced quickly. This will relate to available unallocated funds under the AECF SSW in terms of making decisions on alternative options for reallocation of those funds. This also applies to the uncertainty surrounding the full allocation for Frontier Finance still pending.”

An award letter was originally issued to Dryland Seeds but the award was not progressed for reasons given above. The unallocated funds are detailed above, however, as per DFID South Sudan’s Interim Strategy of February 2014, hitherto unspent AECF SSW funds have been allocated to humanitarian response – together with those from certain other programmes - so no new investments will be made in businesses beyond the existing five supported. It should be noted however that even before the eruption of conflict in December 2013, the AECF SSW was struggling to find a sufficient number of credible agri-businesses to invest in (original target was 11) and it is thought likely that – had conflict not erupted in 2013 – the fund would have struggled to invest more funds in more enterprises within the programme’s time-frame.

Recommendations

A no-cost extension should be granted in recognition of the fragility of the environment, the lack of time the businesses have had since signing contracts, the average time taken for SMEs to become profitable in neighbouring, less fragile states, and the negative impact of the outbreak of conflict upon the enterprises. The review finds that DFID should also give itself more time to assess the impact and value of the AECF SSW programme in a fragile state context. Additionally, non-extension would likely mean that several of the businesses supported over the past two year would fail. The no-cost extension should also enable greater flexibility in relation to achievement of targets and milestones.

## C: DETAILED OUTPUT SCORING

Output Title	Output 2: Increase in commercial private sector investment in agriculture and agri-business
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Amount of private sector finance leveraged through AECF support (AECF requires at least matched funds from companies supported)	By 2014 USD$3.5m	By June 2014 $ 3,220,552 had been leveraged from private sector finance.
% of projects/business ideas that are profitable after 36 months after receiving AECF funding	N/A in 2014 / 20% by 2015	No milestone for this year

Key Points

The amount of private sector finance leveraged from the businesses is at $3,220,552 by June 2014. While not meeting the target milestone of $3.5m it still exceeds AECF programme funding disbursements, which were expected to be $3,934,869 at this stage but in fact have only reached $1,801,206. Matched funding has therefore achieved a leverage rate of 1.79. Adjusting for the lower than expected AECF disbursements against original targets for this stage this can be said to have met expectations. However the projects have not yet reached the end of the disbursement period and AECF is still disbursing money into the project. Due to the delays in identifying businesses to support, and in signing contracts with supported businesses (in year 1 and 2 of the programmes), most project contracts only started in mid-2013, which means they are only 18 months into the 3 year disbursement period.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations in the previous AR:
“Clarify and standardise the definitions of matching funds across the portfolio and maintain consistency in this through the life of the programme. Consider using financial auditors to value capital assets being used as collateral / matched funds. Inconsistency in this area will make tracking difficult and in establishing a level playing field to measure progress”.

The Fund Manager did require business partners to value their capital assets to arrive at a more accurate calculation of in-kind assets. However it is not clear that a consistent valuation system was agreed with auditors. South Farmers has been unable to afford the fees being charged by the auditor to value capital assets due to cash flow difficulties and therefore, having failed to satisfy this requirement, has become ineligible to receive further transfers from AECF.

A real issue remaining is how to achieve consistency across different auditor’s methodologies when valuing capital assets. The Fund manager has stipulated that assets over $10K must be valued. There is always the risk that a partner will try and include older existing assets as part of the valuation and there is no clear methodology for assessing asset-value, nor for accepting or rejecting assets valued on this basis. This is a major issue across the whole AECF portfolio, not just the SSW.

Recommendations

- With grant disbursements having only reached the half-way point, this factor should be considered when determining the duration of any no-cost extension for the programme, including accepting that the ability of business partners to provide matched funding may require an extended time period. This review recommends a no cost extension of at least another full reporting year.
- Fund Manager to continue to follow up on consistent valuation of in-kind assets, addressing concerns from business partners who have been unable to complete this exercise, particularly when cash-flow has been problematic.

## C: DETAILED OUTPUT SCORING

Output Title	Output 3: New business models developed
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
% projects where the new technologies/business models are disseminated through the media, conferences, case studies or published documents	20% by 2014	Honey Care won an award, the Nestlé Creating Shared Value Prize for 2014, for their business in South Sudan. / https://www.flickr.com/photos/nestle/sets/72157646703504240/ / As this is one company out of five financed by AECF this equals 20% and therefore meets this target.
% of projects in AECF's portfolio of approved projects that are marked 3 or above on the AECF innovation scale and thus judged to be innovative and demonstrating new business models that benefit the poor	20% by 2014	Innovation is defined at the beginning of the programme and there is no capacity to adjust this through the programme. / All but one of the funded projects achieved an initial rating of 3 or above

Key Points

The Honey Care Africa honey collection and export business has been particularly successful, demonstrating that against all the odds, even in a country with an ongoing active conflict, in the more stable parts of the country, and under effective management, it is still possible to do business in South Sudan. They were able to continue operating, are still expending their business and won an international award, the Nestlé Creating Shared Value Prize for 2014, that in Nestlé’s words ‘reward initiatives that reflect the spirit of Creating Shared Value by addressing challenges in nutrition, water, or rural development. The winners reflect Nestlé’s belief that for a company to be successful in the long term and create economic and social value for its shareholders, it must also create value for society as a whole. This year, more than 757 applications from 93 countries were received. The overall winner was announced at Nestlé’s annual Creating Shared Value Forum on Thursday 9 October 2014’

The second indicator is more problematic though and has been challenged by the Fund Manager as inflexible, as once an ‘innovation scale value’ is assigned at the start of the project, this cannot be changed during the life of the project. Projects of this nature change their innovation and business approach as they develop. As acknowledged at page seven, none of the businesses supported are particularly innovative and most are based on tried and tested models from other countries. However in the context of South Sudan, all new businesses can be regarded as innovative in that they are all doing something new in a new country where such enterprises are new territory. In relation to the AECF innovation scale (see below), the businesses do not score highly at a global level, but are all innovative in the context of South Sudan. The AECF innovation scale is as follows:

0 Project not considered innovative;
1 Project is new for the company in the country of application;
2 Project is new for the company in Africa;
3 Project is new for the company and new for the country in which it will take place;
4 Project new for company globally, new for country and new for the sector;
5 Project is new for the company and sector in Africa;
6 Project is new globally (A world first)

The initial ratings for the selected projects were

Company	Concept title	Average level on the innovation scale during marking
Honey Care Africa, Ltd.	SWARM Honey Cluster Expansion	4
Century Seed Company Ltd.	Modernisation of Agriculture in the South Sudan Green Belt Area by development and importation of high yield seeds and introduction of modern farming methods like modern agricultural. inputs, fertilizers and pesticides.	3.3
Dryland Seed Ltd	Seeding South Sudan	3
South Farmers Company Limited	Crop Production, Value Addition & Integrated Poultry Venture	3.7
Frontier Microfinance Ltd	Provision of microcredit to micro-enterprenuers in the Agriculture value chain	3.3
Garden of Eden Company Limited	Maize Production, value added services and Market Access for small holder producers in Central Equatoria State	2.7

The ratings system was not set up to be amended through the life of the project and a rating given at the outset may not reflect how the project/business develops over time. This report holds that the scale is too rigid and ideally it should be possible to adjust ratings as the business develops. For example for Honey Care Africa when the original rating was set, the SWARM[16] system was yet to become an established practice, so it was new at that time. However, since the SWARM system has been launched in Kenya on a wider scale. Honey Care has moved away from it in South Sudan and is now only looking at 'traditional' sourcing of honey. Technically then, the innovation rating should fall to a 1.
[16] SWARM is the name for a full service honey production method. Honey Care's SWARM model is innovative in its full service approach. Beekeeping as an amateur, "traditional" activity has existed for thousands of years; managed beekeeping in Africa is new. This allows smallholder farmers to generate significant returns, even if they are personally afraid of bees. One dedicated, expert beehive technician, working with professional methods and modern equipment, can produce more than twice the honey than 100 amateurs working across many small farms. With the SWARM team Hive Technicians effectively guaranteeing commercial quality and yields, Honey Care and its partners can confidently invest in the remaining downstream links of the value chain to ensure a competitive position in the global honey market. The SWARM model is the culmination of more than 10 years of refinement of a beekeeping model capable of scaling to hundreds of thousands of households throughout rural Sub-Saharan Africa, and achieving recognition for rural Africa as a global honey producer.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendations in the previous AR:
The last Annual Review recommended that future Annual reviews assess the use of the £158k budget that has been ring-fenced to disseminate case studies, best practice to communicate on the AECF impact. However given slow progress in implementation this is still a task for the future – but an important one for consideration over the coming year.

There are ongoing discussions over whose role the dissemination of case studies is, whether it falls to the FM (KPMG), or the EM (AGRA). Possibly, it may come out of KPMG’snew Monitoring and & Evaluation function. This is as yet still unresolved.

Recommendations

KPMG and AGRA to resolve the question on the use of the ring-fenced budget for dissemination of best practice. This is still action pending from the recommendations of the last Annual Review.

The AECF innovation ratings system to be reviewed to allow for amendments during the lifetime of the project rather than as a fixed one-off rating.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The key cost drivers identified by the business partners and the Fund manager were:

Competition with NGOs to recruit and retain professional private sector staff. In the ongoing humanitarian emergency in South Sudan there has been further demand for the activities of humanitarian NGOs. International NGOs offer rates of pay for local staff that are in excess of what the local private sector is able to offer. It has therefore become difficult for the private sector to recruit or retain qualified and skilled staff against this competition.

Security concerns have limited travel options for monitoring and this has impacted in a negative way as planned travel to some programme areas has been impossible due to insecurity.

There have been recurrent fuel shortages driving up fuel prices. This is primarily related to inflation. The South Sudan Pound has been losing value but the Government of South Sudan still wants fuel suppliers to maintain their original price. Fuel suppliers have been finding it difficult to do business under this restriction and this has resulted in fuel shortages, which have a multiplier effect on the economy.

Foreign Exchange (FOREX) is in very short supply in the country and has resulted in businesses being restricted in paying for imported inputs into their business operations.

VfM performance compared to the original VfM proposition in the business case

DFID measures value for money based upon the principles known as the three ‘E’s of Economy, Efficiency and Effectiveness.

KPMG remains an effective Fund Manager. As pointed out in last year’s Annual Review, there remains a huge disconnect between the capacity of KPMG as Fund Manager and AGRA as Executive Manager. AGRA is going through some restructuring and the board of AECF is currently considering a new overall management structure that may merge the Executive and Fund management roles. No decision has yet been reached on this and substantial discussions and negotiations are still to be held.

There have been delays in receipt of reports from the Executive Manager which in itself could be seen as a criticism of the efficiency of overall programme management.

There have been serious concerns raised by both the EM and the FM regarding whether the South Sudan business environment was ready for the launch of the AECF SSW back in 2011. The weak performance of this window, exacerbated by the conflict, indicates that a more efficient approach may have been to wait longer, until the new country stabilized. The fact that this did not occur and the country has now lapsed into conflict, indicates that that the environment was certainly not conducive to attracting foreign business investment and it has proved difficult for indigenous businesses to operate.

Assessment of whether the programme continues to represent value for money

Given the level of investment to date ($1,801,206 disbursed) and the fact that in reality only one of the supported businesses (Honey Care Africa) is performing well, with two more businesses potentially viable, but in difficulty (South Farmers and Century Seeds) and two more (Garden of Eden and Frontier Microfinance) uncertain as to whether they can maintain business operations beyond the next year, it is hard to conclude that this programme continues to represent value for money.

However, given that over two years’ investment has been made in the 5 selected businesses; and that with more time, and if conflict remains restricted largely to the three Greater Upper Nile states, more than one of the businesses may become viable, the report holds that it would be poor value for money to close the programme at this stage. A no cost extension to enable businesses to have more time to make up for the impact of conflict is therefore seen as the best option to maximise value for money.

Quality of financial management

There have been significant delays in reporting from the Executive Manager to DFID, which has required repeated requests for reports. This should not be the case for an EM of the calibre of AGRA. The audited accounts for 2013 were only received in December 2014.

Some business partners too have struggled to compile satisfactory accounts and submit them on schedule. This is indicative of the low management capacity of some partners including their inability to recruit and retain qualified accounts staff. There is a very competitive environment in South Sudan for qualified professional finance and management staff, and with the ongoing humanitarian emergency there is a high demand for such staff from NGOs and the UN agencies. The private sector is presently unable to compete in terms of salaries and benefits with the NGOs so find difficulties in initial recruitment, and in subsequent retention.

Date of last narrative financial report	Up until September 2014
Date of last audited annual statement	31st December 2013

E: RISK

Overall risk rating: High

The last Annual Review agreed (with a degree of caution) a risk rating of Medium. In hindsight it is easy to see that this did not pre-empt the conflict which has pushed the risk rating to a High level. There are still parts of the country where the conflict has not impacted as adversely as in others, mostly in the Equatorias and the Greater Bahr el Ghazals. Here conflict risk is less, although the businesses have still suffered from the damage that the conflict has done to the national economy and the investment climate. Across all the prior agreed risk ratings the risk has increased to High and must be reset as such.

Overview of programme risk

Risk management by partners remains the same as described in the last Annual Review

There have been a few problems in terms of adequate financial management (e.g. South Farmers) but lack of an accounts function rather than any suspicion of fraud or misuse.

The risk ratings that remain low are:
- Loss of credibility by AECF deters applicants from business for new competition
- Fraud and misuse of funds by applicant

There is no evidence of loss of AECF reputation or of fraud or mismanagement by the applicant.

Climate and Environment risk remains the same as described in the last Annual Review

Outstanding actions from risk assessment

The Fund Manager is attempting to resume their planned monitoring schedule which was disrupted by the conflict. More regular monitoring is one way of reducing risk. There are still logistical difficulties in reaching more remote regions where the programme is being implemented. DFID also has had field monitoring visits curtailed by insecurity.

No further actions pending from the risk assessment.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

The present accountable grant with AGRA finishes on December 31st 2014. The country office and AGRA will be negotiating a no-cost extension period, subject to approval by DFID South Sudan Head of Office . However there is an inconsistency with Indicators and Milestones in the programme log-frame which are established through to 2016. A discussion is needed as to how longer term impacts and milestones will be monitored ex-post in an out-of-contract period. DFID has no specific funding to support this although it may be captured in an AECF portfolio wide evaluation which is being planned for 2015. For any new businesses in such a fragile political and business environment expecting business success and replicability within 30 months was always too optimistic.

The disbursement of funds, which has been noted in detail under Output 1, is far behind schedule and so far only 41% of the original planned disbursement has been made. 5 out of a planned 11 contracts were signed (and one withdrawn). The programme delivery therefore is significantly behind schedule.

Performance of partnership (s)

The partnership with the Fund Manager has performed well and they have provided a consistent and professional managerial role to the South Sudan window. The Executive Manager has been working under a constrained capacity situation with their own internal management difficulties. This has affected the relationship with fund manager and DFID as an AECF donor. These difficulties are still unresolved and likely to continue into 2015.

Business partners as described have been working under extremely difficult operating conditions, including lack of management capacity. While they have retained a positive relationship with the Fund Manager their own internal systems (with the exception of Honey Care) have been under great strain and this has sometimes impacted on their ability to report back to the FM on time.

Asset monitoring and control

This is undertaken by the FM through their monitoring processes and they do not report any particular problems or issues.

G: CONDITIONALITY

Update on partnership principles (if relevant)

All DFID programmes are required to follow the four partnership principles[17]. These are a set of principles which are used to guide programming and dialogue with the GRSS. A Government Partners’ Forum, chaired by The Minister of Cabinet Affairs, has recently been established which meets regularly to share information and discuss issues and concerns from both sides. The Government of the Republic of South Sudan has shown support for the partnership principles and the main development partners, including the UK, are continuing to work closely together to ensure these are implemented.
[17] The four Partnership Principles (PPs) are: I. A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs)2 The commitment of the partner government to addressing the enablers and constraints to poverty reduction and progress against the MDGs (and successor goals). II. A commitment to respecting human rights and other international obligations3 The commitment of the partner government to respecting human rights, and in particular the economic, social and cultural rights as well as civil and political rights of poor people. III. A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption4 The commitment of the partner government to strengthening the management of public finances and fighting corruption. IV. A commitment to strengthening domestic accountability5 The commitment of the partner government to enabling people to hold the government and public authorities to account for delivering on their commitments and responsibilities.

The partnership principles have been considered by this review. However, given that the project does not work through the Government of the Republic of South Sudan, the review has not carried out a detailed assessment in relation to future implementation.

H: MONITORING & EVALUATION

Evidence and evaluation

Evidence is collected by the FM through their monitoring and reporting process. This has included in the last year:
An Annual Report from KPMG, ‘Africa Enterprise Challenge Fund (AECF) South Sudan Window
Annual Report July 2013 to June 2014
- Post Conflict & South Sudan Window Portfolio Report Learning from the AECF portfolios in conflict affected states
- Thought Leadership Paper: "Risky Business - Promoting Private Sector Development in Post Conflict States"

There is no formal evaluation scheduled as yet, although with the programme now reaching the formal end to the contract (December 31st 2014) and a no-cost extension under consideration, the next Annual Review should be a Project Completion Report. A $3m contract with Ecorys has been signed by the AECF Committee for an evaluation of the whole of the AECF portfolio which will include South Sudan. As a result there will be no need for any additional evaluation work.

Monitoring progress throughout the review period

KPMG were prevented from entering the country due to Duty of Care issues – not resolved until May 2014. Meetings between DFID and KPMG were therefore not possible until then – in the intervening time (Dec to May) the DFID South Sudan Livelihoods Advisor spoke on the phone 3 times with KPMG for updates.

Once KPMG were able to visit Juba from May, they met DFID once. Field visits have been extremely restricted, and trips to Equatorias turned down completely due to them requiring two armoured vehicles to be out of commission (not allowed in the event that Juba needs them to evacuate staff).

The Fund Manager’s normal schedule is to visit in April/May and at the end of October. However the conflict has impacted on monitoring reducing access to more insecure locations. Richard Wangwe (FM) went to Yei in June. Accessing more distant locations is more difficult for KPMG as they cannot travel via United Nations Humanitarian Air Service flights nor, as a profit making organisation, travel using United Nations Mission in South Sudan flights. This means reaching locations such as Yambio has proved impossible.

Partners are required to report to KPMG in January and July. KPMG also conducts informal monitoring and conversations with partners on a regular basis. The CEO of Honey Care will be visiting KPMG in Nairobi soon.

This annual review was conducted by a DFID Livelihoods Adviser in the Growth and Resilience Department with significant experience of South Sudan and the region. It was conducted via a three-day desk-based documentation review - information, documents and data being provided to the reviewer by the DFID South Sudan office - and a five-day visit to Juba in November 2014 where interviews with stakeholders were conducted. Telephone interviews were held where stakeholders could not be met in person. Due to security restrictions, it was not possible to visit businesses located outside of Juba for this review. The views of the DFID-SS Food Security and Livelihoods Adviser and Deputy Programme Manager were also collected.

Representatives from the following organisations were interviewed:

- AECF Fund Manager - KPMG International Development Advisory Services, Africa, Nairobi Office.
- AECF Executive Manager – Alliance for a Green Revolution in Africa, Nairobi Office.
- Century Seeds, South Sudan.
- HoneyCare, South Sudan.
- International Finance Corporation (IFC) of the World Bank, South Sudan.
- South Farmers, South Sudan.
- South Sudan Business Forum
- SPARK South Sudan.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process