## Sheet1
PROJECT NAME: Nepal Public Financial Management Reform
IMPACT | Impact Indicator 1 |  | Baseline (2010/2011) |  |  |  | Target (2015)
An effective Public Financial Management system that facilitates the delivery of better public services to improve the lives of the people of Nepal | Increased Transparency and timely reporting on the Percentage utilisation of approved budget (PEFA Indicator 1). | Planned | 87.41% |  |  |  | 95%
Achieved
Source
Ministry of Finance, Treasury Single Account Reports
| Impact Indicator 2 |  | Baseline (2011/2012) |  |  |  | Target (2015)
| Percentage of budget execution reports and financial statements (meeting acceptable standards of quality, completeness and timeliness) prepared by FCGO using TSA system and published on the FCGO website. | Planned | 70% |  |  |  | 60%
Achieved
Source
Ministry of Finance, Treasury Single Account Reports
OUTCOME | Outcome Indicator 1 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015) | Assumptions
A more efficient public financial management (PFM) system with increased transparency and accountability to citizens. | Number of sectors where information on budget allocation and expenditure is made public 3 times a year. | Planned | none |  | 1 sector | 2 sectors | 3 sectors | 1. Government commitment to policy reforms is maintained despite changes in ruling coalition and a new Constitution. 2. Polarization among political parties does not cause programme delays. 3. Strong citizens’ demand for public goods and services puts pressure on government to deliver on reforms.
Achieved
Source
Data collected by social accountability grantees through pro-poor budget analyses.
| Outcome Indicator 2 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Percentage of budget execution reports and financial statements (meeting acceptable standards of quality, completeness and timeliness) prepared by FCGO using TSA system and published on the FCGO website. | Planned | none |  | 50% | 70% | 100%
Achieved
Source
FCGO Budget reports, FCGO website
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
`
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2010/11) | Milestone 1 (2012) |  |  | Target (2014) | Assumption
Treasury Single Account (TSA) implemented throughout Nepal. | Number of districts implementing Treasury Single Account (TSA). | Planned | 8 districts | 40 districts |  |  | 75 districts | 1. Government commitment to policy reforms is maintained despite changes in ruling coalition and a new Constitution. 2. Polarization among political parties does not cause programme delays. 3. TSA with Core Treasury System is implemented.
|  | Achieved |  |  |  |  | 75 districts
Source
Data from TSA system, FGCO
IMPACT WEIGHTING (%) | Output Indicator 1.2 |  | Baseline (2010/11) | Milestone 1 (2012) |  |  | Target (2014)
| Number of Spending Unit Bank Accounts operational. | Planned | 14000 | 8000 |  |  | 500
20% |  | Achieved
|  | Source | [5 empty] | RISK RATING
|  | Ministry of Finance Reports | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2010/2011) |  |  |  | Target (2015) | Assumptions
Financial reporting and accounting standards improved in Nepal. | Nepalese Financial Reporting Standards (NFRSs) drafted in line with International Financial Reporting Standards (IFRSs) and issued by Institute of Chartered Accountants of Nepal (ICAN). | Planned | No NFRS |  |  |  | NFRS drafted in line with IFRSs and issued by ICAN | 1. Government commitment to policy reforms is maintained despite changes in ruling coalition and a new Constitution. 2. Polarization among political parties does not cause programme delays. 3. ICAN has enough capacity to drive this project.
Achieved
Source
NFRS Report
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Number of pilot ministries with consolidated financial statements preapred in accordance with Part 1, Cash IPSAS | Planned | No ministries with IPSAS |  | Nepal Public Sector Accounting Standards (NPSAS) prepared | NPSAS piloted in 1 ministry | NSPAS piloted in 2 ministries
10% |  | Achieved
|  | Source | [5 empty] | RISK RATING
|  | Pilot ministries's financial statements | [5 empty] | High
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
100%
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015) | Assumptions
Increased capacity and knowledge of keystakeholdes in Nepal on public financial management. | Number of districts where awaireness raising programmes for GoN financial management staff on PFM reforms are carried out. | Planned | None | 10 | 20 | 35 | 56 | 1. Respective researchers have access to relevant information and data; 2. GoN stakeholders show ownership of reports and findings; 3. Capacity and political will of GoN to revise PFM reform plan.
Achieved
Source
Programme agenda, Attendance records
| Output Indicator 3.2 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Number of analytical pieces of work on PFM in Nepal completed and dissiminated. | Planned | 0 | Education Public Expenditure Tracking Survey (PETS) | Operational Risk Assessment (ORA) of PFM in Nepal completed and published | Repeated PEFA Assessment completed and published | Based on findings of all studies, national PFM reform strategy revised
|  | Achieved |  | draft education PETS | final education PETS published, final ORA published
Source
Published documents and dissemination events.
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
25% | Capacity development plan for key PFM stakeholders in Government of Nepal developed. | Planned | No plan |  |  | PFM training needs assessment of key GoN stakeholders undertaken | Capacity development plan for key PFM stakeholders in Government of Nepal developed.
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Training needs assessment and capacity development plan. | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015) | Assumptions
Quality of public sector audits enhanced. | Percentage of financial statement audits substantially within ISSAI framework. | Planned |  |  |  |  | 28 | 1. Capacity of OAG sufficient to undertake these audits; 2. Access for OAG to necessary information and data to perform these audits.
Achieved
Source
Quality assurance team records
IMPACT WEIGHTING (%) | Output Indicator 4.2 |  | Baseline (2010/2011) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Frequency of in-depth performance audit reports. | Planned | 1 per year |  | 2 per year | 2 per year | 3 per year
15% |  | Achieved
|  | Source | [5 empty] | RISK RATING
|  | OAG Nepal Website | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
| 625000 | [5 empty] | 100%
INPUTS (HR) | DFID (FTEs) |  | 20% of (7.5% Administrator and 7.5% Advisor) FTE
OUTPUT 5 | Output Indicator 5.1 |  | Baseline (2010/11) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015) | Assumptions
Improved citizen engagement in PFM reform. | Number of independent budget analyses at national-level conducted and shared by Social Accountability (SA) grantees. | Planned | 0 |  | 2 | 3 | 0 [PRAN 2 has changed this indicator] | 1. Availability of SA practitioners and international trainers for extended time periods; 2. Willingness of practioners to work together; 3. GON provision of access to budget process. 4. Availability of capable training institutions; ability of trainees to invest extended period of time in trainings; 5. Access to VDC based information on entitlements.
Achieved
Source
Pro Public Report
| Output Indicator 5.2 |  | Baseline (2010/11) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Number of districts where Social Accountability media programmes targeting entitlements, budget awareness raising and main PFM issues are piloted. | Planned | 0 |  | 2 | 10 | 15
Achieved
Source
Media concept notes and programme scripts, Focus Group surveys
| Output Indicator 5.3 |  | Baseline (2010/11) | Milestone 1 (2012) | Milestone 2 (2013) | Milestone 3 (2014) | Target (2015)
| Number of VDCs where procurement monitoring, expenditure tracking and budget awareness raising is undertaken. | Planned | 0 | `` |  | 80 | 300 VDCs
Achieved
Source
Local-level Grantee reports
IMPACT WEIGHTING (%) | Output Indicator 5.4 |  | Baseline (2010/11) | Milestone 1 (2012) | Milestone 2 (2013) | Baseline (2014) | Target 2015
| Percentage increase of entitlements being disbursed to the correct beneficiaries, on time and of the correct amount in at least 75% of the 90 targeted VDCs. | Planned | N/A | N/A | N/A | 64.4% | 74.1%
30% |  | Achieved
|  | Source | [5 empty] | RISK RATING
|  | Perception Surveys by New Era | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) |  |  | DFID SHARE (%)
| 3.6 Millon |  |  | 3.3 |  |  | 52.17%
INPUTS (HR) | DFID (FTEs)
0.2 PFM Adviser, 0.2 PFM PM
Note on A3: Robert Bou Jaoude: I am not sure if the work will impact the delivery but will improve the financial reporting on public services and other budget allocations
Note on B72: Robert Bou Jaoude: This has been validated with Mr. Baburam PEFA Secretariat