Annual Review - Summary Sheet

Title: Public Financial Management Reform Programme
Programme Value: £3,600,000		Review Date: December 2014
Programme Code: 114491	Start Date: 23/01/2010	End Date: 31/01/2016

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	B	A	A
Risk Rating	High	High	Medium

The UK is supporting the Government of Nepal’s (GoN) efforts to reform its central-level Public Financial Management (PFM) systems and processes. The UK is providing £3.5m through a World Bank (WB) Multi-Donor Trust Fund (MDTF). This is a highly technical programme which involves detailed and very specialised work in terms of: public accountancy; banking and other fund handling systems; and human resource training and management incentives for Government staff. Reforming PFM systems means that UK funds, provided through the Government, are protected from misuse. However it also means that Nepali taxpayers’ money is protected and better directed to those most in need of support. Over time, this will help lessen Nepal’s reliance on donor funding and international aid.

The project consists of two components:

## Component A is strengthening the Government of Nepal’s own PFM systems. Under Component A, the following areas of support were originally agreed.

Treasury Single Account (TSA) implementation – the Government was previously operating through around 14,000 separate bank accounts. This was inefficient and increased the risk of funds not being monitored. With the rollout of the TSA, these accounts have now been rationalised down to less than one thousand. This will enable better control of finances, better tracking of public expenditure, and a reduction in idle funds by, bringing all government bank accounts under the control of the Treasury.
Nepal Public Sector Accounting Standards (NPSAS) and International Financial Reporting Standards (IFRS) implementation – this will bring the Government of Nepal in line with international accounting standards.
Capacity building and institutional strengthening of the Public Expenditure and Financial Accountability (PEFA) Secretariat in the Ministry of Finance (MoF) and deepening knowledge related to PEFA – this will also ensure that Government officials are following international best practice on PFM.

## Since DFID committed funding, new areas of support have been added to Component A. These are as follows.
Strengthening the Office of the Auditor General (OAG) and the Public Accounts Committee (PAC) of the Constitutional Assembly (CA) – this will mean that Nepal’s parliament and its supreme audit institution can provide better oversight and scrutiny of Government finances.
Strengthening the Government’s budget process so that it is better able to demonstrate actual end results rather than just money expended.

Activities under Component A are also referred to as “supply” side activities because they deal with the Government itself, which essentially supplies funds and services.
## Component B is developing the capacities of Nepali civil society organisations to use social accountability approaches to hold the Government to account and demand better use and management of public finances. This component is currently being delivered via the Programme for Accountability in Nepal (PRAN) in 10 districts. However, the funding for this component was reduced by 50% due to limited overall funding and initial delays in the start of this component. However, a new concept note has just been approved. Activities under Component B are also referred to as “demand” side activities because they deal with the civil society and communities which demand funds and services.

An example of demand side activity :

The programme impact will be an effective PFM system that facilitates the delivery of better public services to improve the lives of people of Nepal. The outcome is “a more efficient PFM system with increased transparency and accountability to citizens”.
The following are the programme results that were agreed originally:

Implementation of Treasury Single Account in all districts to ensure a consolidated and rationalised basis for financial management.

Implementation of international standards of public accounting in the Government of Nepal.

A stronger PEFA Secretariat which can effectively implement and monitor the Government of Nepal’s Public Financial Management Reform Programme.

Civil society, non-governmental and community groups able to:

- Participate and contribute in budgeting processes to make resource allocation more accessible and equitable.
- Track expenditure to its intended beneficiaries and hold public officials accountable for mismanagement and corruption.
- Monitor the performance of local service delivery, including access for marginalised groups, including women and girls.
- Monitoring public procurement to reduce scope for corruption.

Summary of progress and lessons learnt since last review

Overall, after initial slow progress this is now a well performing programme. Government staff, especially in the PEFA Secretariat, have taken strong ownership of the programme and this is evident in the results being achieved. For example, the Treasury Single Account (TSA) process has been rolled out by the Government one year ahead of schedule. Donor support should continue because of this increased ownership and external support including reviews can also help to maintain the pace of crucial PFM reforms.

The last review recommended that the demand side component, Programme for Accountability in Nepal (PRAN) coordinate with the Local Governance and Community Development Programme Phase 2 (LGCDP2), a national local governance programme managed by the Ministry of Federal Affairs and Local Development (MOFALD) and also supported by DFID Nepal. This has happened and we see that this will add value to the national programme as PRAN can influence LGCDP2 to use the lessons learned and to influence the service delivery by local bodies.

The original end date of this programme has been extended to 2016 following the recommendation of last year’s annual review so that it is consistent with the World Bank. The EU delegation and the Embassy of Switzerland have recently joined the PFM MDTF with additional funding. Accordingly the World Bank has requested all donors to consider an extension of the MDTF until January 2018 and they are proposing new activities (such as strengthening the Public Procurement Monitoring Office or further sophistication of the TSA system).

DFID has extended support to the MDTF until January 2016 and will consider options for further extension nearer to that date. With the results of the second Public Expenditure and Financial Accountability (PEFA) assessment, finalised in December 2014, the Government is expected to revise its PFM reform plan. DFID will consider supporting this second generation reform plan through a new Business Case which will be designed in the coming months. Further support to the World Bank MDTF will be considered as an option.

The last Annual Review of this programme was an in-depth assessment by two external DFID staff – a Governance and a PFM expert from DFID headquarters. This review was implemented by DFID Nepal but with a member from a separate DFID Nepal team (the Economic Development Team), to ensure independence. The review team met the stakeholders for this programme such as, officials from the government’s Public Expenditure and Financial Accountability Secretariat, Office of the Auditor General and World Bank Officials.

Summary of key recommendations for the next year

List of all recommendations of the Annual Review

Outcome level recommendations

The Bank has committed to station a full time Programme Manager in Kathmandu from early 2015. It is recommended that this happens as planned and that the person is not tasked with other priorities compromising the amount of time that is devoted to this project.

The Programme Coordination Committee (PCC) meeting recommended that a technical committee is to be constituted by the first quarter of 2015. It is recommended that the stakeholders agree on the terms of reference (TOR) and meetings are held regularly. This should be a forum to hold technical discussions before proposals are submitted to PCC.

PRAN is recommended to continue to work closely with LGCDP2 and the newly formed Governance Facility (a joint donor fund to support civil society) to complement wider social mobilisation and accountability programming and avoid duplication of efforts.

The Public Accounts Committee has recently been formed by the parliament. It is important that the members of parliament are briefed properly about the audit reports submitted by Office of the Auditor General (OAG). Capacity building of the members of parliament as well as the secretariat is recommended.

OAG has consulted the civil society organisations (CSO) during the pre-audit phase to decide on which area to focus on. OAG has collaborated with the civil society after the annual audits are made public. The CSOs use their accountability skills to hold the government officials to account using the audit report. It is recommended that this good practice should continue.

GoN will prepare the second phase of PFM reform strategy following the PEFA assessment. MDTF results framework may need to be tweaked to align it with the government strategy.

Output 1 Recommendations

Staff turnover and rotation remains a big challenge and GoN is therefore recommended to ensure longer tenure of key staff, especially of the PEFA Secretariat coordinator.

The Ministry of Finance and FCGO are recommended to develop a retention strategy for their key IT staff as well as to prepare a needs assessment and to prepare a strategy in ensuring the development of sufficient in-house capacity in this area.

FCGO and PEFA Secretariat, with support from the WB, are recommended to prepare a strategy on making payments directly by bank transfers instead of handing over cheques to the spending units, taking into account challenges of remote locations.

Output 2 Recommendations

The Institute of Chartered Accountants of Nepal, the Accounting Standards Board and the regulatory bodies of the Government are recommended to work together so that there are no slippages in the calendar of operations.

FCGO is recommended to start orienting the respective ministries to ensure that there are no capacity gaps, if the rollout of NPSAS is decided to be carried out in all ministries by next year.

Output 3 Recommendations

It is recommended to finalise a comprehensive capacity development plan as soon as possible following a consultative process encompassing the relevant stakeholders related to public financial management.

It is recommended to continue the orientation on Government financial management and to cover all entities. Advanced training should be given to the participants of the orientation to refresh them on this subject and to give the impression that this is not a one off event.

As recommended by the previous review, the PEFA Secretariat should work across Government. The Secretariat should use the Technical Assistance provided by DFID/Crown Agents to revive the PEFA Implementation Units at the sector ministries.

Output 4 Recommendations

It is recommended that the MDTF extends this area of support to the Office of the Auditor General and Public Accounts Committee from June 2015 to December 2015 to finalise the activities of this phase and extend the technical assistance team’s contract for this period accordingly.

Output 5 Recommendations

PRAN is recommended to work much more closely to strengthen existing Government structures (particularly MoFALD, LGCDP, OAG and the PEFA Secretariat) through which social accountability tools will be operationalised.

PRAN is recommended to continue working closely with the DFID/Danida/Switzerland supported Governance Facility programme to avoid duplication and to complement the programmes and coordinate with other donors and working in this area.

A. Introduction and Context (1 page)
Context / Nepal’s lengthy post-conflict transition remains unresolved nearly a decade after the signing of the Comprehensive Peace Accord in 2006 and the establishment of the first Constituent Assembly in 2008. A new Constituent Assembly, elected in late 2013, has not yet managed to establish a new constitution and this has major implications on the functioning of the governance system at all levels. / This ongoing political crisis has also affected the abilities and capabilities of the public sector, including in areas like Public Financial Management. Various and repeated PFM assessments at national, sector and local level all point to weak PFM systems and high fiduciary risk, including: poor oversight and scrutiny, sub-optimal budget processes, problematic implementation of capital spending, gaps in financial reporting, inadequate staffing and capacity. Fiduciary risks and PFM deficiencies tend to be even more evident at the local and sector levels. It is widely recognised that weak PFM systems contribute to poor governance, and provide opportunities for corruption. This undermines poverty reduction. However, the Government of Nepal has also shown strong initiative and good progress in some areas of PFM reform, including the rollout of the Treasury Single Account to all 75 districts in Nepal. These efforts have also been underpinned by generally sound fiscal management and a professional civil service. / As PFM weaknesses are also evident at local and sector level due to weak capacities and oversight, another DFID Nepal programme – Improved Public Financial Management and Accountability – specifically focusses on support to PFM reform at the local and sector level in Nepal. This enables a comprehensive and complementary approach to support to PFM reform in Nepal. The investment in PFM reform plays a crucial role in improving GoN’s service delivery and reducing fiduciary risks for public funds, DFID’s and other donors’ development funds.

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3860084.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3717433.docx

B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The expected outcome is ‘A more efficient public financial management (PFM) system with increased transparency and accountability to citizens’.

Indicator(s)	Milestones	Progress
Number of sectors where information on budget allocation and expenditure is made public 3 times a year	2 sectors	Expenditure and authorisations are published in all line agency notice boards
Percentage of budget execution reports and financial statements (meeting acceptable standards of quality, completeness and timeliness) prepared by FCGO using TSA system and published on the FCGO website.	70%	100%

Government offices are publishing all expenses and all authorisations of all line agencies on their notice boards throughout Nepal. Furthermore, all government offices in the Kathmandu valley are publishing information about all proposed payments in their respective websites before the payment is made. This has helped in the area of transparency and now the general public can view and make comments before payments are completed.

For the second indicator, the Financial Comptroller General’s Office (FCGO) is publishing budget execution reports for 100% of revenues and expenditures in their website (http://www.fcgo.gov.np/report-publications/). The budget execution report is published on a daily basis and states the actual budgets for revenues and expenditure.

Overall output score and description

Overall progress against the project has been met and it is therefore scored as A. There is good ownership by the government on this project and FCGO has pushed reforms on its own initiative. Expert advice and periodic missions from the World Bank have helped the project to sustain momentum. There is good donor coordination in this sector and the Multi Donor Trust Fund itself is a good mechanism for donor funds to be coordinated and aligned with the PFM reform plan produced by the government.

The Treasury Single Account (TSA) has been an exemplary initiative that contributes to improved public financial management, reduced fiduciary risk and to real savings for GoN as money is not left idle in bank accounts.

The Nepal Public Sector Accounting Standards (NPSAS) have been piloted in 2 ministries and have been certified by International Consortium on Governmental Financial Management (ICGFM). The government is planning to implement this in all other ministries ahead of the original project schedule.

PFM reforms are a slow process and capacity building needs to be done continuously because of frequent staff movement. A capacity building plan is being prepared, which is crucial to sustain the results achieved in this area. The current efforts by the PEFA Secretariat and FCGO in this area need to be continued so that momentum is not lost.

The support to the Office of the Auditor General (OAG) is progressing well. OAG has undertaken in-depth performance audits and is moving to risk based audits. They have also conducted financial audits in accordance with the latest international standards.

The demand side of this project is the support to civil society and is managed by Programme for Accountability in Nepal (PRAN). This component builds capacity of civil society so that they can hold the government to account. Progress in this component is good and the donors have requested the World Bank to extend this component.

Key lessons

This project has proven that PFM reform is possible, even in an unstable political environment, when an appropriate technical approach is taken. For this to happen, reform also needs to be owned and championed by key people in the government and it is important that key people are not transferred.

Capacity development is very important and a strategy needs to be developed to address different ways of working following the adoption of IT-based reforms. Capacity development should be done continuously due to staff rotation.

TSA systems are IT based. Retention of IT staff is a big challenge as staff trained in Oracle systems are much in demand in the private sector which usually offers higher benefits. Government policy to address this is important. Other factors are also very crucial for smooth operations, including: timely renewal of licences; service contracts to maintain computer servers; and ensuring that the latest anti-hacking, anti-virus software is installed.

Key actions at the outcome level

Publishing all expenses and authorisations on notice boards is a good initiative. Publishing information from key sectors that have direct contact with the general public in websites will further increase transparency. Publishing information about all proposed payments in their respective websites before the payment is made will be better if this can be extended to all districts.

The Financial Comptroller General’s Office is publishing budget execution reports for revenues and expenditures on their website. This is a welcome step. The PRAN side component needs to build on this and educate civil society so that they can use this information and help promote accountability.

Outcome level recommendations

Based on the demand from donor partners, including DFID, the World Bank has committed to station a full time Programme Manager in Kathmandu. However, as it took a substantial time for the World Bank to assign a full time Programme Manager initially who was in the end never stationed in Kathmandu due to the restructuring ongoing within the World Bank and moved on after only about half a year in post, DFID sees this as a risk. At the Programme Coordination Committee (PCC) meeting held on 12 Sep 2014, the World Bank committed to assign a new fulltime Programme Manager in Kathmandu at the beginning of 2015. It is recommended that this happens during the first quarter of 2015 and that the person is not tasked with other priorities compromising the amount of time that is devoted to this project.

The PCC meeting recommended that a technical committee is to be constituted by the first quarter of 2015. It is recommended that the stakeholders agree on the Terms of Reference (TOR) and meetings are held regularly. This should be a forum to hold technical discussions before proposals are submitted to PCC.

PRAN is recommended to continue to work closely with LGCDP2 and the newly formed Governance Facility (a joint donor fund to support civil society) to complement wider social mobilisation and accountability programming and avoid duplication of effort.

The Public Accounts Committee has been formed by the parliament. It is important that the members of parliament are briefed properly about the audit reports submitted by Office of the Auditor General (OAG). Capacity building of the members of parliament as well as the secretariat is recommended.

OAG has consulted the civil society organisations (CSO) during the pre-audit phase to decide on which area to focus on. OAG has collaborated with the civil society after the annual audits are made public. The CSOs use their accountability skills to hold the government officials to account using the audit report. It is recommended that this best practice his should continue.

GoN will prepare the second phase of PFM reform strategy following the PEFA assessment. MDTF results framework may need to be tweaked to align it with the government strategy.

Has the logframe been updated since the last review?
Yes. The logframe was updated in line with the recommendations of last year’s annual review. This log frame is aligned with the World Bank’s results framework. More activities have been added to the multi donor trust fund after new donors joined the trust fund. The current log-frame incorporates such outputs.

C: DETAILED OUTPUT SCORING

Output Title	Treasury Single Account (TSA) implemented throughout Nepal
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Number of districts implementing Treasury Single Account (TSA)	75	This milestone was achieved last year (one year early)
Number of Spending Unit Bank Accounts operational.	500	This milestone was achieved last year (one year early)

Key Points

The indicators for this output were achieved last year, one year ahead of schedule, and the output is therefore scored A+ (Output moderately exceeded expectation). This has been a great success and the Government has demonstrated strong ownership in driving the progress. As the target was accomplished a year ahead of the scheduled period, the rollout of the TSA is already producing substantial savings for the government through better management of idle cash balances. The roll-out has also enabled the government to centralize the payment function at District Treasury Controller Offices (DTCOs) and strengthen the TSA system by closing down about 14,000 bank accounts – not an easy feat considering the time and challenges that similar reforms have posed elsewhere in the world. This has saved GoN approximately US$2 million from commissions/operating costs due to closure of accounts.

Through this project, a daily budgetary status is now available that depicts aggregate revenue, expenditures, and budgetary surplus/deficit with only a one-day lag. In addition monthly reports are now available with ministry-wide economic classification of the expenditures, ministry-wide budget & expenditures incurred, and balance available and district-wide budget expenditures. These reports are available at www.fcgo.gov.np/report-publications.

A needs assessment for upgrading the financial management information system (FMIS) of the core treasury system is proceeding satisfactorily. The World Bank shared international experience with the government in developing a blueprint for implementing commitment accounting in the existing TSA system. FMIS software modifications for implementing the recommended blueprint were developed in-house. These will be now piloted in the next fiscal year (FY15/16).

The World Bank has engaged the Financial Comptroller General Office (FCGO) together with Nepal Rastra Bank (NRB) and other stakeholders. A workshop early in 2014 was held with these stakeholders to brainstorm enhanced business processes in the area of cash management, remittances, bank reconciliations, and overall revenue management. As a result, a task force comprising officials from NRB, FCGO, and 5 commercial banks was formed, and a draft recommendation was presented to the stakeholders. This recommendation is now being finalised for field testing and piloting within FY14-15. Furthermore, the Oracle software license has also been procured in a transparent manner, and a contract has been awarded.

Summary of responses to issues raised in previous annual reviews (where relevant)

The last review recommended that staff incentives should continue and this is the case. The issue of staff turnover remains an area of concern. For example, the PEFA Secretariat had 3 different coordinators over the last 12 months, making continuity and strong strategic leadership of PFM reform very challenging. Another area of concern is the retention of key IT staff – currently externally contracted – and with it crucial knowledge of the TSA system.

The current practice of DTCO handing over cheques to the spending units instead of payments being made directly through bank transfers is not ideal. As acknowledged by the previous annual review, a specific plan on how this could be solved, including for recipients in remote areas, remains a challenge. DFID Nepal’s Access to Finance Programme is trying to address this problem by encouraging banks to open branches in remote areas where it is currently not economically feasible.

Another recommendation of the previous annual review, stated that the Office of the Auditor General should get direct access to TSA transaction level data. This has now been granted.

Recommendations

Staff turnover and rotation remains a big challenge and GoN is therefore recommended to ensure longer tenure of key staff, especially of the PEFA Secretariat coordinator.

The Ministry of Finance and FCGO are recommended to develop a retention strategy for their key IT staff as well as to prepare a needs assessment and to prepare a strategy in ensuring the development of sufficient in-house capacity in this area.

FCGO and PEFA Secretariat, with support from the WB, are recommended to prepare a strategy on making payments directly by bank transfers instead of handing over cheques to the spending units, taking into account challenges of remote locations.

Output Title	Financial reporting and accounting standards improved in Nepal.
Output number per LF		2	Output Score	A+
Risk:		High	Impact weighting (%):	10%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Nepalese Financial Reporting Standards (NFRSs) drafted in line with International Financial Reporting Standards (IFRSs) and issued by Institute of Chartered Accountants of Nepal (ICAN).	NFRS drafted in line with IFRSs and issued by ICAN	This milestone was achieved last year. / Calendar of operations issued by ICAN
Number of pilot ministries with consolidated financial statements preapred in accordance with Part 1, Cash IPSAS	NPSAS piloted in 1 ministry	Pilot completed in 2 ministries and Certified by ICGFM.

Key Points

The indicators of this output have moderately exceeded expectations and therefore the output is scored A+. The drafting of the Nepal Financial Reporting Standards (NFRS), modelled on International Financial Reporting Standards (IFRS), by the Accounting Standards Board (ASB) was already achieved last year already after an extensive consultation process. The Institute of Chartered Accountants of Nepal (ICAN) has issued standards with a road map for implementation.

Pilots for rolling out the Nepal Public Sector Accounting Standards (NPSASs) in two ministries have been completed and financial statements in accordance with cash-based International Public Sector Accounting Standard (IPSAS), Part I, have been prepared. This is one more pilot Ministry than originally planned and it therefore represents good progress. Final reporting has been issued by mid-July 2014 and it has been certified by the International Consortium on Governmental Financial Management (ICGFM).

Summary of responses to issues raised in previous annual reviews (where relevant)

The last review suggested that NPSAS should not be rolled out in entirety but rather incrementally to allow capacity to catch up before moving on from a position of relative strength. However, FCGO has plans to incorporate the lessons learned from the pilot and plan to roll this out to all ministries from next fiscal year.

Recommendations

The Institute of Chartered Accountants of Nepal, the Accounting Standards Board and the regulatory bodies of the Government are recommended to work together so that there are no slippages in the calendar of operations.

FCGO is recommended to start orienting the respective ministries to ensure that there are no capacity gaps, if the rollout of NPSAS is decided to be carried out in all ministries by next year.

Output Title	Increased capacity and knowledge of key stakeholders in Nepal on public financial management.
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Number of districts where awareness raising programmes for GoN financial management staff on PFM reforms are carried out.	35	39
Number of analytical pieces of work on PFM in Nepal completed and disseminated	Repeated PEFA Assessment completed and published	PEFA assessment completed and circulated to DPs.
Capacity development plan for key PFM stakeholders in Government of Nepal developed.	Capacity development plan for key PFM stakeholders in Government of Nepal developed.	PFM training needs assessment of key GoN stakeholders undertaken in order to prepare the plan.

Key Points

Overall progress against this output has been met and it is therefore scored as A. Capacity-building activities of the PEFA Secretariat continue to make good progress in reaching out to various stakeholders across the country and to more remote districts, demand-side stakeholders, line departments, and the general public on increasing PFM awareness and building a solid foundation for ensuing PFM reform processes.

The PEFA Secretariat and FCGO have conducted orientation programmes on financial management to the heads of office, accounts and planning staff in 39 districts. The second PEFA assessment itself turned out to be a huge awareness raising exercise as it was carried out by a mix of new civil servants and those experienced in the first PEFA assessment. The PEFA Secretariat conducted various rounds of orientation and training programmes based on the PEFA ‘field-guide’ for undertaking assessments using the PEFA performance measurement framework (published by the PEFA Secretariat in Washington). Furthermore, the PEFA Secretariat (Nepal) carried out training sessions that benefit other donor funded projects as well. For example, a session on how to prepare project accounts and Financial Monitoring Reports (FMRs) and Implementation Progress Reports (IPRs) was conducted.

The GoN, led by the PEFA Secretariat, invested a lot of time to commission, quality assure and to lead the PEFA assessment. A final draft report has been shared with Development Partners for their comments and is expected to be reviewed and subsequently approved by the PEFA Secretariat in Washington by early next year.

Training needs assessment of key GoN stakeholders has been carried out by the PEFA Secretariat/FCGO in order to prepare the full plan. PEFA secretariat conducted consultations with the stakeholders in order to prepare the capacity building plan to get ownership on PFM issues. The consultations have been successful to sensitise stakeholders that PFM is not only the remit of accountants and requires support from wider stakeholders. This is effort to garner support from stakeholders needs to be appreciated as the easy part is to write the plan.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous annual review recommended the PEFA Secretariat to take greater leadership to work across government. The PEFA Secretariat has demonstrated this leadership while undertaking the PEFA assessment and is currently collaborating with the Ministry of Federal Affairs and Local Development to undertake a local level PEFA assessment.

The previous annual review recommended to develop the capacity of accounting professionals. The PEFA Secretariat has tried to respond by carrying out training on project accounts and on procurement to Government accounting professionals.

The previous annual review also recommended better linking of national, sectoral and local PFM programmes. The PEFA secretariat has recently increased its capacity with the help of another DFID Nepal programme (Public Financial Management and Accountability Programme) to recruit a full time local consultant who will work to strengthen the national and sector linkages.

Recommendations

A comprehensive capacity development plan needs to be finalised as soon as possible following a consultative process encompassing the relevant stakeholders related to public financial management.

The orientation on Government financial management should continue and all entities should be covered. Advanced training should be given to the participants of the orientation to refresh them on this subject and to give the impression that this is not a one off event.

As recommended by the previous review, the PEFA Secretariat should continue to work across Government. The Secretariat should use the Technical Assistance provided by DFID/Crown Agents to revive the PEFA Implementation Units at the sector ministries.

Output Title	Quality of public sector audits enhanced
Output number per LF		4	Output Score	A+
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		Yes	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Financial audits of spending units completed in accordance with ISSAI framework	11	11
Frequency of In-depth performance audit reports submitted to Parliament in year	2 per year	3 performance audits submitted

Key Points

Overall the progress against this output has moderately exceeded expectations and is therefore scored A+. Audit planning for financial years 2012-13 and 2013-14 has been attempted by the Office of the Auditor General (OAG) using the International Standards of Supreme Audit Institutions (ISSAI) framework of risk analysis. All auditable entities have been categorized based on the risk as high (A), medium (B) and low (C) risk categories. There is an issue whether the Auditor General should be auditing all the spending units of the country or a risk based selection of the spending units.

Three in-depth performance audits were completed in the last year: Kathmandu Valley Road Improvement Project, Health Service Delivery and Social Security Allowances. These applied the revised performance audit guide procedures, and therefore already met the end-of-project target for the number of in-depth performance audit reports to be submitted to parliament in a year.

A workshop was conducted in July, 2014 to review the experiences of the above pilot performance audits and feed into the second year pilots. The second year performance audits (3 in number which will take the cumulative total to 6 by the project end) have already commenced and are likely to be completed by March 31, 2015. The post audit workshop will be completed by April 30, 2014. In addition to increasing the number of in-depth performance audits conducted, OAG Nepal has made impressive gains in encouraging public participation in the audit process. This initiative began primarily because of the lack of a sitting parliament and functioning Public Accounts Committee and should be continued.

There has been considerable progress with respect to risk based annual audit planning, financial audits, financial audit manual, performance audits, training related to performance audit and the design of the Electronic Working Papers (EWP) – Nepal Audit Management System (NAMS). A peer review report by the Supreme Audit Institution of India, based on the newly developed Performance Management Framework for Supreme Audit Institutions, has been submitted and OAG have commented on the report. The peer review report is expected to be finalised shortly.

50 auditors visited the Supreme Audit Institution of Malaysia in June and August 2014, in order to take customised training in financial audit standards and procedures and in the use of electronic audit working paper software. The consultants from the MDTF together with selected pilot auditors designed a one week training course on the new standard audit working papers to be delivered to approximately 300 audit officers and audit directors. Electronic audit working paper software has been procured and is going to be piloted in 15 audit teams.

As mentioned above (output 1), the OAG has now also been provided access to the transactions-level data in TSA system which greatly facilitates the OAG’s work.

The Auditor General submitted a high quality annual audit report for FY 12/13 to the President in April 2014. This will, for the first time in over two years, be scrutinised by the newly constituted Public Accounts Committee (PAC). The area which is particularly lagging behind is the component relating to the Public Accounts Committee primarily because the Legislature-Parliament was elected after a long gap in Nov 2013.

- Key Results during the past year under this output include: Auditor General submitted the 51st annual report of FY13, in April 2014.
- Move to risk-based auditing approach.
- Project consultants under the MDTF positively reviewed the OAG Quality Assurance Handbook and delivered workshops to senior management and to audit staff on quality assurance.
- The project has conducted 3 performance audits per year. The in-depth performance audits that were carried out were Kathmandu Valley Road Improvement Project, Health Service Delivery, and Social Security Allowances applying the revised performance audit guide procedures.
- OAG collaborated closely with Civil Society Organisations (CSOs) to engage these in the auditing process.
- Electronic Working Papers software has been procured and installed and will be piloted.
- More than 300 auditors have received training on the Financial Audit Manual.

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A as this component was not in the original logframe.

Recommendations

It is recommended that the MDTF extends this area of support to the OAG and PAC from June 2015 to December 2015 to finalise the activities of this phase and extend the technical assistance team’s contract for this period accordingly.

Output Title	Improved citizen engagement in PFM reform
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	30
Risk revised since last AR?		No	Impact weighting % revised since last AR?	Yes

Indicator(s)	Milestones	Progress
Number of independent budget analyses at national-level conducted and shared by Social Accountability (SA) grantees	3	3
Number of districts where Social Accountability media programmes targeting entitlements, budget awareness raising and main PFM issues are piloted	10	10
Number of VDCs where procurement monitoring, expenditure tracking and budget awareness raising is undertaken	80	80
Percentage increase of entitlements being disbursed to the correct beneficiaries, on time and of the correct amount in at least 75% of the 90 targeted beneficiaries.	64%	64%

Key Points

Overall progress against this output has been met and it is therefore scored as A The Programme for Accountability for Nepal (PRAN) had provided grants to 3 NGOs, viz. Freedom Forum, NAREC and SAWTEE, to conduct independent budget analysis of social security, education and health sectors.

One of the three national level CSOs under PRAN, Freedom Forum, conducted two workshops on the theme of Public Financial Management to journalists and students to build their capacity on the issues of PFM. One workshop was dedicated to journalists reporting on Economics and the other for Journalism students. Out of the 17 journalists and students trained on PFM reporting, 16 of them published articles on PFM and social accountability in various newspapers in Nepali language following these workshops.

With the Association of Community Radio Broadcasters (ACORAB), PRAN reached out to all ten MDTF districts through weekly radio programs and public hearings. The interactive radio shows as well as public hearings held in two phases – at ward level and district level – have not only informed the communities about their budget but have also received commitments from local authorities for further development. All public hearings were broadcasted live on radio and follow-up discussions were held on the commitments and the issues raised at those hearings.

MDTF donors requested the World Bank to prepare a three year plan for the demand side component instead of the one year plan that was presented to the Project Coordination Committee (PCC – steering committee) meeting on January 24th, 2014. The Bank has responded and has requested $1.5 million to extend the programme from January 2015 through June 2016, with an option to extend to component to January 2018 with additional funding if progress continues to be satisfactory. This timeframe will allow CSOs to engage in the local budget planning and implementation across one and a half fiscal years (FY15 and FY16), as well as well as permit civil society partners time to exert influence on national institutions and policies. Additionally, this new phase will focus much more on coordinating with existing Government structures (particularly MoFALD, LGCDP, OAG and the PEFA Secretariat). The PCC endorsed the proposal in principle and the project will now run till 30 June 2016.

The key results achieved during the past year under this component include
- Dissemination of preliminary results on social security entitlements.
- Workshop for all CSOsthat implement work in the 10 selected districts on analysis, communication, and dissemination of results.
- Production of information, education, and communication materials on budgetary issues targeted to educate journalists
- Auditor General Office and CSOs developed framework for engagement through a peer-assisted process.
- Public consultation by OAG Nepal in Kapilvastu.
- Simplified booklet on Nepal’s Auditing System and Practices published.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous review recommended extending this component past 2014 to coincide with the end date of the MDTF or beyond. This has been endorsed by the last PCC meeting.

Recommendations

PRAN is recommended to work much more closely to strengthen existing Government structures (particularly MoFALD, LGCDP, OAG and the PEFA Secretariat) through which social accountability tools will be operationalised.

PRAN is recommended to continue working closely with the DFID/Danida/Switzerland supported Governance Facility programme to avoid duplication and to complement the programmes and coordinate with other donors and working in this area.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers are:

1. Technical assistance provided through the World Bank that include international and national consultants, personnel and companies.
2. Software and hardware support for the well-functioning of financial management information system.
3. Research and studies such as the operation risk assessment, PEFA exercise, public expenditure tracking surveys
4. Grant to civil society organisations to hold government to account.
No major changes are noted to these cost drivers.
The allocation of the resources as of 30 June 2014:
Components	USD	Percentage
Supply side component	8,005,000	54%
Demand side component	1,650,000	11%
Studies	384,984	3%
Management /Admin / monitoring / supervision costs	1,055,240	7%
Unallocated	3,776,543	25%
Total	14,871,767

The funding sources from other donors of the trust fund as of 30 June 2014:
Donor Name	Pledged Amount			Receipts as on November 30, 2014		Balance*
DFID	GBP 3.5 m		Eqv. US$ 5.57 m	GBP 2.6 m	US$ 5.57 m	-	-
Norway	NOK 15 m		Eqv. US$ 2.62 m	NOK 15 m	US$ 2.62 m	-	-
Denmark	DKK 2 m		Eqv. US$ 0.38 m	DKK 2 m	US$ 0.38 m	-	-
AusAID	AUD 2.85 m		Eqv. US$ 2.99 m	AUD 2.85 m	US$ 2.99 m	-	-
EU**	€4.5 m		Eqv. US$ 6.15 m	€ 2.25 m	US$ 3.07 m	€2.0 m	US $3.08 m
Note:
* Pledged contributions to be realised
**Exchange rate used		EURs 1=		USD $ 1.37

VfM performance compared to the original VfM proposition in the business case

The World Bank is charging a 2 per cent trust fund admin fee and an additional 4 per cent for the management of this programme. Given the requirement for high levels of oversight and support for outputs this is a reasonable cost and is in line with other such initiatives in other countries.

Although already noted, there is currently no single dedicated person in the World Bank to work exclusively on this programme. An Programme Manager was assigned to this MDTF for about six months in 2014, but the position is currently vacant again. The placement of an international expert in the World Bank solely and exclusively to oversee and administer the programme would initially involve slightly greater admin cost but would be outweighed by the benefits in ensuring momentum is maintained. The World Bank has committed to assign a new full-time Programme Manager based in Kathmandu early 2015. DFID and other MDTF donors are monitoring this closely.

Assessment of whether the programme continues to represent value for money

Strengthening PFM in a challenging operating environment such as Nepal should be seen as a gradual and long-term process that will also require improvements in areas that go beyond the scope of this programme. At the same time, at a strategic level, important VfM gains are likely to be driven by this intervention.

The implementation and rollout of the TSA in particular is an example of VFM for the GoN. Nearly 14,000 bank accounts have been closed through the TSA. The GoN can now use the previously idle money from those bank accounts to address other development priorities. Furthermore, through the TSA the GoN is able to view the treasury position in real time for 100 per cent of expenditures and revenues. This much more accurate representation is of fundamental importance to policy based budgeting and will help government to plan to spend on development priorities appropriately and within budget.

The MDTF also enables several donor partners to coordinate and harmonise their support to PFM in Nepal, saving donors and Government transaction costs and avoiding duplications.

The programme continues to represent good value for money.

Quality of financial management

The World Bank provides financial statements and narratives on the statements every six months. The last semi-annual report was of very good quality and the Bank should continue at the same standard. DFID has been provided access to the Bank’s portal on ‘client connection’ where we can view the audited financial statements of this trust fund.

Date of last narrative financial report	30 June 2014
Date of last audited annual statement	30 June 2014

E: RISK (½ page)

Overall risk rating: Medium

The initial overall risk rating was high, but the previous annual review (2013) recommended to revise the risk to medium as this is a well performing programme, either directly implemented by the World Bank or with very close World Bank oversight where it is recipient executed.

Overview of programme risk
Main delivery risks are as follows:

Risk description	Mitigating actions	Residual Probability	Residual Impact
Lack of GON ownership and support to PFM reform with potential resistance	Approaching PFM reforms in a technical manner to ensure support from Government of Nepal stakeholders and political backing. This approach is working well. There is a minimum continuous support for the agenda and the World Bank oversees the risk of funds for this programme not being used as intended. DFID relies on the effectiveness of World Bank assurance processes and has assessed that these provide adequate control.	Medium	Medium
Frequent transfers of key staff in FCGO, MoF, line ministries and other agencies; leading to lack of continuity and ownership	Ensure overall GON commitment to PFM reform and broader ownership; ensure slower turnaround of key GoN staff through continued dialogue at all levels, including through the annual Nepal Portfolio Performance Review Process.	High	Medium
Inadequate capacity of implementing agencies, including the World Bank.	Strengthening capacity of PEFA secretariat and other GON implementing entities, embedded technical assistance (eg OAG), appoint full time MDTF Programme Manager in the World Bank office in Kathmandu. Capacity needs assessment planned and based on that capacity building strategy will be drafted.	Medium	Medium
Mis-utilisation of funds, corruption and fraud	World Bank oversees the risk of funds for this programme not being used as intended. DFID mainly relies on the effectiveness of World Bank assurance processes and has assessed that these provide adequate control, including procurement oversight etc. Additionally DFID does annual reviews, field trips etc. Also detailed process information maintained by the PEFA Secretariat and close scrutiny by the PEFA Steering Committee chaired by the Finance Secretary will reduce chances of mis-utilisation of funds and fraud allegations.	Medium	Low

Outstanding actions from risk assessment

Some of the risks stated above such as an unstable political environment, limited political engagement, or security risks are beyond the scope of this project but we are closely monitoring these risks and ensuring other means are utilised to mitigate these including political dialogue through the British Embassy. Frequent transfers remains an issue that is yet to be solved, but beyond the scope of the project and is therefore also addressed at higher forums.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Overall there has been good progress and key results have been obtained as expected. This programme is on reimbursable basis and funds not spent may not have correlation with physical progress as it was during this year. Change in public officials and project staff has delayed the pace of financial implementation during 2014. There were disbursements of only USD 850,000 by June 2014 against the target figure of USD 1.3m. This is primarily because of changes of staff in FCGO and which has therefore not been able to get the reimbursements of the funds that have been spent from the government treasury.

The overall financial disbursements of the various projects under the MDTF as reported by the Bank in the MDTF progress report Jan-Jun 2014 are as follows:

Performance of partnership(s)

The relationship between the World Bank and DFID is working well, and with the reappointment of a fulltime Programme Manager early 2015, information flow and interaction should also pick-up again.The World Bank conducts semi-annual missions and provides good technical back stopping to the Government of Nepal. This has worked well. The relation between the Government and the World Bank is also satisfactory. The fact that the project has scored A and A+ in several components show that the this is a well performing partnership.

The main partners are the District Treasury Comptroller’s Office (DTCO), the Financial Comptrollers General’s Office (FCGO), Office of the Auditor General, the PEFA Secretariat Programme for Accountability for Nepal (PRAN) and the WB.

The DTCO is responsible for the TSA rollout at district level whilst the FCGO is responsible for driving the TSA rollout from within central government. The PEFA Secretariat (and Steering Committee) lead on mainstreaming PEFA throughout GoN and led the second PEFA assessment. The Accounting Standards Board sensitise and train staff in state owned enterprises to prepare accounts to internationally recognised standards. PRAN leads on the CS output, sensitising and training CS on social accountability. The review has noted that on occasions various stakeholders had differing interpretations of their roles and responsibilities to those that were originally envisaged. As such when the log frame is revised the opportunity should be taken to reaffirm roles and responsibilities.

Asset monitoring and control

The assets procured by the Government of Nepal are recorded and monitored according their asset monitoring and control procedure. The assets procured by World Bank and civil society organisations are recorded are monitored according to their procedures. There is a need to maintain an IT asset register as such registers are crucial for GON/FCGO to track the expiry dates of various licences that need to be renewed periodically.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Partnership principles are monitored and assessed for all of DFID Nepal’s programmes on a regular basis. The successful implementation of this programme supports evidence on GON’s reform credibility regarding the partnership principle on PFM and anti-corruption.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The World Bank has carried out an Operation Risk Assessment, which is basically a political economy analysis of the public financial management sector. This is a good piece of evidence on the state of public financial management and has recommendations on way forward, parts of which are being implemented under the current MDTF phase.

A repeater Public Expenditure and Financial Accountability (PEFA) exercise was carried out this year and has been finalised by the Government and is being quality assured. This will serve as good evidence on public financial management that is accepted by the Government as well as by the international community.

Monitoring progress throughout the review period

Progress is monitored and decisions are made through the formal semi-annual PCC meetings. The World Bank produces six monthly progress reports. PRAN produces monthly newsletters and shares these with relevant stakeholders. The World Bank organises various review missions where representatives of donors are invited. These reviews are of technical in nature and discuss the progress of the programme and make recommendations for improvements.

A mid-term review was carried out by the Bank and the final report was circulated in November 2014 to the MDTF donors. It states that the objectives of the MDTF are highly relevant and the design is substantially relevant. There has been substantial progress in achieving the sub-objectives of improved efficiency and transparency of PFM systems, and MDTF administered and managed effectively. There has been modest progress in achieving the sub-objective of strengthened accountability, but the Strengthening the Office of the Auditor General Project and Strengthening Civil Society Organizations’ (CSO) Use of Social Accountability to Improve PFM in Nepal subprojects are now on track to meet their Project Development Objective, following delays in approval, effectiveness, and appointment of the Auditor General. The implementation of the TSA system in all 75 districts is the signature result of the MDTF, providing immediate gains in efficiency, and even greater long term potential as a key building block for improved PFM.

This Annual Review is based on both a desk review of evidence as well as meetings and interviews with the PEFA secretariat, the Financial Comptroller General’s Office, the Office of the Auditor General and the World Bank teams. The annual review was led by the DFID Nepal Private Sector Development Adviser and the Public Finance Programme Manager and quality assured by the Senior Programme Manager and the Acting Team Leader of Governance and Service Delivery Team.