Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: / Policy Development Facility Phase II (PDFII)
Programme Value: £18.5m		Review Date: September 2014
Programme Code: 203922	Start Date: 23 Oct 2013	End Date: 23 Sept 2018

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	Medium

Summary of progress and lessons learnt since last review

This is the first review of the PDF II programme covering the period of the approval of the Business case to the commencement of the procurement process for the identification of a supplier. This review is therefore focused on the process leading to the commencement of the procurement process rather than an assessment of programme implementation against programme outputs.

Summary of recommendations for the next year

Recommendation for next year are:
- Ensure a seamless transition from PDF 1 to PDF 2. All relevant sub-projects such as the Embedded Adviser (EA) support to key Nigerian Ministers are smoothly carried over in order to ensure continuity before the new Nigerian economic management team is selected.
- Complete a robust Political Economy Analysis of the post-election political environment – this will help the PDF 2 programme to identify who the new ‘champions of change’ are likely to be under the next Nigerian administration.
- PDF 2 Inception phase should further shape the nature of the programme. Given the elections, the inception phase will be critical to determine whether the shape, nature and size of the programme is still appropriate given the political economy of Nigeria. The logframe and capabilities of the team should be adjusted appropriately. By the time of the 2015 annual review this needs to have been concluded.
- PDF 2 should have developed a robust Value for Money (VfM) strategy and define VfM indicators in line with the 4Es of economy, effectiveness, efficiency and equity.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4030882
DevTracker Link to Log frame:	4030907

Outline of the programme

The Policy Development Facility II (PDF II) is a five year project that supports the Nigerian Government to implement policies that lead to poverty reduction. The project will increase the capacity of Nigeria’s ‘champions of change’ to make increased use of capacity and evidence to enable them to pursue vital economic and social reform. Ultimately this should lead to poverty reduction.

The impact and outcome of this programme are fully aligned with DFID Nigeria’s operational plan. It will help leverage better use of Nigeria’s resources for its national development, unleashing its growth potential. Its approach reflects a principle in the operational plan that better governance and growth are inter-dependent.

Context in which the programme is delivered

The Nigerian government faces major challenges in policy making and implementation of its economic and social reform agenda. These challenges include limited evidence-based policy, weak institutions and weak government agencies. Historically, the bonanza from the oil and gas sector has crowded out the effective development of other employment giving sectors of the economy. Ultimately these challenges mean that, despite over 10 years of economic growth averaging 5% a year, poverty levels in the country have remained roughly the same at around 60 million poor.

President Goodluck Jonathan’s election victory in 2011 led to the appointment of an economic team that included notable reformers. This included renowned Ngozi Okonjo Iweala as his Coordinating Minister for the Economy and Minister of Finance. Other ‘champions of change’ included the Ministers of Power, Trade and Investment, as well as Agriculture. There was already a strong Governor at the Central Bank of Nigeria. This team has been the main government counterpart for the PDF 1 programme. The priorities of this team are focused around Nigeria’s ‘economic transformation agenda’.
The economic transformation agenda aims to achieve the following key reforms:

•	Ensure macroeconomic stability and sustainable growth
•	Carry-out structural reforms, privatization, liberalisation, and deregulation
•	Strengthen institutions, support transparency, fight against corruption.
•	Invest in priority sectors (infrastructure, agriculture, housing and construction, security)

These reforms are vital for economic growth and ultimately poverty reduction. Since 2011, the reform agenda has faced many challenges including:

Capacity Challenges
•	Limited capacity of the civil service to implement reforms at the pace and quality required.

Political Challenges
-	Public backlash and protest when the government attempted to remove the country’s petrol subsidy in January 2012.
-	Public agency backlash, when the Minister of Finance attempted to reduce the number of agencies in Nigeria’s ports from 16 to 6 in order to reduce processing time of goods.
-	Privatisation challenges for the power sector including the resignation of the Minister of Power due to an alleged conflict of interest.
-	Periods of fuel scarcity caused by union action as a result of discontent with stricter processes to verify imports before payments.
-	A number of high profile reports pointing to corruption and mismanagement in the oil and gas sector.

Conflict Challenges
-	Increased instability and conflict in Northern Nigeria

The government has had varied success at overcoming these challenges to reform. In particular areas DFID Nigeria has backed reformers and the transformation agenda with technical support. This approach has already delivered results. Two of the highest Value for Money results achieved from the PDF 1 portfolio are the establishment of Nigeria’s Sovereign Wealth Fund and 6,300 jobs created from the Youth Innovation and Employment programme, ‘You Win’.

PDF 2 will become operational shortly after the 2014 Nigeria elections and at a time when the elected government will be putting together its new economic team. DFID’s engagement during this period, and the composition of the Nigerian economic team will largely determine the prospects for success of PDF 2. The inception period of PDF 2 will be critical in order to ensure the programme can either replicate the PDF 1 model and back the right individuals and policies, or if the number of ‘champions of change’ are substantially reduced, adjust the model in order that the UK can still help Nigeria have positive policy impact in the new political environment.

DFID Policy and wider UK Government context
There is a lot at stake for the UK. Her Majesty’s Government (HMG) has a unique position to support Nigeria as a development partner for the following reasons:
- the historical bilateral relationship;
- limited development partners in country;
- HMG has a broad bilateral relationship on trade and security;
- DFID works closely with the Foreign and Commonwealth Office (FCO) in lobbying and seeking influence – protecting and promoting champions of change, and countering corrupt or poor performance in the public sector.

Effective leverage is critical in Nigeria and has delivered results

HMG’s successes in influencing reforms in recent years include:
- The 2005 Debt Relief Deal, followed by creating sustainable debt management capacity through 3 phases of support to the Debt Management Office (DMO) (now ending), a big institutional and VFM success.
- The Petroleum Industry Bill, improved through political work (with Ngozi Okonjo Iweala) and technical support through Nigeria’s oil and gas sector reform programme (FOSTER) and IFIs.
- Routine Immunisation policies and systems, addressing a collapse in the last 2 years, through extensive lobbying of federal and international development partners.
- Reform of the fertiliser subsidy, harnessing the lessons of DFID’s rural market programme (Propcom), and technical assistance to the Minister of Agriculture’s transformation plans.
- Budget and financial management systems, through various work with the Finance Ministry.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

PDF’s intended outcome is that Nigeria’s ‘champions of change’ make increased use of capacity and evidence to enable them to pursue vital economic and social reform.

PDF 2 was approved in September 2013 and discussions with DFID’s procurement group commenced immediately on the best procurement route which would offer DFID the best Value for Money. Initially DFID choose to take this programme down the route of a restricted tender process which commenced on 20 February 2014 with a view for the programme to be mobilised by 1 October 2014. Unfortunately, unforeseen constraints in DFID Nigeria’s budget for the 2014/15 financial year meant that it no longer made sense to commence the programme during the 2014/15 financial year. A new date was set for 1 April 2015. Due to the time-lag between the existing procurement process and the much later date for mobilisation the initial process was cancelled. Using the experience from the initial restricted tender route, a new open tender process has now commenced. DFID carried out a contract amendment with PDF 1 to ensure that there was sufficient scope for the existing programme to continue to back Nigeria’s ‘champions of change’ in the run-up to the elections.

Given Nigeria’s own political time-table, and the adjustments made to the PDF 1 contract, the overall impact of the delayed contracting of PDF 2 has been negligible on PDF 2’s overall outcome. For instance DFID has still been able to provide flexible support to the creation of Nigeria’s new Development Finance Institution through-out the period of this review. DFID support for the ‘You Win’ competition is in the process of being transitioned across to the World Bank. Ultimately, DFID Nigeria has still been able to back the ‘champions of change’ with the necessary support to implement key economic policies .

The programme is on track to be contracted in time for April 1 2015 to ensure a smooth transition.

Overall output score and description

A – Outputs met expectation.

Given that the programme has not yet been contracted for the reasons outlined under the outcome section, we have assessed the programme against interim contracting milestones that will be cross-cutting for each of PDF 2’s outputs.

Table 1: Basis for assessing PDF 2 performance pre-contracting
Interim Contracting Milestones 2014	Status
Terms of reference for PDF 2 agreed	Complete
Duty of Care assessment approved	Approved
Procurement Initiation Document	Approved
Supplier engagement	Successfully completed for first tender. (February 2014)
Invitation for tender	Commenced in October 2014

Technical bids will be reviewed in November and December 2014, with the objective of submitting a contract to Ministers for approval in January 2015. Overall, the procurement is on track to enable mobilisation by 1 April 2015.

Key lessons

DFID’s programme management mechanism requires that at the anniversary of a project approval a review should be conducted irrespective of whether or not the programme implementation has started. There have been some key lessons from the past year’s experience of the PDF 2 programme.

Changes to budget allocations have an impact on pipe-line programmes as well as existing programmes. Good programme management involves being able to sufficiently adapt the course of the programme in a way that mitigates risk for DFID’s overall delivery and provides the least harm to the overall intended outcome of the programme.

Programmes that depend on partner country’s political environments need to be able to adapt. The political landscape during the time that PDF 2 was approved in 2013 has moved on, with uncertainty around the political landscape post 2015 Nigerian elections. During the inception period of PDF 2, the programme needs to understand the new environment it’s working in, and the scope for partnership and complementary policy agenda’s to DFID’s key objectives.

Key actions

An amendment has been made to the existing contract of PDF 1 to ensure that there is a seamless transition from PDF 1 to PDF 2. The timeline for procurement of PDF 2 is tied to the end of PDF 1 and DFID will work hard to ensure that the new programme is mobilised in time for 1st April 2015.

The quality of political economy analysis that PDF 2 is able to provide during the inception phase will be critical for DFID to target the programme appropriately.

If there are any slippages in the procurement timeline then alternative options need to be explored in good time to ensure that DFID support to embedded advisers continues unabated or, if appropriate, phased out with proper handling with the beneficiary organisations.

Has the logframe been updated since the last review?

No. This is the first annual review, although as the programme has not yet been contracted, interim contracting milestones have been used to assess its performance in this period.
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Relevant and high quality PDF policy research and consultation products delivered to beneficiaries
Output number per LF		1	Output Score	A
Risk:		Low	Impact weighting (%):	45
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Interim Milestones on Contacting Process	Progress
Number of projects assessed as executed satisfactorily or better during implementation	Invitation to tender issued.	Invitations issued in October 2014
Beneficiary, user and DFID perceptions of relevance and quality of PDF-supported policy studies and events	As above	As above

Key Points

Procurement timelines are in place to ensure that the project commences on 1st April 2015 and legacy activities are moved over to ensure immediate delivery of activities .

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as this is the first review

Recommendations
- Ensure a seamless transition from PDF 1 to PDF 2. All relevant sub-projects such as the Embedded Adviser (EA) support to key Nigerian Ministers are smoothly carried over in order to ensure continuity before the new Nigerian economic management team is selected.
- Complete a robust Political Economy Analysis of the post-election political environment – this will help the PDF 2 programme to identify who the new ‘champions of change’ are likely to be under the next Nigerian administration.
- PDF 2 Inception phase should further shape the nature of the programme. Given the elections, the inception phase will be critical to determine whether the shape, nature and size of the programme is still appropriate given the political economy of Nigeria. The logframe and capabilities of the team should be adjusted appropriatelty. By the time of the 2015 annual review this needs to have been concluded.
- PDF 2 should have developed a robust Value for Money strategy and define VfM indicators in line with the 4Es of economy, effectiveness, efficiency and equity.

Output Title	Relevant and high quality PDF organisational support delivered to beneficiaries
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	55
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Interim Milestones on Contacting Process	Progress
Number of projects assessed as executed satisfactorily or better during implementation	Invitation to tender issued.	Invitations issued in October 2014
Beneficiary, user and DFID perceptions of relevance and quality of PDF-supported policy studies and events	As above	As above

Key Points

Procurement timelines are in place to ensure that the project commences on 1st April 2015 and legacy activities are moved over to ensure immediate delivery of activities.

Summary of responses to issues raised in previous annual reviews (where relevant)

Not applicable as this is the first review.

Recommendations

See recommendations from output 1.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

As the programme has not yet commenced, no financial cost has been incurred. The open tendering process should provide sufficient competition to ensure that key cost-drivers represent good value for money (such as no service provider mark-ups on the managed-fund).

VfM performance compared to the original VfM proposition in the business case

As set-out in the PDF 2 business case, VfM will be carefully monitored throughout the programme life span. At every annual review DFID will consider the economy, efficiency, effectiveness and equity of the programme. The 2012 annual review of PDF I provides a good example of how this can be done. This review looked at the economy, efficiency and effectiveness of key flagship sub-projects individually (e.g. sovereign wealth fund support, ‘you win’ programme, and trade policy support). It also provided cross cutting assessments on how costs were controlled for key areas such as:

- Average cost of embedded advisers (and benchmarked with other DFID programmes)
- Average daily cost of expertise brought in for policy studies and research (benchmarks should be used).

The findings of the 2012 PDF 1 annual review economy measures from the managed fund are summarised below and serve as a useful benchmark for PDF 2.

	Short-term (mainly studies)		Monthly (embedded advisers)
	Daily fee rate £	Daily fee rate N[1]	Monthly fee rate £	Monthly fee rate N
Number	74	5	28	3
Mean	497	333	4,778	2,667
Lowest	150	320	1,477	2,600
Highest	950	384	6,767	2,800
[1] Naira converted to £ sterling at the rate of 250.

Maximum payment ceilings will be set for long-term embedded advisers. The 2012 independent review found no evidence that this ceiling under PDF 1 had prevented expertise from coming in.

Case studies around major policies that have been introduced with support from PDF 2 will be carried out (such as in case of Sovereign Wealth Fund and You Win competition), with an attempt to monetise the benefits where this is possible and credible. Finally, on-going monitoring and evaluation of impact, outcomes, and outputs will be a critical part of the PDF 2 management function. Embedded advisers will report on a quarterly basis with updates on progress and contributions to any outcomes. PDF 2 will flag to DFID, via a performance traffic light system, any embedded advisers that are not adhering to their original terms of reference. DFID can discuss with relevant beneficiaries of the technical assistance and agree a way forward that addresses any performance issues.

Finally, as per DFID Nigeria’s recent portfolio review on VfM, PDF 2 will need to set-out during the inception period how it will try and measure the ‘equity’ aspect of the four ‘e’s during implemention.

Assessment of whether the programme continues to represent value for money

As there has been no expenditure to date, it is too early to assess value for money indicators. Assuming that the reform environment provides enough credible partners to work with, the programme will continue to represent good value for money as PDF 1 has done. If however, the number of partners is substantially reduced following the 2015 elections then there may be need for substantial re-design during PDF 2’s inception phase, and a reconsideration of whether the proposed budget is still set at the appropriate level.

Quality of financial management

Financial management is one of the criteria used in the choice of supplier, and has been set out in the tender documents - a sound financial management mechanism. From experience with PDF 1, we know that having opportunistic and flexible programming can bring particularly difficult challenges for financial management. For the routine expenditures, such as embedded advisers’ salaries, the service provider should work with embedded advisers to ensure timely submission and payment of invoices. For the less routine payments, such as larger projects with payments dependent on milestones defined by a beneficiary agency time-table, good communication with DFID will be important.

Date of last narrative financial report	N/A
Date of last audited annual statement	N/A

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The Business Case risk assessment is Medium and it remains so. However, any adjustment to the programme risk will be dependent on political economy analysis on the new government and its appetite for reforms. This will be assessed during the inception phase of the programme in 2015.

Outstanding actions from risk assessment

In the event that the contract is not issued on the proposed date, we would look to extend the end date of PDF I. However, all efforts will be made to ensure that PDF 2 is ready to mobilise by 1 April 2015 and further contract amendment to PDF 1 should not be necessary.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Despite delays to the procurement process, this has proved appropriate due to the Nigerian political cycle and the impact on this towards achieving the overall outcome of the programme has been negligible. The business case did not have a start date but proposed a five year duration. The delay in the procurement and mobilisation means that the end date will now be scheduled for 2020.

Performance of partnership (s)

There are no current project partners

Asset monitoring and control

There are currently no assets.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

The Partnership Principles in Nigeria were developed in 2014 and so were not considered within the project Business Case developed in 2013. Many of the issues covered by the Partnership Principles are relevant to the strategic decisions of where PDF 2 should be targeted. During the inception phase of the programme, the political economy analysis will be influential in determining the ‘game plan’ and how these relate to the partnership principles.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There is no plan for a formal evaluation of this programme. The service provider will routinely monitor the performance of its technical support, and this will be complemented with periodic independent annual reviews.

Monitoring progress throughout the review period

The first step will be the inception period of the programme in 2015 and this will provide a key opportunity to identify key partners and make sure the programme is appropriately targeted.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process