Annual Review - Summary Sheet

Title: Mining Sector Reform Project
Programme Value: £ 28,433,000		Review Date: July - August 2014
Programme Code: 105 844	Start Date: 19/10/2011[1]	End Date: ProMines end date 30 June 2015, Project financial end date 30/04/17
[1] ProMines declared effective by the World Bank

Summary of Programme Performance
Year	2012	2013	2014
Programme Score	C	B	B
Risk Rating	High	High	High

Summary of progress and lessons learnt since last review

There has been progress on some elements of ProMines, notably the revision to the Mining Code, the strategic environmental and social assessment of the mining sector (SESA), and the institutional audit of mining sector institutions, but not across the entire project. Given this continued underperformance, the Mid Term Review, conducted jointly with the World Bank, concluded the need for ProMines to be restructured, a process which was meant to be completed in July in time for this Annual Review. However, this process remains far from complete with significant gaps in the draft restructuring document provided by the World Bank. Combined with budgetary pressures, this has led to the decision to exit from the ProMines project and downscale and restructure the Mining Sector Reform Project to engage in pilot activities bilateraly - with a view to developing a successor mining sector programme if these activities suggest that this would be warranted.

Key lessons learnt include the need for a consistent, high level of in-country engagement both on project implementation and strategic engagement with stakeholders, and the need for flexibility in an operating environment as complex as DRC.

Summary of recommendations for the next year

Implement improvement measures to downscale and restructure the programme, and to prepare the ground for a potential successor programme implemented bilaterally. These measures include:
- Exiting from ProMines.
- Continuing oversight of the Carter Centre Accountable Grant.
- Continuing to engage bilaterally with the extractives sector, exploring possible areas of support including the Extractives Industry Transparency Initiative (EITI), the Katanga Extractives Industry Development Initiative (KEIDI), and conflict minerals.

A. Introduction and Context

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4145425.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4017477.xls

Outline of the programme

DRC is a country with vast mineral wealth. According to World Bank calculations, the mining sector could contribute around 15-20% of GDP and 25% of Government revenues by 2020[2]. However, critical problems in the way in which the mining sector is governed have meant that the revenues generated from the sector have not been used effectively to contribute to sustainable economic development in DRC. Rent-seeking and corruption, insufficient institutional capacity, lack of credible information on mining sector assets, a weak policy, legal and regulatory framework and ongoing conflict in the East have all contributed to the dysfunctional administration of the sector at the national level. The role of State-Owned Enterprises in mining sector deals remains a source of controversy. At the local level, artisanal miners face challenges related to their access to mining areas, their illegal taxation by a multitude of private/ armed group and public state security actors and the lack of sufficient support they receive from the Supervision and Assistance Service for Small-Scale Mining (SAESSCAM - Service d'Assistance et d'Encadrement du Small Scale Mining). Artisanal and Small-scale Mining (ASM) sites are also associated with serious environmental and social problems, including child labour and the sexual exploitation of women. Finally, Congolese NGOs active in this area often lack resources and expertise to hold government and companies to account.
[2] Figures from World Bank ProMines Project Appraisal Document

Between 2011 and 2015 the UK has been providing £27 million through a World Bank-managed single donor trust fund for the ‘Growth with Governance in the Minerals Sector’ (ProMines) Technical Assistance Project in the Democratic Republic of Congo (DRC). It has also allocated an additional £0.5 million to share the costs of a senior mining specialist within the Bank’s Kinshasa office for Project management and sector coordination. The World Bank is contributing $50 million (£33 million) to the Project.

The intended impact of the ProMines project is to improve governance of the mining sector and increase its contribution to economic growth, sustainable development and poverty reduction. At the outcome level, ProMines intends to strengthen the capacity of key institutions to manage the minerals sector, improve the conditions for increased investments and revenues from mining, and help increase the socio-economic benefits from artisanal and industrial mining.

At the output level, ProMines intends to:
- Improve conditions for access to mineral resources to encourage increased investments in and revenues generated by the mining sector.
- Strengthen the Government's capacity to manage the mineral sector.
- Enhance transparency and accountability in mining sector revenue flows.
- Improve the management of the social and environmental impacts of mining activity, both at the industrial as well as at the artisanal mining level.

In addition to ProMines, the Mining Sector Reform Project also provides £1.24 million for General Support to the Minerals Sector of which the remaining £1.02 million was incorporated into this project from the Pilot Phase for DRC Minerals programme as a no cost extension in December 2012. From this, a £136,927 Accountable Grant (AG) with The Carter Centre (TCC) is being funded. This AG supports the third phase of TCC’s mining governance programme in the DRC. The ultimate goal of the programme is to increase accountability and transparency in DRC’s industrial mining sector. The specific AG project works with civil society on advocacy for transparency to increase the Government of DRC (GoDRC) and mining companies’ compliance with their information disclosure obligations, including, but not limited to, those found in: the new EITI Standard, the new Mining Code and Mining Regulation, ministerial decrees, contracts and conventions, corporate governance laws and international standards and best practices.
## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

ProMines has continued to underperform in terms of progress against logframe milestones. Although the logframe and milestones are being revised as part of the restructure process, against the interim logframe agreed at the Mid-Term Review it is not judged that this project will achieve its desired outcome within its lifetime.

Overall output score and description

B – outputs moderately did not meet expectation.

ProMines has had some tangible successes to date. The project’s support for the revision of the Mining Code has been widely praised by NGOs, the Mining Industry and other stakeholders. There has also been progress on a number of analytical studies, including the strategic environmental and social assessment of the mining sector (SESA) and the institutional audit of mining sector institutions, which have been considered useful by other donors, the government and civil society.

However, in spite of those successes, overall progress has been disappointing against most other activities. The follow up to both the institutional audit and SESA has to date been limited. Discussions about next steps for institutional reform are still ongoing between the mining agencies and the World Bank. The findings of the SESA do not feature in the World Bank’s plans for restructuring ProMines which raises concerns that the value of this study is not being capitalised on. There has been little progress on the work on improved revenue estimation and collection, and this now no longer features in the draft project restructure at all, despite this forming a key part of the original project focus. There have been significant delays to the work on Katanga Extractive Industries Development Initiative (KEIDI), despite DFID repeatedly stating that this was a priority for both DFID and the Governor of Katanga. Work on the establishment of RENAFEM, the network of women in the mines, is also suffering delays.

Key lessons

1) The need for close in-country engagement for a project of this nature. This applies both to project management as well as to wider strategic aspects of the project where working closely with GoDRC and other donors is vital. With respect to project management, delays in procurement processes, including long time periods taken to evaluate bids and notify firms and consultants of their successful shortlisting, and issues with financial management, would have benefitted from closer management and oversight.

2) The need for flexibility. ProMines is a complex project, with many different elements. Its failure to meet expectations has led to questions about whether it is too complex and too ambitious covering too many different areas of engagement. This is not judged to be the major problem, but rather the lack of flexibility in such a complex and changing environment. Going forward in our engagement with the mining sector, we would anticipate a more agile and flexible project, able to respond to windows of opportunity as they emerge.

Lessons learnt from the ProMines experience will be disseminated through sharing of this Annual Review across the office, and with key stakeholders, including the World Bank and the ProMines Project Implementing Unit.

Key actions

As this is the third consecutive Annual Review in which the project has scored below expectations, improvement measures will now be implemented to downscale and restructure the programme, and to prepare the ground for a potential successor programme implemented bilaterally rather than through the World Bank. These improvement measures are as follows:

1. Exit from ProMines ensuring all corporate and project cycle management requirements are met by December 2014.
2. Continue oversight of the Carter Centre Accountable Grant until the end date of January 2015.
3. Flexibly engage in pilot activities in line with both the Project Development Objective of ProMines, and the objectives of the Pilot Phase for DRC Minerals programme which was incorporated into the current programme through the General Support to the Minerals Sector component. Activities will be undertaken on an as-needed basis in response to emerging opportunities throughout the year and will be approved in accordance with delegated authority levels. These activities may include:
  1. supporting Katanga’s economic and social development objectives through a Public-Private Partnership with mining companies (the KEIDI initiative). This is already underway through a ProMines-funded scoping study, whose progress we will follow over the coming months.
  2. strengthening DRC’s participation in the EITI process now that DRC has been admitted as a full member. We have built good relationships with the National Secretariat and other donors and would seek to co-fund specific activities that form part of the Secretariat’s workplan.
  3. enhancing wider efforts on scaling up conflict-free supply minerals chains in eastern DRC. We have been in close contact with lead donors and initiatives in this area and would seek to target our engagement on where we can add most value.
  4. engaging more actively in the wider dialogue on extractives, for example through the various Groupe Thematiques and the Peace Stability and Cooperation Framework. This forms part of our ongoing external engagement on extractives, including with the Foreign and Commonwealth Office.
1. On the basis of these pilot activities, design follow-up activities and, in so-doing, determine whether a business case for a new extractives sector programme is necessary.
2. Revise the logframe.

Given the exit from ProMines, 2015/16 spend will be reduced to no more than £2m, and an indicative amount of £3-5m will be allocated to 2016/17 (for either activities to be taken forward under this programme, or those to be taken forward under a new business case as per point 4 above).

Has the logframe been updated since the last review?

Yes – there was a logframe re-fresh conducted jointly with the World Bank at the point of the March 2014 Mid Term Review. This agreed an interim logframe with the below changes:

- Indicator A3 has been moved to C4 to link it to the accountability and transparency output.
- Indicator B4 has been added which covers improved capacity and working conditions of key mining agencies.
- Indicator C1 has been broadened to cover improved revenue transparency in the mining sector rather than production of EITI reports which is not solely in the control of the programme.
- Indicator C2 has been made more specific and measurable to cover more robust estimation of fiscal revenues and targeted improvements in revenue collection
- Indicator C3 has been made more specific and measurable to cover improved implementation and extended coverage of traceability and certification systems.
- Indicator D2 added to cover industrial mining activities and Katanga Extractives Industry Development Initiative (KEIDI). (Previous indicator D2 now becomes D3, D3 becomes D4, and D4 becomes D5).
- Indicators E1 and E2 merged to form a single indicator on establishment of an M&E framework.

A revised logframe as part of the restructure package has not yet been produced.

## C: DETAILED OUTPUT SCORING

Output Title	A: Improve basic conditions for access to mineral resources to encourage increased investments in and revenues generated by the mining sector
Output number per LF		1	Output Score	B
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
(A1) Percentage of geodesic coverage	2013 Detailed plan for national coverage developed / 2014 Network upgrade being carried out	Existing data compiled. Mining cadastre is in the process of validating the work of the consultant on the plan for national coverage following a workshop in mid-July. Once this has been validated ProMines will then go to tender for the network upgrade itself.	Outputs moderately did not meet expectation
(A2) Availability of geological information for the targeted sites (country)	2013 Design of geological database completed / 2014 Regional Geophysical and Geological Surveys over key areas with minerals potential carried out	Consultant recruited for design of geological database, and currently evaluating expressions of interest for geological surveys. Database design and surveys will take 3 years so milestones still need adjusting.	Outputs moderately did not meet expectation
(A3) Revision of the mining code and development of mining regulations integrating all stakeholders' recommendations (Government, Civil Society and private sector)	2013 Recruitment of an international consultant to mediate on the recommendations of the three stakeholders / 2014 Mining Code and regulation of mines (Mining Law) is revised and submitted to Parliament for approval. Translation of the new mining code into national languages	Mining Code currently waiting for Council of Ministers approval. In process of finalising the contract for the consultant to begin work on the Mining Regulation. Waiting for approval in Parliament before translation and dissemination of code can occur.	Achieving 2014 milestone dependent on approval in Parliament. / Outputs met expectation

Key Points

At present delays against the geological indicators mean that this component cannot be judged to be fully meeting expectations. Milestones for A1 and A2 need adjusting to reflect 3 year duration of work.

Summary of responses to issues raised in previous annual reviews

Action has been taken to review the geological components in time for the MTR and efforts continue to get these indicators back on track against milestones.

The indicator relating to the Accountability Platform and Government dialogue with Civil Society has been moved to component C where it better fits, and has been given more specific milestones.

Output Title	B: Strengthen the Government's capacity to manage the mineral sector
Output number per LF		2	Output Score	A
Risk:		High	Impact weighting (%):	30%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
(B1) Improved effectiveness and efficiency of CAMI in key mining provinces	2013 One fully-functioning CAMI office operational at provincial level providing quality information and services within agreed timeframes / 2014 Two CAMI office in Kisangani and Kindu under rehabilitation. Provision of Flexi Cadastre.	Two offices fully refurbished . Awaiting final technical approval. Supply of equipment in process. Contract already signed for flexi cadastre. Duration 3 months so on track to be completed this calendar year.	Outputs met expectation.
(B2) SAESSCAM has a clear and coherent strategy and improved its services in target provinces	2013 Institutional audit carried out / 2014 SAESSCAM starts first draft of its national strategy on ASM.	Institutional audit completed. SAESSCAM have drafted their strategy. In process of negotiating contract for a consultant to work with them on this first draft. This contract will be signed in August.	Outputs met expectation.
(B3) Technical training program at the University of Lubumbashi (UNILU) is adapted to the requirements of the mining industry	2013 Surveys of academic programs in the DRC concerned with mining started. / 2014 Surveys completed and identification of pilot partner completed.	Reform of programme with education institutes. Will sign contract with consultant who will look at Mutushi and UNILU in mid-August. Contract duration 75 days so on track to complete this year.	Outputs met expectation.
(B4) Improved capacity and working conditions of key mining agencies	2013 Institutional audit carried out / 2014 Technical feasibility study for building renovation in provinces covered by the project and in Kinshasa. Building renovation and support to equipment and supplies. Development of strategic training plan based on audit recommendations.	Insitutional audit undertaken. GoDRC proposals about requirements already agreed with consultant but now need to be agreed with World Bank. Currently above value of what is available. Report about what rehabilitation needed still to be discussed by GoDRC with World Bank. Strategic plan still needs to be developed. / Four training courses have started covering environment, OHADA, mining royalties and statistics.	Process delayed. / Outputs moderately did not meet expectation.

Key Points

Activity against this component has been limited to interim activities pending the in-depth review on institutional reform recommended by the MTR as necessary to feed into the restructure process. So though this output scores an A overall, it should be noted that this is against the reduced ambition of the post MTR interim logframe milestones. In moving forward, the level of ambition would have to be significantly increased in line with the recommendations of the institutional audit and review of component B undertaken by the World Bank as part of the restructure process.

Summary of responses to issues raised in previous annual reviews

An indicator on institutional capacity (B4) was added as recommended in the last Annual Review.
Output Title	C: Enhance Transparency and Accountability
Output number per LF		3	Output Score	B
Risk:		High	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
(C1) Improved revenue transparency in mining sector	2013 Government and mining sector companies provide necessary information for mineral resources in the EITI reconciliation report for financial year 2011. Previous report recommendations acted on. / 2014 Government and mining sector companies provide necessary information for mineral resources in the EITI conciliation report for financial year 2012. / Previous report recommendations acted on.	DRC achieved compliance. Collection of data for the 2012 report has begun and report should be available by end of year. ToRs for EITI impact study being worked on with EITI secretariat but this is the only EITI related workstream ProMines is currently supporting.	Outputs met expectation. EITI remains a poor indicator milestone as this is outwith the power of the project.
(C2) More robust estimation of fiscal revenues from mining sector, targeted improvements in revenue collection and efficiency.	2013 Inventory of mining sector related taxes (formal and informal) and procedures for payment. / 2014 Study mapping past and current intervention in mining sector revenue collection conducted, to identify gaps. Fiscal projection updated. Tax administration training delivery.	Audit mining sector taxes, particularly on Article 225 (list of goods benefitting from preferential customs regime) of the Mining Code will be carried out this year. / Study on updating fiscal projection not currently in PIU workplan. / Tax elements have been dropped altogether in the restructure plan.	Outputs substantially did not meet expectation.
(C3) Improved implementation and extended coverage of traceability & certification systems in Eastern DRC & Katanga	2013 Financial support continues with projects from 2012 with additional financing to support the capacity of SAESSCAM in three provinces (Katanga, Maniema and South Kivu) / 2014 Evaluation of current initiatives completed and Ministry's strategy developed to improve coordination and harmonisation of partners	Contract signed to undertake evaluation of current initiatives. Three month contract so on track to be finished by end year.	Outputs met expectation.
(C4) Formalized more regular dialogues between the government, civil society and private sector	2013 The Congolese Government has formalised the creation and put in place the platform of accountability in the mining sector / 2014 Ministry organises at least 4 communications events (newsletters, roundtables, conferences)	First meeting in February and second in July. Plenary scheduled for November.	Outputs met expectation.

Key Points

DRC has recently achieved compliance with the EITI standard, but the issue remains that EITI reporting is not the best indicator milestone as this is largely outside of ProMines’ control.

The Accountable Grant with the Carter Centre contributes towards the EITI process as it works with civil society on advocacy for transparency to increase GoDRC and mining companies’ compliance with their information disclosure obligations. This is not solely focussed on EITI, but the new EITI standard is covered.

Summary of responses to issues raised in previous annual reviews

EITI has been removed from the indicator description in indicator C1, but remains in the milestones. As outlined above this perhaps still needs further consideration. In the ProMines 2014 workplan, an EITI impact study is anticipated and this should help shape future activity.

Activity against C2 on mining revenues remains limited. It was hoped that future engagement in this area would be addressed in the restructuring paper, but tax elements have been taken out altogether.

Recommendations

EITI remains a priority area for DFID. Despite withdrawing from ProMines, we should continue to engage closely with the EITI agenda, both through the Accountable Grant with the Carter Centre which includes work on the new EITI standard, and through possible support to activity within the EITI National Secretariat’s workplan if required.

Output Title	D: Develop innovative approaches to improve socio-economic impacts of artisanal and industrial mining in three provinces
Output number per LF		4	Output Score	B
Risk:		High	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
(D1) Improved understanding of major social and environmental impacts of mining sector in DRC and enhanced government capacity to manage these impacts	2013 Assessment (SESA) carried out in target provinces. Identify suitable mechanisms for community participation / Policy and institutional reforms to reduce environmental and social risks from expansion of the mining sector identified and agreed with community involvement / 2014 Risk assessment of selected polluted sites in Katanga and Kasai carried out with community involvement	SESA carried out. / Consultants on the ground to begin evaluation / risk assessment. 3 months contract so will be finishing this year. / No SESA follow up in restructure paper so unclear that this is on track to meet milestones.	Outputs moderately did not meet expectation.
(D2) Integration of industrial mining activities in provincial and local economic development	2013 Preparation of ToRs for the consultant to facilitate consultation between provincial authorities, mining companies and local communities / 2014 KEIDI design study completed	ToRs for KEIDI designed and procurement process undertaken but still in in final stages. Contract duration 2 months so could still be completed this calendar year – though more behind than ideal at this stage.	Outputs moderately did not meet expectation.
(D3) Improved systems for the registration of artisanal miners and formation of cooperatives	2013 Successful implementation of at least two pilot projects / 2014 Review of lessons and start replication in other areas	Consultant starting 1st week August to work on Diamond Development Initiative. Report completed on past work in Kasai. Based on this replication work will begin. Equipment purchased to reinforce capacity but has not yet allocated. DDI plan will outline what needs to be done after miners are registered. Katanga 10 sites selected - with give equipment but then need to monitor impact. SASSCAM will provide document about how will monitor.	On track. / Outputs met expectation.
(D4) Economic & social empowerment of women in the mining sector	2013 Preparation of the TOR for women in the mining sector network / 2014 Design of RENAFEM completed	Two consultants for this – one in the East already on ground. Second in process of being chosen. 6 month contract for design – so milestone will not be met within timeframe.	Delays. / Outputs substantially did not meet expectation.
(D5) Reduction of child labour and presence in artisanal mines (in selected area of Katanga)	2013 Selection of an artisanal mining site for the pilot projects on reduction of child labour and presence reduction strategy / 2014 Implementation of pilot projects	In process of finalising contract for World Vision who will put in place pilots - 22 months contract so full implementation will not occur by milestone.	Delays / Outputs moderately did not meet expectation.

Key Points

There has been some progress against these milestones, but still remains slow. There has so far been little follow up to the SESA, and nor have plans for follow up been included in the draft restructure package.

Summary of responses to issues raised in previous annual reviews

As discussed above SESA follow through has been limited despite this being highlighted as an important part of the entire programme.

An indicator related to KEIDI was added as recommended in the last Annual Review.

Recommendations

KEIDI remains a priority area for DFID. Despite withdrawing from ProMines, we should continue to engage closely with this workstream and the findings of the scoping study once this has been completed.

Output Title	E: Establish monitoring and evaluation (M&E) framework for evaluating project implementation and its impact
Output number per LF		5	Output Score	B
Risk:		Medium	Impact weighting (%):	5%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Status
(E1) M&E framework established	2013 Implementation of an effective M&E system at the PIU level with competent and qualified M&E staff / Quarterly project monitoring reports produced / Project supervision missions with participation from range of stakeholders / 2014 Implementation of M&E system. Quarterly project reports including monitoring of indicators by the PIU; Monitoring of all activities involving data collection by the PIU; Integration of report results and updating into the database by the PIU. / Project supervision missions with stakeholders	New M&E expert appointed to the PIU. Some progress towards functioning M&E system. MTR agreed an interim logframe – to take the project up to the end of the restructure process. Quarterly project reporting has been on hold since the MTR.	Outputs moderately did not meet expectation.

Key Points

A new M&E expert has been appointed and has been working on the M&E system. However reporting has been on hold for since the start of the calendar year, first in the absence of an M&E expert at the PIU, then as a result of the MTR and restructuring period.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

There have not been any changes to cost drivers for the programme. Spending for this programme is indirect via partner funding in the case of ProMines, through the World Bank. The cost and value consciousness of the World Bank were judged to be satisfactory in the Multilateral Aid Review.

VfM performance compared to the original VfM proposition in the business case

Originally, the economic benefits and value for money measures for ProMines stem from the assumptions that the project will: a) strengthen the government’s capacity to manage the mining sector, thus increasing the sector’s contribution to revenues; and, b) help make the mining sector in DRC more attractive to investors, thus further increasing the revenues generated by the sector. Revenues can then be re-invested in poverty reduction. Given lacklustre progress in these areas, ProMines cannot be deemed to be achieving the level of VfM performance originally envisaged. Moreover, the ProMines draft restructure paper removes all tax components from the project which were originally deemed necessary to justify the VfM of the project. Despite this, an updated economic appraisal and VfM assessment has not been done, and so at this point we cannot make an accurate assessment of the likely VfM performance of ProMines in future.

Assessment of whether the programme continues to represent value for money

In light of the removal of the tax elements which were the basis for VfM metrics, the project’s continued underperformance and limited progress towards achieving outcomes, we judge that ProMines no longer represents value for money. As such the decision has been taken to exit the project and redirect our extractives funding elsewhere, and with more limited ambition. VfM assessments of all future interventions will be conducted as a matter of course.

Quality of financial management

As a World Bank Trust Fund, the ProMines programme has a payment schedule determined by the Administration Arrangement (AA). Since the project’s inception, DFID has contributed $14.3m (£9 million) to the World Bank Trust Fund. DFID made three payments (of £3 million each) against the agreed schedule: on signing the AA; in April 2012, and then in October 2012. In late 2012, we identified that project spending was not on track against original forecasts, largely as a result of the delayed start of the project and continued slow progress. DFID negotiated a new disbursement schedule in early 2013 with the World Bank, which postponed all future payments until Q2 2014. In 2013, the project continued to perform very slowly, and there was therefore no need for further DFID contributions into the Trust Fund. A new disbursement schedule was once more negotiated ahead of the Mid Term Review, which postponed all further payments until Q2 2015. The decision to exit the project means that no further contributions will be paid into the Trust Fund.

US$ 6.7 m of DFID funds have been spent to date (end July 2014). The remaining DFID funds within the Trust Fund have been committed against the 2014 interim procurement plan agreed with the World Bank at the MTR which totals $23m, and as such will not be returned.

Aside from issues around slow disbursement of funds, there have also been issues with poor financial management of the project at the level of the ProMines Project Implementing Unit. This has led to a number of in-depth investigations by World Bank teams. Serious weaknesses in financial management were found, but no sufficient evidence of fraud. In response to these investigations, and following the Mid Term Review, targeted measures were put in place to address the financial oversight of the project, including reducing the Project Implementing Unit’s spending authority threshold and closer oversight by the World Bank financial management team. Together with the more limited spending ambition in the interim between the Mid Term Review and the conclusion of the restructure process, these measures were considered sufficient to reduce the project’s exposure to fiduciary risks.

Date of last narrative financial report	Financial reporting contained in July 2014 quarterly report (last stand alone financial narrative report received December 2013 )
Date of last audited annual statement	IDA External Audit (July 2012 – June 2013) received March 2014 / PIU 2012 External Audit Report received December 2013

E: RISK

Overall risk rating: High

Overview of programme risk

The following table, based on the risks identified in the original project memorandum, provides an overview of the main risks to programme delivery.

Risk	Probability	Impact	Mitigation Strategy	Update
Uneven commitment/ political will for sector-wide reform	High	High	Work with international development partners to achieve maximum influence over the GoDRC, including through the Groupe Thematique Mining, Hydrocarbons and Electricity and in consultation with the IMF / Politically back up the PIU on delicate issues such as the Institutional Audit and the reform of the Mining Code / Expand network of contacts in government, civil society and the private sector to inform debates through a number of entry points	This risk materialised. The mitigation strategy was implemented, and has helped to some extent, however to this will be added: / Retain flexibility in terms of the programme’s focus areas – this will particularly be the approach now we are withdrawing from ProMines. Remaining funding will be used flexibly to respond to emerging opportunities.
Reputational risk	High	High	Provide renewed impetus to ensure that ProMines is well-targeted, well-resourced internally, and well-managed by the World Bank	ProMines is not judged to be well-targeted, or well-managed by the World Bank, despite dedicating significant resource internally to trying to get it back on track. / As such the mitigation strategy now becomes to exit from the project, but maintain engagement in the mining sector.
Conflict in Eastern DRC	High	Medium	Retain flexibility in terms of the project’s focus areas / Strengthen coordination of interventions in Eastern DRC with partners operating there	Conflict continues in Eastern DRC. / Going forward, flexibility remains a key mitigation strategy and one which will be particularly important now we are withdrawing from ProMines. Remaining funding will be used flexibly to respond to emerging opportunities.
Poor coordination with other sector interventions and activities and failure to take into account new developments	High	Medium	World Bank to appoint in-country senior mining expert to better manage relationships with the Government, other donors, civil society and the private sector / Hold monthly donor coordination meetings / Share information and knowledge on ProMines widely and in a systematic manner / Actively seek to learn lessons from other donor projects in the sector / Map out other projects relevant to ProMines	The mitigation strategy for this risk has been largely successful in ensuring donor coordination. However, an in-country senior mining expert has not yet been appointed. DFID is particularly linked up with GIZ through joint funding of the Carter Centre, and are engaging closely with other donors on the EITI process to ensure complementarity.
Reduced engagement from the World Bank following project approval, in particular the lack of a senior mining expert in Kinshasa	Medium	High	The original mitigation strategy was to come to an understanding with the World Bank that a senior mining expert will be based in Kinshasa during Project implementation.	This risk materialised and we did not see sufficient engagement from the World Bank in country. It was only following the November 2013 mission that the World Bank finally agreed to begin recruitment for an in-country Task Team Leader. The recruitment process is well underway but an individual has not yet been identified.

Outstanding actions from risk assessment

- Responsible exit from ProMines
- Continue to maintain communication with other donors active in the mining sector to ensure complementarity and coordination.
- Ensure flexibility of future engagement in the sector, in order to best respond to risks around conflict and uneven or poor political commitment.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe: N

ProMines was originally expected to become effective in September 2010, but the actual start date was delayed to October 2011. A revised logframe with updated milestones to reflect the delayed start was agreed with the World Bank before the August 2013 Annual Review. The logframe was again revisited as part of the MTR, and an interim logframe agreed. As can be seen in the detailed output scoring above, the project is still not delivering against this revised logframe. The logframe included in the draft restructure package remains incomplete.

The Carter Centre Accountable Grant started on 1st October 2013 and was due to end 30th September 2014. The end date has now however been extended to 31st January 2015 to allow for delays which occurred in the first few months of the project. The logframe was adjusted to reflect this and the project is on track against revised milestones.

Performance of partnership (s)

Concerns about the World Bank’s engagement and performance in relation to ProMines were highlighted in the last two Annual Reviews. Following the August 2013 Annual Review a second PIP was agreed from September 2013 – the MTR. In advance of the MTR it was judged that there had been limited progress against this and that commitment by the WB to the PIP has been slow to materialise, and not consistent against all actions. Nevertheless, the World Bank did agree to the appointment of an in-country Task Team Leader, a priority of DFID’s since the project’s inception, and the recruitment for that post is well underway. Crucially, however, progress with respect to the restructuring of the project has been insufficient on the part of the World Bank. Significant gaps remain in the draft restructuring paper received on the 14th July, including:

- Context within which the project is taking place: this has not yet been updated. DFID funded a political economy analysis for the mining sector and have shared this with the World Bank to aid the drafting of this section.
- Components and Activities of the project: Overall, the activities proposed are in line with MTR discussions and within the spirit of the original PAD, although there is significant scope to further simplify the project. Key activities, such as reforms to revenue collection and the follow-up to the Strategic Environmental and Social Assessment have, however, been omitted, suggesting that they have not been considered in the required depth. The draft proposal has also not taken into account the Governance Analysis that was conducted and links to other donor-funded projects have not been explored. Finally, no updated ‘theory of change’ has been developed which would give credibility to the restructured programme.
- Economic Appraisal: This has not been updated despite the removal of components of the programme that were originally deemed necessary to justify the value for money of the project.
- Financial Envelope: It was not made clear how much DFID would need to contribute into the Trust Fund between now and ProMines’ extended end date of December 2017.
- Institutional and Implementation Arrangements: The plan outlined in the original PAD has not worked and needs updating to reflect lessons learned. This has not yet been done.
- Logframe/ Results Framework: This remains incomplete.
- Risk Register: This has not been updated.

In terms of lessons learnt, in the case of ProMines, one of the major problems in DFID’s view has been the absence of an in country Task Team Leader. Although there was a verbal understanding between the World Bank and DFID at the outset, this was never formally agreed in writing. Going forward in similar projects with the World Bank it will be important to formally agree expectations at the outset.

In terms of the Carter Centre Accountable Grant, the partnership has been working well. The Carter Centre has been highly engaged from the outset, and very quick to respond flexibly to DFID reporting requirements at an early stage. We are also now exploring links between this project and the Carter Centre’s work with other donors which has been beneficial.

Asset monitoring and control

The World Bank hold an asset register of all equipment provided to the ProMines Project Implementing Unit which is shared with DFID. Spot checks on equipment are conducted as part of the regular World Bank audits of the ProMines project.

Questions about the Project Implementing Unit’s management of downstream assets were raised during the MTR by the World Bank financial management team and an action point relating to this included in the follow up plan.

G: CONDITIONALITY

Update on partnership principles (if relevant)

The Partnership Principles are primarily about conditionality applied to aid to the Government. In the case of ProMines the World Bank is our immediate implementing partner and we did not have an MoU with the Government of DRC. Given that we have made the decision to withdraw from ProMines applying Partnership Principles to this project will no longer apply, but they will be important for our future engagement in the mining sector when working with Government DRC. The Partnership Principles assessment for the DRC country programme is still to be produced, however, once the country level assessment is completed we shall consider how elements of the findings might be applied to our engagement in the extractives sector through this project.

H: MONITORING & EVALUATION

Evidence and evaluation

Despite the decision to exit ProMines, the high level impact and outcome statements for DFID DRC’s extractives programme will remain the same for our future engagement in the sector. Sub-level logframe and theories of change will be developed at the intervention level for the future portfolio of activity, but at present these interventions are not fully known.

The original project appraisal document does not provide for a separate impact evaluation and, as at the last Annual Review, one is not anticipated.

Monitoring progress throughout the review period

ProMines support for the revision of the Mining Code has been widely praised by NGOs, the Mining Industry and other stakeholders. The strategic environmental and social assessment of the mining sector (SESA) and the institutional audit of mining sector institutions, have also been considered useful by other donors, the government and civil society.

Since the last Annual Review there have been a number of joint supervision missions conducted in collaboration with the World Bank. These took place 10-26 September 2013, 18-26 November 2013, and 20-31 January 2014. The Mid-Term Review mission was conducted 22 March – 4 April 2014.

This Annual Review was conducted by the DFID DRC Economic Development team in July and August 2014, drawing on project documentation and reporting, findings from the mid-term review, and meetings with stakeholders.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programme issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process