Business Case and Intervention Summary

Intervention Summary

## Title: Supporting the Delivery of Sierra Leone’s Education Sector Plan: The MEST (Ministry of Education, Science and Technology) Change Unit

What support will the UK provide?
The UK will provide £4.4 million from 2013/14 to 2015/16 to deliver the reforms required for the Ministry of Education Science and Technology (MEST) to successfully deliver the 2015/16 targets of the Sierra Leone Education Sector Plan (ESP), monitor progress against the Plan’s delivery milestones and evaluate the impact of the Plan. / DFID’s support will be managed through a trust fund managed by the World Bank which is also the managing entity for the Government of Sierra Leone’s application for a $17.9 million grant to finance the ESP over the period 2012-15 from the Global Partnership for Education (GPE).

Why is UK support required?

In the decade since the end of the civil war, Sierra Leone has made significant progress towards all the MDGs and has achieved political and social stability with three peaceful elections. Although it is in transition from fragile state to low income developing country (LIDC), Sierra Leone remains the eleventh poorest country in the world according to the United Nations Human Development Index. Low mean years and expected years of education are estimated to contribute one third towards total poverty.[1] / Government spending in education is above the Fast Track Initiative benchmark of 20% and averaged 22% between 2004-9.[2] 50% of spending goes to primary education and 16.5% to Junior Secondary Schools (JSS). Overseas Development Assistance (ODA) to the education sector is the lowest of all major government ministries at 15% of total spending, compared to 44% in health.[3] / There is currently no financial instrument through which donors can align their support to the MEST and follow best practice in terms of aid effectiveness. The Paris Declaration and Busan Partnership for Effective Development Cooperation are clear about the features of effective development aid. Establishing a multi donor trust fund is an important first step to achieving these in the education sector. / The ESP supports the Government of Sierra Leone’s new poverty reduction strategy paper the Agenda for Prosperity (A4P) and forms part of the MEST’s application for US$17.9 million. This will form part of the financing for the ESP and therefore the A4P as well. DFID Sierra Leone has endorsed the A4P along with other donor partners as well as the ESP. / DFID’s country education programme, Improving Schooling In Sierra Leone (ISIS), is providing £15.4 million over three years to expand access and improve completion in primary and JSS schools, improve students’ learning outcomes, and strengthen institutional capacity at national and local levels. These three strategies are directly reflected in the ESP. In particular, DFID’s co-financing of the ESP would strengthen and add value to the capacity development strategy within ISIS and the strategy to improve learning outcomes. / The capacity of the MEST and local councils, which have administrative responsibility for basic education, to effectively deliver these education services is low. An evaluation of the capacity of the MEST and councils in 2011 resulted in the development of a MEST Capacity Development Strategy[4] (CDS) designed to enable the MEST and Local Councils to effectively deliver education services. / There is currently no financial instrument through which donors can align and harmonise their support to the education sector for achieving the objectives of the A4P and ESP. The MEST also needs support to deliver and measure results and impact to ensure mutual accountability. DFID can, and as the largest bilateral donor, should provide leadership in implementing the Busan principles in the education sector.
[1] DFID 2012 Sierra Leone Growth Diagnostic Analysis
[2] Pole de Dakar 2013 Sierra Leone Country Status Report
[3] GoSL 2012 Budget Statement
[4] Education For Change/GoSL (2011) Capacity Development Strategy

What are the expected results?
The impact of the programme will be more children enrolled in schools with more of them achieving better learning outcomes. The outcome of the programme will be increased and more equitable access to more effective schooling. / DFID’s support to the MEST is expected to result in the following results by 2016 which will be disaggregated by gender: / 116,000 children supported in primary school / 10,000 children supported to complete primary school / 11,300 children supported in JSS every year / It will also contribute to the 2015 targets of the ESP, which have a focus on girls and achieving parity in access and outcomes at primary and improvements at JSS. These include: / An increase in the proxy[5] primary completion rate from 73% in 2011 to 91% in 2015 / Improvement in the Gender Parity Index at primary from 0.92 to 0.94 (1=equality) / An increase in transition rate from primary to JSS from 77% in 2011 to 83% in 2015 / Once a baseline has been established in 2013 there will also be targets for improvement in learning outcomes for literacy and numeracy in grades one to three. / DFID’s funding is also expected to leverage funding from other multilateral and bilateral donors who have expressed an interest in contributing to the implementation of the ESP.
[5] The proxy completion rate in the number of children completing primary school compared to the number entering in grade 1. It is used where it is impossible to calculate net enrolment and completion.

Business Case

Strategic Case

A. Context and need for a DFID intervention / In the decade since the end of the civil war, Sierra Leone has made important progress towards all the MDGs and has achieved political and social stability with three peaceful elections. Although it is in transition from fragile state to low income developing country (LIDC), Sierra Leone remains the eleventh poorest country in the world. Low mean years and expected years of education are estimated to contribute one third towards total poverty.[6] Government spending in education is above the Fast Track Initiative (FTI) benchmark of 20% and averaged 22% between 2004-9.[7] 50% of spending goes to primary education and 16.5% to Junior Secondary Schools (JSS). Overseas Development Assistance (ODA) to the education sector is the lowest of all major government ministries at 15% of total spending, compared to 44% in health.[8] / The New Education Sector Plan / The Education Sector Plan (ESP) (Annexes 1 & 2) supports the Government of Sierra Leone’s (GoSL) new poverty reduction strategy paper the Agenda for Prosperity (A4P). The plan forms part of the MEST’s application for $17.9 million from the GPE which will form part of the financing for the ESP and therefore the A4P. The ESP is structured around three main strategies: increasing access and equity; improving learning outcomes and building effective capacity. DFID SL’s country education programme Improving Schooling in Sierra Leone (ISIS) goes part of the way to support the ESP and shares the same main strategies but there are still gaps in support for the ESP. / There is currently a funding gap estimated at US$7 million between the size of the GPE grant allocation and key activities this funding is expected to support in the ESP.[9] The activities that are underfunded are germane to the DFID SL ISIS programme and focused around institutional capacity building. They include: / Project management and monitoring of the implementation of the ESP – this was a major weakness of the previous ESP / Improving school performance / Supporting decentralisation of data collection and planning at the local council level / Overall there is 15% funding gap in the five year life of the ESP, although there is an expectation that domestic revenues will increase more rapidly than the scenario used for modelling in the ESP. About 50% of the gap relates to years 2013/14-2015/16 which explains the initial front loading of DFID support.[10] / The Fit with the DFID Country programme (ISIS) / Through ISIS DFID is providing £15.4 million over three years to expand access and improve completion in primary and JSS schools, improve students’ learning outcomes, and strengthen institutional capacity at national and local levels. These three strategies are directly reflected in the ESP. In particular, the proposed DFID co-financing of the ESP through a trust fund would strengthen and add value the capacity development strategy within ISIS and the strategy to improve of learning outcomes. / The establishment of the Teaching Service Commission is a central part of the Capacity Development Strategy with is partly funded by the ISIS programme. This will also strengthen public financial management of the teachers’ payroll, which constitutes 50% of civil service wage spending, and add value to DFID’s programme of general budget support. A reading programme which will be funded by the bulk of the GPE funds will add value and strengthen component four, school improvement, of the ISIS programme and compliments component five, early grade reading and early grade mathematics learning assessments. There are a number of other synergies between ISIS and the ESP which mutually strengthen and add value to each programme. These include: / The ESP and ISIS complement each other in the collection, analysis and use of data through an Education Management Information System (EMIS). / Both programmes complement each other in learning assessments with the ESP creating the framework for assessments and ISIS trialling early grade assessments. / An implementation and monitoring unit for the ESP will better coordinate and add value to both programmes – especially for the components six and seven of ISIS which are designed to improve the effectiveness and efficiency of the MEST. / The ISIS programme will provide the necessary technical assistance to improve public financial management in the delivery of educational services and the ESP will provide the scope to institutionalise reform / Co-financing will also provide DFID SL with a role in the supervision and monitoring of the GPE fund that will enable DFID to have more influence on decisions that will affect the implementation of the ISIS programme. / Education and Poverty Reduction in Sierra Leone / Poverty has fallen over the last 8 years from 66.4% in 2003 to 52.9% in 2011 according to the Integrated Household Survey (IHS).[11] However, education indicators in IHS appear to indicate a declining trend as both net and gross enrolment rates have decreased. The potential significance of declining educational attainment is apparent in the growth diagnostic commission by DFID for Sierra Leone. This diagnostic found that low education attainment was the greatest single factor explaining poverty. Education policy that ensures access, learning and equity in education is the single-most effective intervention to reduce poverty. / Education Attainment in Sierra Leone / Despite significant improvement since the end of the civil war, education outcomes in Sierra Leone remain low and are unfairly distributed. According to official figures there is one primary school for every 165 children of primary school age[12]. Provision of schooling therefore appears adequate. However, 75% of children do not enrol in primary school at the correct age and account for a large proportion of the estimated 232,645 out of school children at primary level. 14% of children will never go to school[13]. The poorest and those in rural locations are 8.5 times more likely to be out of school and less likely to complete a full cycle of education. There are approximately 0.8 girls for every boy in JSS and 0.6 girls for every boy at SSS. Poverty and rural location reduce the chances of children going to secondary school and impact hardest on girls, perpetuating gender inequity.[14] Cost is reported as the main barrier to enrolling and attending primary school. 55% of households pay fees for primary school and 40% report having children excluded for non-payment of fees.[15] / Learning Outcomes in Sierra Leone / In additional to the issues of access to higher levels of education and inequity, learning outcomes at all levels of education are low. The data available indicate that the majority of children who complete a full cycle of primary school are not literate or numerate at the most basic level. In regional grade 12 examinations the pass rate was 1% and Sierra Leone performs well below its Anglophone neighbours in mathematics and English.[16] Girls’ achievement lags behind boys’ in terminal examinations at each level of schooling. In the National Primary School Examination (NPSE) girls achieve a pass rate of 72% compared to 76% for boys, girls are also less likely to sit for the exam. In the Grade 9 Basic Education Certificate Examination (BECE) girls achieve a pass rate of 39% compared to 47% for boys. Only 40% of the entries for the BECE are girls.[17] Grade repetition, as a result of slow progress in learning, is very high at 16% in primary and 13% at JSS and SSS and is rising. Proxy completion rates are good by regional standards but one in two students who enrol at JSS fail to complete the level and three in every four fail to complete at SSS. Formative learning assessments are not part of the school system only terminal cycle examinations. A government report in 2010 identified the unprofessional conduct of teachers as the main reason for poor student performance.[18] Teacher absence is reported at 8%-23%, varying by district, and worse in the most rural areas.[19] There are also big variations in the levels of teachers’ education with the most educated and qualified teachers centred in the Western Region which includes Freetown. / Institutional Capacity / The capacity of the Ministry of Education, Science and Technology (MEST) and local councils, which have administrative responsibility for basic education, to deliver effectively education services is low. A consultancy contracted to evaluate the capacity of the MEST and councils in 2011 developed a Capacity Development Strategy[20] (CDS) which was designed to enable the MEST and Local Councils to: / Make informed choices for the education sector / Plan and deliver educational services / Ensure educational quality in ways that can identify and respond to change and drive improvement / The ISIS programme supports the implementation of four key strategic objectives of the CDS managed by UNICEF. To achieve these objectives technical assistance will be procured through ISIS for: / An annual human resource planning process / Procurement policy and quality assurance system / The establishment of a decentralised integrated Education Management Information System / The development of a budget execution and monitoring system for the sector. / The sustainability of the improvements as a result of technical assistance to the MEST will only be assured if the MEST is able to reform and change so that it focussed on delivering educational services as efficiently as possible and has the technical capacity, knowledge and information to achieve this. This trust fund will support the MEST to: / Reform staffing, systems and processes to deliver the ESP targets and produce sustainable improvement in the delivery of education services / Establish the systems and processes with appropriate staff to effectively monitor and evaluate the implementation of the ESP and educational services in general / To provide the leadership, management and technical expertise to lead change management in the MEST and coordinate other technical assistance within the ministry. / Aid Effectiveness and the Busan Global Partnership for Effective Development Cooperation / The Paris Declaration and Busan Partnership for Effective Development Cooperation are clear about the features of effective development aid, donors should where possible: / Ownership: Developing countries set their own strategies for poverty reduction, improve their institutions and tackle corruption. / Alignment: Donor countries align behind these objectives and use local systems. / Harmonisation: Donor countries coordinate, simplify procedures and share information to avoid duplication. / Results: Developing countries and donors shift focus to development results and results get measured. / Mutual accountability: Donors and partners are accountable for development results. / There is currently no financial instrument through which donors can align and harmonise their support to the education sector for achieving the objectives of the A4P and ESP. The MEST also needs support to deliver and measure results and impact to ensure mutual accountability. DFID can, and as the largest bilateral donor, should provide leadership in implementing the Busan principles in the education sector. / Establishing a multi donor trust fund, with an effective manager, is a first step to enable donors and the MEST to work towards the Busan principles. It can be hoped that in the future this can develop from a trust fund into a sector wide approach and finally into sector budget support. This will support Sierra Leone’s transition from a fragile and conflict affected state to a low income developing state and provide the required aid architecture for other donors to effectively support the education sector.
B. Impact and Outcome that we expect to achieve / The impact that DFID’s funding is expected to achieve is reduced poverty as a result of better educational outcomes. The outcome is increased access to primary and lower secondary education and improved learning outcomes. / The proposed funding will deliver the following results during the life of the programme and these will be disaggregated by gender, and focus on achieving gender parity in primary enrolment and significant improvement in gender parity in JSS enrolment. / 116,000 children supported in primary school / 10,000 children supported to complete primary school / 11,300 children supported in JSS every year / DFID SL’s Operational Plan and DRF Education Targets for Sierra Leone for 2015 are: / 206,000 children supported in primary school (50% girls) / 24,200 children supported to complete primary school (50% girls) / 36,300 children supported in JSS every year (more than 50% girls) / The proposed funding represents a significant portion of these results and continues DFID support for the education sector beyond the life of the current operational plan. The balance of the Operational Plan results targets will be delivered through a combination of the ISIS programme and General Budget Support. / The funding will also contribute to the ESP targets which, have a clear focus on improving outcomes for girls at primary, JSS and SSS levels and include: / An increase in the proxy primary completion rate from 73% in 2011 to 91% in 2015 / In improvement in the Gender Parity Index at primary from 0.92 to 0.94 / An increase in transition rate from primary to JSS from 77% in 2011 to 83% in 2015 / Once a baseline has been established in 2013 there will also be targets for improvement in learning outcome targets for literacy and numeracy in grades one to three. / DFID’s funding is also expected to leverage funding from other multilateral and bilateral donors who have expressed an interest in contributing to the implementation of the ESP.
[6] DFID 2012 Sierra Leone Growth Diagnostic Analysis
[7] Pole de Dakar 2013 Sierra Leone Country Status Report
[8] GoSL 2012 Budget Statement
[9] Wolrd Bank GPE supervising entity
[10] MEST 2013 Education Sector Plan 2014-2018
[11] World Bank (2013) Sierra Leone Integrated Household Survey
[12] GoSL 2012 Making Progress – Schools and Students in Sierra Leone
[13] GoSL 2012 Draft Country Status Report
[14] UNICEF 2012 MICS 4 Final Report; GoSL 2012 Making Progress – Schools and Students in Sierra Leone
[15] IRC 2011 Primary Education in Sierra Leone: The State of Quality and Access
[16] GoSL 2011 education Sector Review; West African Examinations Council quoted in SLEDEF 2012
[17] GoSL 2011 Education Sector Review
[18] GoSL 2010 Gbamanja Report
[19] World Bank 2008 Textbook Provision and Educational Outcomes, Sierra Leone Baseline Report
[20] Education For Change/GoSL (2011) Capacity Development Strategy

Appraisal Case

A. What are the feasible options that address the need set out in the Strategic case? / Option 1: Establish a World Bank managed hybrid trust fund / Option 2: Establishing a Basket Multi-Donor Fund / Option 3: Expand current support for capacity development through UNICEF / Option 4: ‘Do nothing’ counter factual / Summary of the Feasible Options / Option 1: Co-financing the Sierra Leone Education Sector Plan with GPE funds a using a World Bank hybrid trust fund / In option one DFID SL would contribute funds to a World Bank managed trust fund. In line with DFID policy it is expected that the trust fund would be a multi donor fund and it is expected to be a hybrid Bank Executed/Recipient Executed fund. At the moment DFID’s funding would complement the funding from the GPE to cover part of the ESP funding gap. DFID’s funding through the trust fund would: / Reform staffing, systems and processes to deliver the ESP targets and produce sustainable improvement in the delivery of education services / Establish the systems and processes with appropriate staff to effectively monitor and evaluate the implementation of the ESP and educational services in general / Provide the leadership, management and technical expertise to lead change management in the MEST and coordinate other technical assistance within the ministry. / DFID’s funds would be catalytic and transformative. They would be targeted to remove persistent blockages and create a more effective MEST that can deliver the outputs of the ESP, generate the data necessary to measure progress and provide the technical input to ensure continued progress in service delivery. / The funds would be managed by the World Bank and subject to the agreed framework with the Bank in terms of the reporting requirements. The Bank’s no objection would be required for procurement of goods and services along with DFID’s approval. Following DFID guidance on setting up trust funds and the size of the ESP funding gap the trust fund will be above the £3 million minimum at £4.4 million over three years. The fund would also provide a mechanism to provide financial support for the ESP up to the 2018 end year of the plan and beyond the end of DFID Sierra Leone’s current operational plan. / Results will be measured in two ways. DFID’s support will be used to calculate results according to DFID’s official methodology for sector and general budget support. There will also be a schedule of key performance indicators linked to the ESP implementation plan which will measure progress in the short and medium term and will be focussed on improvements in service delivery and institutional capacity. / DFID’s contribution to the trust fund is linked to the current application for GPE funds and it would be able to provide pre funding to the selected objectives of the ESP prior to the approval of the GPE application anticipated to happen in November 2013 with funds available from April 2014. This would be particularly important for the timely commencement of ESP activities which could begin as soon as the fund was established and would strengthen recent actions to improve the management of the teachers’ payroll. / DFID will negotiate in the agreement arrangements to have audited financial statements in addition to the usual attestations from the Bank’s auditors. / The full arrangements for the fund will be approved by DFID in the Project Appraisal Document (PAD) developed by the bank to establish the fund. Funds will not be disbursed until the PAD has been agreed by the DFID Education Adviser. As well as management of the fund the PAD will define the role of the Bank in managing implementation and support to be provided if there are difficulties in implementing the interventions supported by the fund. / Option 2: : Establishing a Basket Multi-Donor Fund / In option two DFID would contribute to a pooled basket fund managed by the MEST to support the implementation of the ESP. The MEST would manage these funds according to agreed management arrangements outlined in an operations manual. / This form of basket fund was created to assist the financing of the previous ESP, which has now been superseded but the current Plan. The Education Sector Support Fund (ESSF) was initially used by UNICEF to support the production of the last ESP and by DFID to finance a teacher verification exercise. It was then used by the Swedish International Development Agency (SIDA) to support a grant made through the Education For All Fast Track Initiative. / The ESSF experienced a number of problems: DFID withdrew from the Fund, UNICEF did not disburse any further funds through the Fund and of the $8.75 million allocated by SIDA only $2.76 million was disbursed, of which $631,618 was returned unutilised in 2013.[21] / In the completion report to SIDA the problems identified for the poor performance of the fund were all related to procurement of civil works and the management processes within the MEST. These weaknesses were identified in the consultancy that developed the CDS and will be addressed as part of the new ESP. However, the example of the ESSF indicates that the MEST requires further investment in development the technical and professional skills along with the appropriate processes, systems and procedures necessary to manage this type of fund. / Based on the performance of the ESSF this option has been discarded. / Option 3: Expand current support for capacity development through UNICEF / As mentioned in the strategic case ISIS includes providing technical assistance to the MEST managed by UNICEF to address a number of strategic objectives in the CDS. In option 3 DFID could expand its current work through UNICEF to encompass the whole of the CDS. / UNICEF is the lead education partner in Sierra Leone and is the coordinating agency for the GPE. It is therefore the best placed agency to operate in partnership with the MEST and why it was selected to manage DFID’s support to the CDS. UNICEF has a clear work plan agreed with the MEST, which includes the aspects of the CDS which DFID is funding. UNICEF also has the capacity and technical expertise to expand its current role through its wider global network. / The principle drawbacks of expanding existing work with UNICEF would be that: / It does not establish a funding mechanism in the education sector which will lead donors towards the Busan principles and provide a path way towards more effective aid instruments both for DFID and other donors. / It would lack the flexibility of the trust fund to respond to and align with the changing priorities of the sector. / Mutual accountability for achieving results between the GoSL and donors would be weakened as accountability passed to UNICEF. / It would shift ownership for change and reform from the MEST to UNICEF / UNICEF’s performance in managing and delivering the outcomes of the CDS is unproven. / Option 4: ‘Do nothing’ counter factual / DFID SL could decide to do nothing. This would leave a funding gap for the ESP which no other donor would currently step in to fill. The only alternative donor is currently the European Union (EU). The EU does not yet have its EDF and funding approved for Sierra Leone and would be a new player were it to come into the education sector. The EU has a preference for sector budget support but does not expect to be able to use this mechanism for several years until PFM conditions can facilitate sector budget support. Therefore without DFID support from 2013 there will be a unfilled gap in the ESP and delay to implementation. This poses not only a risk to the current national poverty reduction strategy but also to the DFID SL country education programme. Doing nothing may therefore be discounted as harmful and increasing the risk to funds that DFID has already committed to the sector.
B. Assessing the strength of the evidence base for each feasible option including delivery routes / Option 1 / The World Bank successfully managed the use of EFA-FTI funds for the previous ESP despite significant challenges and the Bank remains the supervising entity for next application for Global Partnership for Education Funding for the ESP. The Bank managed the disbursement of $11.7 million out of the total allocation of $13.9 million between 2009-12 in a high risk environment.[22] The performance of the fund improved from moderately unsatisfactory according the Bank’s own review to moderately satisfactory. The GoSL were also rated moderately satisfactory. The World Bank is the only agency with significant and successful experience of managing a fund for the MEST. The depth of its experience enabled the EFA-FTI grant to be restructured when necessary to overcome difficulties related to procurement of civil works and to enable the majority of the funds to be utilised. The bank has learned valuable lessons through the management of the EFA –FTI funds that can be applied to the management of a Multi-Donor Trust Fund to Support the implementation of the ESP. / DFID Sierra Leone Fiduciary Risk Assessment (FRA) of social sector Ministries, concluded that the MEST’s fiduciary risk rating was ‘high’, marked by weak public financial management and controls and poor budget execution with only 74% of the MEST budget being utilised in 2010.[23] The Auditor General’s 2010 Report states in the executive summary that: ‘administrative and financial management of the school system is out of control.’[24] Although the CDS would help to tackle some of the concerns identified in the FRA particularly around procurement and financial management the impact and success of the CDS would not be known and improvements would not be achieved until the end of the intervention. An effective fund manager, with strong fiduciary risk management, like the World Bank, is therefore essential. / Recent DFID research into pooled funds found that performance is mixed and often falls short of expectations.[25] However, the research recognises that pooled funds have a number of advantages when, as in this business case, they support a variety of other aid instruments in the sector. The advantages identified with pooled funds[26] are: / Reduced transaction costs / Harmonisation and coordination – the proposed World Bank trust fund will be the only mechanism for harmonisation and coordination of donor funds in the education sector. / Predictability and timeliness of funding linked multiple years of support / Government engagement and proactive fund manage approach to support government / In Sierra Leone, where the DFID country programme and the ESP have major strategies based on systems strengthening and capacity development at the national and local council levels working through government systems is essential and a World Bank managed fund is the most feasible option in an environment of high fiduciary risk and limited alternatives for a managing agency. / Selecting the appropriate fund manager is essential to the success of a trust fund. The Bank has shown with the previous EFA-FTI fund that it is flexible and will deploy the staff necessary to effectively manage the fund. The ESP Secretariat has already been established since 2009 in the MEST. The ISIS programme, the ESP and this trust are designed to strengthen the capacity of the MEST to manage and deliver implementation of the ESP, monitoring its progress and evaluating its impact. DFID’s research into pooled funds identified that the appropriate context for the Bank to manage a fund is ‘development contexts with a legitimate government but without unmet humanitarian needs’[27] which adequately describes the Sierra Leonean context. / As managing entity for the EFA-FTI funds the Bank successfully achieved eight and missed only one target taken from the previous ESP. On the other hand the ESSF, which was not managed by the Bank, failed to utilise two thirds of the allocated funds made available by SIDA.[28] / Establishing a World Bank managed multi-donor trust fund will enable DFID and other donors to improve the effectiveness of their development aid to the education sector in Sierra Leone moving towards the five Busan principles of ownership, alignment, harmonisation, results and mutual accountability. / Option 3 / UNICEF’s effectiveness in delivering reform in the MEST through the CDS is as yet unproven. UNICEF is currently procuring technical assistance to deliver the strategic objectives from the CDS included in the ISIS programme and implementation is planned to begin in October. Therefore this is no operational evidence on which to judge the efficacy of UNICEF in systems strengthening in the MEST or whether expanding this work would be effective. / UNICEF, as lead education partner, did have a key role in establishing the ESSF and supporting the MEST in managing and implementing the interventions associated with the ESSF. The evidence from the performance of the ESSF points to limited success on the part of UNICEF to influence reform at the MEST. UNICEF’s own country programme in Sierra Leone has focussed on service provision rather than supporting the CDS which was developed with funding from UNICEF. Beyond the management of specific technical assistance therefore the evidence for UNICEF to expand its work from service delivery to capacity development and systems strengthening is limited. / There is no evidence that indicates expanding the current work of UNICEF would improve aid effectiveness and any expansion would not provide the financial instruments required by donors to increase future support for the sector. Removing ownership for reform and results from the MEST and not developing the aid architecture necessary to move to more effective aid instruments may inhibit development. / Evidence Rating for the Feasible Options / Option Evidence rating / 1 Strong / 3 Limited / 4 Not applicable / The Preferred Option is therefore option 1
C. For each feasible option, what is the assessment of local capacity? Is the intervention likely to strengthen capacity in a durable manner? / The principle output of the options is to expand and develop local capacity in a sustainable manner that facilitates the MEST to deliver the results targets in the ESP and to deliver general education services more efficiently and effectively. The schedule of performance KPIs that will be developed to monitor the progress of the intervention will also measure the improvement in local capacity as will progress against the monitoring indicators in the ESP. / Establishing a multi-donor trust fund will also increase the capacity of the MEST to manage, coordinate and utilise development aid more effectively and transition current development support away from project based interventions to support for interventions delivered using local systems.
D. What is the likely impact (positive and negative) on climate change and environment for each feasible option? / The UNDP Climate Change Country Profile for Sierra Leone[29] notes that the potential impact of climate change on Sierra Leone is likely to be felt through changes in rainfall patterns and the durations of the wet/dry seasons, with impacts on agriculture and freshwater resources, and through increased risks of flooding, salinisation and damage to marine habitat as a result of rising sea levels. / There seems however to be a lack of a good scientific basis on which to predict the impacts of climate change on Sierra Leone. Understanding of the processes causing tropical rainfall is insufficient to allow a prediction of the direction of change with any certainty. The IPCC identify this as an area requiring further research to understand the variety of model responses in this region. / There is a low level of public awareness and insufficient attention being given to climate change and environmental issues. It may be possible to integrate environment and climate change issues (impacts, adaptation, mitigation) into the curriculum, particularly focusing on the impacts likely to be experienced in the local area – droughts and flooding plus storms in coastal areas, and promote the establishment of school gardens and water harvesting as an educational intervention with a particular focus on adaptation[30] and low carbon technologies[31]. There needs to be flexibility to develop school learning materials that relate to appropriate climate change and environmental responses where this is relevant to the locality of schools. / Gender differences in loss of lives due to natural disasters are directly linked to weaker women’s and girls’ economic and social rights. Improving literacy and numeracy will enhance the ability of girls to earn livelihoods in the context of mounting environmental pressures. It is seen as one of the best climate change and disaster prevention investments, with high social rates of return.[32] / The options considered in this appraisal case relate to the mechanisms for implementation and managing the three components of the programme. Likely climate and environmental impacts will therefore be the same for the two delivery options. The third option, do nothing, will have no direct influence on climate change and environment. The programme strategy, components and outcomes are focussed on improving learning outcomes through increasing school attendance and improving the quality of education and education services. The programme thus provides an opportunity to improve awareness and knowledge of climate and environment issues through better education. The programme itself will not have direct climate impacts. This analysis is reflected in the Table following. / DFID’s funding for the programme will not support infrastructure development or transport. Hence, there should be no direct negative environmental impacts. / Categorise as A, high potential risk / opportunity; B, medium / manageable potential risk / opportunity; C, low / no risk / opportunity; or D, core contribution to a multilateral organisation. / Option Climate change and environment risks and impacts, Category (A, B, C, D) Climate change and environment opportunities, Category (A, B, C, D) / 1 Implementation and funding through the MEST B/C / 2 Implementation and funding through a mix of multi-laterals and NGO partners B/C / 3 Do nothing counterfactual C
E. If any, what are the likely major impacts on social development? / The major impacts on social development will be through the intervention’s contribution to the results targets in the ESP which feed directly into the GoSL’s new poverty reduction strategy paper the Agenda for Prosperity (A4P). Key impact on social development will be: / Increased access and attainment in primary education with proxy completion increasing from 73% in 2011 to 91% in 2015 / Improved access and attainment in JSS with transition rates increasing from 77% in 2011 to 83% in 2015 / Improved gender parity at primary school and JSS level / Improved learning outcomes for students in primary early grades
F. For fragile and conflict affected countries, what are the likely major impacts on conflict and fragility, if any? / This intervention does not address fragility and conflict directly. However, unequal access to educational opportunities was identified as a driver of the conflict in Sierra Leone that ended in 2001. Access has been expanded hugely in the last decade and expectations have risen but there are still inequalities in access to JSS based on location and gender. This intervention will support the improvement of equity in access to educational services at all levels and greater equity in the distribution of education resources and educational outcomes. It therefore contributes to the peace and state building process in Sierra Leone.
G. What are the costs and benefits of each feasible option? Identify the preferred option. / The total cost of the intervention is $17.9m (£11.2m), of which £4.4m (39%) will be from DFID between 2013/14 and 2015/16 (see section F of the financial case). DFID staff inputs to oversee and monitor the project, as well as provide technical advice, will also have a cost implication but these are not quantified since DFID does not capture complete data on the cost implications of staff time. / The benefits of the intervention are wide-ranging since it seeks to support implementation of the ESP. This appraisal therefore focuses on quantifiable benefits at the outcome level: increased access to and completion of primary and junior secondary schooling. It assumes that the GPE support would be instrumental in enabling MEST to achieve the targets set out in the ESP. Without it, education access and outcomes would continue on current trends. / If the targets for primary completion, transition to JSS and JSS completion are achieved, more children will complete more years of schooling. The value of completing each tier of schooling is assumed to be a wage premium above not attending school based on a study by Psacharopoulos and Patrinos (2004) that estimated that an additional year of schooling increases earnings by 11.7% in Sub-Saharan Africa. This is used as the best available estimate for Sierra Leone at this time.[33] For 6 years in primary school, this represents a 70% increase in expected earnings and an additional 35% for three years in junior secondary school. The lack of a workforce survey means that GNI per capita is used to proxy the wage level.[34] The opportunity cost of potential lost income through children attending school is approximated by applying the wage of primary school completers to the marginal reduction in JSS drop-outs as a result of this programme. / The potential benefits of the intervention are calculated over a 20 year period and discounted using a 10% discount rate, in line with other economic appraisals in DFID Sierra Leone. The balance of discounted costs and benefits is summarised in Table 1. / Table 1: Discounted Costs and Benefits / Costs Benefits Opp. Cost NPV* BCR / GPE £9.62m £73.73m £15.60m £48.51m 2.92 / DFID contribution £4.10m £29.10m £6.16m £18.84m 2.84 / * Benefits minus opportunity costs minus project costs / Based on these assumptions for the impact on wages alone, the project will generate a significantly positive net present value (NPV) of £19m for DFID’s contribution and should go ahead on this basis. In addition, the benefit-cost ratio indicates that for each £1 spent, £2.84 of benefits will be realised, representing good value-for-money. Other benefits will derive from improvements to the gender parity index at primary level, with associated social benefits, and improvements to learning outcomes for literacy and numeracy in grades one to three that should increase private and social returns further. / Other Costs and Benefits / Improved health and social returns: This analysis has not monetised other private benefits, such as improved health and wellbeing that are often associated with improved education, though evidence suggests that these could be substantial.[35] Similarly, it has not attempted to monetise the wider social benefits of a more educated population, which would be a significant challenge to do given the lack of data. This means that the benefits presented in the appraisal under estimate of the actual benefits of the programme. / Political stability in a post-conflict environment: / There is a body of evidence that supports the impact of increased educational attainment on citizens’ political agency and democratic participation. Increased education also results in increased awareness and capability to exercise rights. Disparities in educational access and opportunities were identified as one of the causal factors in the civil war and these are essential factors in building peace and stability in the post conflict environment in Sierra Leone. / Fiscal implications: By increasing lifetime earnings, it is reasonable to assume that the intervention would also result in an increase in total revenue, primarily through increased collection of income tax but also through increased indirect tax collection that may result from higher consumption levels. If the intervention also has positive growth effects emanating from higher productivity, the revenue take might be even greater. / Cost to government: Some costs are also not monetised in the analysis. Increased enrolment will have a cost implication for the Government at the end of the intervention and, even though they will be incurred in the future and discounted, are likely to be substantial. The longer-term ESP has identified a significant funding gap if its targets are achieved and it is unlikely to be filled through increased revenue from growth alone. / SENSITIVITY ANALYSIS / The analysis is sensitive to improvements to the JSS transition and completion rates that the programme targets. If the primary completion rate improves but there is no change to the transition or JSS completion rates, the discounted benefits fall by £2m but the project remains cost-effective. The main driver of wage benefits is the increase in primary completion and the cost-effectiveness of the project would come into question if the completion rate did not exceed 76% by 2016. This would not be an automatic decision however, since the analysis does not quantify other potentially significant benefits, particularly around health outcomes, that would likely mean that the benefits continued to exceed costs even at this lower completion rate. / CONCLUSION / This project is designed to catalyse significant transformation in the education sector and enable the Government to achieve the targets set out in its ESP. By increasing primary and JSS completion, the project will generate significant private returns in the form of increased wages, as well as greater social returns e.g. from health externalities. The targets are ambitious but the analysis suggests that even if a small improvement to primary completion were realised, the project would bring about positive net benefits. Finally, it should be noted that this project will enhance the benefits calculated for the ISIS programme, which applied the existing completion and transition rates for large cohorts of the programme
H. Theory of Change for Preferred Option / The proposed funding aims to be catalytic and transformative by working on the tipping point represented by assumption one in the theory of change. The funding will facilitate the delivery of the rest of the theory of change by building service delivery capacity at MEST and local council levels. This was a fundamental weakness identified in the execution of the previous ESP.
I. What measures can be used to monitor Value for Money for the intervention? / As the fund will contribute towards a range of outputs rather than deliver them exclusively the range of potential VfM indicators is limited. Key indicators that can be used will focus on costs and include: / The administrative and management costs of the fund / The costs of technical assistance procured through the fund / The costs of key staff associated with the fund / It will be possible to compare the rate of disbursement and spending against the rate at which key performance indicators are achieved as a means of monitoring whether the intervention is becoming more costly. / The World Bank PAD will establish further VfM measures.
J. Summary Value for Money Statement for the preferred option / This project is designed to catalyse significant transformation in the education sector and enable the Government to achieve the targets set out in its ESP. By increasing primary and JSS completion, the project will generate significant private returns in the form of increased wages, as well as greater social returns e.g. from health externalities. The targets are ambitious but the analysis suggests that even if a small improvement to primary completion were realised, the project would bring about positive net benefits. Finally, it should be noted that this project will enhance the benefits calculated for the ISIS programme, which applied the existing completion and transition rates for large cohorts of the programme. / Based on the assumptions for the impact on wages alone, the project will generate a significantly positive net present value (NPV) of £19m for DFID’s contribution and should go ahead on this basis. In addition, the benefit-cost ratio indicates that for each £1 spent, £2.84 of benefits will be realised, representing good value-for-money. Other benefits will derive from improvements to the gender parity index at primary level, with associated social benefits, and improvements to learning outcomes for literacy and numeracy in grades one to three that should increase private and social returns further.
[21] MEST 2013 Education Implementation Report on SIDA Grant
[22] World Bank 2013 Implementation Completion Report
[23] Fiduciary Risk Assessment: Education, Health and Water Sectors, Sierra Leone, unpublished, August 2011.
[24] GoSL 2011 Auditor General’s Report on the Accounts of Sierra Leone p8
[25] DFID 2013 Pooled Funding to Support Service Delivery: Lessons of Experience from Fragile States and Conflict Affected States.
[26] DFID 2013 Pooled Funding to Support Service Delivery: Lessons of Experience from Fragile States and Conflict Affected States.
[27] DFID 2013 Pooled Funding to Support Service Delivery: Lessons of Experience from Fragile States and Conflict Affected States p49
[28] MEST 2013 Education Implementation Report on SIDA Grant
[29] UNDP Climate Change Country Profiles http://country-profiles.geog.ox.ac.uk
[30] “Coping with Drought” https://practicalaction.org/coping-with-drought, “Preparing for Flood” https://practicalaction.org/preparing-forfloods-
[31] See http://tech-action.org/Guidebooks/TNA_Guidebook_AdaptationAgriculture.pdf
[32] World Bank (2010) Adaptation to Climate Extremes in Developing Countries. The Role of Education. Policy Research Working Paper 5342
[33] Psacharopoulos (1994) estimated the social returns to investment in education to be 20% for primary and 22% for secondary school in Sierra Leone but did not assess the private returns.
[34] The most recent living standards survey, completed in 2011, found that poverty levels dropped progressively as the education level of the household head increased, particularly in female-headed households. Reliable wage data from the survey are not yet available.
[35] The OECD (2006) found considerable evidence that “education is strongly linked to health and to determinants of health such as health behaviours, risky contexts and preventative service use”. These tend to be slightly higher for girls due to implications of delayed pregnancy, reduction in maternal and infant mortality. A study by De Walque (2004), based on data from Uganda, estimates that each additional year spent in school reduces both women and men’s probability of contracting HIV/AIDS by 6.7%.

Commercial Case

Delivery through a third party entity (multilateral organisation; civil society organisation or support to government)

A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / The World Bank successfully managed the use of EFA-FTI funds for the previous ESP despite significant challenges. The Bank managed the disbursement of $11.7 million out of the total allocation of $13.9 million between 2009-12 in a high risk environment. The performance of the fund improved from moderately unsatisfactory according the Bank’s own review to moderately satisfactory. The GoSL were also rated moderately satisfactory. To date, the World Bank has had a successful experience of managing a fund for the MEST. The depth of its experience enabled the EFA-FTI grant to be restructured when necessary to overcome difficulties related to procurement of civil works and to enable the majority of the funds to be utilised. The consistent improvement of the EFA-FTI fund’s performance suggests that the new fund will build on the previous fund and improve further. / The Government of Sierra Leone is experienced in working with the World Bank systems and processes, and requested that the Bank serve as the Supervising Entity of the next allocation of GPE funds, managing the implementation of the $17.9M Project. The bank has learned valuable lessons through the management of the EFA –FTI funds that can be applied to the management of the new project and Multi-Donor Trust Fund to Support the implementation of the ESP.
B. What assurance has been obtained on capability and capacity to deliver? / The experience, expertise and success of the World Bank in managing, and turning around the performance of, the EFA-FTI fund, along with the very poor performance of the ESSF, provides a firm evidence base for selecting the Bank as managing partner and a World Bank Trust Fund as the funding mechanism. / The selection of the Bank is further supported by its leading and coordinating role working with the MEST to submit the most recent application for GPE funds and its intention to contribute IDA funds to the fund, as well as the potential to leverage funds from negotiations with other bilateral donors. The Task Team Leader has an established relationship with the MEST and the Minister of Education. / The Bank’s strong performance in mitigating high levels of fiduciary risk and provides a funding mechanism for future donors in the sector is another important factor in the decision to select. This is bolstered by the absence of an appropriate alternative multilateral or private sector option.
C. Is there an opportunity to negotiate on anticipated costs? / The current fee structure for World Bank Trust Funds has been established by DFID as: / Trust Fund Type Size Management Fee Admin Fee / Bank Executed All 3% 2% / Recipient Executed <$100 million Customised 2% / There is also a set-up fee of $35,000. / The fund is expected to be a hybrid of Bank Executed and Recipient Executed (based on no objection letters received from the Bank and agreement from DFID). There is scope therefore, to negotiate on the management fee if the trust fund is recipient executed. Discussions with the Bank have been opened to achieve the lowest possible costs.

Financial Case

A. Who are the recipients of all proposed payments? / Payments for the programme will be paid directly into a MDTF managed by the World Bank. Funds will only be disbursed on the basis of need and progress on implementation of activities. No disbursement will be made in advance of need (i.e. if there are enough funds in the trust fund to cover expenditure over the next quarter). Given the hybrid nature of the TF, most activities will be executed by the Government of Sierra Leone (recipient entity) while others will be directly executed by the World Bank (managing entity).
B. What are the costs to be incurred directly by DFID? / The cost of the programme to DFID is £4.4 million over three years
C. What are the costs to be incurred by third party organisations? / The MEST will work with the World Bank will develop a detailed breakdown of costs incurred for the programme financed through the trust fund in the Programme Appraisal Document.
D. Does the project involve financial aid to governments? If so, please define the arrangements in detail. / The programme does not involve the award of financial aid to the Government of Sierra Leone.
E. Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin? / The funding will come from the current programme resource allocation.
F. What is the profile of estimated costs? How will you work to ensure accurate forecasting? / The programme costs are as follows: / Financial Year Amount £ millions / 2013/14 £2 million / 2014/15 £1.4 million / 2015/16 £1 million / The additional cost in year one is associated with initial start-up costs and to cover the period between the approval of the MEST’s application for GPE funds and the expected disbursement of funds in April 2013. / Payments for the main component of the programme will be paid directly into a MDTF managed by the World Bank. After an initial payment in advance to cover start-up costs, funds will only be disbursed on the basis of need and progress on implementation of activities. No disbursement will be made in advance of need (i.e. if there are enough funds in the trust fund to cover expenditure over the next quarter). / Forecast and expenditure reports, clearly demonstrating the need for funds, will be required for approval prior to disbursement of funds.
G. What is the assessment of financial risk and fraud? / DFID Sierra Leone’s Fiduciary Risk Assessment of Social Sector Ministries rates the financial and fraud risks as high. As explained in the relevant sections of the business case, the World Bank is the preferred partner to manage the trust fund because of its strong reputation in managing financial and fraud risks and proven track record through managing the EFA-FTI fund in doing this in the MEST. / The proposed trust fund will be a hybrid of a recipient and a Bank- executed trust fund. Bank policies and procedures apply, covering preparation, appraisal, supervision and evaluation and including fiduciary, safeguard and other applicable policies. All funded activities are subject to the Bank’s procurement guidelines, which specify the circumstances under which contracts must be awarded by international competitive bidding, local competitive bidding, or other methods, which in turn determine the need for WB prior review. / As with all WB recipient-executed trust funds, the implementing entity will be required to maintain adequate financial management systems, prepare annual financial statements in accordance with accounting standards acceptable to the Bank, and have these statements audited by independent auditors acceptable to the Bank. The implementing entity is also required to submit interim financial reports acceptable to the Bank. Each WB recipient-executed trust fund operation involves a Financial Management Specialist who reviews financial management compliance of the implementing entity. / The WB will retain a role for the implementation of the programme, including activity identification, preparation, execution, appraisal and supervision of the activities. A recent evaluation of WB trust funds “encountered no reported instance of financial mismanagement either in the country studies or the random sample”[36]. / Based on the risk rating of the project and the current financial arrangements, it is expected that during implementation, there will be two on-site visits at project sites to ascertain continued adequacy of arrangements, supplemented by desk reviews of Interim Financial Reports and audit reports. The financial management supervision mission’s objectives will include ensuring that strong financial management systems are maintained for the project throughout project tenure. In adopting a risk based approach to financial management supervision, the key risk areas of focus will include assessing the accuracy and reasonableness of budgets, their predictability and budget execution, compliance with payment and fund disbursement arrangements, and generation of reliable financial reports.
H. How will expenditure be monitored, reported and accounted for? / Reporting will follow the framework agreement requirement between DFID and the World Bank. Reporting will therefore be structured in the following way: / Activity Progress Reports provided by Task Team Leader (TTL) The Bank's standard reporting commitment to donors is to provide: i. An annual consolidated report on the progress of activities financed by the contributions. ii. A completion report on the activities financed by the Trust Fund, within six months of the End Disbursement Date. / These reports are prepared by the TTL, sent to the donors, and filed in IRIS/WBDocs under the Trust Fund Number. 2. Financial Reports (provided by CTRTF) The Bank's standard reporting commitment to donors is to provide: i. Current consolidated financial information related to receipts, disbursements and fund balance. ii. Final financial information related to receipts, disbursements and fund balance, within 6 months after all commitments and liabilities under the trust fund have been satisfied. This information is provided automatically in a standard format in the Client Connection – Donor Center (the Bank’s external website). It is updated on a daily basis with information as of the previous day and a PDF of the “Trust Fund Financial Report” is provided as of each month-end. (www.clientconnection.org) / The financial reporting will include full details of expenditure against agreed budget lines. There will be a clear link between expenditure and activities carried out, themselves linked to expected results within the logframe. / Regular DFID field visits will be carried out. A physical check of assets will be carried out during field visits.
I. Are there any accounting considerations arising from the project? / Annual audited accounts for the trust fund will be required from the implementing partner to be carried out by an international audit firm following World Bank framework agreement rules. Any audit recommendations will be monitored along with the quarterly work plans to be submitted to DFID.
[36] Trust Fund Support for Development. An Evaluation of the World Bank’s Trust Fund Portfolio. Independent Evaluation Group. 2011. p.51.

Management Case

A. What are the Management Arrangements for implementing the intervention? / DFID will have overall management oversight of the programme through the MoU with the Bank. Day-to-day responsibility for management and fiduciary risks lies with the Bank which is responsible for sub-contracted partners. The management arrangements with the MEST will be detailed in a separate MoU. / The Trust Fund will be administered by the World Bank education team within the Africa Region. Because of its hybrid design, bank-executed activities will be directly managed by the Africa Region Education team while its recipient executed activities will be the responsibility of the Ministry of Education, Science, and Technology (MEST) with regular clearances provided by the World Bank. Fiduciary and procurement reviews will be carried out regularly, at a minimum semi-annually, as part of supervision missions. / Regular implementation support in the areas of procurement, financial management, and project administration will be provided by members of the Bank team who are based in the country office. Additionally, support on issues related to safeguards will come from Bank staff based in regional offices, with knowledge of the Sierra Leone portfolio and cross-cutting issues. Twice annually (minimum), technical support missions will be carried out, focusing on specific elements of the operation and bringing international expertise as needed to ensure high quality results. These experts will also be used to reinforce the technical capacity at the national level. About 15 months after effectiveness, a comprehensive mid-term review will assess the programme’s overall progress and make any necessary recommendations (and follow on actions) to the Ministry. / Technical input will be provided as certain activities get underway. International expertise will be provided to help the Government develop the necessary monitoring system, prepare the relevant reports and address capacity issues along the way. / The programme will be overseen by a Steering Committee including representation from MEST, Ministry of Finance, the World Bank, DFID SL and relevant development partners. The committee will be co-chaired by MEST and WB. This Committee will meet quarterly. / DFID will meet monthly with the WB to ensure that implementation of the programme is on track. The WB will consult MEST and DFID on major technical/programmatic issues. DFID will be closely and systematically involved in WB review missions including drafting of ToRs, participation in key meetings and receiving the mission aide memoire. / DFID and the WB will jointly organise annual reviews for the programme which will assess achievements against the logframe, the evolution of risks identified in the risk matrix, and the validity of assumptions made in the theory of change. / Coherence with other DFID Education programmes / The ISIS programme also contains a component for capacity development and systems strengthening. A steering committee is planned to co-ordinate the activities of ISIS with the ESP and involve the MEST in the management of ISIS. To ensure coherence the capacity development component of ISIS will be transferred from the ISIS Steering Committee to the trust fund steering committee. / Coordination with other donors will be achieved through representation on the steering committee and reports shared with the Education Donors group in Sierra Leone. / Duty of care / The World Bank is considered to have adequate systems to ensure duty of care for its personnel and for the health, safety and security of such persons and their property.
B. What are the risks and how these will be managed? / There are risks at the political, implementation and management levels. / At the technical level there is support for reform however, the political leadership to make the required changes to create the conditions for reform is less clear cut. There have been important and encouraging decisions recently, such as the removal of 4,000 unverified teachers from the official payroll and agreement to establish a Teachers Service Commission to manage teachers. / The poor performance of the ESSF is indicative of the challenging operating environment and the risk of implementation failure. However, the ability of the World Bank to turn around the performance of the EFA-FTI fund through its management of programme activities shows what can be achieved with strong and effective fund management. / Risk Likelihood Impact Mitigating Actions Timescale / Lack of political leadership and will M H Build the ownership of the MEST for reform through the trust fund / Maintain the improvement in MEST donors relations / Use the collective influence of the Educations Donors group / Establish a monitoring and reporting role for the Education Development Partners in the delivery of the ESP / Ensure that the budget support Performance Assessment Framework is closely aligned to the ESP L / Fiduciary Risk H H Selection of World Bank to manage the fund / Strong and robust management and supervision arrangements / Clear consequences for the programme if fraud or corruption is identified / Application of DFID-SL anti-corruption strategy where appropriate L / Lack of technical capacity in the MEST to deliver the scope of change M H Early assessment of technical capacity linked to the CDS as part of ISIS / Close management by World Bank, MEST and DFID of implementation against agreed plans and key performance indicators to identify issues early / Availability of funds to support areas of technical need L / In ability to recruit appropriate MEST staff M H Funds available to incentivise recruitment / Alternatives to provide short term consultancy to address short term gaps M / Slow implementation & funds under utilised H H Using the lessons learnt from the ESSF contained in the final report to address weaknesses / Appointment of World Bank to manage the fund / Leveraging other donor contributions to spread the risk and increase the influence / Close management arrangements M / World Bank not performing adequately L H Close monitoring by DFID of programme performance. / DFID sign off on the PAD / Annual and midterm reviews M / DFID SL will monitor the level of risk through the regular management cycle of reports and meetings as well as through quarterly performance against agreed key performance indicators (KPIs). KPIs will be developed and agreed and guide quarterly steering committee meetings. Along with the regular cycle of financial and management reports they schedule of KPIs will provide clear evidence, at an early stage, of increases in the level of risk associated with the successful implementation of the programme
C. What conditions apply (for financial aid only)? / This does not apply.
D. How will progress and results be monitored, measured and evaluated? / Results and progress will be measured and evaluated using a variety of strategies. / The intervention will establish the monitoring and data generation and collection mechanisms for tracking the progress of the ESP in achieving its targets. The rate of progress towards these targets and reporting against them will form one of the monitoring strategies. / In terms of the specific progress and results of the fund, a schedule of key performance indicators linked to the strategic objectives of the fund will be developed with SMART milestones that will be reported against at quarterly steering committee meetings. This will constitute the small steps that need to be accomplished at quarterly intervals to achieve the objectives of the intervention. / A number of stand-alone evaluations, or programme evaluations of development partners have been planned for the period 2013-15 and these will provide independent evidence of the impact of the intervention. As part of the DFID ISIS programme, it is planned to evaluate the elements of the CDS managed by UNICEF, this can be extended during the inception period of the evaluation to be broader and include the trust fund. / The World Bank PAD will add further strategies to how the intervention will be monitored, measured and evaluated.
Lograme / Quest No of logframe for this intervention: