Strengthening Emergency Preparedness and Response Capacity in Kenya

Intervention summary

What support will the UK provide?
UK will provide up to £1 million over three and a half years between December 2014 – May 2018, with the possibility of access to an additional £500,000 for emergency response activities should needs require (contingent on available resources)

Why is UK support required?
Kenya faces a range of disaster risks, including droughts, floods, landslides, conflict and terrorism. Whilst drought and often associated food price shocks affect most people, floods, conflict and other disasters still affect 100,000s of people every year, leading to loss of life, suffering and loss of dignity and livelihoods. The poorest and often disabled, children, elderly and women are disproportionately affected by these disasters. Ongoing climatic variability, urbanisation and political tensions mean disaster risks are likely to continue to evolve and unlikely to reduce in the short term. / The Kenyan Government (GoK) holds primary responsibility to reduce and respond to the disasters and the emergency needs of its population, but clarity on: policy; institutional responsibilities (especially post devolution); capacity; and financing are still evolving. Gaps in emergency preparedness and response remain – especially following conflict and other sudden onset disasters. Civil society, including the Kenya Red Cross Society (KRCS), and international donors have a key role in accelerating the development of these systems and capacity. There is good and growing evidence regarding the enhanced value for money of investing in disaster preparedness, rather than just response and this is one key tangible aspect of the resilience agenda. / UK support is therefore needed to both ensure the needs of communities and individuals are met in a timely and effective manner, but also to strengthen domestic Kenyan emergency preparedness and response capacity - thereby reducing the need for future external support. DFID will fund the British Red Cross who will provide oversight and technical support to implementation of activities by the KRCS.

What are the expected results?
The impact of the UK’s support will be to save lives, reduce suffering and maintain dignity of people affected by disasters in Kenya / The priority outcome: enhanced timely and effective Kenyan response to small and medium disasters / Overall response effectiveness, coverage, quality and timeliness improved / Direct support to relief response to over 3,400 men, women and children per year / Three main outputs and examples of key activities are: / Output 1: Increase in Kenyan capacity to prepare and respond to disasters / Output 2: Increased response efficiency and accountability / Output 3: Increased learning and technical capacity

Strategic case

A. Context and need for DFID intervention / What are the major disaster risks and needs now and how might this change? / Fig.1: Natural hazards in Kenya (UNDP, 2004[1]) / Kenya is vulnerable to a range of hazards, including droughts, floods, landslides, fires, geophysical and epidemics (see Fig 1). Seasonal climatic hazards - especially drought (and often associated food price shocks) have the largest impact geographical spread and socio economic impact[2]. / Kenya is rated high on DFID’s global humanitarian risk register, but vulnerability to disasters is not uniform geographically, or across income groups. Kenya’s arid and semi-arid lands (ASALs) are most exposed to drought and host the most vulnerable populations with the highest poverty rates. Food insecurity and rates of acute malnutrition routinely rise above emergency thresholds. Seasonal rains routinely cause floods in riverine and low lying communities, destroying property, roads/bridges, flooding schools, homes, livelihoods and causing displacement (over 200,000 in 2012) and loss of life. Post-drought flooding also often affects normally dry ASAL counties. / Kenya is also vulnerable to conflict and terrorist attacks. The 2013 elections passed relatively peacefully (unlike 2007/8), but clashes have increased since (over 200,000 temporarily displaced in 2014). They often involve traditional disputes over resources, but are politically instigated and exacerbated by manipulation of devolution politics. Kenya is also host to nearly 600,000 refugees. / Geophysical risks are relatively low[3], but Kenya remains vulnerable to other disasters, including landslides in highlands, fires or chemical disasters in urban areas and epidemics throughout the country (e.g. polio etc.). / The poorest routinely suffer the highest socio-economic impact of disasters, because they either most exposed (e.g. living on poor quality flood prone land or congested fire prone informal settlements); have least capacity to withstand (not insured or least adaptive livelihoods and unable to pay to travel out of conflicts); and live in areas where the state disaster management capacity (including emergency response) is weakest. / Vulnerability is not uniform at household level. Disasters can have a disproportionate impact on children and women (due to risk of injury or death from clan fighting, sexual violence and disruption to household food security, health services and education). Children under five years of age (and also pregnant and breastfeeding women) are at specific risk of morbidity and mortality. However, the elderly, those with specific disabilities and marginalised groups may also be at additional risk due to inability to flee to safety insecurity/floods / Kenya’s disaster risk profile is evolving, but not reducing. Many poor Kenyans are already struggling with current climate variability, but future climate change is likely to exacerbate the risk of extreme weather events. Without good mitigation measures, existing conflict risks could intensify and spread in the run up to the 2015 elections. The rapid rate of urbanisation suggests that an increasing population may be at risk in informal settlements. / How are resilience building efforts (and specifically emergency preparedness and response) organised and how is it changing? / The Kenyan Government (GoK) at national and county level has primary responsibility to respond to the needs of its population, but clarity on policy, institutional responsibilities and capacity is evolving. Through its Vision 2030 Policy GoK lays the foundations for development and the Medium Term Plan also sets out in more detail GoKs efforts to end drought emergencies. A new bill and policy was recently agreed on IDPs, and a draft disaster risk management policy has been prepared. / Clarity on roles/ institutional responsibility for disaster management is evolving, especially in light of the devolution which began in 2013. The disaster management portfolio within the national Government structure falls under the Office of the President and Deputy President. The relatively new National Drought Management Authority (NDMA), under the Ministry of Devolution and Planning, is taking a visible role in leading drought management issues in the ASALs at a national level and supporting County Government efforts. / Arrangements and responsibilities are less clear outside of drought management/ ASALs and for more sudden onset disasters. The draft disaster management policy makes provision of the creation of a National Disaster Management Authority (NADIMA) in charge of coordination of disaster management activities, but to date there still remains some uncertainty over the division of roles and responsibilities (including resource allocation) for rapid onset disasters preparedness and response between County and National authorities. / There are a large number of civil society organisations with some capacity to prepare and respond to emergencies, but most have limited geographical scope and sector capacity. The Kenya Red Cross (KRCS) is the largest, with a nation-wide network of branches, staff and volunteers. KRCS’s response to the 2007 post-election violence (PEV) and various disasters since is widely acknowledged. The KRCS responds through activation of Red Cross Action Teams and utilization of prepositioned stocks, equipment and multi-sector technical expertise in hubs across the country. The KRCS is an auxiliary to the Government of Kenya (GoK) and takes a holistic approach to disaster management. KRCS is recognised by other international humanitarian organisations as the primary responder to disasters in Kenya and is well placed to support devolved county authorities with their disaster preparedness and response planning. / The international response architecture is led by the United Nations (UN), but is transitioning given the evolving context. With support from the UN Office for the Coordination of Humanitarian Affairs (OCHA), the UN humanitarian coordinator chairs the humanitarian partnership team (KHPT), involving UN agencies (WFP, UNICEF, UNHCR etc), INGOs, donors and KRCS. The KHPT provides strategic direction to the international response and usually works within the framework of the Kenya Emergency Humanitarian Response Plan (EHRP) - a multi-year strategy and financing framework. / However, the KHPT recommended a review of humanitarian coordination and financing arrangements in 2013 in light of the evolving situation (incl. absence of large scale election-related violence), recognition that more developmental GoK-led structures were more appropriate to tackle drought risk (see below) and in light of devolution. OCHA’s Kenya country office has now transitioned to a regional office (OCHA East Africa) though retains some coordination capacity in Kenya at a National level. However on-going dedicated capacity will be scaled down with the option to provide surge support if needed. The EHRP was not renewed for 2014 and the UN managed Emergency Response Fund (ERF) has been closed. There remains the option to issue a Flash/Consolidated Appeal in case of a new big scale emergency. / Fig 2. Donor commitments in 2013, OCHA FTS – downloaded on 14 Aug 2014 / Donors normally contributed to past emergency on an annual basis. This support is evolving (for the better) in the ASALs, but investment in emergency preparedness elsewhere, and for disasters other than droughts, remains low. The 2013 KHRP was 56% funded, with donors providing $435 million for activities inside and outside the KHRP (See Fig 2 for a list of top 10 donors).[4] Some 60% of this funding was allocated towards refugees. However, since the 2011 crisis, many donors (EU, DFID, World Bank, AUSAID) are making longer term investments to support systemic drought-related emergency preparedness and response in the ASALs (e.g. the Hunger Safety Net Programme). / Following the end of the KHRP, donors produced a joint paper articulating that future financing for likely small and medium scale disasters (not droughts or refugees) would be most effectively channelled through the KRCS in the first instance (with the option of funding others should KRCS capacity be exhausted). Donors supported KRCS in preparation for possible election-related violence in 2013, but there have been no significant donor investments in emergency preparedness since, with most waiting until a disaster occurs to fund. / Why does DFID need to respond further, what results achieved to date and what needs to change? / Given disaster risks and needs, DFID Kenya is prioritising humanitarian and resilience efforts in the ASALs[5]. The existing portfolio includes a range of multi-year programmes (e.g. hunger safety net, nutrition, health, livelihoods and governance/security) aimed at strengthening the resilience of vulnerable populations to droughts and other shocks, but also to build sustainable systems that if necessary can be financed by GoK. DFID also has a £44m programme (2012-15) to support refugees across Kenya. Some of these programmes are investing in efforts to prepare and respond to disasters. / Whilst such investments contribute to multi-hazard disaster preparedness and response, many needs will still go unmet – especially following conflicts and sudden onset disasters. Ongoing DFID programmes can contribute (e.g. Nutrition programme provides services to those displaced by recent violence), but they are often constrained from fully responding due to their: geographical focus (e.g. only active in parts of the ASALs, but needs are elsewhere in the country); response modality (fast response in difficult (insecure) operational conditions may be required, but ongoing activities focused on building sustainable systems are ill prepared for such a role); and sector focus (e.g. shelter, WASH, protection and food assistance (beyond four focus counties) are not covered). / Other global DFID investments may also help, but are limited in scope and size. DFID centrally is planning support to INGOs in Kenya through its Disaster Emergency Preparedness and Response programme (£3m over three years across five countries and sixteen NGOs, but not KRCS and only targeting staff training). Support is provided centrally to the Red Cross Movement, for example through a Programme Partner arrangement (PPA) with the British Red Cross Society (BRCS) (£1.6m/annum and scored A in last two annual reviews) and core funding with International Federation of the Red Cross (IFRC) (£8m/annum and scored B in last annual review). However, these programmes are spread globally and unallocated to Kenya. Finally, DFID is planning matching grant funding with BRCS in Kenya, but focused on longer term development in the water and sanitation sector. / Remaining gaps are unlikely to be filled in the short term by GoK at national or county level. Private fund raising is increasing, but external donor funding and civil society operational support is required. GoK ownership of emergencies and disaster management is evolving and increasing, but gaps in clarity, resourcing and capacity remain. Even if GoK funding increases, continued CSO operational support will be required. / UK policy and plans provide a justification for an additional DFID response. DFID response is consistent with: / DFID Secretary of State Speech: “A humanitarian system for the 21st Century” (2014)[6], which highlighted keys areas requiring greater focus, including: emergency preparedness; for countries to deal with disasters themselves (including through support to domestic civil society); efforts to strengthen accountability; and an increasing role for cash-based responses / the DFID Business Plan to “ensure that the basic needs of people whose lives have been ruined by disaster are met, and to ensure that emergency relief aid is targeted at those areas where the threat to life is most severe, the extent and the depth of suffering greatest and response capacities of communities and authorities are most limited”; / Humanitarian Emergency Response Review (HERR), UK’s Humanitarian Policy; and position paper on resilience (2011); / DFID Kenya Operational plan (2013 update) and DFID Kenya Humanitarian Pillar Contingency Plan / The Kenya Humanitarian Country Team and multi-donor position paper on transition / Wider HMG objectives, as UK consular objectives following disasters or terrorist attacks in Kenya may be partially met by the domestic Kenyan emergency response system / DFID has previously supported emergency preparedness to conflict/ sudden onset disasters in Kenya, with some success. In 2013, DFID provided £0.51m through the British Red Cross (BRCS) to support a multi donor preparedness programme with KRCS in advance of national and local elections. DFID funding supported the training of more than 400 KRCS staff/volunteers; procurement of non-food relief supplies sufficient for over 10,000 people; and the prepositioning of these supplies in strategic hubs/hard to reach areas. The programme completion report for this component of DFID’s election programme scored an A+ (outcomes moderately exceeded expectations). Some residual stock from this response remains unused given a calmer than feared election period (these issues discussed in more detail in the financial/management case). An independent review of KRCS’ 2013 response identified areas requiring further strengthening including: sustaining contingency planning, staff skills and preparedness; improving systems, tools and accountability, and improving learning. / Given anticipated future risks, additional DFID support could offer best value for money if it: continues to support emergency preparedness, rather than just response; if provided over a multi-year basis; and if it has the flexibility to respond to possible additional spikes in need. The evidence base is strengthening globally that emergency preparedness and multi-year programming offer better value for money in meeting ongoing and anticipated needs, compared to annual post disaster approaches[7][8]. Further spikes in need beyond the “usual” are predictable and response timelines, costs and associated suffering, mortality, and livelihood loss can be reduced through preparedness, but also a predictable scaled up donor response when needed. The Independent Commission for Aid Impact recommended this approach following its review of DFID’s emergency response to the 2011 crisis in the Horn of Africa[9]. There is emerging best practice in implementing such measures, including through the establishment of “internal risk facilities” or IRFs. / What is the proposed DFID portfolio size and approach? / DFID support should be guided by humanitarian principles, be realistic given our capacity, proportionate, but still have sustainability as an explicit objective. In line with the principle of impartiality, DFID’s humanitarian support through this programme should be directed to wherever needs are greatest and not existing DFID strategic geographical, sectoral or programmatic interests. However, DFID’s capacity to engage on systemic and broader resilience efforts beyond its current focus on drought in the ASALs is limited. DFID support should therefore be: proportionate; flexible enough to respond to increasing needs; focused on civil society and emergency preparedness, rather than GoK-wide system strengthening and resilience; and be of sufficient scale to add value and capacity, whilst not reducing domestic accountability for action and funding. / Despite the focus on emergency preparedness, rather than broader resilience and risk mitigation, this programme should still consider issues of sustainability as far as possible. For example, the focus should be on strengthen domestic Kenyan capacity to prepare and respond to disasters, avoid building costly systems which are difficult to sustain and strengthen systems of accountability such that other donors (including Kenyan public and private sector) feel more confident to support in the future. / A DFID contribution of £1,000,000 over three and half years, would amount to approximately 3% of KRCS disaster management spending in 2013 (this includes KRCS refugee and drought spending) or 0.2% of overall KHRP’s donor funding outside of refugees (Nb. no KHRP data available for 2014).
B. Impact and outcome expected / The impact of the UK’s support will be to save lives, reduce suffering and maintain dignity of people affected by disasters in Kenya / The priority outcome: enhanced timely and effective Kenyan response to small and medium disasters / Overall response effectiveness, coverage, quality and timeliness improved / Direct relief response to 3,400 men, women, girls and boys per year / Three main outputs and examples of key activities are: / Output 1: Increase in Kenyan capacity to respond to disasters / Biannual contingency planning implemented and information alert system enhanced / Commodity procurement of key relief commodities, stockpiling and prepostioning (or preparedness if cash) undertaken to reach 6,800 men, women, girls and boys per annum / Training of female and male staff and volunteers in assessment, analysis and response / Conduct assessments, analysis and reach most vulnerable with assistance / Output 2: Increased response efficiency and accountability / Development and dissemination of appropriate tools and guidelines / Development and dissemination of a beneficiary complaint mechanism / Mainstreaming of value for money skills / Output 3: Increased learning and technical capacity in disaster management / Conduct a technical capacity assessment and develop a capacity development strategy / Develop clear systems and procedure for sharing emergency response information with other humanitarian agencies, supporting partners and the wider public / Use information from response operations to inform policy and practice / Develop evidenced based case studies to inform humanitarian action
[1] UNDP (2004) Kenya Disaster Risk Profile
[2] DFID (2013) Hazard Risk Assessment
[3] GSDRC (2013) Assessing seismic risk in Kenya
[4] Downloaded from OCHA FTS http://fts.unocha.org/pageloader.aspx?page=emerg-emergencyCountryDetails&cc=ken&yr=2013) on 14 August 2014
[5] DFID (2012) DFID Kenya Resilience Strategy
[6] https://www.gov.uk/government/speeches/justine-greening-a-humanitarian-system-for-the-21st-century
[7] Courtenay Cabot-Venton (2013) Value for Money of Multi-year Approaches to Humanitarian Funding
[8] Kellet and Peters (2013) Dare to Prepare: taking risk seriously, ODI
[9] ICAI (2012) UK Emergency Response in the Horn of Africa downloaded from http://icai.independent.gov.uk/wp-content/uploads/2012/09/ICAI-report-FINAL-DFIDs-humanitarian-emergency-response-in-the-Horn-of-Africa1.pdf

Appraisal case

A. What are the options: / There are three options for addressing the issues set out in the strategic case: / Option 1: Funding through British Red Cross Society (BRCS) / To support a multi-donor programme to strengthen the emergency preparedness and response capacity of the Kenya Red Cross. / Option 2: Funding through another organisation, including the UN or NGOs / To support a UN agency or NGO consortium (e.g. DFID will contribute to a UN agency appeal. DFID funds a NGO consortium) to support emergency preparedness and capacity strengthening. / Option 3: Do Nothing / DFID does not provide further funding for preparedness and response, but continues with existing investments, geographical and sector focuses. Other donors may support and national organisations (e.g. KRCS) are trying to work towards self-financing and sustainability. / However, sustainability is not realistic in the next three years. Furthermore, support through other DFID channels focused on drought responses will not reach many flood, conflict or other disaster affected populations. Other donors still look to DFID for leadership on humanitarian issues and without UK support it is unlikely that humanitarian needs will be met and our desired outcomes and impact will be achieved. Not intervening would therefore mean that the UK does not meet its policy and operational objectives. This option has therefore been discounted. / There are other design questions to be considered within options 1 and 2 / How should these mechanisms take into account issues of gender equality, age, disability and minorities / Whether to provide multi-year funding or just respond to adhoc UN , INGO or Red Cross appeals / How flexibly to provide funding - in terms of earmarking, disbursement tranches and whether to include an internal risk facility / _______________________________________________________________________________ / B. Cost and Benefits / Administrative costs and overheads / Whilst KRCS would implement all activities within the proposed BRCS/KRCS programme, DFID policy is to fund national Red Cross societies (e.g. KRCS) through the BRCS. This allows an additional level of monitoring/quality assurance and technical support. It is also coherent with the Red Cross principle of unity, avoids National Societies competing within a given territory and allows DFID/BRCS engagement to be consistent and for a robust relationship to develop in a way that fragmented engagement would not. Overhead administrative charges through the BRCS (who maintain some presence in Kenya) are low (1%) on top of KRCS admin overhead of 7%. / KRCS relies on national staff and costs are therefore routinely relatively low compared to other international actors and as a result the ratio of funding allocated to outputs compared to overheads (including staff programme management costs) are relatively good – around 65% for the proposed programme. / BRCS will contribute a minimum of £150,000 of their own funds towards the programme, while working to source other donor support. KRCS lacks flexible funding to allocate against such capacity development programmes, but both KRCS and BRCS will still contribute through unbudgeted staff and technical support - financed internally or through other sources. Other Red Cross Movement partners may also participate. Therefore the value of the intervention is substantially higher than the financial cost to DFID. / International NGOs (INGOs) charge administrative overheads of approximately 7%. However, INGOs also include more expensive in-country international staff and normally work with national partners who also require an overhead. Experience suggests that managing an NGO consortium requires considerable DFID programme officer input – this may prove cost effective if the consortium is of a sufficient size, but will offer less value for money if small. / United Nations humanitarian agencies include an administrative overhead of 7-13% for managing DFID funding. Additional indirect administrative costs are incurred when channelling funds through the UN because their NGO implementing partners also include administrative charges. DFID analysis in 2012 suggested that that £2 million of funding channelled through the UN rather than to NGOs directly may have additional indirect administrative costs of around £100,000. / Legitimacy, access, capacity, effectiveness and sustainability / KRCS is an auxiliary to GoK and also the GoK/UN/donor recognised first-line responder to sudden onset disasters. KRCS’ operating model (less reliant on international staff than others) and perception among communities (as neutral and impartial) has meant it has been able to access areas which are relatively insecure and where international humanitarian agencies (UN/INGOs) have struggled. / KRCS’ multi-sectoral approach enables it to respond to all needs, but its experience on cash based responses is limited. However, its geographical coverage is unsurpassed – facilitating a fast response and coordination with devolved county authorities. / KRCS has a core group of skilled Kenyan disaster professionals, but is reliant on a broader network of volunteers, which is KRCS’ strength in terms of sustainability and speed of response. However, it can also be its weakness as some volunteers may lack skills and experience (Featherstone, 2014). However, BRCS, other participating national societies and the IFRC can also provide international capacity and support. / In addition to international donors, KRCS has developed perhaps the most advanced system of resource mobilisation of any Red Cross national society in Africa, drawing on the private sector, its own private sector enterprises and the wider Kenyan public[10]. In the longer term, there is some hope that this, together with potential GoK national or county resources, could provide a more sustainable source of support for small and medium disasters. / KRCS’ response to recent disasters is good. An independent review of its overall multi-donor funded response to the 2013 elections found cause for “considerable credit…..contingency planning was thorough…collaboration in planning and response was impressive and KRCS’s ability to deliver timely and effective response was in evidence during the election period” [11]. / Outside of Kenya, DFID Uganda is providing £2.8m in support to a similar programme with BRCS and the Ugandan Red Cross (URCS). This programme has scored A or A+ during its annual reviews over the last three years. Key learning from this programme include: the need to have a good inception period; to be realistic over timescales to design and incorporate new systems; the need to further strengthen VFM measures; and to not underestimate the risks to the programme. / Some benefits of UN/INGOs are that they can draw on lessons from around the world, international operational expertise, capacity and resources. However, this support is reliant on international donors, which can result in delays and is unsustainable in the longer term. In 2010/11 DFID supported the UN’s Emergency Response Fund (ERF) in Kenya, which played a useful role in financing effective drought response activities, but was slow and therefore unlikely to perform well in more sudden onset disasters. The ERF has since closed. / The UN and international NGOs have better developed systems of coordination, monitoring/evaluation and donor reporting than the KRCS – an area that the recent review found requiring further development. / The UN has capacity and a specific mandate to not just respond to crises, but also press for and support increasing GoK investments in disaster resilience, including response. Whilst KRCS is not perceived widely as a public advocacy organisation, it has the potential to play an important role (through often more private advocacy) with GoK at national and county level and the wider Kenyan public. As a respected Kenyan organisation, its voice will often be heard more than some others. / Other design questions: / How should these mechanisms take into account issues of gender equality, age, disability and minorities / Ongoing humanitarian efforts in Kenya do try to focus on where needs are greatest and take account of the differing needs of specific groups, but further efforts are needed. Whichever appraisal option is chosen, additional efforts are needed: / to ensure that preparedness and relief responses make even greater efforts to take into account the differing impact of disasters on women, girls, boys and men, the elderly, disabled and marginalised or minority groups. Appropriate responses and interventions should be tailored to specific needs. / to strengthen the evidence base by: undertaking a review of the appropriateness of past interventions; what can be learnt; and undertake specific analysis of potential impact of an increase in cash programming on household dynamics / to integrate lessons into revised response policies, contingency planning and tools / to undertake a training needs assessment of staff/ volunteers and integrate the findings into capacity development strategy and training activities / to disaggregate key baseline and response data by sex and age / to ensure responses are guided by humanitarian principle of impartiality – resources are prioritised where needs are greatest and most appropriate activities / Whilst not the primary objective of the programme, activities should also have some positive impact on social inclusion and the influence of previously marginalised groups. This can be achieved by: / Considering the impact of interventions on gender equality (the impact of the intervention on women/girls and men/boys and the relationship between them). The degree of consideration should be proportionate depending on the context and assistance in question. / Establishing beneficiary communication and complaint mechanisms which are accessible to all / Promoting the active participation of women in leadership roles through involvement in leadership training and inclusion in local disaster committees to different groups / Whether to provide multi-year funding / Annual funding includes some benefits, including the ability to allocate funds more flexibly (UK not locked into long term agreements with partners); the possibility of easily changing partners if performance is poor; and the ability to direct and adapt short term assistance to target areas flexibly. / However, multi-year funding can offer significant benefits, including allowing partners to: more effectively plan over the medium term; invest in and retain key skilled staff; and maintain the capacity/flexibility to respond to needs as and when required. It can also result in significant better value for money, for example through reduced procurement and inland logistics costs, reduced staff costs, savings on proposal writing and reduced currency risk. Our partners have expressed strong support for a multi-year approach and this has become best-practice across DFID. / Whether to earmark funding within the programme and whether to provide a risk facility / Earmarked funding can help ensure adequate financing of key DFID priorities – especially if the overall donor response does not fully meet needs, and makes it easier to attribute specific results to DFID support. Un-earmarked funding on the other hand provides greater flexibility for partners to allocate resources where they are needed, especially in a context where other donors are earmarking their assistance. / If there is a reasonable level of confidence in partner systems and prioritisation, unearmarked funding is preferable. However, in this context, it may be useful to agree at the implementation/project proposal stage some broad parameters for funding reflecting the main cost drivers. In the 2013 elections preparedness most funding was earmarked to stocks, logistics and training. / Whilst resource requirements for output two and three are likely to remain constant throughout the lifetime of the programme, those required for output one (and specifically for actual responses - such as commodities/cash etc.) will vary depending on the context and levels of need (could be better or worse; more or less). Figure 3 below outlines three funding options for the programme: / Fig. 3 / Outlook/ scenario Funding approach Advantages Disadvantages / Positive/ Best Only commit funds now for outputs two, three and those components of output one which are not dependent on contextual changes. If needs increase then release funds for preparedness and response No unused contingency stock or resources held by DFID partners. No improvement in preparedness and little benefit of multi-year programme. Responses likely to be slow given time to agree additional funding when disaster strikes and plan, procure and preposition stock etc. / Realistic/ Most likely Commit funds now for outputs two, three, but also one – including resources sufficient to meet a reasonable UK burden share of small/medium size disasters. Reasonable level of preparedness. Actual requirements may be more or less – leading to either stock or resources sitting with partners or a slow response / Pessimistic/ worst case Commit funds now for outputs two, three, but also one – including resources sufficient to meet a reasonable UK burden share of large scale disaster based on the worst case scenario Good level of preparedness for even major disasters DFID resources may not be used (leading to criticism of payment in advance of need). Stock shelf life may expire. / The main driver for this programme is the reasonable assumption that small and medium scale disasters will occur during the next 3.5 years and so planning for the most likely scenario would appear to offer the best value for money and ensure the most effective response. The risks associated with this option (if context is better or worse than expected) can be mitigated by: / Regularly reviewing the context, actual requirements and resource utilisation under output 1. Findings should allow disbursement plans to be lowered if situation better than expected / Having a preapproved risk facility, which allows DFID to channel additional funds to scale up components of output 1 if the situation is worse than expected, and a proportionate additional UK response is justified. / Preferred Option / The preferred option for this business case is therefore: / Support the British Red Cross programme with a budget of £1,000,000 over 3 and half years, including a six month inception phase / This budget equates to approximately 50% of the overall BRCS/KRCS programme request. BRCS will contribute £150,000 of their own funds and seek other donors to cofinance the residual programme amount. / Support will be initially unearmarked against the BRCS/KRCS programme. However, if the BRCS/KRCS programme is not fully funded within the inception period (or if other donors attempt to tightly earmark their own funding), DFID will reconsider earmarking its support to ensure priority objectives and needs are met. / Take the “most likely” outlined in para 53-54. Figure 4 below shows the anticipated resource allocation against each output within the BRCS/KRCS programme - highest proportion for output 1 and within this to direct relief delivery. These ratios also provide a guide should the BRCS/KRCS programme need to be reduced in size (if no other donors cofinance) or DFID decides to earmark. / Fig. 4 / Output Approx % of DFID funds / Output 1 Increase in capacity to respond to disasters 73% (of this, 70% for direct relief) / Output 2 Increased response efficiency and accountability 21% / Output 3 Increased learning and technical capacity 5% / To mitigate the risks of taking the “most likely” scenario, DFID/BRCS should regularly review and if necessary revise disbursement schedules downwards if the situation better than expected. DFID should also have a pre-approved risk facility of £500,000 allowing additional resources to be channelled through BRCS if the situation worse than expected additional resources are needed and available. If Red Cross capacity is exhausted, DFID may also consider other channels for the risk facility (e.g. UN, INGOs or direct DFID procurement). / BRCS/KRCS will prioritise the use of DFID response resources under output 1 on small and medium sized disasters (i.e. not drought or refugees). This is due to the specific niche of the KRCS in responding to such disasters and the availability of larger DFID and other donor resources through mechanisms other than Red Cross. During the inception phase, BRCS/KRCS should produce and agree with DFID a brief paper which details the criteria used to decide response priorities and the KRCS governance of response funding through this programme. / An inception phase will be required to develop baselines and further define DFID attributable results
[10] Drummond and Crawford (2014) Humanitarian crises, emergency preparedness and response: the role of business and the private sector: Kenya case study
[11] Featherstone, A (2014) 2013 Kenya General Elections: KRCS preparedness, planning and response review

The Theory of Change for the preferred option is: / If KRCS….. If KRCS…. If KRCS…. / establish an effective disaster surveillance system / and …. / use analysed information, knowledge and understanding to prepare and update contingency plans regularly / and …. / recruit and continuously train motivated staff and volunteers / and …. / ensure stocks and financial resources are available to respond / and …. / have clear and accountable systems for managing resources have clear policies, procedures and guidelines / and..... / review and update systems to record and share early warning/early action information / and …. / recruit and continuously train motivated staff and volunteers / and .... / ensure that SOPs and protocols are implemented and monitored / and …. / have clear systems for communicating with disaster response teams / and …. / involve beneficiaries in response operations and ensure mechanisms exist to ensure their voices are heard / and .... / strive to improve the value for money of our work document its work / and …. / develop and share evidenced based case studies and good practices / and .... / invest time to reflect on its work / and …. / participate in structured fora for sharing and reflecting on practice / then KRCS…. then KRCS… then KRCS…. / will have an increased capacity to prepared and respond to disasters r will be more efficient and accountable in its disaster response operations will be able to use learning to improve its work and influence others / and as a result there will be … / an enhanced timely and effective Kenyan response to small and medium disasters / Additional donor risk financing if a major shock / Cofinancing from other donors / Up to / £1,000,000 DFID resources to BRCS / BRCS funding and technical support to / KRCS
C. Strength of the evidence base / Evidence rating Medium / There is good and growing global evidence regarding the cost effectiveness of multi-year support to emergency preparedness and response. There is good evidence regarding the effectiveness of the Red Cross Movement globally and also at Kenya level. / There are some gaps regarding: / Value for money of different interventions and preparedness measures for sudden onset disasters in Kenya. The preferred option will therefore use the existing BRCS VFM planning tool to improve country level analysis, planning and monitoring, with specific VFM metrics to be established during the inception phase / Knowledge regarding the differing needs of disaster affected groups in Kenya, the most appropriate responses and the skills/ capacity of KRCS to undertake these responses. The preferred option will undertake a review of past responses, their appropriateness, and a training needs assessment for staff and volunteers / D. Value for money assessment for the intervention / As flagged above, there is growing global evidence of improving VFM of preparedness and response measures, but there are some gaps. However one can argue that: / Economy: Support to preparedness and multi-year support can reduce input costs, by allowing partners to decide when to procure specific commodities according to when prices are lowest, rather than just when donor funding comes available and also negotiate better terms with suppliers given longer term commitments. Following a recent review of DFID’s approach to VFM[12], greatest attention will be paid to economy and key cost drivers (procurement, staffing and logistics). / Efficiency: Support to contingency planning and prepositioning of stock can reduce output costs (e.g. cost per beneficiary reached with assistance). Partners can choose the most cost effective logistics option during periods of low commercial demand, rather than waiting for emergencies to happen when demand and associated prices are high, or when trucking is impossible (given access constraints) and items have to be flown at much greater cost. / Effectiveness: As detailed in the economic appraisal, support through BRCS/KRCS (implementation by KRCS), rather than INGO or UN international actor should also reduce overall cost per outcome. Kenyan partners should have lower overall staff/operational costs and have better access and coverage than international actors for sudden onset disaster responses. This can result in a cheaper and more effective response than would otherwise be possible.
[12] Coffey (2012) A review of DFID Kenya and Somalia’s approach to value for money in humanitarian operations

Commercial case

Indirect procurement
A. Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner? / DFID will support an existing BRCS/KRCS programme to strengthen disaster preparedness and response. DFID will sign a Memorandum of Understanding (MOU) with the British Red Cross (BRCS) and BRCS will be responsible for all associated DFID reporting. BRCS will enter a grant agreement with KRCS who will implement the programme activities (including procurement), with BRCS engaging in strategic discussions and regular programme meetings with KRCS. / The scope to undertake a call for proposals for the delivery of this programme in order to drive commercial advantage is limited because: / KRCS is an official auxiliary to the State and has been designated by GoK, UN/donors as first responder to sudden onset disasters. / KRCS is the only domestic organisation with a sufficiently large nationwide volunteer/staff network and proven capacity to provide a multi-sectoral response, at scale and on time, to sudden onset disasters. / DFID already has positive experience of delivery through BRCS/KRCS in Kenya (component scoring an A+ during 2013 PCR). / BRCS is pre-qualified under DFID’s global Rapid Response Fund criteria and was successfully awarded a Programme Partner arrangement (PPA) in 2011. PPA funding is contingent on BRCS either already having the relevant processes, systems, staffing and practices in place to deliver value for money or had agreed to timed conditions relating to improvements in these areas, would we agree to PPA funding. / DFID centrally (CHASE) is planning support to INGOs staff training in Kenya through its Disaster Emergency Preparedness and Response programme (see strategic case). Further support to NGOs risks duplication, but BRCS and INGO partners CHASE’s programme will be requested to share staff training tools and resources where appropriate. / A 2013 DFID Kenya due diligence exercise gave BRCS/KRCS a green rating. It acknowledged significant investments made by KRCS in strengthening its management, financial (including procurement/ stock management) and operational systems / The level of award is sufficiently low that any prolonged procurement process would not represent good value for money in terms of administrative load for DFID, applicant organisations and would result in a delay in response. / Given a call for proposals is not appropriate in this context, value for money will be assured though other measures: / During the six month inception phase, DFID will further review budgets and logframes to ensure they represent good value for money by assessing against cost comparators from operations elsewhere (and if necessary support from CHASE procurement specialists over procurement comparators and Red Cross institutional leads regarding overhead and staffing cost comparators). / During the inception phase DFID/BRCS will establish key VFM metrics to be monitored during the course of the project and reviewed formally during annual reviews (The programme includes a specific activity to strengthen KRCS capacity regarding VFM and costs) / Funds will be provided in arrears on a six monthly basis on of a statement of financial need. Performance will be reviewed on a quarterly and annual basis. Should reviews find that performance slow or inadequate, we will be able to delay, shift or withdraw funding.

Financial case

How much will it cost, how will it be funded and how flexible does this need to be? / This programme has a budget of up to £1,000,000 over 3.5 years (December 2014 to May2018). Funds will be drawn from within the DFID Kenya framework. The inception phase will review whether any modest amount could be charged as capital expenditure. / If the context deteriorates and needs increase an additional £500,000 virtual risk facility is in principle available over the life time of the programme and could be called on to scale up certain preparedness and response activities under output 1. The management case provides further details regarding the governance of this facility. However, even if triggers are breached, release of IRF funding is reliant on availability of funds (though central contingencies or underspends from elsewhere in DFID’s portfolio) and a DFID calculation of a reasonable donor burden share (i.e. currently no guarantee of funding). / Indicative allocations and forecast profile are detailed in the table below, but may be refined during the inception period and will be reviewed on quarterly and annual basis. / Recipient Financial Year Total Possible IRF / 2014/15 2015/16 2016/17 2017/18 / BRCS £65,000 £300,000 £300,000 £300,000 £965,000 Up to £500,000 / M&E and potential audit costs DFID £10,000 £10,000 £15,000 £35,000 / Total £65,000 £310,000 £310,000 £315,000 £1,000,000 / DFID funds will be channelled through BRCS who charge a 1% overhead and will be responsible for monitoring further downstream spend by KRCS and reporting to DFID. KRCS will charge a 7% overhead. Principle cost drivers are the costs of relief response (cash or commodity procurement and prepositioning) and staffing. The overall ratio of budget allocated to outputs compared with admin overheads and staffing is a healthy 65%. / DFID’s contribution to this BRCS/KRCS programme amounts to less than 50% of the overall £2,051,727 requirements and other support is therefore required. BRCS will put in £150,000 of their own funds (7% of requirements) and other donors have also already expressed an interest in supporting. If this does not materialise, DFID/BRCS/KRCS will review the logframe/budget and priorities and DFID may consider earmarking funds against specific activities and outputs. Whilst the outcome would only partially be met, the programme would remain viable. KRCS will continue to seek alternative domestic funding (e.g. GoK, private) to sustain relevant activities beyond the lifetime of the programme. / BRCS is committed to optimising resources and deriving maximum value from all its income. Income received is kept in high-interest business accounts to ensure best rate of return. Expenditure in major currencies other than GBP is hedged to mitigate against fluctuations in the foreign exchange market, minimising risk of forex losses. / How will funds be paid out and what flexibility is required? / Statements of financial need will be provided by BRCS and payments will be made in in arrears on a six monthly basis. To avoid delays, the funding commitment will be made for the entire 3.5 years and funds will be remitted as per the initial MoU agreement without the need for annual approval. However, the programme will be reviewed on annual basis and funding reduced or stopped depending on performance. / However, it is not just performance, but context, which may impact on disbursements. Whilst unlikely given the disaster risks, expenditure and disbursements may be less than currently anticipated for the response component if the situation is more stable than expected and humanitarian needs less (theoretically feasible that final expenditure within the 3.5 year period could be less than £1,000,000 budgeted). Conversely, if the situation is worse than expected and the risk facility is mobilised, rates of spending could be more than the £1,000,000 budgeted. / Disbursements may also be lower than anticipated given residual resources from previous DFID support. Some £180,000 of NFI funded through the 2013 election preparedness programme remains unused (mostly held in KRCS’ Nairobi central stockpile) because election related violence was less than feared. With DFID approval, some of this stock has been used in response to other disasters since, but stock funded by donors with more restrictive conditions has been distribution first. With DFID approval, KRCS also temporarily loaned some stock to ICRC to support the exceptional South Sudan response. At our request, BRCS has kept DFID Kenya regularly updated on residual stock levels. Following the inception period of the new programme, BRCS will not request funds for commodities/NFI until this residual stock has reduced further. / The annual review will act as a milestone to consider all these aspects, to revise the future disbursement schedule and seek approval for these changes from the senior responsible officer (SRO) / How expenditure will be monitored, reported, and accounted for / Expenditure will be monitored through BRCS quarterly financial and results reporting, six monthly full narrative and financial reporting in accordance with DFID’s humanitarian funding guidelines[13].
[13] DFID funding guidelines: https://www.gov.uk/humanitarian-response-funding

Management case

A. Oversight / DFID carried out a full due diligence assessment of BRCS/ KRCS in 2013 in advance of providing £510,000 for election preparedness and response activities. We judge that assessment made in 2013 remains valid and an additional exercise is not needed in 2014, especially given the relatively short time since the 2013 assessment, the similarity in scope (e.g. objectives and activities) of this new programme and relatively small budget (only £300,000 per annum). / The 2013 DFID due diligence assessment gave BRCS/KRCS a green rating. It acknowledged the significant investments made by KRCS in strengthening its own management, financial (including procurement and stock management) and operational systems, but some medium/low risks were identified. BRCS has actively followed up to ensure KRCS address recommendations made. For example, the management of bank reconciliations has been changed to improve the speed with which they are completed and the finance manual has been updated with, among other things, a requirement that asset verifications are undertaken. KRCS retains a large number of bank accounts, but this is often at donors’ request. / The 2013 audited accounts of the British Red Cross raised no issues of concern. A programme level audit of the 2013 BRCS/KRCS election preparedness programme is planned for 2014 and DFID will be consulted over the TORs. / B. Management and M&E / A DFID Senior Responsible Owner (SRO) will be appointed for the programme and will manage the programme team encompassing advisory and programme staff. BRCS will be DFID’s principle point of contact, including its liaison with KRCS. / Monitoring will rely on formal BRCS quarterly financial and results reporting, six monthly full narrative reporting and annual financial/narrative reporting – all against agreed programme logframe targets. Baselines, targets and methods of measurement for some indicators will be developed during the inception phase. The logframe provides further detail on the data sources for monitoring. / DFID will put in place a quarterly system of meetings, biannual field trips and more expansive annual reviews. If the risk facility is triggered, DFID/BRCS may decide to increase the regularity of such meetings and field monitoring. / Triggers for utilisation of the risk facility will be agreed during the inception period, but may include an emergency of sufficient scale that IFRC/KRCS launch a global appeal and other internal BRCS contingency funding is exhausted. In such a case, the DFID Senior Responsible Officer for the programme will seek approval for the use of the risk facility from the DFID Kenya Head of Office. If approved, DFID will then liaise with BRCS to clarify revised logframe targets (for output 1 and at outcome level), revise the disbursement schedule and adjust the MOU. / An informal coordination group of donors supporting BRCS/KRCS was established in the run up to the 2013 elections (incl. ECHO, DFID, US, Norway, Switzerland and Australia). This coordination facilitated consistent messaging with BRCS/KRCS, avoided duplications and improved accountability. This group still meets and if others support the programme BRCS/KRCS, we will also establish a biannual donor board meeting to review progress. / The draft logframe will be revised during the inception period (including identifying DFID specific attribution within any pooled funding and identifying key indicators that could be easily adapted in the future if additional risk facility funds were channelled through the programme). Approval for the revised logframe will be sought at the appropriate level. / Poor performance or a changing context which means the programme (or certain components) are no longer relevant will result in recommendations being escalated to senior DFID management for the programme and associated spend being revised or ended. The annual review provides the critical milestone for these decisions. / The overall programme has a heavy focus on learning, with a specific objective (output 3), activities and indicators. However, these indicators need to be further defined during the inception to provide a greater assessment of the quality of learning (not just the establishment of learning fora/ products) and how this will be measured. The planned staff skills and training needs assessment should provide a valuable baseline for this work. / No evaluation specific to DFID’s funding is planned. However, a mid-term evaluation of the overall BRCS/KRCS programme is planned and budgeted for. DFID will be consulted over the terms of reference and constitution of the implementing team for this activity. / As discussed earlier, there is no risk of duplication between DFID’s central and country level support to the BRCS/KRCS, but it does represent an opportunity for a more strategic dialogue with BRCS over performance and learning at the HQ level. DFID Kenya will therefore continue to liaise closely with DFID London (and DFID Uganda given their BRCS investments) and explore the feasibility of joint involvement in annual reviews etc. / The timeline for implementation is detailed below: / Activity Timing Purpose DFID staff resources / Inception Dec-May Initial studies, assessments, development of baselines and, finalisation of plans, logframe and budgets. / Produce position paper on criteria guiding utilisation of response resources through this programme / Agree triggers for possible call on risk facility Programme Team (5% hum advisor, 5% senior programme officer; 5% programme officer) / End of inception stocktake May 2015 Assess donor commitments against overall BRCS/KRCS programme. / If not fully funded then negotiate priorities and revise budget/logframe. / If necessary, DFID reconsider earmarking. Programme team / Full implementation June 15 – May 18 Full implementation Programme Team / Mid term evaluation tbc BRCS commissioned mid-term evaluation BRCS / Annual review Nov 15 / Nov 16 / Nov 17 Track progress on results/logframe, VFM and review risks. / Recommendations for programme continuation, alterations and future resource needs/future disbursement schedule 10% cadre support, external consultant or regional humanitarian advisor from Nairobi / Project Completion Report May 18 Assess whether project achievement against logframe 10% cadre support, external consultant or regional humanitarian advisor from Nairobi / UKAid visibility will be supported where possible, but DFID recognises that this will not always be possible, particularly where there are demonstrated security risks for staff and given the specific neutrality and independence of the Red Cross and its emblem. BRCS is exempt from some of the DFID’s standard requirements in this regard. / C. Risks of intervention and how these will be managed / Specific programme risks and associated mitigation measures will be updated during the inception period, and then reviewed formally every six months and during annual reviews. / Risk Likelihood Impact Mitigation / Delays in supply shipments and/or logistical bottlenecks (e.g. rains) Low Medium BRCS/KRCS used to working in this environment and are focused on prepositioning supplies and timing training etc when mobility is possible. / Poor stock management means supplies are spoiled or inefficiently utilised Low Medium KRCS conducts monthly stock count of all supplies. / Specific activity to strengthen stock management policies, systems and processes / Corruption or diversion of supplies – especially at sub national levels Medium High KRCS will maintain records for procurement and distribution of supplies. BRCS will maintain oversight, including on procurement, pre-positioning and tracking of stock funded through this programme / BRCS/KRCS maintain the bulk of DFID-funded stock in Nairobi and balance the benefits of prepositioning stock in more remote hubs with possible increased risks where capacity lower / Implementation of beneficiary complaints mechanism / Political pressure nationally or locally affects impartial targeting Low High KRCS will coordinate its planning and any response with national and local government authorities and other humanitarian actors while, at the same time, upholding the principles of independence (from political influence, manipulation and interference) and impartiality. / Insecurity limits access by KRCS staff Low Medium Previous experience is that KRCS manage to access insecure environments where international agencies have not. / Inflation outside budget range Low Low Supplies will be integrated into routine KRCS pipeline for utilisation in emerging crisis (e.g. floods, adhoc conflicts etc) / Reporting is inadequate to meet DFID requirements Medium Medium BRCS will provide additional support to KRCS on reporting and provide additional assurance. / Staff turnover or lack of engaged leadership Low Medium Involve leadership in programme cycle. All staff in programme provide comprehensive handover notes / Non-compliance of contractual obligations or adherence to organisation policies and procedures Medium Medium Training to staff on policies and procedures / Regular DFID/BRCS/KRCS meetings DFID/BRCS/KRCS meetings / 6 month review by BRCS and establishment of clear Q&A system (including audit) / Lack of other donor support or low replenishment of emergency fund Low High Review mobilisation strategies and involve DFID advocacy as well as BRCS/KRCS / If necessary early review of planned outputs and reprioritisation of budget / As last resort, DFID consider earmarking funds to specific outputs and activities / Major disaster has to be prioritised over system development components Medium Medium Dedicated programme management capacity for the programme / Programme itself will strengthen capacity to respond / Revision of programme timelines as a last resort / Ill-considered humanitarian action inadvertently contributes to conflict risk Low High Interventions guided by humanitarian principles, including impartiality / KRCS has good conflict analysis / Support provide not sustainable and gains in capacity drop off when DFID funding ends Low Low Systems and tools will be designed to be sustained at low cost and without future DFID support / Efforts to strengthen accountability will build donor confidence allowing diversification of funding sources / Additional detail on specific risks and measures taken / Fraud and corruption / Delivering programme interventions in Kenya has risks. Civil society organisations, including the Red Cross reflect the societies they work in. They also often work in more remote and insecure contexts, where levels of monitoring are sometimes less than in other more stable situations. The capacity of Kenya Red Cross chapters may also differ across the country. / The risk matrix above flags major risk and mitigation measures. We have no evidence of past fraudulent activity within BRCS/KRCS involving DFID funds, but from experience with other partners’ programmes, we can anticipate that the greatest risks of fraud and corruption in this programme include: the misuse or sale of goods, fraudulent payments/incentives for workers/volunteers, and false claims for attendance at workshops etc. Whilst risks cannot be removed, additional mitigation measures beyond those detailed in the table above include: / BRCS is fully accountable for funds provided to them by DFID and money fraudulently used can be recovered by DFID. Under the MOU, BRCS must inform DFID immediately of any suspected fraud and DFID Kenya will inform DFID’s Counter Fraud and Whistleblowing Unit). / The 2013 due diligence assessment did not flag any risks for BRCS and only some medium/low risks for KRCS (see para 72, regarding satisfactory follow up). / Three BRCS/KRCS programme audits will be undertaken during the lifetime of the programme. DFID will review whether this is sufficient or whether additional audits, specific to DFID’s funding, are required. DFID spot checks will also be considered. / KRCS maintains better access than some humanitarian agencies and so is less liable to fall into more risky remote management techniques, with senior staff not from disaster zones, still able to monitor activities. DFID is globally and regionally undertaking an evaluation and research on best practice in remote management and aid in more insecure settings. Relevant lessons and recommendations from these studies will be incorporated into this programme. / We are liaising closely with DFID Uganda regarding learning from a recent corruption case involving senior Uganda Red Cross Officials and an ongoing investigation into whether a small amount of DFID funds may have been exposed. DFID Uganda is pleased with how the BRCS has responded to the allegations. / BRCS report that where KRCS has identified fraud in the past, this been brought to the attention of Senior Management through internal audit process and by whistle-blowers. Investigations were undertaken satisfactorily and disciplinary hearings held to provide implicated employees with an opportunity to explain anomalies. Where employees were found culpable disciplinary measures were taken including dismissal and criminal proceedings instituted. Where suppliers were involved they were blacklisted from participating in our procurement. KRCS has a human resource policy and guidelines where ethical standards relating to fraud are detailed. KRCS is in the process of developing an anti-fraud policy which is due to be submitted to the National Executive Council (NEC) for review and approval during 2014 / The risk matrix for this programme will be updated with BRCS during the inception phase of the programme. / Conflict sensitivity / The risks of humanitarian action, unintentionally contributing to conflict are significant (see risk matrix above). Without a well-developed understanding of the conflict dynamics, assistance can fall into the wrong hands and can generate conflict. Inappropriate messaging and posture by humanitarian actors can also unintentionally add to distrust and tension – impacting both on humanitarian access, staff safety and conflict dynamics. / To mitigate these risks, DFID only funds partners who adhere to humanitarian principles and have a “do no harm” approach built into their policies and procedures. Operational adherence to this will be reviewed during the field reviews and annual reviews. / Whilst not funded through this programme, KRCS is active in promoting peacebuilding through facilitating ceasefires and inter-communal peace dialogues.