Type of Review: Project Completion Review

Project Title: Malawi Education Sector Reform Programme (MERSP)

Date started: March 2010	Date review undertaken: May 2014
Instructions to help complete this template: / Before commencing the review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note) - Reviewing and Scoring Projects, / the most recent annual review and other related monitoring reports. / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / Two scores are produced at project completion - one based on achievement of the outputs and one based on achievement of the outcome. You should assess and rate both the individual outputs and the overall outcome using the following rating scale and description: / Output Description Scale Outcome Description / Outputs substantially exceeded expectation A++ Outcome substantially exceeded expectation / Outputs moderately exceeded expectation A+ Outcome moderately exceeded expectation / Outputs met expectation A Outcome met expectation / Outputs moderately did not meet expectation B Outcome moderately did not meet expectation / Outputs substantially did not meet expectation C Outcome substantially did not meet expectation

## Introduction and Context
What support did the UK provide?
The Malawi Education Sector Reform Programme (MESRP) was DFID’s £50 million programme to support transformational change in Malawi’s education sector (2010 - 2013) as part of a £200 million donor pooled fund in a Sector-Wide Approach (SWAp). A no cost extension was added up to the end of June 2014. / DFID originally intended to disburse £42 million over three years as pooled and earmarked Sector Budget Support (SBS) to the Ministry of Education, Science and Technology (MoEST), £5 million over three years for improving domestic accountability and sector governance and £3 million provided to the MOEST to further construction of classrooms began under a preceding programme (ESSP). In addition a separate Education SWAp Technical Assistance instrument provided £624,490 support in the late 2009 – mid 2012 period on design and early phase implementation support. / There were deviations from the original funding intentions of MERSP, as outlined in the table below. A lower volume of SBS was provided in 2010/11 (£11.667 of £14m), with the remainder going to UNICEF for school construction. This reallocation was linked to unsatisfactory progress on infrastructure reform. The 2012/13 payment of £14m was front loaded in a single payment to the treasury, for onward release in the planned two phases to MoEST. Relatively little (25%) of the £5m intended for ‘domestic accountability and sector governance’ was used as intended, some funds (£0.84m) were used for infrastructure via non–government providers and around £3m is unspent. / Proposed / (Programme Memorandum, 2010) Actual / (ARIES data, April 2014) Total spent / £3 million Financial Aid for school construction (April 2010) March 2010 £3m / SBS (*): £14 million per Malawian FY 2010/11 (July 2010 50%, Jan. 2011 50%) July 2010 – £7m £13.97m / Dec. 2010 – £3.1m / March 2011 – £1.566 m / UNICEF Child Friendly Schools £2.3m (2011 – 2012) / SBS (*): £14 million per Malawian FY 2011/12 (July 2011 50%, Jan. 2012 50%) May 2011 – £7m £14m / Dec. 2011 – £4.67 m / March 2012 – £2.33m / SBS (*): £14 million per Malawian FY 2012/13 (July 2012 50%, Jan. 2013 50%) June 2012 – £14m £14m / £5 million for improving accountability and sector governance Support to Education Sector Joint Donor Unit in Malawi £274,367 (2010-2012) £2.03m / Kalondolondo Civil Society scorecard construction monitoring £ 177,812 (2013) / Procurement of services; studies et al. £227,121 (2010 -2014) / Training of Mothers Group £212,310 (2011) / Mzuzu Diocese School Construction £238,221 (2011- 2014) / UNICEF Water and Sanitation Infrastructure £600,000 (2012) / World Bank studies £300,000 (2013) / £50m £47m (96%) / (*) 1st 50% as soon as the budget (reflecting spending targets) is approved by Parliament, usually in July each year. 2nd 50% in January each year if the Joint Sector Review (JSR) concludes that satisfactory progress is being made on nine key reforms areas (benchmarks, not formal conditions).

What were the expected results?
Five major donors (DFID, World Bank, Global Partnership for Education (GPE), Germany and UNICEF) pooled funds in this Sector-Wide Approach (SWAp) to support implementation of the ESIP (Education Sector Implementation Plan 2010- 2013). Key results targets (aimed to be achieved by June 2013) and actuals achieved are summarised below, (although there are numerous inconsistencies in the data): / Target Achieved Actuals / 3,000 primary classrooms constructed / rehabilitated (target from World Bank PAD). Mostly 2,332 classrooms constructed (944 EIMU, 1288 LDF). A further 342 classrooms scheduled for completion by end June 2014. / 14,100 new primary teachers trained Yes 16,636 newly qualified teachers via both regular and distance learning graduated between 2010 and 2014. / Equal numbers of girls and boys in Form 1 of secondary school No In 2012/3 gender parity index at 0.9 (9 girls for 10 boys) but up a bit in Form 1. GPI 1:1 until Standard 5. / Repetition falls from 20% of all pupils in school to 5% No By 2012/3 it had risen to 24-25%. / Pupil Teacher Ratio (PTR) falls from 78:1 to 62:1 Mostly Primary PTR fallen from 81 (2009/10) to 69 (2012/13). / All primary schools supported by direct grants Yes By 2013/14, all primary schools received schools received School Improvement Grants (SIGs). / More detailed outputs against the logframe outputs and outcomes are given later, however clearly the volume of expected ‘outputs’ to be financed from the pool was lower than anticipated and delivery was severely delayed.

What was the context in which UK support was provided?
The Malawi 2009 Millennium Development Goal (MDG) Report indicated that MDGs 2 and 3 were ‘unlikely to be met’. Gender parity was achieved to Standard 5 in primary education but not in secondary, where the ratio of girls to boys was 0.9:1. The overall primary school completion rate rose from 26% in 2005 to 35% in 2009, but was still too low. More than 600,000 primary school-age children were not enrolled in school, while 698,000 children enrolled in primary school in 2008 were repeating the same grade. Gender and regional disparities persisted, and the quality of teaching and learning in primary schools was generally low. / Government and donors agreed that fundamental changes in policy and practice were required to bring about transformation in the education sector. However, given the poor prospects for achieving the MDGs in education, and with only 44% of the Government budget allocated to primary education (and much spend poorly targeted), GoM and donors recognised that ‘business as usual’ could not continue. Primary education needed to be better financed, and resources allocated more equitably between districts, income groups, and learners at different levels of the system. Resources needed to be used more efficiently, to avoid the losses involved in high rates of grade repetition and school dropout. The most urgent reform was to reduce class sizes. This required more teachers; more permanent classrooms; stricter control of repetition; and the use of classrooms for two shifts each day. The recruitment of additional, auxiliary teachers and their training on-the-job by distance-learning was proposed to kick-start the process. / To implement these priority actions, the Ministry of Education, Science and Technology (MoEST), Ministry of Finance, and donors agreed to pool funds through government systems, under the Joint Financing Arrangement (JFA). The education SWAp sought to enhance mutual accountability (GoM, donors and civil society) and internal accountability (MoEST and MoF). By using government systems and stimulating better coordination between government and donors, it was expected to reduce transaction costs with substantial efficiency gains in programme management and reporting. DFID intended to engage with civil society in holding government accountable for the use of public funds, however little of the original budget for this was used as planned as the space for civil society engagement was increasingly constrained between 2010 and President Mutharika’s death in April 2012. Thereafter a community score-carding exercise was undertaken on the Local Development Fund’s construction of teachers’ houses and primary classrooms. / Overall many of the reasons for the under achievement in output and outcome terms of this programme can be explained by looking at the top level ‘goal / impact‘ assumptions of the original logframe as was highlighted in the preliminary political economy analysis in January 2013. The following assumptions were required to hold, but few of them did in the 2010 – 2013 period. / Assumptions Assumption Hold? / Political Commitment to education remains Partially At least in political statements and allocation of budget for education and primary sub-sector. However political leadership and education policies weak and reforms unenforced. / No major drought, flood, earthquake or other natural disaster Partially Cyclical drought / flooding leading to food insecurity. / Macro-economic stability and economic growth are maintained No In May 2012 the Kwacha was floated resulting in rapid devaluation which caused an economic crash. / Political stability in the country with progressive democratic system maintained Partially President Mutharika’s death in 2012 prompted a succession crisis and changes in policy, however few changes in Cabinet. / Partnership principles (PP) between DFID and GoM are not broken No 2011 political dispute led to British High Commissioner’s expulsion and 2013 Cashgate scandal led to conclusion that PPs broken. / No major corruption scandals in GoM No ‘Cash gate’ crisis led to suspension of financial aid and decision not to proceed with a cost extension. / Whilst the technical and political leadership under the MoEST was weak and clearly there were capacity gaps, the major reasons for this programme’s under-delivery lie at the macro-political economic level. Until this point the programme, despite teething problems, was largely considered to be on track. It should also be noted that in addition to much lower releases of funds from the pool as intended from the central Treasury to MoEST, one major donor (Germany) released only a third of its original pledge. Germany suspended disbursements due to concerns with the first financial audit report; DFID however released 94.5% of the SBS funds.

## Section A: Detailed Output Scoring
Output 1: Expanded and more equitable access to each level of education
Output 1: final score and performance description: B (Outputs moderately did not meet expectation) / Indicator 1.1: Number of primary school classrooms constructed or rehabilitated per year, and unit cost of classrooms Progress against this indicator was weak in the first 2 years of implementation when only 382 and 274 were completed respectively against an annual target of 1000. Despite a well-planned transition from donor project implementation units (PIUs) to a central Education Infrastructure Management Unit (EIMU) there was a lack of government commitment. This was evidenced through long delays in recruitment for key positions, a reluctance to follow tried and tested procedures and structures from the former PIUs and a souring of relations with the private sector due to long delays in payments to contractors. Coupled with the need to adjust to World Bank procurement procedures, construction all but ground to a halt. / Nevertheless the government did recognise systemic inefficiencies and, in a bid to increase the speed of construction, the Local Development Fund (LDF: originally established to undertake community construction under the World Bank MASAF programme in 1994) was funded through District Councils in August 2012 to construct 1000 classrooms. Since then a total of MWK 11.5 billion has been used to construct 1,730 classrooms (of which 1,288 are complete), 207 teachers’ houses, 407 VIP latrines and 12 girls’ hostels. / Whilst the LDF greatly altered the landscape of school construction and was a necessary addition to the sector, concerns remain over the quality of construction. This was highlighted in the DFID funded, community score-carding Kalondolondo report which was critical of the use of local, unskilled artisans, the lack of supervision of construction, the lack of real community engagement and the leakage of both funds and materials evidenced on a number of sites. The environmental impact of the use of burnt bricks as the community contribution is also a concern. In response to such criticisms LDF has committed to trialling soil stabilised bricks (SSBs) and has purchased 100 machines, they have also agreed to hire only skilled labour, reconsider oversight mechanisms for site supervision and revise regulations to include an appraisal system for contractors before contract award. / No. of primary classrooms constructed/ rehabilitated Milestone 2010/11 Milestone 2011/12 Milestone 2012/13 Completed in NCE 2013/14 / Planned 500+ 500+ 500+ No DFID funding / DFID attribution of total (EIMU and LDF only) 31% 23% 39% 0 / Total EIMU (573) 0 274 288 11 / Total LDF (1630) 0 110 1178 342 / Achieved (through pool) 384 1466 353 / DFID EIMU 63 112 0 / DFID LDF 0 25 459 138 / DFID £3m initial grant 0 0 242 0 / Diocese Mzuzu grant 0 0 0 18 / UNICEF grant CFS 0 40 48 0 / DFID attribution 128 861 156 / Unit costs of classrooms are higher than the target at the outset of the programme however new approaches, such as community construction through the LDF, have led to substantial cost savings as show below. / Construction unit Cost per classroom block / UNICEF £22,350 / EIMU £18,520 / LDF £10,900 / Mzuzu Diocese £7,794 / As noted in the context above, DFID supported the EIMU to complete a number of education infrastructure sites which were started under a previous programme (ESSP) and should have been completed by the SWAp through the EIMU. A major failure of the EIMU has been the completion of these buildings and to date 304 classrooms, 83 teachers’ houses, 36 administration blocks and 523 pit latrines are yet to be completed. This has been an ongoing reputational risk for DFID (as communities identify the sites as ‘DFID schools’) and DFID has pushed hard for their completion. The vast majority are now 80% complete and we expect them to be finished by the end of 2014 nevertheless the slow progress has undermined the performance of the pooled fund. / Indicator 1.2: Survival Rate to Grade 5 (proportion of pupils starting grade 1 who reach grade 5, by sex). A mixed picture exists in terms of survival rates although the target was consistently exceeded as shown in the chart below. Survival rates increased sharply between 2009 and 2010 and slightly in 2011 however they subsequently fell to below their 2009 level at 59% (58% boys and 59% girls) in 2012. Survival rates to standard 8 show a similar decrease over the period from 49.7% in 2011 to 38% in 2012. The data also show a widening gender gap between standard 5, where gender parity exists, and standard 8 by which time a 6% difference is seen (girls survival rate is 35% compared with 41% for boys). In both cases however the survival rates are well below average for Malawi’s neighbours. The dramatic drop might be partially attributed to the economic crash which occurred in 2012 and the subsequent hyperinflation (although confirmation would involve an in-depth analysis beyond the scope of this review). What is clear is that, despite the introduction of Free Primary Education (FPE) in 1994, hidden costs remain. A recent study by UNESCO IIEP found that the cost of sending a child to primary school in Malawi in 2012 was on average 6.06% of households’ annual income compared with an average of 4.8% in 1993 prior to the introduction of FPE. The economic crash may have therefore prevented families from meeting those costs and their children dropped out or were excluded from school. / Survival rates to Standard 5 / The issue of reliability of data is critical. 2011 saw the introduction of district level collection of education data, the DEMIS (District Education Management System), and in 2012 the Integrated Household Survey (IHS) III was released. As a result many indicators have been revised and data shifts can be partly attributed to more reliable data collection techniques suggesting the earlier figures were based on erroneous data. / Indicator 1.3: Transition Rate from primary to secondary school (male/female), and actual difference between the numbers of boys and of girls in Standard 8. / Despite a drop between 2010 and 2011, transition rates to secondary are on an upwards trajectory for both boys and girls. In fact girls have seen a larger increase from 30% to 34% between 2012 and 2013 compared to 30% to 32% for boys. Nevertheless the actual difference between boys and girls enrolment rose to 18,504 in 2013 from 14,349 in 2012.
However it should be noted that an increase in transition rates to secondary education are limited by the absorptive capacity of the secondary schools which is low; there are only places for approximately 30% of children who pass the PSLCE (Primary School Leaving Certificate in Education). In recognition of the need to support the expansion and quality of secondary education the pooled fund eligible expenditures were expanded in May 2012 to include secondary education. This has led to increased provision of secondary Teaching and Learning Materials (TLMs) through school level procurement and liberalisation of textbook policy which has increased efficiencies in procurement and availability of TLMs. / Final results: Despite the dramatic increase in classroom construction in the past 18 months the overall numbers of classrooms constructed was well below targets and the PCR remains unacceptably high (see graph below). In fact the PCR has increased over the programme period although prolonged engagement of LDF is likely to see a reversal of this trend. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk: High / Revised since last Annual Review? No / Pupil Classroom Ratio / PCR / Year

Output 2: Improved quality and relevance of education, with effective learning
Output 2: final score and performance description: B (Outputs moderately did not meet expectation) Indicator 2.1: Number of primary school teachers trained per year (national total, plus number attributable to DFID). / This is an area where the pooled fund met targets; achieving a significant drop in the Pupil Teacher Ratio as a result of the broad scale investment in the training of teachers. The target of 14,100 teachers trained over the period was surpassed: 16,636 were trained. This was achieved through a combination of traditional, face-to-face teacher training (IPTE) delivered at teacher training colleges (TTCs) (12,958) and the introduction of a classroom based, Open and Distance Learning (ODL) teacher training course (3,678). The first cohort of ODL graduates were hired in 2012 which is evident in the significant drop in PTR between 2012 and 2013. The ODL course attracted teachers to rural areas (ODL teachers are based in their home areas) and immediately boosted the numbers of teachers, albeit trainees, in classrooms. The 2013 Joint Sector Review reports that there were 19,762 teacher trainees (comprising 3,895 IPTE 7, 4,318 IPTE 8, 5,521 ODL II and 6,028 ODL III) in classrooms in 2012/13 which is a tremendous boost to an overstretched teaching force. / The MoEST has done its own analysis of the requirements of teacher supply up to 2020 (Annex 2) which suggests an average of 5,300 additional teachers need to be hired annually, making a cumulative total of 42,000 teachers by 2020. Given that the current number of teachers in the system is around 56,000 the scale of the problem becomes apparent. There are of course other considerations, for example, the projections assume no change in the efficiency of the system (i.e. repetition rates remain constant) which therefore puts additional pressure on the number of teachers required. This clearly highlights the need to tackle the internal efficiency of the system if PTR is ever to come down (see indicator 3.1 below for more on this). / Indicator 2.2: Primary school completion rate (PCR), (Std 8 enrolment, minus repeaters, as % of 13 year old population). / The figures for 2012 suggest that the total primary completion rate is 59% with 65% male and 54% female thereby exceeding the original target. These figures need to be interpreted with caution however as the last reliable census data was collected in 2008. If we assume a population increase of 10% since 2008 (on the basis of the projections from the 2008 census) the picture worsens with a 54% total PCR, 59% male (still slightly exceeding target) but only 49% female (slightly below target). In the absence of accurate census data a reliable figure cannot be quoted for the PCR. Despite this being a World Bank ‘core indicator’, the Bank no longer uses this in Malawi due to the unreliability of the data. Instead they used the Standard 8 survival rate as a proxy. At only 31% in 2013 (an ongoing decline from 50% in 2011) this does not paint as rosy a picture. / Indicators 2.3 and 2.4: % pass rate in Primary School Leaving Certificate Examination (PSLCE), and Malawi School Certificate Examination (MSCE). / The PSLCE pass rates have remained at 69% since 2010 with a very slight dip to 68% in 2013. The consistency with which these results are achieved suggests the exams are norm referenced (i.e. an agreed % of candidates must ‘pass’ every year regardless of their responses) rather than criterion referenced (i.e. only those who meet pre-established criteria pass which generally produces greater fluctuations year on year). It also brings into question its use as an indicator of achievement. Gender parity in exam pass rates has not been achieved. In 2012 only 42% of successful candidates were female and in 2013 this had dropped to 40%. Unfortunately the data is incomplete in earlier years therefore the trajectory cannot be plotted. The pass rate for the MSCE rose substantially from 2009 to 2010 from 38% to 52% respectively and to 58% in 2013; far in excess of the 40% target. However the scale of the increase and lack of obvious improvements in secondary education means that the figures must be treated with caution. In summary these do not appear robust indicators of system quality and improvement.
Final results: Whilst the number of teachers trained has exceeded the target the outcome is limited by number of teachers that can be absorbed on the government pay roll; 10,000 newly qualified teachers could not be hired in January 2014 due to budget constraints. To achieve the target 60:1 PTR ratio will involve hiring an additional 75% of all current teachers. In a resource constrained environment this is unrealistic. By the MoEST’s own estimates PTR will begin to rise again to 88:1 by 2020 unless additional funding can be sourced and internal efficiency measures realised. Therefore the biggest issue facing the MoEST regarding teachers is teacher management rather than teacher training and any subsequent programming should reflect this. There is questionable data on student progression and summative assessment measures. Regardless Malawi needs to develop more consistent measures of learning outcomes that can be tracked over time to ensure investments in the education system translate into learning gains. / Impact Weighting (%): 35% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

Output 3: Improved governance and management of the system, with more efficient service delivery
Output 3: final score and performance description: B (Outputs moderately did not meet expectation) / Indicator 3.1: Repetition and dropout rates in primary schools / Repetition is a major cost driver in the Malawian education system and one of the major causes of internal inefficiency. According to Southern and Eastern African Consortium for Monitoring Education Quality (SACMEQ), 60% of learners in Malawi repeat at least one grade before completing standard 6. Despite an MoEST circular in 2011 stipulating strict guidelines on reducing repetition, the rates have increased. Girls’ repetition rates increased from 19% in 2008 to 24% in 2013 and boys from 20% in 2008 to 25% by 2013. There are a number of factors which contribute to high levels of repetition and not all are tied to achievement (attendance, behaviour, socio-economic status and gender are often informal factors). In fact, a 2010 World Bank study, ‘The Education System in Malawi’, found that more than 30% of repeaters are not in the lower third of students at the national level as measured by SACMEQ assessment tests. Drop-out rates are also on the increase as demonstrated by extremely low survival rates. These have decreased from 74% in Standard 5 in 2011 (72% girls, 75% boys) to 64% in 2013 (62% girls, 66% boys). / 2012 Repetition Rate by Standard and Sex / There are signs of hope however. In 2011 the issue of repetition was largely considered a donor preoccupation and gained little ground within the government itself (and less so amongst parents and teachers). In 2014, partially because of significantly reduced GoM budgets due to the withdrawal of donor support, the MoEST is reconsidering the issue. Recent figures generated by the MoEST (Annex 2) show the likely impact of semi-automatic progression (i.e. where repetition is only permitted every other year e.g. in Standards 2, 4, 6 and 8). Such a policy, if implemented, would lead to 25% less students in the system by 2020 compared to a ‘no-change’ scenario (approx. 4.1m pupils, roughly equal to today’s enrolment). Most strikingly semi-automatic progression would lead to a MWK 35 billion cost reduction; equivalent to 26% of the full education budget. Reducing repetition rates is now one of four priority areas in the revised Education Sector Implementation Plan (ESIP) II and there appears to finally be consensus across the MOEST that repetition must be tackled. / Indicator 3.2: Unit costs (in Malawi Kwacha, and as a percentage of GDP per capita) by level of education, with 'unit cost' meaning public recurrent expenditure per student per year / The measurement of unit costs in kwacha and US dollars is shown below. Dollar rates are calculated at the value on 01.05.2011, 2012 and 2013 respectively. The 2012 devaluation means that what looks like an increase in funding to all sectors in 2012/13 is actually a significant decrease in real terms in primary and secondary unit costs. The unit costs for students at TTCs reduced significantly in 2011/12 due to the introduction of high numbers of ODL teachers at much lower costs than the IPTE teachers. / Year 2009/10 2010/11 2011/12 2012/13 / Primary / No data 4494 ($29) 6244 ($37) 9186 ($21) / Secondary / No data 20972 ($138) 28206 ($167) 39160 ($93) / Teacher Training Colleges / No data 204969 ($1,346) 84985 ($503) 260522 ($623) / Although the unit costs for higher education are not captured in EMIS, these are included in the 2012 ESIP Review. A snapshot from 2011/12 shows per capita higher education costs are 169.5 times those for primary. / Indicator 3.3: Timing of approval of the annual work programme, education sector budget, and the procurement plan / Targets on the timing of the approval of work plans and budgets have been met throughout the programme and transparency has increased over the period. By the third year of the programme pre-budget meetings on eligible expenditures were held between MoEST and DPs instigated by the MoEST. However the picture on procurement is less positive. The existence and timing of the procurement plan itself (as per the target) is not the major issue; rather its execution is. Major issues in the procurement function include the lack of involvement of user departments in procurement process, the lack of a monitoring framework in the procurement and delivery of text books to schools, the lack of evidence based analysis for estimating the number of text books needed and the length of time from the beginning to end of procurement process. To address these MoEST recently instituted a number of changes including establishing a monitoring system for the distribution of textbooks which is under review by the World Bank, establishing a TLM committee chaired by the Director of Inspectorate and Advisory Services (DIAS), engaging Malawi Bureau of Standards (who engaged South African Bureau of Standards, SABS) to verify the quality of the books and decentralising the provision of teaching and learning materials (such as exercise books, pencils, pens) to districts. These reforms were introduced within the last year and beyond the original programme implementation. / Although the procurement and distribution of 9 million text books for standard 3-8 is now complete, the standard 1-2 textbooks procurement process, initiated in 2012, was cancelled was in mid-2013 and replaced with procurement for 10.1 million standard 1-5 textbooks and 822,000 secondary textbooks. This led to a prolonged period where textbooks were not in schools. An analysis of the school level TLM data (conducted by World Bank using EMIS 2012) reveals that on average the number of text books available was only a third of those needed to meet the target pupil: text book ratio (PTbR) of 1:1 ratio cited in ESIP. Unfortunately a significant proportion of schools did not receive the textbooks they were expecting; of the 3941 schools listed in textbook distribution list only 27% reported receiving standard 8 English textbooks and only 37% received maths textbooks. / The first procurement audit for FY 2010-11 was completed only recently and a draft report is being reviewed by MoEST. The FY 2011/12 procurement audit is yet to start. World Bank undertook annual internal audits on Bank supervised procurement but did not share with pooled partners until recently and major audit gaps remain.
Final results: / The pooled fund was successful in improving systems in the MoEST, particularly budgeting and planning functions however the execution of plans, particularly procurement, was weak. Textbook as well as TLM procurement was disappointing with the average length of time for a full procurement to take place being two years. MoEST has taken steps to address this through decentralising the procurement of TLMs to district level since 13/14. The MoEST, Department of Inspectorate and Advisory Services (DIAS), Malawi Institute of Education (MIE) and private sector publishers are in talks to decentralise primary textbook procurement. This has been successfully trialled in the secondary sector. Overall Government of Malawi resources have increased to education over the period and as a share of the national development budget. The sector’s development expenditure has increased from 4.4% in 2008/9 to 12.6% in 2012/13. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: High / Revised since last Annual Review? N

## Section B: Results and Value for Money.
1. Achievement and Results
1.1 Has the logframe been changed since the last review? No / 1.2 Final Output score and description: B (Outputs moderately did not meet expectation) The programme has delivered marked improvements in PTR, number of teachers’ trained, targets achieved in school based management through school grants, expansion of CBE and decentralisation of TLMs. However, as described above, overall cumulative progress was below expectation. Significantly lower volumes of construction were delivered and, while ODL teacher training proceeded well, no real progress was made on reducing class sizes, improving progression rates or demonstrating any measurable gains in student learning.
Direct feedback from beneficiaries / Reactions of senior government officials to the pooled funds were generally positive although many were cautious to give strong opinions that they thought might influence DFID’s future investment plans. Both funds and technical support were considered highly beneficial, although one commented that the system of ‘eligible expenditures’ had become too complex and a simpler system to protect priority spending would be preferable. The District Education Manager (DEM) in Dedza thought that the process of decentralisation over the past 4 years had been highly beneficial in improving the pace and responsiveness of education service provision. There were fewer requests to the central Ministry and more ability to respond to community needs. / In schools visited the impact of new construction and financial grants to schools were frequently commented on by school leaders and teachers; requests for further additional support were made. Two trainee female teachers who had been hired through the ODL distance course were also clearly happy to be employed and to have received training and the accompanying status it gave them in their communities. / Community perspectives around the major construction programme are perhaps the most useful beneficiary feedback to cite. The Kalondolondo civil society programme undertook research using community scorecards in 13 districts in late 2013. Since not all of those asked were literate, facial expressions helped communities associate their emotions and perceptions to the score associated with cartoon expressions. A rich range of responses came back, notably most communities were content (to varying degrees) on the extent of community labour requested but were keen to point out structural problems or poor workmanship. There were some instances of abuse, for example learners excluded from school if their parents had not contributed to the programme. In all districts positive ratings were received on the overall impact of classrooms on the learners and the community in general. Examples cited included: / Improved learning environments especially where some classes were previously conducted outside; / The new classrooms have added ‘beauty to the schools’ and learners appreciate this because it gives them confidence in their schools and they can ‘keep their heads high’ when amongst peers; / Some schools have been able to upgrade from Junior Primary to Full primary schools; / Disruption of lessons has been minimized, especially when there are rains or in the height of summer; / Teachers in beneficiary schools say it is easier to control learners in classrooms rather than outside; / Family budgets for sanitary products like soap have gone down because of cleaner, dust-free environments; / Provision of new school blocks has helped protect young children from walking long distances.
1.4 Overall Outcome score and description: B (Outcomes moderately did not meet expectation) / Outcome indicator Achieved Actuals / % of GoM discretionary recurrent budget allocated to education Mostly The target was missed in 2010/11 but exceeded in thereafter (see graph below). / % of the education budget devoted to primary education Mostly 60% target met in first 2 years; third year reduced to 55% due to budget restrictions / % of funding to the recurrent education budget released by MoF to MoEST within year No The target was not met in the first year of implementation but improvements in the second year meant 92.3% budget release achieved by end 2011/13. / Pupil Teacher Ratio (PTR) in primary school Mostly Primary PTR fallen from 81 (2009/10) to 69 (2012/13). Target was 62:1 / Student Teacher Ratio (STR) in secondary school No STR remained static at 22:1 / Outcome Indicators / These were largely met as shown above, although the second only achieved 55% in 2012/13, with external pressures caused by the economic shock arising from the rapid currency devaluation in 2012. The percentage of recurrent education budget released varied from quarter to quarter causing the Internal Audit Department (IAD) to query a release of funds in July 2012. However, despite quarterly variations, by the end of FY 2011/12, 92.3% of the recurrent budget had been released. / One of the successes of the pooled fund has been the resulting increase in GoM education expenditure. The graph below shows the upwards trajectory of education funding since the introduction of MESRP in 2010. / Source: World Bank Public Expenditure Review 2013 / The fourth outcome indicator, national average primary PTR, dropped from 81 to 69 from 2009/10 – 2012/13, missing the target of 62 but still demonstrating a positive outcome. PTR may have reduced further if teacher recruitment had not been impeded as a result of the financial crisis. Whilst the drop in PTR, and hence class sizes is welcome, large inequities exist both within schools and between schools. Typically early grade classes are much larger than upper grade classes (an average of 153 in Standard 1 compared to 42 in Standard 8, EMIS 2011). As the chart below demonstrates there are huge variations in PTR at individual schools, with over 500 schools having a PTR over 100. In many neighbouring countries a range of 40 – 60 would be expected; 60% of Malawian schools are above this range. / (The above chart is the average PTR per school, not weighted by enrolment.) / The fifth outcome indicator, national average secondary PTR has seen little change, with the indicator at 22 in 2012/13, well below the target of 30. The programme has had little impact in seeking to increase the number of qualified teachers and reduce inefficiencies of small class sizes and subject specialised teachers, particularly in rural secondary schools. / Impact and Sustainability / The pooled fund has enabled a number of pilot initiatives, particularly school grants, Complimentary Basic Education (CBE) and Open and Distance Learning (ODL) for trainee teachers, to be taken to scale. The roll out of the Primary School Improvement Programme (PSIP) and the delivery of School Improvement Grants (SIGs) has been a major success. What started as a World Bank funded initiative in 2006, was further supported by DFID, then USAID and is now fully integrated in government systems. Expansion has been rapid; increasing in size and scope from 6 districts at 250,000MWK per school in 2010/11 to 12 districts and 300,000MWK per school in 2012/13. In the FY 2013/14 the school grants programme achieved nationwide coverage in all 34 education districts and has increased in value to 600,000MWK per school. Funding is provided directly into school bank accounts and is spent against an agreed School Improvement Plan (40% to improve access and equity, 50% to quality and relevance and 10% to governance and management). This demonstrates government’s capacity to learn from pilots and take them to scale. The Ministry is currently undertaking an evaluation across 198 schools in 33 districts focusing on whether PSIP-schools have improved inputs, outputs and outcomes. / CBE is another example of a successful pilot taken to scale and is an interesting collaboration between MoEST and NGOs (who deliver the CBE programme with GoM funds). The programme originally received support from GIZ, DFID and UNICEF and has been funded by government since 2011. Through a network of CBE centres the Malawi CBE programme provides out-of-school children with a basic education and an opportunity to return to school. It has now been expanded to 600 centres, received recognition in the Global Monitoring Report of 2012 and is being replicated in Zimbabwe and Namibia. Keen to learn from this experience MoEST undertook an evaluation of CBE’s cost effectiveness in late 2013 which came out favourably. / The open and distance learning (ODL) approach to teacher training was adopted to address the critical shortage of teachers. The programme trained large numbers of teachers on-the-job as an alternative to conventional pre-service teacher training. Although planned as a temporary measure results from a World Bank study proved positive and the programme will continue as an additional track to teacher training. This not only boosts numbers of teachers in classrooms but also addresses teacher shortages in rural areas. All three pilots were successfully taken to scale as a result of pooled funding and are therefore much more likely to be sustainable. / Impact indicators included in the programme logframe included primary ‘correct age’ enrolment approaching 100% and with gender parity. There were no major changes in these indicators. The percentage of overage / underage enrolment is high at 49.4% (EMIS 2013) and has only reduced slightly from 53.5% in 2009. Problems with cross border enrolment and the inclusion of many under 6 year old children in class are likely explanations for the very high net enrolment rates observed. Broadly enrolment has tracked population growth, with gender parity in lower primary, but a noticeable and persistent imbalance in upper primary and secondary school. / The Malawian education system remains highly dependent upon external support. Whilst some more sustainable models of service provision have emerged from the programme, these are vulnerable to collapse or erosion over time if further financial support, technical support and capacity building are not continued. / Primary Pupil Teacher Ratio 2013 / Avg 72.1, st. dev. 30.6 / Primary PTR / Percentile ranking of 5356 schools / Normal SSA Range

2. Costs and timescale
2.1 Was the project completed within budget / expected costs: Yes / Given the bulk of the funds was provided as sector budget support, there was no over-run, in fact only around 96% of the original finance was disbursed, even after a one year extension. / 2.2 Key cost drivers / The main cost driver of the programme relates to the unit cost of construction given the intention for DFID finance to fund (indirectly and directly) 2,000 classrooms and a logframe intention for a unit cost of under £13,000. This suggests around £25 million or 50% of the total original DFID budget would fund construction. More detail on actual unit costs of construction are given in the VfM section below. / Other cost drivers from input provision include the cost of teaching and learning supplies, teacher training and indirectly salaries of teachers and trainee teachers, given the intention to expand the teaching workforce to reduce class sizes. The sudden devaluation of the Kwacha was also a major factor affecting costs, which caused shortages, spikes in commodity prices and many problems associated with the lack of liquidity. / 2.3 Was the project completed within the expected timescale: No / A business case for a cost extension to the programme was prepared in 2013 to allow more time to complete the delayed activities, in particular construction and procurement contracts for education materials. This did not progress due to the 2013 ‘Cashgate’ crisis resulting in a suspension of Financial Aid instruments from DFID (and most other development partners) to the Government of Malawi. An alternative no-cost extension was agreed up to the end of June 2014.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and what this meant for the project. / In the last 18 months a range of analytical work has been undertaken including a snapshot political economy analysis and studies on decentralisation and community perceptions on construction. In addition the World Bank undertook a Public Expenditure Review in early 2013. USAID has conducted three rounds of EGRA assessment on early grade reading in 2010, 2011 and 2012. A Public Expenditure Tracking Survey (PETS) and Service Delivery Indicators (SDI) study with the World Bank will complete Dec 2014. The results of the studies so far suggest that the institutional landscape, incentive structures and assumptions behind expanded education services were overly optimistic in MESRP. As documented on page 3 many of the purpose level assumptions did not hold. / 3.2 Set out what plans are in place for an evaluation. / No formal evaluation was budgeted or planned for, however a joint donor evaluation of the SWAp could have been useful and is something to consider for future education programming. PETS analysis will be undertaken in the near future utilising World Bank expertise. In addition the SACMEQ IV standardised testing is due in 2014/15 which tests 6th grade students in all countries in the region. These will provide a valuable measure of actual learning outcomes and the extent of change over time since the last round in 2010 and Malawi’s relative standing amongst its neighbours.

4. Risk
4.1 Risk Rating (overall project risk): High / Did the Risk Rating change over the life of the project? No / 4.2 Risk funds not used for purposes intended / The 2009 education sector FRA concluded the fiduciary risk was substantial but noted that this would be revised to moderate if five key measures were put in place. The 2011 update recognised that these were addressed but stated it was not possible to revise the risk rating downwards without more in-depth analysis. An education sector FRA was undertaken in July 2013 and concluded that the risk level remained substantial. Regular checks on financial management have been carried out by the World Bank and KfW, as well as through instruments like PEFA’s and FRAs. / The cash-gate scandal came to light in autumn 2013 and it is difficult to say with any certainty what, if any, allegations will be laid at MoEST. The Secretary for Science, Education and Technology (SEST) and Principal Secretary for Basic and Secondary education (PS Basic) insist MoEST will not be accused of any wrong doing. The SEST very publicly closed loopholes over allowances in February 2013 which led to a series of strikes by staff, a three week closure of MoEST and a number of job losses. / Internally the MESRP programme has been subject to two audits by the National Audit Office (NAO) in November 2012 and the Internal Audit Department (IAD) in November 2013. The latter highlighted concerns regarding fiduciary discharge and oversight, accounting discharge, assessment of need for payments, breached conditions of the Joint Financing Agreement (JFA) and unclear roles and responsibilities between pooled partners. DFID Malawi highlighted the fact that their concerns were recognised at country level and steps were already underway to address them by the time of the audit. / Some degree of leakage is inevitable in budget support programmes of this type and the overall value of funds managed at the local level was limited. Funds directly transferred to schools also greatly limited the scope for misuse at intervening levels of government however the planned PETS survey will shed more light on its relative efficiency. / 4.3 Climate and Environment Impact / The climate and environmental impact of MESRP hinges on the construction of the school blocks. In order to mitigate the impact of land clearing a policy was agreed and enforced that any trees cleared for construction would be replanted in the same number once construction is completed. However the overarching environmental risk stems from deforestation due to the use of burnt bricks in LDF school construction. Central construction under EIMU minimised the environmental impact as environmentally friendly building materials were used. However the increasing use of LDF funds for primary construction involving community contributions in the form of burnt bricks, means the negative impact on the environment has increased. In recognition of this the LDF is currently piloting the use of Soil Stabilised Blocks (SSBs), and are training and equipping the districts. The target is to have 100 classrooms made from SSB in 2013/14.

5. Value for Money
5.1 Performance on VfM measures / Value for Money (VFM) is defined by DFID as the relationship between what we invest (the ‘money’) and what we get in return (the ‘value’) therefore VFM is about linking results to the allocation of resources. This can be broken down into three parts; economy, efficiency and effectiveness. / Economy / Economy in education relates to the key inputs (cost per year per child supported, classroom construction, teacher salaries and textbooks) being procured at the best price, while ensuring that they are of appropriate quality. The main indicators used to measure the economy of an education system are: / Unit cost per child per year / Teacher salary / Average cost of a primary textbook / Classroom constructions cost / Malawi has one of the lowest unit costs for primary education per child per annum in the countries DFID supports (see 3.2 above for unit costs) however lower prices are not necessarily indicative of better value for money. Given that teacher salaries typically absorb a large amount of the recurrent budget the amounts left for teaching and learning materials may be insufficient. As Malawi moves towards a ratio of 1 textbook per child we expect costs to increase here as programmes seek to improve quality. / The cost of textbook production in Malawi is relatively high ($3 compared to an average of $1.9 in the countries where DFID works) reflecting the practice of government printing through the Malawi Institute of Education (MIE) which is neither competitive nor cost effective. MoEST has successfully released the copyright for secondary textbooks to boost competition and the market for local printers. Talks are currently underway between MoEST, MIE, DIAS and publishers to put the same system in place for primary textbooks. A pilot scheme with local publishers is expected to start in FY 2014/15 which should improve economy in textbook provision in the long run. The decentralisation of procurement and distribution of TLMs (excluding textbooks) to districts should drive down costs and improve service delivery as compared with the central model. / The costs of classroom construction are above average for DFID supported countries however new approaches, such as community construction through the Local Development Fund, have led to substantial cost savings. The introduction of LDF construction has considerably reduced costs– an LDF classroom costs approximately 60% of an EIMU one (see section 1.1 for price comparisons). However the community score-carding of the LDF construction revealed concerns on quality, durability and fiduciary risk therefore these aspects of community construction need to be addressed before conclusive conclusions on VFM of this option are drawn. / Efficiency / Efficiency in education refers to how well inputs are converted into outputs. An efficient system is one in which children learn and remain in school. It is also one where schools are open when they should be, students and teachers turn up regularly, and time in school is spent on teaching and learning. The main indicator is survival rate/primary completion rate. In Malawi there has been a large drop in survival rates to grade 5 from 75% in 2011 to 59% in 2012. Further detail is provided in Section A, 3.1 above. / While enrolment, survival and completion data can be tracked through the national Education Management Information Systems (EMIS), indicators of systems efficiency, such as pupil and teacher absenteeism, are more challenging and are not currently captured by MoEST or DPs. / Effectiveness / An effective education system has children not just enrolled, but learning. The main indicator is learning outcomes, using measures available locally. The MESRP attempted to improve (although not measure) learning outcomes through ensuring the basics were in place for the education system to function: e.g. more classrooms, more TLMs and more teachers. Many of the outputs in these areas fell short of expectations therefore no improvements in learning outcomes have been observed. It is worthwhile noting of course that Malawi does not have a regular assessment of learning outcomes. Currently summative exam results are used although these are an unreliable proxy, SACMEQ data (though this is irregular) and EGRA data (which tests only reading skills). Much remains to be done in measuring learning outcomes. / No specific VfM metrics were set as this programme’s design pre-dated their use, but a range of unit costs related to education inputs and the cost of education delivery are embedded in the project logframe that may be used as a measure of performance. Drawing firm conclusions on the programme’s VFM is compounded by the difficulty in comparing year on year without converting to hard currency. Unit costs per level of education per year are shown in Section A, 3.2 above. / Another factor in the unit costs is that of Complimentary Basic Education (CBE) which has expanded rapidly to provide non formal education for 20,000 out of school children mostly in the 9 -14 year range. With its origins in the GoM response to EFA, CBE initially received support from GIZ, DFID and UNICEF and has been funded directly by MoEST since 2011. Through a network of CBE centres the Malawi CBE programme provides out-of-school children with basic education and an opportunity to return to school. It received recognition in the Global Monitoring Report of 2012 and as a result a number of other countries are replicating the model (Zimbabwe, Namibia). Its delivery cost p.a. has been calculated (V. Dub Jan. 2014) as approximately a third of the cost of primary education (taking into consideration a range of factors and assuming that primary schools are fully resourced with more trained teachers and inputs than is presently the case). Actual unit costs of primary education are much lower, due to the very large class sizes observed and other factors. It clearly represents an interesting alternative for scaling up education access in a resource constrained environment however budget availability is currently uncertain. / 5.2 Commercial Improvement and Value for Money / Value for money, though compromised by the failure to deliver infrastructure on the scale originally planned, has improved over the course of the programme. The move from central construction through EIMU to LDF has dramatically reduced unit costs and improved value for money. Mzuzu Diocese has also managed to construct at significantly lower costs than even LDF however the time period is much greater; almost three years compared to 9-12 months. UNICEF unit costs are higher than EIMU however this has to be weighed against the quality and complexity of construction and the expediency in completion (EIMU having failed to complete construction at multiple sites). The direct funding of schools through the PSIP programme has improved levels of direct support and value for money at school level. Competitive tender for construction, textbooks, TLMs (at district and central level) has helped to assure that value for money is delivered in procurement. / 5.3 Role of project partners / The main project partner in MESRP was the Government of Malawi through the MoEST. MESRP and the pooled fund more broadly suffered from a lack of government commitment to education reform, particularly in the first 2 years. This was evident through the lack of policy reform, political leadership and failure to establish the mechanisms to deliver basic inputs e.g. under resourcing of EIMU and procurement department. However there have been significant changes in MoEST over the last 18 months (the Secretary for Education, Science and Technology, Principal Secretary for Basic and Secondary Education, Director of Finance, Deputy Director of Finance, Director of Planning, Director of Basic Education and the Director of Secondary Education were all replaced, sometimes more than once). The changes in personnel have brought with them a greater push towards reform. In addition a number of analytical studies have been undertaken by MoEST showing increasing interest in learning, greater transparency with both donors and civil society has been apparent (key members of the latter as well as the Teachers Union of Malawi were keynote speakers in the 2013 JSR) and there is a strong push towards evidence based programming and budgeting from within. / Pooled donors, World Bank, GPE, UNICEF, Germany were also key partners. The role of pooled partners in implementing and supporting the pooled fund has been mixed. In the original Programme Memorandum it was proposed that the World Bank would take the lead oversight role in finance and procurement. However, understandably, the World Bank were primarily focused on the performance of Bank (and GPE) funds rather than the performance of the pooled funds as a whole. This was highlighted in the Internal Audit Department’s review of December 2013 and the Education Fiduciary Risk Assessment in August 2013. It was suggested that DFID play a stronger oversight role in PFM and procurement to mitigate risks associated with SBS in those areas. / Concerns were also raised regarding the incoherence of pooled partners’ disbursal mechanisms: each measured performance differently and disbursed or withheld funds on different schedules. This undermined the pooled fund and increased the transaction burden on MoEST (something a pooled fund is intended to reduce). Germany in fact only disbursed the first of three planned tranches of funding due to unresolved issues with the first financial audit and the lack of procurement audits as stipulated in the JFA. UNICEF were very much a token partner contributing $250,000 a year into a separate bank account from the rest of the pooled funds. / In order to address the above issues and improve donor coordination monthly pooled partner meetings were established in 2013. Negotiations were underway to revise the Joint Financing Agreement and pooled conditions in preparation for a revised phase of sector budget support when the Cash-Gate scandal broke. / 5.4 Did the project represent Value for Money : No / On balance the programme did not represent good value for money. In simple terms the expected volume of outputs from the programme were not achieved, especially in capital intensive construction and with the bulk of funds already transferred as budget support, these are not ring-fenced beyond the list of eligible expenditures. However the impetus of the crisis in 2012 has led to more cost effective ways of construction and teacher training and decentralised service provision which provides the potential for better value in the future.

6. Conditionality
6.1 Partnership Principles and specific conditions / The annual sector budget support payments were designed to be transferred bi-annually with the first 50% transferred as soon as the budget reflecting spending targets is approved by Parliament, usually in July each year. The second 50% should be transferred in January each year if the Joint Sector Review concludes that satisfactory progress has been made on nine key reforms areas (benchmarks, not formal conditions). The table below sets out these 9 areas, with a summative evaluation of progress and direction of travel. / MESRP Nine key reforms areas Summative Assessment of progress (2010 – 2014) / Construction and rehabilitation of school infrastructure Poor overall, Pupil Classroom ratio increase 7%, but more positive outlook with transition to use of LDF: lower unit costs and stronger performance management and PFM. Overall volume completed lower than targets / Reduced primary GERs and increased NERs (towards 100%) Hard to judge, targets not feasible and data on age specific population uncertain. Enrolment broadly increasing with demographic growth, enabling most of the primary age cohort (6-13 year) to receive some level of schooling. / Gender parity in primary and secondary school enrolment Primary GPI 1 achieved, static in all years reported. Secondary GPI around 0.85, inequity building in late primary and transition/exams. / Reduced Pupil: Teacher Ratios (PTRs) in primary schools PTR dropping from 81 to 69 nationally. Still major inequities (1,000 schools > 90). Fiscal space has limited hiring of new ODL teachers in 2014, risking loss of investment and attrition / Measurement and monitoring of learning outcomes Examinations static pass mark suggests norm based, not useful as metric. SACMEQ 2014 not yet conducted preventing one key measure. EGRA and some local assessment promising / Systematic and regular inspection of all educational institutions Very limited school inspection, (5% in last 6 months 2013) linked to finance release. Unreformed practices, but some CPD occurring. / Decentralisation of management and financing of primary education Many positive examples of decentralisation, accelerated by 2012 shock: LDF construction, PSIP school grants, Complimentary Basic Education (CBE), District finance for supplies and book fairs, ODL teacher training. MoEST stopping central staff allowance abuses. / Improved efficiency through reduced repetition and dropout rates Repetition and dropout increasing in 2013, no policies towards semi-automatic promotion introduced and financing crisis may also contribute / Increased role for the private sector and private financing Growth in private secondary schooling is demand based. Potential for LDF to attract private finance if it became autonomous institution. / Overall 2 of 9 clearly positive, 2 of 9 clearly negative, 5 of 9 mixed / Overall Amber / In addition three key budget commitments and spending targets were jointly agreed: / 20% of the discretionary GoM budget allocated and spent on education, each year from 2010/11 (donor funds additional); / 60% of the education budget spent on primary education by 2013 (50% in 10/11, 55% in 11/12, 60% in 12/13); / 90% of funding to the recurrent education budget released by MoF within year (80% in 10/11, 85% in 11/12, 90% in 12/13). / The first was achieved in the last two years (see Section B, 1.4 above), with the second only being missed in the last year (55%, not 60%). The budget releases have also been met (90.5% in 2012/13), although tracking this has proved difficult. Overall there was not judged to be sufficient grounds to block SBS disbursement on these budget and spending commitments. In the first of the three years, poor performance in three of the nine key reform areas, especially school infrastructure led to £2.33m of SBS being withheld. This amount was provided instead to UNICEF for direct spend on child friendly school construction. There were some questions from the MOEST Budget department on the unintended consequences of the 60% allocation to primary education commitment. As financial allocations to tertiary institutes are made directly through subventions and are often politically influenced, this led to a squeeze on finance for secondary education in the reporting period. Ideally all sub-sector’s needs and priorities would be considered jointly.

7. Conclusions
Overall much of the reasons for the under achievement in output and outcome terms of this programme can be explained by considering the top level ‘goal / impact‘ level assumptions made within the original programme logframe. Assumptions were expected to hold, but clearly few of them did in the 2010 – 2013 period. Overall government political leadership and coherence to improve service delivery was weak. Whilst the technical and political leadership under the MoEST was less than perfect and there were clear capacity gaps, the major reason for ‘moderately unsatisfactory’ outputs lie at the macro-political economic level. / In the first 24 months there were a number of institutional and bureaucratic blockages around the establishment of new structures and processes required for the pooled fund. These were greatly under-estimated by both government and development partners, despite the provision of five technical assistants, thus capacity and will to introduce new ways of working were insufficient. / The new construction management unit (EIMU) struggled to interact with MoEST’s internal procurement department and using government financial systems dramatically slowed down payments (e.g.16 steps were being needed in comparison the former PIU had dedicated bank accounts and paid within 30 days). More broadly a complex system of eligible expenditures and procurement requirements emerged that were sometimes driven by World Bank requirements and conflicted with government procedures that were more familiar to staff. The first financial audit led to huge demands for documentary evidence that were later scaled back. Neither government nor audit staff were able to cope with these new demands for financial reporting. / Finally in mid-2012, as some of these bottlenecks were being resolved and reform action taken, for example to use the LDF for more rapid decentralised construction, the transition to the new President was swiftly followed by a very rapid devaluation of the currency that caused massive disruptions to many of the procurement and financial systems and further inhibited fund flows. While there has been promising progress and reforms in certain areas, notably the provision of school improvement grants, ODL teacher training and Complimentary Basic Education, these have proven insufficient to impact on the quality of education delivered. / More qualified teachers are employed, but 10,000 were not employed in 2014 due to limited finance to expand the payroll and since October 2013 the Cashgate crisis has suspended direct Financial Aid from DFID and most other donors. This has limited reductions in Pupil Teacher Ratio and the lack of classrooms has led to increases in class sizes and the use of outdoor tuition. Furniture has not been supplied to schools, nor have semi-automatic promotion policies been introduced that contribute to huge, ineffective early grade classes and high rates of repetition and dropout. There are limited measures of student learning available, exam pass rates are unaltered and EGRA and SACMEQ results suggest low acquisition of skills, especially literacy and numeracy. / Recommendations / Whilst the events described have been far from ideal, the crisis response has led to reform in the education sector and capacity does exist within some parts of MoEST to expand and rollout reforms. Malawi actually has good school level data, an ability to plan and provide distance learning professional development and a viable model to expand decentralised construction. It is recommended that in the short to medium term DFID Malawi: / Not abandon support to the education sector in Malawi and the large investments made in infrastructure and capacity over decades. Whilst identical budget support modalities to MERSP are not suggested, other modalities should be actively considered that limit fiduciary risk and continue to build government ownership and drive improved performance. / Exploit and support expansion of some of the new approaches that have emerged from the 2012 crises: LDF construction, PSIP grants, CBE non formal education, ODL training of locally engaged teachers. These have a real potential to enhance Malawi’s quest for quality basic education for all, with efficient and inequitable expansion of access. / Combine improvements in access with a major drive to focus on pedagogic improvements in early grades, so that reading and numeracy skills are quickly embedded. Consider partnerships with USAID’s reading agenda and other mechanism to introduce global best practice, including assessment and curricula reform. / Support further engagement and strategic planning and policy work with the government and main development partners, especially the World Bank and GPE, to redefine plans and approaches of co-operation for the coming 5 years, exploiting opportunities and changes to the landscape as political elections are held, financial aid restrictions relaxed and post 2015 priorities emerge. / Support the planning department of MoEST to balance the relative expansion of needs and priorities of the education sub-sectors and seek opportunities to promote a pre-school readiness year and early years’ holistic interventions. Avoid prescriptive input based, linear models of change and blueprints in programme design, support Malawi to be able to rapidly adapt and course correct. / Consider results based finance approaches, ideally in partnership with others, that drive performance on shared priorities and outcomes. Consider incentives to local actors, especially district councils to provide better services. Expand and open up the existing school level data and mapping information to stimulate demand for equity and greater accountability and transparency in the provision of education. / Support institutional change, reform and development at various key units such as the EIMU, LDF, MIE, the examination body and the colleges providing ODL to adapt and improve their core businesses. / Given DFID’s long association with school construction expertise in Malawi, supporting research into adaptation of construction methods and design away from burnt bricks and that maximise efficiencies and duration with community engagement should be considered.

8. Review Process
This Project Completion Summary Review was conducted in-house by the DFID Malawi Education sub-team with support and guidance from the DFID Tanzania Education Adviser who provided a 5 day working input mission using 10% Cadre time. The process included review of reports and discussions with key informants from MoEST, the LDF, development partners and former Technical Assistants to MoEST. A Sector Working Group meeting was attended in Lilongwe; in addition a visit to schools and the District Education Office in Dedza district was undertaken. The report has benefited from reviews and quality assurance by the DFID Malawi Human Development Team Leader, the Programme Board, and the Deputy Head of Office. / Stakeholders met: / Ministry of Education Science and Technology (MoEST) / Secretary Education Science and Technology, Dr. MacPhail Magwira / Principal Secretary (Basic and Secondary Education), Dr. Anjimilie Oponyo / Budget Director, Planning Department, Mr Job Mwamlima / Budget Office (Education Economist/ODI Fellow), Victor Steenbergen / SWAP Secretariat, Chris Naunje / PSIP Coordinator, Noel Mwango / Director of Basic Education, Dr Joseph Chimombo / Local Development Fund (LDF) Exec. Director Sam Kakhobwe / LDF Director Fin. Mgt. Steve Mchenga / LDF Education Programme Manager John Ngambi / Development Partners / GIZ Technical Adviser to MoEST Jorgen Friis / JICA Project Formulation Advisor in Education, Norihide Furukawa / JICA Project Officer, Maxwell Nkhokwe / UNICEF Chief Basic Education and Youth, Charles Nabongo / UNICEF Education Officer, M & E, Eva Hardardottir / German Embassy, Deputy Head of Development Cooperation, Kerstin Henke / KfW Country Economist, Lamulo Nsanja / USAID Education Office Director, Christine Djondo / GIZ Senior Adviser Complementary Basic Education and Teacher Education, Ken Longden / Nick Hall Financial Adviser to MERSP (2010 – 2012) / Jim Craigie, Construction Adviser to EIMU (2008-2010) and for Phalombe Teacher Training College / Documents sourced / MERSP Programme Memorandum (Jan. 2010) / Education Sector Wide Approach (SWAp) Technical Assistance (TA) Project Completion Report (July 2012) / Annual Review MERSP (July 2013) / Kalondolondo LDF CLASSROOM BLOCK SCHEME SERVICE DELIVERY SATISFACTION REPORT FOR MALAWI (Nov. 2013) / Rudderless decentralisation: fragmented governance and local service delivery in Malawi (ODI, Nov. 2013) / PIEQM World Bank: Implementation Support Review conducted with Joint Sector Review (Dec. 2013) / Out of school children and Comparative Cost analysis of CBE and primary education, Viola Dub (ODI Fellow, Jan.2014) / Local Development Fund School Construction Progress Report via SWAP (April 2014) / EMIS Education Statistical Bulletin 2013 (MoEST Feb. 2014) / Education Sector Progress Report for Quarter Ending 31st Dec. 2013 (MoEST, April 2014) / Scoping Study on Malawi’s Education Sector for DFID (HEART, Feb. 2014) / Internal Audit Report, DFID Malawi / Public Expenditure Review, World Bank, 2013 / Education Sector Performance Reports 2010 -2 2013 / EMIS 2010, 2011, 2012, 2013

Annex 1: Field Trip April 30th, Dedza District

A day’s field visit to schools and the District Education Office in Dedza district was undertaken in conjunction with representatives of government (senior MoEST staff and from the LDF technical support team) and partners (from German Embassy/KfW and UNICEF). Schools visited were purposively selected (non-random) and not far from the main road, all had received some infrastructure support from the pooled joint budget support programme.

Nthulu Full Primary School

A large primary school with 1,600 students around 2-3 km from a busy market. A large campus, relatively well organised, with old brick classrooms (said to date from the 1950’s), a new LDF constructed classroom block (appeared well made and finished), two thatched temporary structures (no furniture) and a very large entry class learning under a tree. Huge variation in class size (4 times enrolment in Std 1 vs. Std 8), with the better rooms and experienced teachers reserved for smaller, higher grades. Two teachers per large class used in lower grades.

Functional toilet blocks in use, but with no water. Slightly more girls than boys overall, but with female enrolment dropping off in upper grades, due to pressure to marry young in some communities. The Mothers group was said to be very helpful in countering this phenomenon.

In meetings with school leadership the process of school improvement planning and PSIP grant use was explained, it seemed to comply with central guidance. Clearly useful application of funds on inputs, staff training and other items, including some textbook purchase. Some local textbook purchase was reportedly ‘buying’ resold ‘not for sale’ govt. books from a local seller. Centrally procured textbooks came late and in low volumes. Doubling of the grant for the current school year was most welcome. The Deputy Head teacher was very unsure how a switch to English as the language of instruction could be effectively handled next year.

LDF construction community engagement was described and transparency process in showing materials purchased and the role of district explained.

Kampini Full Primary School

Brief visit to this roadside school with 1,000 students in a quiet rural area. Again a major classroom deficit with two classes underway under trees. Standard 3 children could read adequately from local language textbooks. Somewhat surprisingly classroom construction underway was with community funds, while LDF had constructed a large teacher house, which was occupied by a senior teacher and his family. Eight other teachers and trainee teachers lived in a much smaller ‘hostel’ house next door. Other teachers lived elsewhere.

Standard 6 class visited had only around 30 students, all sitting on floor, with bad posture for writing. Student teachers’ running class in pairs, the one present was using fairly traditional didactic techniques, but was enthusiastic and appeared committed.

Dedza District Education Office (meeting District Education Manager Mr. Banda)

Interesting discussion on trends observed with Mr. Banda (DEM Dedza), clearly an experienced and dedicated manager. Overall he thought that the process of decentralisation over the past 4 years had been highly beneficial in improving the pace and responsiveness of education service provision. There were less requests to the central Ministry and more ability to respond to community needs.

There had certainly been challenges, for example LDF construction quality was improving from a low level, after a 3 week training course for artisans. For financial and procurement matters, the Council’s centralised secretariat handled processes that could sometime stall without active leadership, the latter was the determining factor in differences in performance between districts. All financial transfers to the District and procurement tenders were publicised on notice boards, the mission was informed.

Future priorities for investment suggested by Mr. Banda included continued work on primary deficits, but also expanding secondary access via Community Day Secondary Schools (CDSS). For example 5 major primary schools feed into a single CDSS with an intake of 50 students. With such limited space, students were discouraged to complete primary school and drop-out, especially girls. Problem of teachers housing was acknowledged: motivation effect, but high unit cost and inequity in provision.

Teachers trained and upgraded through the ODL (open and distance learning) initiative were welcome. Whilst they may have less overall knowledge, primary inspectors (PEA) generally thought they worked hard and were more committed than those trained via pre-service colleges.

After the meeting it was attempted to visit a Complimentary Basic Education (CBE) centre for non-formal education out of school. It did not prove possible to locate one. A catholic mission school was visited which was empty for the day, mock examinations were on-going. A group of Standard 8 students were met who were living informally at the school for the weeks leading up to the exam to revise. They spoke adequate English for a conversation and were keen to go to secondary or resit examinations if necessary.

Mazengera Full Primary School

Visited partly by chance, this school had been selected for major (8) classroom provision by DFID finance through the centrally managed EIMU contractor model. This site had stalled a year ago when last visited due to disputes over payments following the currency devaluation, but was now also most complete, with final painting underway.

Visually and by design the classrooms looked superior to the LDF classrooms: attractive paint, smooth gentle ramps, good lighting and internal store room space. Surprisingly these and the existing classroom had no furniture, just smooth cement floors and according to Mrs Fainess the head teacher, there was none provided or was the community able to provide. This is a major issue, given the high investment cost.

The classrooms looked, and were probably superior in design, finish and durability than the LDF constructed block visited earlier. In addition ‘Sand Cement Blocks’ were used to avoid the negative environmental impact of more commonly used burnt blocks. However whether this justifies the much higher unit cost and lack of community engagement is questionable, especially given the huge national deficit and pace of construction procurement.

A librarian was met who carefully recorded student reading and book borrowing, her supply was a carrier bag with around 15 donated books

Annex 2

Teacher projections to meet 60:1 PTR up to 2020, (MoEST, 2014)

Impact of Semi-automatic promotion on primary enrolment rate up to 2020, (MoEST 2014)