## Sheet1
PROJECT NAME
IMPACT | Impact Indicator 1 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
|  | Planned | 0 | 25% | 50% | 75%
Improved policy making and programmes for sustainable Ethiopian development | Proportion of DFID Ethiopia teams who have accessed the Fund outputs, that have find the information ‘Very useful’ in programming decisions* *(Programme teams are: WCCC, GST, LHT, and HD) | Achieved
Source
Analysis from Fund Manager, Corporate Effectiveness Team
| Impact Indicator 2 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
|  | Planned | See Partnership Principle assessment Nov 2012 and other relevant docs. | Some progress in each of 3 areas against baseline. | Evidence of policy progress in GTP2 | Evidence of progress against the policy priotities
| Evidence of greater GoE policy focus on DFID CPRD priorities: economic development, women and girls, and poorest sectors of the population | Achieved
Source
Qualitative analysis of GoE policy statements and reports & Staff Survey
OUTCOME | Outcome Indicator 1 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016 | Assumptions
|  | Planned | 0 | 50% | 75% | 90% | Lessons learned lead to changes and are reflected in future programming. Evidence is used in decision-making and takes context fully into account. Evidence is fully informed by gender considerations, including disaggregation of data, and where relevant climate and environmental impacts.
Increased availability and use of evidence in DFID Ethiopia, Government and Development Partner programming decisions and policy discussions | Proportion of DFID E staff aware of outputs of Fund projects and how to access them | Achieved
Source
Staff survey
| Outcome Indicator 2 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
|  | Planned | 0 | 75% | 80% | 100%
| % of new DFID Ethiopia business cases using evidence from Fund outputs | Achieved
Source
Staff survey
| Outcome Indicator 3 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
| Level of awarness of Fund outputs among Government and development partners | Planned | NA | Some partners aware of the Fund | Evidence of Fund research used in partner / Government discussions | Evidence of demand from partners / Government to quote evidence or develop similar analyses
Achieved
Source
Possible stakeholder survey
Source
Staff survey, government reports and meetings
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 1.25 | 0 | 0 | 1.25 | 100%
INPUTS (HR) | DFID (FTEs)
1
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016 | Assumption
|  | Planned | 0 | 5 | 10 | 15 | Resarch outputs are of high quality and relevance. Capacity is developed to ensure appropriate uptake of researh findings. Evidence is brought to the attention of users.
Production of evidence and analysis to strengthen knowledge base and generate innovative ideas for policy planning | Number of research and analytical products delivered (cumulative) | Achieved
Source
Fund management information
| Output Indicator 1.2 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
| Percentage of research and analytical products delivered scored as "good" or "excellent" by DFID E staff | Planned | 0 | 75% | 90% | 100%
Achieved
Source
Staff survey
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Target: March 2016
75% | Number of high level policy workshops discussing Fund outputs, with high level stakeholders (cumulative) | Planned | 0 | 4 | 8 | 12
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Fund management information |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 1 | 0 | 0 | 1 | 100%
INPUTS (HR) | DFID (FTEs)
0.8
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (April 2013) | Milestone 1: April 2014 | Milestone 2: April 2015 | Milestone 3: March 2015 | Assumptions
|  | Planned | 0 | 0% | 50% | 100% | A significant proportion of research and analytical products are unclassified.
Unclassified knowedge products (research papers, briefings, and policy papers) are made accessible. | Number of unclassified research and analytical products made available in open access format. | Achieved
Source
Research for Development website (R4D)
IMPACT WEIGHTING (%) | Output Indicator 2.2 |  | Baseline | Milestone 1: April 2014 | Milestone 2: April 2015 | Milestone 3: March 2015
25% | Percent of selected DFID external implementing partners judge unclassified research and analytical products as "good" or "excellent" | Planned | 0 | 0 | 55% | 66%
Achieved
|  | Source |  |  |  |  | RISK RATING
|  | Survey of key implementing partners |  |  |  |  | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
|  | 0.2 | 0 | 0 | 0 | 100%
INPUTS (HR) | DFID (FTEs)
0.2