Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Monitoring and Evaluation of the UK’s Framework for Results for Malaria (“Breaking the Cycle: Saving lives and protecting the future”) and RMNH (“Choices for Women: Planned pregnancies, safe births and healthy newborns”)
Programme Value: £4.5m		Review Date: January 2015
Programme Code: 203368	Start Date: April 2012	End Date: July 2017

Summary of Programme Performance
Year	Jan 2014	Jan 2015
Programme Score	B	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

This programme was set up to deliver a mid term review (MTR) and final evaluation for the Frameworks for Results on malaria and reproductive, maternal and newborn health (RMNH), which were published in December 2010. The mid term review was completed by end 2013.

During the year covered by this Annual Review, the mid term review was published (in May) along with DFID’s response. As recommended by last year’s Annual Review, the approach for the final evaluation has been fundamentally reconsidered. New Terms of Reference were developed and externally reviewed. Apart from completing payments for the mid term review, there was no spend from this programme.

An external reviewer examined the Terms of Reference and concluded that the final evaluation was feasible but unlikely to be good value for money. Synthesising and sharing evidence and lessons from DFID malaria and RMNH programmes was more likely to generate more widespread lesson learning at lower cost.

Summary of recommendations for the next year

DFID’s Human Development Department (HDD) should add key Framework commitments not currently included in the DFID Results Framework into its mid year report publication in February 2015.

HDD should work with the HOP during January to June 2015 to synthesise lessons from implementation of programmes under the Frameworks for Results, including how value for money is assessed and monitored. These should be captured and shared with country offices.

HDD should revisit the approach for the final evaluation in summer 2015, taking into account the purposes for the evaluation as set out in the Frameworks: 1) to synthesise and examine DFID’s progress and results for accountability and 2) lesson learning. The decision should also take value for money into account.

HDD should review the logframe should in autumn 2015 to ensure the 2015 milestones are realistic in the light of changes to the timeframe for the programme.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	3744994
DevTracker Link to Log frame:	4330685

Outline of the programme

The UK government is committed to reduce poverty in poorer countries, in particular through achieving the Millennium Development Goals (MDGs), including MDG 4 (Reduce child mortality), MDG 5 (Improve maternal health) and MDG 6 (Combat HIV/AIDS, malaria and other diseases). While progress is being made towards attainment of the MDGs, the rate of progress is insufficient to attain the MDG targets in some countries, with particular challenges in reaching the poorest and most disadvantaged.

To support attainment of the MDGs, in December 2010 DFID published Frameworks for Results on malaria and reproductive, maternal and newborn health (RMNH):

- Breaking the cycle: Saving lives and protecting the future. The UK’s Framework for Results for malaria in the developing world and
- Choices for women: Planned pregnancies, safe births and healthy newborns. The UK’s Framework for Results for improving reproductive, maternal and newborn health in the developing world.

 These set out frameworks for delivering on UK Government commitments to:
   •	help halve deaths from malaria in at least ten high burden countries by 2015;
   •	provide access to modern methods of family planning for 10m additional women, including 1m young women aged 15 – 19 by 2015;
   •	prevent more than 5m unintended pregnancies by 2015;
   •	ensure at least 2m safe deliveries, particularly for the poorest 40% by 2015; and
   •	save the lives of at least 50,000 women during pregnancy and childbirth and 250,000 newborn lives.

Together these two Frameworks for Results committed up to £7 billion (up to £4.4 billion for women’s and children’s health and up to £2.5 billion for malaria).

This programme was set up to evaluate the implementation and outcome of the two Frameworks for Results. A mid term review was completed in 2013. In addition, the programme has delivered a review of the progress DFID has made towards the commitments laid out in the 2011 HIV position paper Towards Zero Infections.

The following was planned to be delivered:
In-depth case studies on a select number of Framework interventions and thematic areas.

Final evaluation and evaluation report: The evaluation of the Frameworks for Results will cover the period up to Dec 2015. The scope of the evaluation will be clarified following the results of the initial evaluability assessment and production of the mid-term review.

A contribution to the evidence base for malaria control and the improvement of reproductive, maternal and newborn health outcomes for DFID and the wider global community.

Effective dissemination of the findings and lesson learning to key partners and stakeholders.

This approach has been reviewed and revised following the mid term review.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
The aim of the programme is to improve the effectiveness and value for money of DFID and partner malaria and RMNH programmes.
The mid term review (MTR) found that the Frameworks for Results have served an important and effective role. They have strengthened DFID’s influence in international forums and contributed to sustaining or reinforcing international attention on malaria and RMNH. The evidence reviews supporting the Frameworks were found to be high quality and had an independent value in providing an authoritative assessment of the evidence on effective interventions. The bilateral/multilateral funding split and the bilateral spend by country were considered to be broadly appropriate. The Frameworks have avoided potential risks related to their results-focused orientation, largely because of DFID’s continuing commitment to partnership working and support to health systems. DFID is broadly on track against the spending and results commitments within the Frameworks.

The MTR did not recommend any major changes to DFID’s policy direction on malaria and RMNH although it did find that continued attention to strategies to reach marginalised people will be key to meeting global and DFID targets. It also found that strengthened health systems, together with increased government efforts and commitment of resources, will be required to sustain the gains made.

The findings from the mid term review were shared with internal and external stakeholders and discussed with DFID health advisers. Discussions with country offices have also taken place this year about measuring value for money in health programmes.

Overall the programme has delivered its planned outputs so far, but there is more to do to learn lessons from the implementation of DFID’s malaria and RMNH programmes and share across country offices to improve effectiveness.

Overall output score and description
The programme scored a B last year. Although written products were produced to an acceptable standard within the timeframe, this was not a straightforward process either for the Framework for Results Mid Term Review or for the HIV position paper review. Much input was required from DFID staff and robust management of timescales. On the Mid Term Review, additional input was required from external experts to support the process.
This year, the programme has scored an A. It has not funded new work but has communicated the mid term review and reviewed the approach for the final evaluation. Findings from the Mid Term Review have been taken forward. For example DFID has explored incorporating results information into its aid management system and work has started on development of a results module for the new Aid Management Platform. The Africa Regional Malaria Programme has been extended and lessons have been shared on improving value for money in health programmes.

Output 1: Availability of evidence on effectiveness and relevance of Frameworks for Results (A, weighting 80%)
Performed as expected. The mid term review (MTR) was published with DFID response and new Terms of Reference were developed and reviewed.

Output 2: Strengthened accountability for malaria and RMNH across DFID (B, weighting 20%)
Performed just under expectations. New evidence products were developed and shared, and the MTR findings were communicated externally and internally. Awareness of the MTR and its findings is not high in country offices because many of the findings related to weaknesses in DFID corporate systems rather than programme issues.

Key lessons

The Frameworks for Results have served an important and effective role. They have strengthened DFID’s influence in international forums and contributed to sustaining or reinforcing international attention on malaria and RMNH. The evidence base was of high quality and had a value in its own right.

DFID is broadly on track against its commitments in the Frameworks. DFID’s

Evaluation of such wide-ranging strategy documents is extremely complex and challenging to do in a way that generates useful learning. The draft Terms of Reference for the final evaluation focused on three key areas. The expert review concluded that these areas are appropriate and the evaluation is feasible. However it found that learning could be generated at much lower cost and reduced risk through synthesising evidence and lessons learned across the RMNH and malaria themes.

Key actions

HDD should incorporate key Framework commitments not currently included in the DFID Results Framework into its mid year report publication in February 2015.

HDD should work with the HOP during January to June 2015 to synthesise lessons from implementation of programmes under the Frameworks for Results, including how value for money is assessed and monitored. These should be captured and shared with country offices.

The approach for the final evaluation should be revisited in summer 2015, taking into account the purposes for the evaluation as set out in the Frameworks: 1) to synthesise and examine DFID’s progress and results for accountability and 2) lesson learning. The decision should also take value for money into account.

The logframe should be reviewed in autumn 2015 to ensure the 2015 milestones are realistic in the light of changes to the timeframe for the programme.

Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Availability of evidence on effectiveness and relevance of Frameworks for Results
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	80%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2014	Progress
1.1 Concise reports delivered as specified by TORs on the evaluation of the FfRs on time, with only 2 drafts needed befor final version and with limited comments from external reviewers.	None	On track. The Mid Term Review was published in May 2014, along with summaries of the MTR and DFID’s response.
1.2 Deliverables as specified by TORs for the review of the 2011 HIV Position Paper, complete on time to publish DFID review paper by World AIDS Day 2013	None	No further action.
1.3 Number of products reviewed externally with comprehensive comments delivered within agreed deadlines.	2	On track. The Mid Term Review report and draft TORs for the final evaluation of the Frameworks was reviewed by an external evaluation expert.

Key Points

Output 1.1: The Mid Term Report (MTR) was delivered by external consortium ePACT in December 2013. The consortium also produced two page summaries of the report, one for malaria and one for RMNH stakeholders. The MTR and the summaries were published in May 2014. At the same time DFID published its response.
Last year’s Annual Review found that it is not feasible to aim to evaluate the impact of the Frameworks as a modality in themselves as evidence on their impact does not exist. It recommended that the approach for the final evaluation of the Frameworks should be fundamentally reconsidered, including revising the Terms of Reference.

Because of this change in approach, in April 2014 the contract with ePACT was terminated. A new draft set of Terms of Reference (TORs) were developed. Following consultation within DFID, these focused on three areas likely to be useful for DFID’s future malaria and RMNH programming:

- the extent to which current programmes are reaching the poorest
- how to strengthen and integrate health systems and
- the balance of different funding instruments operating in country.
Output 1.2: No further action was planned for this output in 2014.
Output 1.3: The Mid Term Review and the new draft TORs were reviewed by external evaluation expert. His report concluded that these areas are all highly appropriate and proposed improvements to strengthen the TORs. The review concluded that such an evaluation is feasible. However it also questioned whether it would be advisable given that the learning from such an evaluation could be generated at much lower cost and reduced risk through synthesising evidence and lessons learned across the RMNH and malaria themes.

Two main aims for the evaluation were envisaged in the Frameworks for Results: accountability for results and lesson learning.

The accountability function is fulfilled by ICAI, the NAO (who conducted a VfM study on malaria in 2013) and the IDC (who conducted a study on health systems strengthening this year). Each of these bodies scrutinise DFID’s expenditure and what has been achieved. In addition the DFID Results Framework monitors most of the headline results commitments in the Frameworks and progress is reported in DFID’s Annual Report. An evaluation which focused on accountability would duplicate these processes. There are some commitments which are not included in the DFID Results Framework (unintended pregnancies averted, progress for the poorest 40% and adolescent girls) and these should be included in DFID’s mid year report publication in February 2015.

Learning lessons for future DFID programming would be extremely valuable. This was the rationale for reducing the scope to three key policy questions in the draft Terms of Reference. There is a need to learn lessons from current programming, pulling together information from Annual Reviews across the portfolios. The approach for the approach for the final evaluation should be reviewed again, in the light of this work, during 2015.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation from last Annual Review: The approach for the final evaluation of the Frameworks should be fundamentally reconsidered, including revising the TORs. HDD should clarify the purpose and scope of an evaluation and its evidence needs and, in discussion with the MERG, agree a revised approach and revised logframe by March 2014.
Response: This has been done. It has been agreed to synthesise lessons from existing programmes initially and review the approach for the final evaluation again in 2015.

Recommendations

Key Framework commitments not currently included in the DFID Results Framework should be incorporated into DFID’s mid year report publication in February 2015.

The approach for the final evaluation should be revisited in summer 2015, taking into account the purposes for the evaluation as set out in the Frameworks: 1) to synthesise and examine DFID’s progress and results for accountability and 2) lesson learning. The decision should also take value for money into account.

The logframe should be reviewed in autumn 2015 to ensure the 2015 milestones are realistic in the light of changes to the timeframe for the programme.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 2: Strengthened accountability for malaria and RMNH across DFID
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones 2014	Progress
2.1 Number of DFID health advisers contributing to the gathering of evidence	15	Partially achieved. Health advisers have contributed to gathering of evidence on accountability but less so on lesson learning.
2.2 Number of DFID Departments or country offices involved in discussions on implementing the recommendationsf rom the MTR and evaluation.	10	Achieved. There was wide consultation on the DFID response to the MTR, covering 10 DFID departments.
2.3 % of health advisers aware of MTR and evaluation findings	100%	Partially achieved. The findings from the MTR were communicated internally and externally but awareness among health advisers is not universal.

Key Points

Output 2.1: Health advisers contribute to the gathering of data on progress against headline targets for the DFID Results Framework, including for the Lives Saved indicators, for which training is organised on the use of the Lives Saved model. There have been discussions on lessons learnt, for example through the weekly health adviser network, but more could be done to generate a systematic sharing of evidence and lessons.

Output 2.2: A wide range of departments were involved in discussions on the DFID response to the MTR. These included Finance, Corporate and Performance Division, Research and Evidence Division, Africa Regional Department, Asia Regional Department, Multilateral Effectiveness Department, United Nations and Commonwealth Department, Global Funds Department, Global Statistics Partnership Department, Evaluation Department, and Human Development Department teams.

Output 2.3: A communication plan was developed to communicate the findings from the Mid Term Review internally and externally. This included an Insight Notice on DFID’s intranet, a meeting with DFID’s health advisers in April 2014, and communication to external stakeholders. One of the key issues raised by the MTR, how value for money is treated in health programmes, was covered in a follow-up meeting with health advisers in November 2014. This discussed the experience of incorporating value for money into DFID health programmes in Mozambique and Zambia. However, because the findings from the MTR primarily related to DFID’s systems rather than its programming, the focus has been on engaging on key issues such as value for money rather than the Mid Term Review itself. As a result it is unlikely that all health advisers are aware of the findings of the MTR.

Summary of responses to issues raised in previous annual reviews (where relevant)

Recommendation from last Annual Review: HDD should develop a communication plan to share the findings from the MTR and rebuild the confidence of internal stakeholders in the report. This should be based around the consultation process for the MTR response. The communication plan should also include external communication. By end January 2014.
Response: This was done.
Recommendation from last Annual Review: HDD should consult widely on the DFID response to the MTR including with senior management to ensure there is support for the commitments made. By end February.
Response: This was done.

Recommendations

HDD should work with the HOP during January to June 2015 to synthesise lessons from implementation of programmes under the Frameworks for Results, including how value for money is assessed and monitored. These should be captured and shared with country offices.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The costs for the programme are determined by the fixed term agreements established under open competition. These are driven by salary costs and particularly the mix of personnel involved in the consortium and the number of days they are used. Experience from the MTR is that having the sufficient days from relevant health experts built into the contract is critical.

Costs for work carried out in 2014 were £5,250 for the external expert review of the draft Terms of Reference for the final evaluation.

VfM performance compared to the original VfM proposition in the business case

VfM for the Mid Term Review was as envisaged in the business case. The reports were delivered on time while financial payments slipped by about one month. However it required a lot of input from DFID Advisers and staff to ensure that OPM met the TOR product requirements. It also required a few days of additional evaluation specialist consultancy support to advise the consultants and improve the product.

It should be noted that the initial estimate for the evaluation costs (£4.5 million) in the business case have so far proved to be more than was needed. The evaluation assessment and Mid Term Review together cost £664,912,000.

Assessment of whether the programme continues to represent value for money

The approach to the final evaluation will be determined on value for money considerations. The external review of the new draft TORs recommended that DFID should consider effective and value for money approaches of synthesising evidence and lessons learned relating to RMNH and malaria. These will be taken forward during 2015, and will inform a decision on the approach for the final evaluation.

Quality of financial management

The contract was a fixed price one. ePACT provided an estimate of the requitred inputs and costs of the evaluation as part of the inception report which was agreed by DFID. They also proposed a payment schedule based on the attainment of milestones, such as the production of reports. These provided to be realistic and accurate apart from the final part of the mid-term evaluation when it transpired consultancy input days exceeded planned days.

ePACT requested a virement of contract inputs to increase the number of consultancy input days, which would have within the overall cost envelope by using savings from the in-country visit costs. This was refused by DFID in view of fixed price nature of the contract.

Date of last narrative financial report	n/a
Date of last audited annual statement	n/a

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk

The risk log has been reviewed, see table below. The key risks are that stakeholders across DFID do not have the commitment or capacity to contribute, that the evaluator does not have sufficient expertise to conduct the final evaluation and that insufficient DFID monitoring data is available for the evaluation.

Risk	Impact	Like-lihood	Direction / of travel	Action to mitigate risk
MERG members do not have commitment or capacity to conbribute, or authority to take decisions and implement required decisions.	M	H	↗	The MERG has not been active during 2014, and will be involved in the final evaluation as appropriate to ensure continued engagement.
Insufficient expertise and capacity within IMG to maintain momentum over time.	M	M	→	Ensure there remains an evaluation expert on the IMG. Include responsibilities in job objectives of members of the IMG. Keep relevant team leaders in HDD up-to-date on progress.
Portfolio of individual project and programme evaluations insufficient to generate new evidence to inform policy and programme design.	L	M	→	Review with EvD the DFID portfolio of relevant evaluations.
External evaluator does not have sufficient expertise to conduct the final evaluation.	H	H	↗	Focus on lesson learning and review the approach to the final evaluation in the light of this.
Findings from lesson learning and final evaluation not acted on.	M	M	↗	Ensure there is wide-spread involvement in lesson learning activities and key issues are raised with senior management.
Insufficient reliable DFID monitoring data available for the evaluation.	H	M	→	The approach to the final evaluation must be feasible and take account of availability of information on DFID programmes.
Evidence generated is not disseminated to external stakeholders.	M	L	→	Develop communication plan for internal and external stakeholders from lesson learning and final evaluation.
Partners do not act on evidence generated.	M	M	→	HDD teams identify opportunities to influence for change through global forums.

Outstanding actions from risk assessment

The key actions to mitigate the risks are:

- to use the Monitoring and Evaluation Reference Group sparingly and strategically to ensure continued engagement.
- To focus on lesson learning across the portfolio of malaria and RMNH programmes, and review the approach to the final evaluation in the light of the findings, so that it is feasible, provides good value for money and good quality evaluators are likely to be available to carry it out.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The only product delivered this year, the review of draft TORs, was delivered to deadline.

Performance of partnership (s)

No longer applicable since the contract with e-PACT was terminated.

Asset monitoring and control

Not applicable.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

No further evidence has been gathered this year. Further evidence of what works across the malaria and RMNH portfolios will be gathered through the lesson learning exercise next year.

Monitoring progress throughout the review period

Little monitoring has been required this year as the contract with ePACT was terminated.

This review has been led by Penny Innes, Senior Responsible Owner, with input from team leaders and advisers from the Health Services Team and Aids and Reproductive Health Team and Scott Hardie, project officer.