Programme Completion Report - Top Sheet

This Top Sheet captures the headlines on the programme performance over the course of its lifetime. Teams should attach summary sheets from each annual review over the life of the programme.

Review Date:	05/01/2015

Title: Trade Transparency Project
Programme Code: 203530	Start Date: July 2012	End Date: October 2014

Summary of Programme Performance

Year	2013
Programme Score	A++
Risk Rating	Medium

Financial Position

Original Programme Value	Approved budget: £300,000
Extensions/ amendments	Original dates: August 2012- August 2013 / Extended to October 2014 (Phase 2)
Log-frame revisions (with dates)	2013 – Output Indicator 1.3 added following June 2013 Annual Review and user targets were increased to be more ambitious.
Total programme spend	£198,845

Follow up actions required following closure

Request Annual audited statements for CCHubs. The final expenditure for CCHubs was in October 2014, therefore the audited statements are expected to be delivered after the auditing process in January 2015.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/3717598.doc
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/3589104.xlsx

Outline of programme and what it has achieved

Programme aims

Our support aimed to illustrate to the general public the impact of trade barriers on the prices they pay for everyday consumer goods. This support would help to inform consumers in the developed and developing world about the impact that their government’s trade policy decisions have on them, encouraging debate and ultimately lobbying governments to reduce trade barriers.

The UK supported two organisations – Co-creation Hubs (CCHubs) and RLabs to:

- collect and analyse trade and consumer data;
- to design, develop, and produce online tools (such as interactive websites, games or infographics) and mobile applications based on the analysed data to make this data more accessible to ordinary people.

Initial support of £300,000 running from August 2012 to August 2013 was planned. However in September 2013, a second phase was launched which aimed to take some of the best apps or tools and provide support to partner organisations to develop them further and disseminate them more widely to reach larger numbers of users. No additional funds were required for the second phase, as the first phase was delivered at substantially reduced costs.

Results achieved

Phase 1:

‘Hack days’ were held in Lagos (Nigeria), London (UK), and Cape Town (South Africa), bringing together a mix of IT coders and developers, graphic designers and community activists to come up with locally relevant solutions/apps for presenting trade relevant data. The process was filmed in all three locations to enable the team to share lesson-learning with DFID colleagues given that hack days had never been tried before.
- The apps developed were hosted on an online website – Rewired State. (http://hacks.rewiredstate.org/events/dfiddc2012)
- The three most developed tools were demonstrated at the Omidyar Open Up conference and the DFID Digital Development Day in November 2012.

Phase 2:

This phase supported the further development of 5 selected mobile apps in South Africa and Nigeria to help consumers better understand the implications of trade policy decisions and give them ideas on how to participate in trade. CCHubs were supported to further develop the following apps:

  - Trade Viz - an online visualization tool that breaks down trade data and presents them in charts for easy understanding. It also provides simplified access to factors such as tariffs, steps to trade, prohibition lists.

  - Trade Critic - an online tool that promotes transparency in trade and government policies and their effect on prices of selected goods and services. The platform draws, analyses and interprets data on trade barriers and trade related cost on selected consumer goods, demonstrating the eff­ects of government policies on the prices of consumer goods.

RLabs continued to maintain the following apps, hosted on the Mxit platform:

  - Wdiza - Mobile and Mxit interface displaying a visualisation of the world development indicators. This application had the potential to inform, raise awareness and debate, through disseminate data amongst users in an accessible format.

  - Vlisto - Crowdsourcing consumer pricing for goods in daily use inspired by the Economist and DFID dataset of consumer data. It started as an application comparing prices for consumer goods but quickly became a place for users to understand pricing and market needs, making market information more accessible for interpretation.

  - DevTraders - An application for promoting locally produced products and services in their communities. It enables informal traders to leverage the power of digital technology to promote their services or goods. It also provides local community members with an opportunity to support the local informal economy through accessing this data.

- CCHubs organised feedback sessions, attended by bankers, technologists, government agencies and academia to demonstrate and gather feedback on two of the apps, which were then iteratively developed further.
- Finally the apps were promoted on social media (Facebook, twitter, blogs) and outreach numbers were measured.

As well as number of users reached, the apps had a social impact. For example, one beneficiary, Suzanne used to be part of a gang culture in South Africa – she was involved in selling drugs and keeping guns. She has two children, who she could not take to school for fear of being shot at if they left the house. Support from RLabs has helped Suzanne turn her life around. Through TTP funding, she has developed a mobile application, DevTrader, for informal traders to showcase their services and products. She launched the DevTraders application to a group of business professionals in South Africa and it is still growing.

Contribution to operational plan and DFID’s international objectives

This project directly contributes to Trade Policy Unit’s Operational Plan, by informing consumers in developed and developing countries of the impact of trade barriers. The ‘Hack Days’, apps and social media promotion of technical trade information has informed a number of beneficiaries in developing countries, as well as raising awareness of trade issues within DFID in the UK. The number of beneficiaries reached through these apps would represent the results of this project. With citizens better informed, it is hoped that public debate and advocacy on free trade will increase. Ultimately, a better understanding of trade barriers, would stimulate debate among citizens. The long term impact would be increased citizen interest and advocacy to reduce trade barriers, and increased trade benefits.

DFID’s Economic Development Strategic Framework published in January 2014, firmly sets out our support to reduce trade costs and barriers, under pillar 2. Through informing consumers of trade costs and barriers via apps, it is hoped that this will lead to debate and consumer advocacy for reducing trade costs and barriers. This project will deliver through mobile phones, enabling inclusive benefits for girls and women, another key pillar of the strategy. Prior to this, supporting increased trade in the poorest countries is a critical part of DFID’s wealth creation agenda as identified in DFID’s Structural Reform Plan (2011-15).

The critical role of trade is also recognised in the UK’s Trade and Investment White Paper (February 2011) which sets out the Government’s commitment to providing support to developing countries to follow sustainable paths to growth through trade and investment. There is a wide body of evidence showing that growth is the most effective means of raising incomes, creating jobs and reducing poverty in the developing world. We know that trade is a key driver of economic growth and development.

This was an innovative project that had not been attempted before and represents an opportunity for DFID to learn from novel projects. As well as informing citizens about trade policy, this project increases transparency, and builds evidence of what works for future DFID programmes. The Trade Transparency Project was used as a case study in the reformulated DFID Digital Strategy and has strong support from the Digital Team: “This project is exactly the sort of exemplar we need” (Julia Chandler, Digital Strategy Implementation Lead). The new experience of running ‘Hack Days’ was filmed and lessons learned were shared with other teams in DFID at the DFID Digital Development Day.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Overall Outcome Assessment

The outcome was met and exceeded.

The outcome was defined as ‘Citizens are informed about the costs of trade barriers and engaged with the free trade debate’. Engagement is difficult to measure, however we used the number of users online (social media) as well as offline media coverage as measurable indicators for this outcome.

Evidence that outcome was exceeded:

- The ‘Hack Days’ succeeded in informing and engaging a variety of different people about trade issues, many of whom had very little knowledge to begin with. The number of users and comments on the Mxit apps also indicates some level of educating or informing users. The ‘Hack Days’ generated a buzz in the local area and on social media sites: ‘Hack Day’ participants tweeted about their work, one wrote a blog about the experience and in Cape Town the event was covered by a local radio station and newspaper.
- In the UK, attendees at the Omidyar Open Up conference and the DFID Digital Development Day engaged in the trade conversation. It was suggested that increased visibility from senior DFID staff or Ministers at the UK hack day might have increased this visibility yet further and reached more people as a result.
- CCHubs organised feedback sessions, attended by bankers, technologists, government agencies and academia to demonstrate and gather feedback on two of the apps.
- The Trade Critic app was reported in a Nigerian national newspaper, as well as two other online blogs, in September 2014. On Facebook, 1,300 likes were received and the twitter handle (@tradecriticNG) attracted 1,500 followers, exceeding expected outcome milestones.
- The Trade Viz app was reported in 5 blogs, with one blog receiving 10 positive comments in reaction, exceeding expected outcome milestones.
- The reach of the 3 apps hosted on Mxit continued to grow. The WDiza application has achieved 182,177 users with more than 9.32 million page views in total. Vlisto have increased its users to 41,005 from 101 countries. DevTraders increased users on their platform to 4,985 within 3 months.

Output Score and Description

The overall output score is A++, substantially exceeded expectations.

The project had a single output defined as ‘Online tools are launched, developed and effectively disseminated to help ordinary people understand trade and engage with trade-related issues’.

All milestones and results have been achieved as indicated on the project logframe, in time for project completion.

Lessons and how these have been shared

It was found that beneficiary knowledge and understanding of international trade and economics was much lower than had been anticipated. During the ‘Hack Days’ a lot of support from DFID teams was required to explain economic and trade concepts. The technology hubs sought assistance from UCT Business School and a consultant trade expert, who delivered a presentation at the ‘Hack Day’. This is an important lesson for the design of trade projects going forward – ordinary people will not engage unless their understanding is increased.

Original plans to host tools or apps on DFID IT systems proved to be unrealistic. DFID systems were not suitable and they do not engage with the target audience of citizens in developing countries. More suitable alternatives were discovered that could disseminate these apps to many more people (namely Mxit and standalone sites) although DFID lost some oversight of the content as a result.

Outreach – Phase 2 of the project included feedback and good engagement from a mix of local people in Nigeria. However the implementation partner suggested that visibility of the project could be increased further through presenting at specialist investment tours and trade shows. Additionally raising the profile of these apps amongst the Nigerian diaspora overseas, would increase discussion and debate as these groups would have greater financial capability and impact on trade influencing.

This innovative project is useful for guiding the future design of technology based hack day projects. The need for flexibility, support to understand the datasets and an eye to future hosting and dissemination from the outset are all lessons that have been shared with other DFID teams.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Online tool is launched to illustrate the impact of trade barriers on consumer prices
Output number per LF		1	Output Score	A++
Risk:		Medium	Impact weighting (%):	100
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
- Online tool launched	Full launch by January 2014	Completed – 25 online apps were developed during Phase 1.
1.2 - Apps are developed continually in line with user feedback	Evidence in quarterly reports	Completed – 2 apps were demonstrated in Nigeria and feedback used to develop them further.
1.3 - Number of people reached through communication channels	Target: 350,000	Trade Critic unique users: 9,841 / TradeViz : Est. 409,000 reach / WDiza: 182,177 / Vlisto: 41,005 / DevTraders: 4,985

Key Points

- During Phase 1 several online tools and mobile phone applications were launched, substantially exceeding the single tool expected in the business case.
- During Phase 2, 5 apps were further developed. Two apps were developed by CCHubs, and this was followed by promotion efforts largely on social media, but also on newspapers and blogs. Three apps that had been developed during Phase 1 were maintained and hosted on Mxit, to allow the user base to grow.

Summary of responses to issues raised in previous annual reviews (where relevant)

The Annual Review 2013 recommended adding another output indicator to reflect that ‘apps are developed continually in line with user feedback’ and increasing milestones to reflect greater than expected popularity of apps. This recommendation was implemented as output indicator 1.3, in a logframe revision.

It was also recommended that the apps are continually developed in line with user feedback and that usage statistics be monitored closely. This recommendation was implemented in Phase 2 of the project, where CCHubs organised stakeholder feedback sessions, and developed apps in response. For example, the feedback session highlighted a bug, which was then addressed. Quarterly reports from CCHubs provide usage statistics, and the trends have been positive.

Recommendations for future programmes

Future projects of this nature should appreciate the lower capacity amongst participants to understand trade data and economic concepts. This was a barrier that was partly overcome by expert presentations and knowledge sharing at the ‘Hack Days’. Projects need to be more realistic and should seek to assess the level of existing knowledge and understanding early on.

‘Hack Days’ are excellent in starting the debate – however establishing long term plans for app hosting and on-going development is vital to make a lasting impact.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The ‘Hack Days’ were found to be significantly more cost effective than originally anticipated, hence the large underspend during Phase 1.

The cost of hosting websites and applications was overestimated in the original business case. The lower actual costs were largely due to the decision to host applications in locally suited sites and platforms, rather than the UK.

The Trade Critic app was based on data from the Economist Intelligence Unit (EIU). The EIU services costs were higher than other service providers due to the app making some of their proprietary data public. This should be noted for future projects – however overall the data and analysis provided were thorough and justified the expenditure.

VfM performance compared to the original VfM proposition in the business case

The programme delivered significantly better VfM than the original business case. This is because the ‘Hack Days’ during Phase 1 were much cheaper than originally forecast. The cost of Phase 1 of the project came to £130,606, much lower than the original £300,000 budgeted. As ‘Hack Days’ were a new process for DFID, forecasting methods were not as accurate as they can be for future programmes.

The reduced costs for Phase 1 enabled a second phase to be funded under the same budget as the initial business case. The total cost of both phases was £198,845, over 30% lower than the initial budget. This represents excellent value for money, and is a good example of learning through attempting innovative projects like this.

Assessment of whether the programme represented value for money

This was a low cost project with potential to reach a large audience. In addition, the lessons that DFID is able to learn through this project, further justify the spend, making the impacts effective twofold. The use of mobile technology, social media promotion and ‘Hack Day’ made the spend very efficient as large numbers of people were reached quickly, often on a scale of days. In terms of sustainability, some of the apps will continue to be promoted and developed, for example CCHubs plans to continue developing TradeViz further and integrating it with other services and visualisations. TradeCritic will continue being developed by CCHubs for a further 6 months after the project completion date. The apps were a means of raising awareness about trade issues, and therefore development will not continue on all apps as this was not a project objective in itself. Given the nature of technology development, supporting all apps for significantly longer periods would not have been appropriate or best value for money. It is however hoped that the lessons learnt from this innovative project will continue to be of use to our project partners and their communities. Future projects may want to consider a longer term strategy for sustaining the most promising apps.

Therefore the project represented excellent value for money.

Quality of financial management during programme

Good – all contractual payments were paid promptly after demonstrated achievement of project milestones. All quarterly reports were delivered on schedule. We are still awaiting the final audited statement from CCHubs, and in future we could set out timescales for this more firmly in contracts.

Date of last narrative financial report
Date of last audited annual statement	RLabs: 28/02/2014 / CCHubs: awaiting

E: RISK (½ page)

Quality of risk management over the life of the programme

The original output risk rating was medium, however the 2013 Annual Review suggested that this could be reduced to low after results exceeded expectations.

Financial and delivery risks were kept low by ensuring that payments were only made after successful demonstration of output delivery, and time bound output milestones detailed in all contracts. Quarterly reports were reviewed to ensure funds were being used as intended. There was one case of delayed payment by DFID due to a lost contract in the postal system and problems with DFID’s payments system, but this represents reasonable business risks.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Almost all delivery has been along planned timeframes. There was one case of delayed payment by DFID to CCHubs in July 2013. This was due to a lost contract in the postal system as well as problems with DFID’s payments system. Implementation therefore began in October 2013, rather than July 2013. As a result DFID agreed to extend the delivery end date from July 2014 to October 2014.

Performance of partnership (s)

Due to the small size of the contracts with service providers (well within the OJEU limits) single source procurement was used for partnerships. The partnership with both Rlabs (a registered social enterprise) and CCHubs (a commercial social innovation centre) has been effective. This has been evidenced by regular quarterly reports and telephone updates both partners. CCHubs have reacted effectively to our requests to provide more detailed usage data. The partners were based in benefitting countries and they were able tap into the local networks and knowledge. Contract negotiations ensured that the costs were reasonable and it was possible to benchmark proposals against each other.

Asset disposal and value obtained by DFID

There were no physical assets involved in this project.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

RLabs were able to provide usage evidence of Mxit apps disaggregated by age, gender and geographic location. The overall reach of these app is estimated to be 12.7 million, significantly more than the 2 million reach expected in the business case. Approximately half of users of the Mxit apps were in the 18-25 age group, largely urban and male. The Annual Review did highlight concerns over this narrow user base, but also suggested that this still is good evidence of meeting the programme aims – given the technological nature of this project, it is not surprising that it has a young mobile user base. The DevTraders app was the brainchild idea of two women – this is evidence that the ‘Hack Days’ approach was accessible to women.

CCHubs usage data has not been disaggregated by age or gender. However the attendance at the feedback sessions was largely professionals (technologists, bankers, government officials etc.). In future projects, more though could go into engaging the wider society, though it does seem that the professional user is likely to have greater impact when advocating for trade.

A pilot evaluation was conducted by DFID’s Trade Policy Unit in March 2013, during the project pilot phase. The evaluation highlighted early success signs in informing and engaging a variety of different people about trade issues, many of whom had very little knowledge to begin with. It also suggested the use of crowdsourcing data to make apps more widely relevant, which was a method later adopted by the Vlisto app.

Monitoring progress throughout the programme

Beneficiaries were able to provide direct feedback in person at the ‘Hack Days’. In Cape Town the event was credited with “bringing together diverse people with diverse sets of skills putting their resources and their efforts into using those talents for good” (Marlon Parker, RLabs). In Lagos, a hackathon participant praised the concept of giving data to the people “to see what they think about it, what they can do with it, rather than making assumptions” (Chuka Ofili). These participants are direct beneficiaries of the programme in that their understanding of and engagement with trade data has been increased, but they will also play a crucial role in sharing this understanding with other people through the apps and tools that they create. They “used the data not just to empower themselves but also to add value for other community members” (Marlon Parker, RLabs). During phase 2 CCHubs organised feedback sessions, attended by bankers, technologists, government agencies and academia to demonstrate and gather feedback on two of the apps. For example the TradeViz app originally a visualisation to display trade data, however following feedback, the app was reiterated to include landing costs for importing goods to Nigeria. Full details of the feedback were provided in the quarterly reports from CCHubs. Feedback from RLabs apps was also positive showing that the project informed users (““Thx 4 showing me info that I neva knew existed”) and even encouraged advocacy on wider economic issues (“Unemployment mus b lukd at by our gov”).

Monitoring activities throughout review period (field visits, reviews, engagement etc.)

The ‘Hack Days’ in Phase 1 were filmed by a small film company. A short film covering the process was widely shared within DFID via a lunchtime seminar and the DFID Digital Development Day. The monitoring film was invaluable for sharing lessons learnt within DFID.

Quarterly reports and regular telephone discussions provided by CCHubs and RLabs were used to inform this project completion review.

The Annual Review process

A DFID Annual Review was conducted in June 2013, with the project scoring A++ overall. The Annual Review reported that Phase I of the project reached at least 143,219 users. This figure was based on the usage statistics for just the two applications hosted on Mxit for which there was data available at the time. An annual review was not conducted in June 2014 as the project end date was within 3 months of the annual review date; in this case DFID SmartRules exempt the annual review in anticipation of a Project Completion Review.

Smart Guide

The Programme Completion Report is the opportunity to reflect on the entire programme, its performance, achievements, lessons and how learning will be shared to inform future programming.

The Programme Completion Report assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with headline information on the programme and any follow up actions
Introduction and Context
Briefly outline the programme, results achieved and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Outcome Assessment / Brief assessment of whether the programme achieved the Outcome
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations for future programmes
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case. Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme represented value for money? / Overall view on whether the programme was good value for money
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Quality of risk management over the life of the programme. How were risks managed, the degree to which they were realised and/or mitigated.
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset disposal and value obtained by DFID / How were assets managed throughout the programme? How have they been (or will they be) disposed to get maximum value?
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the programme / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process