Supporting Economic Transformation: ODI Accountable Grant 2014/15 – 2018/19

Intervention Summary

This Business Case is for a £4.266 million accountable grant to the Overseas Development Institute to manage a programme of support to DFID, donors and governments to support putting into practice the policy insights on economic transformation at the country level and to develop further evidence based on demand-led analysis on priority issues. The Business Case includes £90,000 for independent evaluation of the programme and £120,000 for monitoring and reviewing the programme implementation of this new are of programming. The total business case is for £4.475 million.

Economic transformation is a central part of DFID’s Economic Development Strategic Framework (EDSF) and of the narrative between growth and poverty reduction. Governments in partner countries are also expressing a strong interest in transformation.

But we don’t know enough about policies and programmes to promote transformation in particular contexts. The debate on economic transformation remains too theoretical and academic although there are promising leads. We also do not know enough about the political economy of transformation.

Design of the programme reflects discussions with DFID offices which have a deep interest in shifting their programmes in light of the economic development strategy. It is important that policy-making and programmes have a focus on long-term economic transformation and are informed by a strong-evidence base. This programme will help DFID to overcome shortfalls in this area as identified by both the Growth Portfolio Review and ICAI’s review on DFID’s private sector work. With DFID planning to spend £1.8bn of our bilateral budget on economic development by 2015-16 small improvements in effectiveness of this expenditure would represent good value-for-money on this spend. DFID is undertaking growth diagnostics in all focus countries in order to improve impact of economic development work; this programme will support the first round of these diagnostics and enable deeper work to be undertaken to inform future diagnostics.

ODI have sent DFID a proposal – Supporting Economic Transformation (SET) – to support DFID and development partners to respond on economic transformation. ODI proposes a 4 year Accountable Grant, locking together country level policy and advisory work, high quality policy analysis, support to DFID growth diagnostics, knowledge and learning management and communications on economic transformation. The intervention is intended help to bridge the gap between our aspirations on transformation, and the practical actions needed to achieve change.

Productivity and growth is one of ODI’s five strategic priorities and will benefit from strategic inputs from multidisciplinary experts. The proposal specifically incorporates inputs from across ODI’s sector and thematic expertise, including political economy/governance and social development/gender as well as economic inputs.

Analyses under SET will for instance inform policy dialogue with partner governments, help shape economic development portfolios and contribute to new growth and poverty diagnostics by DFID and those undertaken by governments and other donors.

Consultation with country offices has shown strong interest in this proposed programme including expressions of interest in support under the programme during the first 12-18 months.

The expected outcomes of the programme are:

- Better global knowledge on how policies can support growth by accelerating economic transformation
- DFID and other donors better able to demonstrate how economic development investments can lead to stronger, more inclusive growth and poverty reduction over the long term,
- Governments supported with policies to help foster economic transformation
- Adjustment of DFID policies and programming towards a stronger focus on transformation including through support to DFID growth diagnostics
- Private sector and business engaged in policy dialogue on transformation
- Better use of data to support analysis of transformation and the quality of growth in developing countries.

1. Programme outputs will be:
  1. Policy advice to DFID, other donors and Government. The programme will be judged by evidence of traction on policy debates and decisions.
  2. Support to DFID in undertaking growth diagnostics in country offices in early 2015
  3. Data portal / website sharing knowledge
  4. Events / communication strategy implemented

The main risks of the programme relate to the quality and timeliness of advice and the ongoing demand for support. The programme will be managed using a performance framework to ensure value for money and quality and impact of the work from the Accountable Grant. The performance framework will provide management information that will be used to revise subsequent budgets or to stop funding if necessary. The programme will start with a six month inception phase which will be used (1) to gauge demand from DFID, governments and other partners and to match expertise with this demand; and (2) to pilot support to two country offices. A recommendation will be made to GRD’s Head of Department on whether to progress to the implementation phase.

Strategic Case

Context and need for a DFID intervention

The problem

Economic transformation is a central part of DFID’s Economic Development Strategic Framework (EDSF) and of the narrative between growth and poverty reduction. Economic transformation is needed for the type of growth which leads to poverty reduction. This is growth which (a) generates income broadly across the income distribution (b) is robust against price shocks and price cycles and (c) increases the opportunities and options for future economic growth. Focusing on economic transformation involves understanding determinants of growth and productivity at the micro/firm and macro level, including how resources shift to higher value uses and diversification of a country’s productive capabilities, including its exports.

But governments and development partners don’t know how to act on insights about transformation and the quality of growth. Countries transform as they grow – the Growth Commission report of 2008 describes this for the 13 success stories of the mid/late 20th century. And some transformational things are happening in DFID countries – shoes in Ethiopia, agro-processing in Nigeria. But what we’re finding is that growth spurts that aren’t underpinned by changes in indicators related to ‘transformation’ turn out not to be sustained. These indicators include measures of diversification and increased productivity. So the question is, what do the insights about transformation tell policy makers and donors about how to get healthy growth processes going?

The debate on economic transformation remains too theoretical and academic but there are promising leads. There are some excellent analyses that have deepened our understanding about how firm structures and economies change as they grow (Hsieh & Klenow, Rodrik). There are good insights on the macro/structural policies that seem to be associated with diversification (IMF 2014[1]) and some healthy competition for ideas about smarter approaches to designing specific or industrial policies (Rodrik, Page, Lin) that learn from past success and failure. But we don’t know enough about policies and programmes to promote transformation in particular contexts. We also do not know enough about the political economy of transformation; pursuing transformation objectives may suggest tackling vested interests even more than shorter term adjustment or reform policies.
[1] Sustaining long-run growth and macroeconomic stability in developing countries, IMF 2014

ODI have produced a proposal for an accountable grant for DFID funding that promises to fill this gap. The proposal (Annex 1) lays out a programme of action-oriented, policy focused work that takes into account the political realities of the policy change process. This is to help DFID and others respond to the insights from the literature on economic transformation, and adapt their policy and programmes.

Economic transformation and DFID focus countries

Economic transformation is essential for creating jobs and raising incomes in developing countries on an adequate scale. At present only 16% of work in DFID countries is in waged employment in modern, productive sectors. The bulk of people work in unproductive or subsistence work in rural and urban areas. Changing this picture significantly even within 15 to 20 years would require accelerated economic transformation. There are opportunities for significant improvements in patterns of inclusive growth if resources were to reallocate between sectors and to higher value techniques in existing sectors. The graph below shows differences in productivity between sectors in Africa and the share of employment in the least productive sectors.

DFID focuses on the poorest countries so it is no surprise that these countries have experienced limited transformation when looking at aggregate data. The chart below, compares DFID focus countries to three countries during the initial 20 year period when they took off from GDP per capita levels similar to DFID focus countries. In DFID Africa and DFID Asia, manufacturing actually declined in importance, with non-manufacturing industry (mostly extractives) offsetting the decline.

Much of Africa has experienced very slow progress against indicators of transformation. Exports have not diversified. Since 1995, the proportion of LDC exports of primary goods has increased from 60% to 70%, suggesting a reverse transformation in the world’s poorest countries (this increase is explained largely by commodity booms). For several natural resource exporters especially in Africa, the agricultural sector’s share of total employment is significantly larger than would be suggested by either GDP per capita or agriculture’s share in GDP, reflecting very low productivity levels in the sector. The discovery of non-renewable resources has catapulted these economies up the per capita ladder without producing the kind of economic transformation typically associated with economic growth. Such transformation as there has been has seen labour shifting from unproductive agriculture to services that are unproductive rather than higher value. This has been accompanied by a rise in ‘consumption cities’, that is, urbanisation due to resource rents spent on urban goods and services, rather than urbanisation due to industrialisation.

Governments in partner countries are expressing a strong interest in transformation. African countries are pushing for ‘industrialisation’ to feature strongly in the post-2015 goals targets. Countries including Ethiopia and Nepal are framing their policy discourse in terms of economic transformation and are looking for best practice in doing so.

Getting the economic fundamentals right and pursuing open economic policies are important but this is not enough to help policy makers or inform Ecdev policies. The IMF argue that there is a core set of macroeconomic and structural policies that are associated with indicators of increased transformation – such as increasly diversified economies and shifts to higher value production. This is correct but leaves much to be determined at the regional and country level by policy makers and development partners.

Weak institutions and low levels of infrastructure make the process of transformation difficult. Countries often become trapped in undiversified and inefficient growth paths. Growth based on the extraction of a narrow resource base, for example, does not have these properties. Growth based on (i) increasingly diversified exports and domestic capabilities and (ii) labour, land and investment moving to higher value uses, does.

Tilting economies towards exports and encouraging agglomeration effects are likely to increase the chances of unlocking transformational growth processes. Evidence shows that trade can support transformation, increases productivity through learning. Productive cities, road corridors and economic zones can lead to greater externalities and thicker input markets for producers. Policies framed in terms of economic transformation are likely to be more forward looking, creating more productive opportunities in the future.

But actual policy choices and their implementation challenges will be country-specific. A wide range of constraints need to be removed in sequence or in tandem to unlock better growth paths. These will involve a wide range of policies interventions from macroeconomic, fiscal and trade policies to investment climate, infrastructure or more targeted industrial policies or long term processes such as urbanisation. Political economy factors will often stand in the way of optimal policies especially for long term, structural policies.

ODI concept note for an Accountable Grant on Economic Transformation

ODI have sent DFID a concept note to support DFID and development partners to respond on economic transformation. ODI proposes a 4 year Accountable Grant, locking together, country level policy and advisory work, high quality policy analysis on specific issues and comparative analysis, knowledge and learning management and communications on economic transformation. The concept note involves working with country partners, top academics, consultants, think tanks and government and donor agency staff, including south-south cooperation and African institutions. The intervention is intended help to bridge the gap between our aspirations on transformation, and the practical actions needed to achieve change.

The programme proposes four outputs that will be highly interdependent:
1. Policy advice to DFID, governments and other development partners
  1. Support to DFID country offices and central departments
    1. Analysis to help understand potential patterns of transformation and how to orient policies and programmes to unlock this potential;
    2. Support to DFID to undertaken growth diagnostics in January to May 2015;
  2. Support to country governements on strategies to accelerate economic transformation
  3. In-depth and comparative analyses focused on specific issues proposed by DFID and other partners
  4. Periodic anchor papers on major economic transformation issues
2. Promoting economic data for transformation including a portal to sources of data bases on economic transformation (housed in various IFIs and academic institutions) and new analyses based on these sources including that undertaken in component 1; and
3. A communication component to promote evidence from the programme and important policy issues on the quality of growth processes.

Transformative growth is one of five priorities in ODI’s 2014-17 Strategic Plan. ODI has hosted a number of transformation-themed events over the last 18 months and has delivered on a wide range of work related work at international and country levels, including trade, infrastructure and finance as well as governance. ODI has extensive networks to draw on the best available expertise in a wide range of sectors and themes that will be necessary for this flexible programme for supporting improved performance on economic transformation by DFID and others.

This programme is different from existing initiatives because it focuses on (a) applying insights from transformation and growth in countries and (b) solving practical policy questions asked by DFID departments, governments and other partners. In particular the programme will:

- Focus on economic transformation and the longer run determinants of growth and poverty reduction
- Address policy responses, including applying existing evidence to questions of transformation
- Directly support DFID, other donors and partner country Governments on policies and programmes
- This programme delivers quickly. It will respond to requests and deliver tailored products and advice within short time frames (mostly 3-6 months for responsive work)
- Combine expertise across different sectors, country level expertise, political economy and social development and gender advice as well as expertise in policy and aid management to respond to requests
- Use ODI’s international and country-level networks to draw in the best expertise globally in combination with ODI experts on issues related to economic transformation.

The ODI proposal (Annex 1 especially pp. 3-4 and 7-9) details the products that will be delivered. It also lists some of the analytical tools that will be developed and applied to specific country and sector contexts, the main policy insights that provide points of departure for the programme and potential international experts and institutions that ODI will seek to partner with. These include south-south partnerships including with countries with experience of successful transformation and appropriate institutions in developing countries (such as the Africa Centre for Economic Transformation/ACET).

To ensure work under the programme is from existing programmes criteria will be used to ensure fit with programme objectives. There are synergies with several DFID programmes that are underway or being developed including growth diagnostics work (See Box 1) and IGC. Activities should fit at least 3 of the following:

- Will lead to longer term impact on economic development (i.e. 5-15 year time horizon)
- Leads to improvements in government policy, international systems, aid management or other aspect of development assistance
- Significantly promotes acceleration in labour, finance and land moving to higher value uses in an economy
- Supports one of (i) tilting toward exports, (ii) building firm capabilities, (iii) promoting agglomeration effects
- Involves multiple sectors/theme.

Box 1 – links between the ODI programme and the growth diagnostics programme / The aim of a growth diagnostic study (or inclusive growth diagnostic) is to look across the economy and determine the main constraints to (inclusive) growth. This involves analysing a range of economic fundamentals, including access to finance, education, health, infrastructure, institutions and macroeconomic risks. This wide ranging scope gives a useful framework for prioritising the most significant barriers to growth in an economy. However, this breadth also means that policy prescriptions are relatively high level. The programme of work proposed by the ODI has a more specific focus on the drivers of economic transformation and with a greater emphasis on policy/programming. This means that it will cover areas that would be included in a good diagnostic, but in much greater detail. The ODI work will usefully overlap with the diagnostic work – for example, drilling into detail on areas identified as constraints in the diagnostic, or diagnosing more specific constraints to drivers of economic transformation.

Strategic fit with DFID priorities

DFID’s Growth Portfolio Review (GPR) 2013 showed that only half of DFID’s wealth creation spend targeted growth and economic transformation. The GPR recommended that current DFID programmes should be adapted to have a greater impact on the most pressing constraints on economic transformation. A lack of focus on high productivity sectors and measures to improve the investment climate for medium to large firms means that we are not necessarily supporting the areas which will drive economic transformation in our countries. The GPR also highlights that DFID may need additional expertise to address the challenges of economic transformation.

The EDSF requires increased attention to economic transformation. The economic development strategy argues that ‘Economic development takes place when a country achieves long term, high rates of economic growth and when this growth is accompanied by a wider economic transformation that benefits the poor and shares prosperity broadly’. These priorities are reflected in the 2015/16 to 2017/18 RAR.

The recently published ICAI report on private sector development also emphasised DFID’s role on transformation. The report recommended that DFID should provide clearer guidance to its staff on how to design a coherent and well-balanced PSD country portfolio that matches its goals for an end to extreme poverty through economic development and transformational change. This includes the need to review donor programmes through two lenses: (i) contribution to economic transformation; (ii) political economy.

Analyses under the SET will also be able to contribute to new growth and poverty diagnostics by DFID country offices. DFID offices are to undertake growth diagnostics in all focus countries in early 2015. This process will inform economic development policies and options for scaling up programming. SET will support the first round of these diagnostics directly and more detailed work that country offices are likely to want following on from this process. SET analyses will also feed into and complement those undertaken by governments and other donors e.g. World Bank Systemic Country Diagnostics.

Consultation with some country offices has shown strong interest in this proposed programme. The main needs from DFID offices point of view includes:

- Stock take of countries’ growth path from a transformation perspective, including understanding aggregate patterns of sectoral shifts and diversification
- Interest in taking stock also involves looking at major investments and trends already underway in many countries that are understood as transformational (e.g. FDI in new sectors), understanding the potential implications, thinking about scalability.
- Fresh input to policy dialogue with governments. A number of governments are talking afresh about ‘industrialisation’. The theme of transformation may provide a constructive way to renew dialogue on economic policy.
- Input to thinking on the overall impact of wealth creation/ecdev portfolios in-country. Several countries are already introducing a ‘transformation’ theme into their programming and are interested in learning from other contexts on how to do this.
- Specific advice on projects at the pre-appraisal stage e.g. making M4P or similar projects address more ambitious systemic issues that help move into higher value sectors.
- Interest in spatial dimensions of national economic development e.g. developing policies for integrating marginalised often conflict-affected regions of countries into healthy growth processes.
- Ensuring that analysis includes a strong political economy lens
- Policy and programming work in transitional contexts, developing flexible programming solutions where there is currently limited engagement with government.

The consultation also highlighted important factors in terms of delivery that have been taken into account during design and will be taken forward into the Inception Phase. For this type of support to be effective it needs to be (a) timely – hitting windows of opportunity for programming and policy dialogue; (b) excellent quality – including getting top quality international and local experts that have credibility; and (c) distinct from other analytical and research products as the ODI proposal suggests.

Following initial consultations with several departments, the following DFID offices have expressed interest in support under the programme during the first 12-18 months: Nigeria, Kenya, Uganda, Tanzania, Burma and Nepal. The Inception Phase that will start on approval will include ODI starting support to two countries.

Gender

Transformation processes have differentiated impacts on men and women. Recent research in economic transformation has begun to pick up important differences in how the economic opportunities for women and men change as economies transform. As economies experience structural shifts – jobs moving between sectors and patterns of productivity altering – people do not fare equally. The picture varies by country and for different groups of people e.g. in rural and urban areas, of different ages and educational levels. This is important for equality of opportunity and outcomes but also for efficiency of economic outcomes if, for instance, women or indeed other groups such as youth or geographically marginalised areas, are left out of growth processes.

This programme will prioritise gender dimensions of economic transformation. DFID and our partners needs to understand how to shape policies and programmes to take into account the different impacts on men and women. This will require work on data sources as well as analysis and country-level policy work. The programme can include a thematic work stream on gender (component 2) and all analysis will be disaggregated by sex where there are likely to be good returns to this work.

Impact and Outcome that we expect to achieve

The expected outcomes of the programme are:

- Better global knowledge on how policies can support growth by accelerating economic transformation
- DFID and other donors better able to demonstrate how economic development investments can lead to stronger, more inclusive growth and poverty reduction over the long term
- Governments supported with policies to help foster economic transformation
- Adjustment of DFID policies and programming towards a stronger focus on economic transformation
- Private sector and business engaged in policy dialogue on transformation
- Better use of data to support analysis of transformation and the quality of growth in developing countries.

Indicators will be set by the end of the inception phase when the logframe is finalised. Outcome indicators are likely to include the following indicative targets:
Outcome / Indicators will include: / DFID portfolios in at least eight focus countries giving greater weight to transformation themes / Four centrally managed programmes designed and implemented differently due to the programme / Private sector associations in three countries and large firms/multinationals engaged in policy dialogue and/or coordinating with other investments with a view to entering a new sector as a result of the programme / Other donors or multilateral agencies adopting policy or programming choices due to accessing the programme in four cases

These outcomes will help contribute towards the following impact goal:
Impact / Significant contribution to global knowledge on best practice policy and programming on growth and economic development, evidenced by: / Government policies reflecting advice in countries supported / DFID and other donors’ programming and policy work in specific countries and across DFID portfolio / Private sector engagement in discussions on economic transformation / Better coverage in the media of economic transformation and awareness amongst civil society organisations and think tanks.

The impact and outcomes of the programme will be achieved through support to four outputs, which are described in full in the log-frame.

Outputs: / Policy advice to DFID, governments and other development partners / Support to DFID country offices and central departments to inform policies and programmes, including support with growth diagnostics; / Support to country governements on strategies to accelerate economic transformation / In-depth and comparative analyses focused on specific issues proposed by DFID and other partners / Periodic anchor papers on major economic transformation issues / Data portal to promote better use of economic data in analysis on economic transformation and a website for sharing knowledge / Implementation of a communication strategy including events to promote understanding of economic transformation.

Appraisal Case

What are the feasible options that address the need set out in the Strategic case?

This section assesses whether an Accountable Grant with ODI delivers value for money (VFM) when compared against other options and what VFM indicators will be used to check that the programme continues to represent a good use of resources. The options considered as potential alternatives are:

Option 1a: Accepting the ODI proposal for a 4-year stand-alone Accountable Grant on Economic Transformation.

Option 1b: Incorporating the ODI proposal into the existing think tank core agreement that DFID has with ODI

Option 2: Building into the work programme of the International Growth Centre as (i) an additional research component; and/or (ii) ensuring these issues are included in country programmes

Option 3: Setting up a new contract for a private provider or foundation or think tank to bid for

Option 4: Using Economics and Private Sector Professional Evidence and Applied Knowledge Services (EPS Peaks) to support DFID’s work on Economic Transformation.

Option 5: Doing nothing

B. What are the costs and benefits of each feasible option? Identify the preferred option.

The options have scored in terms of:
- Fit with mandate, corporate interest in growth and transformation
- Own in-house expertise on relevant sectors and aid management
- Networks, ability to mobilise teams
- Cost

Option 1a is to support the ODI’s proposal Supporting Economic Transformation (SET). This will provide policy makers and donors with policy advice and analysis on economic transformation using a political economy lens. This option provides a means to utilise ODI’s areas of expertise and comparative advantage to pursue DFID policy development priorities under a consolidated and coherent programme of work. In contrast to a ‘business as usual approach’ i.e. commissioning work on an ad hoc basis, this approach has a number of strengths e.g.:

- It provides a systematic approach to our relationship with ODI – allowing evidence to build and reducing the risk of duplication;
- Avoids multiple engagements, leading to lower transaction costs;
- Facilitates long-term thinking – i.e. provides the space for ODI and DFID jointly to consider future policy challenges and agendas based on economic transformation, rather than responding to short-term needs.
- Reduces the uncertainty for ODI’s International Economic Development Group (IEDG), so that they can focus fully on the work-stream, rather them to respond to other development agendas in order to seek funding; and,
- Achieves value for money or efficiency savings (based on scale and security of funding).

The Accountable Grant approach to funding ODI has a number of potential risks. Firstly, there is a risk that it reduces the capacity of GRD to work with other organisations on policy products for this thematic area. In addition, there is a risk that accountable grants may not correspond with changing DFID priorities as the programme advances. Where this is the case a risk exists that DFID advisers may lose interest in engagement or even object to spending time on issues not of priority interest.

Option 1a: ODI’s SET proposal fits with DFID’s interest in economic transformation that stems from the new Economic Development Directorate. The 3.5-year programme, locks together high quality policy analysis, country level policy and advisory work, and public affairs on economic transformation. By aiming for changes in policy and country programming in-country, it can address the findings of the Growth Portfolio Review, which found programmes not sufficiently adapted to the process of economic transformation. Also, by being more responsive to donors and Government, it may address the problems raised by ICAI, which suggested PSD staff were not given sufficient guidance on the topic of economic transformation. In addition, SET will fill gaps in global debates on economic transformation, and bridge sectoral analysis with national level diagnostics.

The programme will be led by ODI’s IEDG. The IEDG is organised around three thematic areas, which includes: transformative economic growth (productivity, industrial policy, economic transformation, emerging powers and G20); trade and trade-policy (WTO, EPAs, Aid for Trade, Regions, value chains, climate change); and international finance (capital flows and development finance). The work extends beyond economic analysis to include policy advice to developing countries and International Organisations. The proposal incorporates inputs from across ODI’s sector and thematic expertise, including political economy/governance and social development/gender as well as economic inputs. The team works with other economists in Europe and in developing countries. Projects range from multi-year, multi-country comparative analysis to studies to answer immediate policy questions. The IEDG team have sufficient experience of working in-country and significant experience in policy relevant analysis.

In leading the Evidence and Policy Group for the DFID-ESRC Growth Research Programme, ODI has worked with leading academics in the field of economic transformation (e.g. Dani Rodrik, Maggie McMillan, John Page, Thorsten Beck etc). They have also been able to demonstrate their convening power amongst academics by holding policy debates on economic transformation and growth identification. These networks are not exclusively academic as ODI is part of the unique DFI network ‘Let’s Work’ based on their significant work on DFIs for DFID, DFID research (including communication of the findings) and EDFIs. They also have strong networks in partner countries and have held a workshop with ACET in May 2014.

The combination of these strong networks and ODI’s existing body of internal knowledge on economic transformation will facilitate an ability to respond quickly to DFID policy needs on economic transformation. This will be enhanced by its strong links with donors. However, unlike IGC, ODI do not have the focus country presence and thus relationships will need to be developed, which will take time.

Option 1b is to incorporate the ODI proposal into the existing think tank core agreement that DFID has with ODI. The four year programme of work under the AG with ODI carries on to autumn 2015. However, the AG does not provide a vehicle for new commissioning, as the basis work themes having been set at the outset – the MDGs and post-2015, climate finance, achieving sustainable governance transitions and transforming the lives of girls and young women. An additional work programme on economic transformation wouldn’t benefit from being part of this programme especially as the new proposal has a much stronger direct policy focus than the existing AG. Therefore, this option is ruled out.

Option 2 is to build into the work programme of the International Growth Centre as (i) an additional research component; and/or (ii) country programmes. DFID is currently supporting the second phase of the International Growth Centre with funding of £47.9m from January 2013 to December 2016. The IGC already work to improve economic growth policies and programmes in 15 DFID focus countries to increase economic development for poverty reduction. The IGC have met expectations in their past two annual reviews on delivering high-quality, independent and demand-led policy advice based on frontier research and analysis in order to promote sustainable economic growth.

However, the focus on aid policy and management would be different from what IGC has been established to deliver. The demand for IGC’s work is supposed to come directly from government rather than also from DFID and other donors.

Option 2: The IGC already works to improve economic growth policies and programmes in 15 DFID focus countries to increase economic development for poverty reduction. The existing presence would allow IGC to support DFID country offices quickly in adapting current programming and designing new interventions to support transformative change. The IGC has strong internal expertise and is directed by a strong Steering Group which includes Sir Paul Collier, Tim Besley and Tony Venables amongst others. They have a track record of producing high-quality research and strong networks across the academic world. However, the IGC is a demand-led organisation which does not tend to provide research and services for donors. This poses two problems: firstly, it compromises the IGC’s position as an independent demand-led organisation with partner country governments; and secondly, it has weaker links with donors than other organisations. For more information on the comparable strengths and weaknesses between IGC and ODI see Box 2.

Box 2: Links between the ODI programme and the International Growth Centre / The International Growth Centre provides growth policy advice to partner Governments based on existing and new frontier research. Whilst the main types of output of the IGC may be similar to the ODI programme (policy advice and analysis) the mode of delivery and focus of the work is different. The IGC offers demand led policy advice to Government on a range of growth issues. The work of ODI will be focused on narrower issue (long term economic transformation) with a wider ‘customer’ base, including DFID, other donors and Government. / There are likely to be instances when the focus of the ODI work in a particular country/thematic area is similar to work of the IGC. In these instances the ODI should build on the work of IGC and benefit from their strong relationship with Government stakeholders in order to make their work as policy relevant as possible. For example, the IGC enterprise maps provide a good evidence base on the origins of successful industrial companies. The ODI could usefully build on this research work and the policy follow up that the IGC has done as a result of the enterprise maps (for example, building on the IGC policy work on the reform of the investment agency in Ethiopia or local content policy in Tanzania).

Option 3 would involve setting up a new contract for a private provider or foundation or think tank to bid for. DFID can draw upon experience from existing programmes of support to organisations for growth analysis. However, scoping and design work would need to take place in order to estimate the costs and benefits of this option. Specifying the various outputs would be difficult to pin down in a contract. It would also be difficult to incentivise/require a provider to involve a full range of experts in delivery when the incentive (with all proposals, but especially a contract) will be to maximise internal resources used rather than people from other organisations.

Option 3: A contract awarded following a competitive tender could lead to a strong consortium to deliver the programme. However, there are a number of reasons why a competitive tender presents problems in delivering this work. A contracting process takes time, realistically five to seven months; GRD have received expressions of interest from a number of country offices for early access to support under the programme. One country office would have benefited from the support if it had been offered three months ago. There will be future opportunities to support them and this programme will run for several years building knowledge in this area. But there is an early need in DFID and externally to help a step change in analysis and programming to reflect new thinking on diversification and transformation and, in DFID’s case, on economic development priorities.

It is uncertain if a private provider would be able to deliver TORs requiring this range of expertise and activities at a lower cost. ODI have significant existing expertise in this area and are a not-for-profit organisation. Finally, there is a risk that a contract reduces the flexibility that can be achieved in comparison with an accountable grant. If priorities of the programme change, it may be harder to tailor the programme to address our altered objectives.

Option 4 would deliver the programme objectives throught EPS PEAKS. PEAKS provides DFID advisers and other staff with access to specialist consultants and operational support in the areas of economic and private sector development. The quality of these services have been graded overall as ‘good’ by DFID Senior Research advisers. PEAKS services are available when rapid operational and super-specialist support is required because of a need for surge capacity, or when specialist expertise is not available within house. Individual departments would be able to commission separate studies by PEAKS. But the framework isn’t set up to deliver and learn across multiple interventions, to combine this with analysis, disseminate findings etc.

Option 4: EPS Peaks has the advantage of a wide network to respond to DFID needs for rapid, specialist support when not available in-house. This network also enables quality delivery through its access to in-house expertise and relevant in-country networks. However, each piece of country work will require its own terms of reference, which will be highly management intensive. There will also be little synergy between project outputs and lessons learned from one project or programme may be lost over time. These factors are likely to limit the ability to opportunistically influence key policy processes.

Option 5 would imply no additional support is given to action-oriented analysis and policy advice on economic transformation.

DFID’s new economic development strategy presents a marked change in development policy and a shift in departmental spend. By 2015-16, DFID plans to target £1.8bn of our bilateral budget on economic development, more than doubling the amount spent in 2012-13. To ensure DFID achieves value-for-money on this spend, it is important that policy-making and programmes have a focus on long-term economic transformation and are informed by a strong evidence-base. DFID’s Growth Portfolio Review suggested that ‘our bilateral portfolio could be adjusted to have a greater impact on the most pressing growth constraints and on economic transformation. Similarly, the ICAI Review on DFID’s private sector development work argues that ‘DFID should provide clearer guidance to its staff on how to design a coherent and well-balanced PSD country portfolio that matches its goals for an end to extreme poverty through economic development and transformational change’. There is a demand for new, well evidenced thinking in the areas highlighted in the proposal so the Do Nothing option is not preferred.

In summary, the scorings against the decision criteria is as in Table 1 below. GRD’s opinion is that the programme objectives would be best achieved through an accountable grant to ODI with a supporting performance framework to address potential risks in delivery.

Table 1: Summary comparison of options
	Option 1a: / ODI – new AG	Option 1b: / Add to existing ODI AG	Option 2: / IGC	Option 3: / Contract	Option 4: / EPS/PEAKS
Fit with mandate/interest	4	3	3	4	3
Own in-house expertise	3	3	3	3	2
International, local networks	4	4	2	2	3
Synergies across outputs	3	3	2	3	2
Cost	3	3	3	2	3
Total	17	16	13	14	13

F. Theory of Change for Preferred Option

The success of this programme will come from good solutions provided at the country level and on specific policy areas or themes. Success will also see lessons being transferred from one context to another and the programme providing a coherent addition to global knowledge about what economic policies can do to support growth.

At the country level success will depend on: getting clarity on the questions to ask; high quality inputs bringing together global and regional/local experts; excellent stakeholder management especially involving government, researchers and donors; and timing and complementarity with other processes and analysis. At the aggregate level, success will depend on good knowledge management, engagement with other thought leaders on growth and transformation and strong communication of findings.

The figure below summarises the Theory of Change. This is based around the draft indicators for the logframe identified in the Strategic Case though with (a) descriptors for the Activities that emphasise what needs to be different and work well with this programme and (b) the requirements (or Assumptions) necessary to get from one activities to outputs to outcomes and impact.

G. What measures can be used to monitor Value for Money for the intervention?

The value for money of the Accountable Grant for ODI is assessed on three levels: economy, efficiency and effectiveness. These three levels build and improve on the value for money indicators identified in the business case.

The Economy of the project will be measured by negotiating and then monitoring the unit cost rates that make up the bulk of programme costs:

Fee rates – These will include both staff salaries and the cost of any external adviser, including academic researchers, other research/analysis policy teams and local think tanks when conducting country work. These will be compared with fee rates of similar DFID programmes. The average sub-contractor daily rate for the past 12-month period has dropped by more than £100 in comparison with the equivalent figure for the first year of the AG. This has demonstrated that ODI put a strong focus on achieving VfM.

The daily fee rates will be £950 for the SET programme director (equivalent to his rate under PEAKS EPS), £650 for the economist in SMT, and £250 for the programme co-ordination/manager in CMT. Average fees for the experts undertaking the activities will be reimbursed as follows (Table 2):
Table 2: Benchmarked Fee Rates
Role	Level	Average Daily Rates for Programme	Equivalent call down rates for EPS PEAKS
Super Specialist	RF3	£850	£825-£985
Principle Researcher / Consultant	RF2	£755	£605-£875
Senior Researcher / Consultant	RF1	£650	£430-£655
Research Officer / Junior Researcher	RO	£552

ODI apply a standard set of measures and processes to ensure that their fee rates are fair, competitive and benchmarked against both the market and similar contracts conducted previously. ODI has carried out an assessment of the current market and historical rates for similar contracts when bidding for any assignment. In this way, they aim to ensure a financial offer that provides DFID with value for money and a combination of both high-quality services and effective and efficient delivery. Table 2 above has benchmarked the rates in this bid against the fee rates used in EPS PEAKS which provides consultancy services in-country as well as research.

- Percentage of budget spent on management costs – ODI have stated that they expect to spend approximately 16% of the programme budget on overall programme management. For a programme with these types of outputs, the dividing line between management costs and output delivery is marginal. The assumptions about costs/time that should be attributed to management costs rather than output delivery (especially the programme director and economist) will be revisited during the Inception Phase. The Financial Case below provides further details.
- Travel Costs – The conditions and value of travel expenses will be monitored to ensure that they are in-line with DFID’s own. Accommodation costs and daily subsistence allowances will also be monitored.

The Efficiency of the programme will be measured by comparing the outputs delivered to those estimated in the logframe. This will not only measure if the outputs were completed, but also whether they were completed on time and at reasonable cost.

Accurately measuring and assessing the efficiency level is difficult due to the wide range of outputs produced under this AG (from advising country portfolios to seminars). Given that no two outputs are the same it is difficult to compare outputs to inputs. The cost per output would be a blunt measure, as it struggle to take into account elements of quality, scale and difficulty. However, this will be easier to monitor as the AG goes forward where annual reviews can be used as a benchmark against the next assessment.

Cost comparators – The VfM will be assessed by comparing the unit costs of certain outputs by the ODI, IDS, IGC, CGD and IIED. In the 2013 Annual Review for ODI’s 4-year Accountable Grant with policy division, their costs for outputs compared favourably against the original rough costs comparators used in the original business case. This can be seen in Table 3 below:

Table 3: Benchmark rates for comparing costs of outputs under SET
Output type	Average cost
Policy brief	£4,774
Indepth /comparative analysis sector/thematic analysis	£20,764
Full policy report/note/Working Paper	£34,661
Case study	£34,613
Blog/opinion piece	£680
Other (written) output	£11,208
Public event	£3,044
Other event e.g. workshop/roundtable	£5,656
(ODI participation in) external events to disseminate policy findings	£1,357

The ODI’s unit costs lie somewhere in between the costs of other major think-tanks (IIED, IDS, CGD) and so represent good value for money. This comparison should be interpreted with caution however as in many cases the unit costs are not directly comparable. While value-for-money in terms of costs is an important consideration, the quality of the analysis is also important. This will be assessed under ‘effectiveness’.

Effectiveness. In order to get a holistic assessment of VfM the benefits of the programme (outcomes) would need to be monetised and compared to the costs/inputs. In practice this is not possible due to the complexities of mapping policy advice through to policy change and ultimately impact on the economy. However, there are a number of ways in which we can measure the effectiveness of certain outputs:

- Evidence of country offices using advice on ways to adapt programming to better the process of economic transformation. This will include through the adoption of new programmes based upon ODI’s advice.
- Evidence of reorientation of central programming on the basis of advice given to DFID.
- Feedback from country offices on quality of country portfolio assessments conducted by ODI.
- Evidence of supporting national governments on specific programmes within sectors.
- Assess the quality of policy relevant analysis. This may be conducted by either qualitative measures, such as a survey; or, by quantitative measures e.g. number of citations or number of visits to specific webpage.
- Number of visits to ODI’s Economic Transformation portal/website
- Attendance (including online viewers) at ODI’s seminars in relation to the Accountable Grant.

Some of these effectiveness criteria are reflected in the key performance indicators that will be used as part of the performance management framework for modifying future budgets under the programme (see Commercial Case and Annex 4). Information on performance will come from GRD’s quality assessment and feedback from other DFID departments, governments, donors, ODI’s own self-assessment, as well as members of the Advisory Committee.

J. Summary Value for Money Statement for the preferred option

The benefits to be derived from the ODI are intrinsically difficult to forecast. It is important that policy-making and programmes have a focus on long-term economic transformation and are informed by a strong-evidence base. This programme will help DFID to overcome shortfalls in this area as identified by both the Growth Portfolio Review and ICAI’s review on DFID’s private sector work. With DFID planning to spend £1.8bn of our bilateral budget on economic development by 2015-16 small improvements in effectiveness of this expenditure would represent good value-for-money on this spend.

This proposal has come from ODI and this is deemed to be the best delivery option for this work-stream based on ODI’s perceived strengths and reasonable costs. Its strong networks in relevant academia and policy-making, alongside its existing capabilities on issues related to economic transformation and its experience of aid policy and management mean it should be able to deliver on DFID policy needs and contribute to global knowledge significantly. ODI has existing knowledge of DFID that will help engagement with a range of DFID departments work smoothly.

Other options were ruled out due to them being deemed less flexible, having higher transaction costs for DFID internally or – in the case of the merging with IGC – run counter to the objectives of the existing programme. As a non-profit institution, GRD believe it will be easier to incentivise ODI to get the best available expertise rather than maximise days delivered by ODI staff.

The value for money of the programme will be monitored by focusing on a set of unit costs (economy), assessing the quality and adequacy of teams and their delivery of outputs (efficiency) and whether the outputs together provide valuable new insights and analysis that have traction with policy makers, donors and researchers (effectiveness). The performance framework which will determine budgets in the subsequent period will be used to ensure quality and VFM.

Commercial Case

Up to £4,340,500 is required to commission the ODI to help DFID and others to adapt their programmes and policies, in line with the insights from the best literature on economic transformation.

This project emanates purely from the ODI and therefore we cannot put this work out to competitive tender. We have been advised by Procurement and Commercial Department advise that we cannot put their ideas out to the market place, unless they are significantly modified, in order to achieve added value. The ODI proposal, as it stands, fully meets DFID requirements and the ODI is uniquely placed to carry out this work; they have the knowledge and existing relationships in place to effectively carry out their project proposal and shift global debates on economic transformation. The cost of delivering a similar programme through a private supplier would be considerably higher, without the same links to established international networks or significant experience in policy relevant analysis and knowledge of aid management.

The most appropriate funding mechanism is an Accountable Grant. ODI is a not for profit organisation that has approached DFID with a proposal that fits our needs to take forward DFID’s new economic development strategy (January 2014). We have the flexibility in the accountantable grant to use performance tools, such as an inception phase, payment by results, key performance indicators (KPIs) and break points, to and put greater responsibility on the ODI to deliver good quality products to DFID country offices and partner governments; incentivise better performance; and build in opportunities take corrective action and take stock.

Payments will be made to ODI on the basis of outputs against a rolling work plan that will be revised in light of performance summarised in Box 3. In order to incentives performance and minimise the risk of ODI not delivering a good quality product, workplans will be based on performance in the previous period. Therefore more risk of delivery will be passed to ODI. A draft performance framework is attached at Annex 4.

Output-based payments will be made against the budgeted outputs and budget that the ODI is providing, which will be the reference document attached to the Accountable Grant. The Grant will make it clear that DFID reserves the right to withhold part or all payment if agreed outputs have not been achieved to a satisfactory standard.

Box 3: Framework for revising SET work plans based on performance / The proposed performance framework passes more risk for performance to ODI and incentivises better performance by giving greater consideration to whether outputs achieved their intended impact. GRD/DFID will be responsible for changes in budget based on a consultative process that is simple and transparent. It is consistent with current process for scoring work under DFID accountable grants. It maintains adequate predictability in financing; performance in one period will inform level of funding in the subsequent period. / All outputs will be scored against KPIs by GRD drawing on feedback from other DFID depts., other clients (governments, donors), ODI (self assessment), member of Advisory Committee and for some components, surveys and data on use of online resources. DFID will draft a decision on the forward Starting from December 2015 to the Advisory Committee. The final decision will be reflected in budgets from April 2016. This process will be done on a six monthly basis. Revisions can be up or down or the work plan can be left the same. / It also recognises that other factors should also affect revisions to future work plans e.g. absorptive capacity of ODI and level of demand for outputs. The framework also recognises that factors out of DFID/ODI’s control influences impact.

The Grant will also make it clear that ODI must trawl outside its own organisation, to ensure that we capitalise on its network of contacts and get the best expertise available; we understand that ODI has excellent links with donors, policy makers and good convening powers with academics and local researchers. DFID will expect to see the proposed teams and CV’s, where appropriate, before commissioned work can commence, especially for Outputs 1 and 2.

There will be a 6 month inception phase will allow detailed work-plans to be drawn up, further countries to be identified and a timeline with delivery milestones established. Year one KPIs will be agreed during the inception phase and annually thereafter, to further incentivise performance. This will, for example, help ensure that analysis undertaken is demand led and the ODI does is not producing work to serve its own ends. Possible performance indicators are the number of DFID country offices and policy makers provided with advice and analysis, the number of DFID country offices and partner governments satisfied with the quality of the services provided and the number of policy changes attributable to ODI advice. These will be initially drafted by DFID using the ones in place for the International Growth Centre as an example. This will be a good example, since the IGC also carry out policy advice and reseach The accountable grant will make it clear that there will be a break point after two years, in order to take stock and assess whether we wish to make any necessary adjustments to the programme, scale the programme up or down or withdraw.

DFID, as the procurer of services, will retain intellectual property rights.

The economic transformation programme will be led by ODI’s International Economic Development Group (IDEG), which is a group of around 10 economists. Their work extends beyond economic analysis to include policy advice to developing countries and international organisations. The team works with other economists in Europe and in developing countries. The Accountable Grant will also make it clear that ODI must trawl outside its own organisation, to ensure we get the best expertise and DFID gets best value for money. It has excellent links with donors and policy makers and good convening powers with academics, local researchers and policy makers and we will expect it to take advantage of this. The Accountable Grant will make it clear that we would like ODI to share information about the composition of the project teams being used, in order to ensure that we are getting access to the best expertise available.

Although ODI is an established not for profit organisations, we will make every effort to negotiate on anticipated costs as a detailed programme budget is developed during the project inception phase. ODI will be obliged to meet DFID’s terms and conditions and travel will be by economy class and costs will be challenged where they are thought to be unnecessary. We will look at the budget carefully and strip-out anything we deem to be surplus to requirements.

## Financial Case

Up to £4.266m will be paid directly to the ODI for staff costs and to provide sub-grants to experts trawled from outside for the provision of policy advice, analysis and synthesis papers to DFID country offices and partner governments. Money will also be used to develop an on-line portal/website on economic transformation and to provide management support. £90,000 is provided for evaluation and £120,000 for programme review and monitoring in an innovative area.

The required funding will be available throught the current resource allocation and it will be charged to the programme budget.

The overall costs to ODI for 3.5 years (Dec 2014 – June 2018) would be £4,265,500, with £160,250 for the first quarter, £319,250 for the first half and about £1,262,000 for each full year thereafter. The shares by task are somewhat fungible, but are roughly divided into policy advice and policy analysis and advice (76%), central management team related costs (10%), data portal and website (8%), and public affairs (5%). The budget for policy analysis and advice is included as one budget line – the detailed budget lines for policy advice and analysis are indicative and can be vired across. The cost profile for core/admin costs and the three components is estimated as in Table 1 below:

Table 1: Annual and total estimated costs for SET

The management overheads include the programme director (80 days per year), 60 days an economist (60 days working on TORs, assembling teams), a full time coordinator/administrator (full time) and other costs not assigned to specific outputs. The director and economist will also contribute time against the four outputs; once the programme starts costs will be able to be attributed more accurately against outputs to gauge overheads on management of the programme which is likely overstated in the above table.

The schedule of payments will be agreed and set-out in the Accountable Grant. The DFID programme team will approve annual budgets in advance, revised in line with the performance framework (see Commercial Case for description of Performance Framework). Finance and the payment profile will be a recurring agenda item at the ODI/DFID management meetings, which we envisage will happen quarterly, to check that spending is on track.

The anticipated expenditure profile is as in Table 2 below. The first payment will be following signing of the Accountable Grant. The second payment will be made based on the Inception Report to be received in June 2015. Payments for each period thereafter will be based on a quarterly report detailing the use of resources for outputs in the previous period. Quarterly reports will be due by end March, June, September and December.

Table 2: Expenditure profile for payments for first 18 months

We assess the risk of financial risk and fraud as medium – a temporary and conservative scoring until ODI undertakes a due diligence assessment in line with DFID requirements which we anticipate will be early during programme implementation. DFID has commissioned work from the ODI in the past although the only due diligence assessment undertaken relates to a specific assignment for DFID South Sudan. If necessary a further due diligence will be undertaken during the first year of the programme. We will make every effort to ensure there are adequate controls to mitigate the financial risks identified. Fraud and corruption is covered in the Accountable Grant and a zero tolerance approach is conditional on signing.

Value will be added through the number of requests from DFID country offices and partner governments that Growth and Resilience Department receives for the services of the ODI and the number of DFID economic programmes and partner government policies the ODI can influence and whether these can be scaled up.

Management Case

The Senior Economic Adviser for the Growth Team, Stuart Tibbs, is responsible for the overall delivery of the programme and will be the SRO. He will be accountable for the vision and overall performance of the programme and provide leadership throughout the life cycle of this project. He will be accountable for

- Delivery of DFID’s objectives as set out in the programme’s Business Case and Delivery Plan;
- Adapting programmes to changing contexts, based on learning and feedback;
- Compliance with the Smart Rules (with respect to design, delivery & closure of programmes);
- Being objective about areas of under-performance, taking action to improve, restructure or close.
The SRO will manage a task team, including part of the time of an Economic Assistant and a Programme Manager. The project will be managed using a DFID logical framework matrix (logframe) that will be prepared during the inception phase. The Programme Manager will be responsible for co-ordinating the team to deliver annual reviews and monitoring and managing relations with the ODI and managing the budget. Economic Assistant will support quality assuring all technical inputs and advice.

The organogram below shows the simple structure of the programme described further in Section (B), pp. 5-6 in ODI’s proposal, Annex 1. The Advisory Committee will meet

Organogram for SET programme

The programme will start with a six month inception phase which will be used (1) to gauge demand from DFID, governments and other partners and to match expertise with this demand; and (2) to pilot support to two country offices. A recommendation will be made to GRD’s Head of Department on whether to progress to the implementation phase.

During the 6 month inception period, DFID will meet ODI at least twice and stay closely involved with the development of ODI’s detailed four year work plan. As the internal growth diagnostic process is relevant and high workload for DFID between now and mid-2015, the SRO will involve lead advisers on the diagnostic in gauging what opportunity the programme provides for its implementation.

Duringthe implementation phase, DFID will also agree with ODI on a timetable for regular management meetings every three months to monitor performance and agree annual workplans and budgets in advance. DFID will communicate significant concerns over ODI performance (operational or otherwise), through the Senior Economic Adviser responsible for delivery of the programme. DFID will ensure regular engagement with DFID country offices where ODI is engaging both during the design phase of country office support programmes and during on-going delivery to ensure linkages to DFID economic growth priorities and thinking and DFID county programmes.

The programme’s Advisory committee will consist of members of DFID, ODI and independent members and will meet every six months. They will be resoponsible for providing guidance on work plans and steering the programme and will review draft decisions on whether work has been completed satisfactorily which inform performance based budget decisions.

Evaluation

An independent evaluation will be undertaken during the programme. The evaluation is expected to use qualitative approach to answer an evaluation question related to: (i) the quality and additionality of policy advice and analysis under the programme and (ii) its impact in changing the policies and programmes of governments and donors. The design will benefit from the experience in GRD of managing a larger scale evaluation of the IGC. The evaluator will be either be selected from a mini-competition of known experts or through using an existing framework contract or other appropriate DFID facility e.g. 3iE. An indicative budget is shown in the table below. Design will take place at the beginning of the implementation phase with inputs during years 2 and 3 and final report in year 4.

Programme Support
103.	The programme will have a dedicated budget allocuation of up to £120,000 for programme assistance by a third party. Such support will be only be used to inform wider development thinking on economic transformation, for a target audience/recipients outside of DFID.

Risks and risk management

The main risks of the programme relate to the quality and timeliness of advice and the ongoing demand for support. The programme will be managed using a performance framework to ensure value for money and quality and impact of the work from the Accountable Grant. The performance framework will provide management information that will be used to revise subsequent budgets or to stop funding if necessary.

The main risks of the programme are:
Risk	Probability	Impact Before Mitigation	Mitigating Strategy
ODI analysis/policy advice is not aligned with with DFID and partner govrnments requirements	M	M	DFID will quality assure ODI team’s offering advice and payment will be withheld if analysis/policy is unsatisfactory. The programme will be steered by a governance committee that meets at least every six months and DFID will raise any concerns directly with ODI.
ODI’s policy advice and analysis is not implemented by DFID country offices and partner governments.	M	M	DFID will keep in regular contact with DFID country offices. / ODI will receive steering and guicance by the programme Governance Committee. / Customer satisfaction with ODI advice and analysis will be built into the KPIs. / A mid- programme break point will give DFID the opportunity to take stock of the project and consider whether to scale down or withdraw.
ODI’s communication strategy is not effective.	M	M	Plans to be shared with DFID during the six month inception phase. / ODI give regular updates in quarterly reports. / Regular consultations with DFID country offices. / Fifty percent of payment for this component will depend on quality assurance from the Governance Committee.
ODI’s on-line web portal is not good and receives few unique visitors			Design to be agreed during the inception phase. / Number of unique visitors to be a key performance KPI.

Annex 4: DRAFT Performance framework for SET Accountable Grant (TBC at end of Inception Phase)

This annex sets out a draft performance framework for SET. It describes the principles behind the framework and how it will operate in practice.

Principles:
- GRD/DFID decides changes in budget based on a consultative process
- Passes more risk for performance to ODI and incentivising better performance
- Gives greater consideration to whether outputs achieved their intended impact
- Consistent with current process for scoring work under DFID accountable grants
- Maintains adequate predictability in financing; performance in one period will inform level of funding in the subsequent period
- Recognises that factors out of DFID/ODI’s control influences impact
- Process needs to be simple and transparent
- Other factors also affect revising future work plans e.g. absorptive capacity of ODI and level of demand for outputs.

Procedure and sequencing
1. All outputs will be scored by GRD based GRD’s own assessment drawing on inputs from (i) ODI, (ii) the client (other DFID dept, govt, other donor), (iii) Advisory Committee, (iv) other targeted surveys; (v) data on utilisation of online materials.
2. From April 2016, work plans will be revised up or down or left unchanged based on scoring, absorptive capacity, level of demand for outputs and other factors
3. Work plans can be modified each six months i.e. in April and in October. The decision will be made at least 3 months before i.e. by Dec 31 and by Jun 31 respectively.
4. DFID’s initial or draft decision will be discussed by the previous Advisory Committee meeting starting in Dec 2015.

Indicators and scoring
Performance scoring will be based on the existing scoring for Accountable Grants with letters converted to numbers to assist combining scores from different sources i.e.

Description	AG score	Value
Substantially exceeded expectations	A++	4
Moderately exceeded expectations	A+	3
Met expectations	A	2
Below expectations	B	1

Scores weighted roughly based on share of funding: Output 1 40%; Output 2 40%; Output 3, 10%; Output 4, 10%.

Output 1: Support to DFID departments, governments, other donors
Indicator	Means of verification	Target and scores
1.1 Assessment of output based on quality or technical work and stakeholder engagement	Score with rationale from (i) ODI self-assessment, (ii) client (DFID dept, govt, donor) / (iii) Adv Committee member	4 to 1 based on above table
1.2 Cross-referencing to other sources (TBD)	TBD	TBD
Output 2: Data portal and analysis
Indicator	Means of verification	Target and scores
3.1 Quality of portal	Satisfaction survey from 5-10 targeted users	4 to 1
3.2 Use of the portal – TBD	No.s of hits, downloads, use of tools, links to other data sources	>Z,000 = 4 / >Y,000<Z,000 = 3 / >X,000<Y,000 = 2 / <X,000 = 1
Output 3: Communications on economic transformation
Indicator	Means of verification	Target and scores
4.1 Quality of website	Satisfaction survey from 5-10 targeted users	4 to 1
4.2 Website use	No.s of hits, downloads	>ZZ,000 = 4 / >YY,000<ZZ,000=3 / >XX,000<YY,000=2 / <XX,000 = 1

- Across the whole programme, weighted averages of the following range will lead to directions of change in levels of programming as in the table below.
- Other factors that DFID will consider include:
  - Absorptive capacity
  - Demand for outputs
  - Anomalies in scoring scheme that distort scoring against performance

Average Score	Direction of revision in work plan
<2.5	Decrease
>2.5<3.0	No change
>3.0	Increase

Scale of work plan adjustments
Adjustments will depend on the factors in the paragraph above. They are likely to be e.g. reduction in no. of countries / studies etc.