## Template
Supporting Economic Transformation
2016-04-28
PROJECT TITLE: Supporting Economic Transformation
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (30 June 2018)
|  | Planned |  | TBC
A significant contribution to global knowledge on best practice policy and programming on growth and economic development. | DFID and other donor programming and policy work in specific countries strengthened. | Achieved
Source
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (30 June 2018)
Planned
Achieved
Source
OUTCOME 1 | Outcome Indicator 1:1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018) | Assumptions
DFID , governments and other development partners design and implement economic development investments to foster structural economic transformation in order to give rise to stronger, more inclusive growth and poverty reduction in the long term. | Number of DFID country portfolios influenced by SET research and advice, in design or delivery | Planned | 0 | 1 by October 2015 | 4 by October 2016 | 6 by October 2017 | 8 by June 2018 | 1. Shifts in international thinking on economic transformation impact on national-level transformation. 2. The profile of economic transformation would remain constant for SET programme partners, in the absence of the SET programme 3. International economic stability in the face of shocks (e.g. ebola, natural hazards)
Achieved
Source
| Outcome Indicator 1:2 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
| Number of DFID centrally managed programmes influenced by SET research and advice. | Planned | 0 | 1 by October 2015 | 2 by October 2016 | 3 by October 2017 | 4 by June 2018
Achieved
Source
| Outcome Indicator 1:3 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
| Number of other donors, governments or multilateral agencies adopting policy or programming choicees through SET programme influence. | Planned | 0 | none | 1 case by October 2016 | 2 cases by October 2017 | 3 cases by June 2018
Achieved
Source
OUTCOME 2 | Outcome Indicator 2:1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018) | Assumptions
Better coordination between private sector/ business and government on economic transformation. | (i) Policy processes being changed by private sector participation (ii) Private sector firms/associations operations/plans changed by interaction with the SET programme | Planned | 2015 | 1 case by October 2015 | 3 cases by October 2016 | 5 cases by Octobr 2016 | 7 cases by June 2018
Achieved
Source
OUTCOME 3 | Outcome Indicator 3:1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018) | Assumptions
Better global knowledge on how policies can support growth by accelerating economic transformation | SET programme demonstrates it is a centre for knowledge on economic transformation by the global community (NGOs, thinktanks, academia). | Planned | 0 | Develop baseline on ET by June 2015 | 2 cases by October 2016 | 4 cases by October 2017 | 6 by cases June 2018
Achieved
Source
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018) | Assumptions
Policy advice to DFID . | DFID country offices and central departments policies and programmes supported by SET research outputs, including support with growth diagnostics (see KPI for 1.1 below); | Planned | 0 | 2 country offices by June 2015 1 central department by December 2015 | 4 country offices by October 2016 2 central departments by October 2016 | 6 country offices by October 2017 3 central departments by October 2017 | 8 country offices by June 2018 4 central departments by June 2018 | Economic transformation dialogue of DFID/govts/partners engaged in the SET programme is an outcome of the SET programme.
Achieved
Source
| Output Indicator 1.2 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
| In-depth and comparative analyses focused on specific issues proposed by DFID and other partners (see KPI for 1.2 below). | Planned | 0 | 1 comparative analysis by October 2015 | 2 comparative analyses by October 2016 | 4 comparative analyses by October 2016 | 6 comparative analyses by June 2018
IMPACT WEIGHTING (25%) |  | Achieved
|  | Source | [5 empty] | RISK RATING: Medium
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
Policy advice to governments and other development partners . | Support to country governments on strategies to accelerate economic transformation (see KPI 2.1 below). | Planned | 0 | 1 country govt by June 2015 | 3 cases to at least 2 country govts by October 2016 | 5 cases to at least 3 country govts by October 2017 | 7 cases to at least 4 country govts by June 2018
Achieved
IMPACT WEIGHTING (25%) |  | Source | [5 empty] | RISK RATING: Medium
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018) | Assumptions
Private sector and business engaged on the role of econimic transformation in policy dialogue (KPI 3 below) | (i) Policy processes in which private sector participate (ii) Private sector firms/ associations operations/plans interacting with the SET programme. (see KPI 3.1 below) | Planned | 0 | 1 case by October 2015 | 3 processes by October 2016 3 interactions by October 2016 | 5 processes by October 2016 5 interactions by October 2016 | 7 processes by June 2016 7 interactons by June 2016
Achieved
IMPACT WEIGHTING (20%) |  | Source | [5 empty] | RISK RATING: Medium
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
Data portal to promote better use of economic data in analysis on economic transformation in policy dialogue . | Quality of portal | Planned | 0 | Portal live by December 2015 | Survey of DFID country offices in SET focus countries reveals 70% have knowledge of data portal. | Survey of DFID country offices in SET focus countries reveals 80% have knowledge of data portal. Surveymonkey of target audience reveals 80% of respondents rate the portal as 'good'. | Survey of DFID country offices in SET focus countries reveals 80% have knowledge of data portal. Surveymonkey of target audience reveals 80% of respondents rate the portal as 'good'.
IMPACT WEIGHTING (15%) |  | Achieved
|  | Source | [5 empty] | RISK RATING: Medium
| Output Indicator 4.2 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
| Number of data portal downloads | Planned | 0 | TBC | TBC | TBC | TBC
Achieved
Source
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
Implementation of a communication strategy including events to promote understanding of economic transformation. | Development and implementation of communication strategy | Planned | 0 | Development of communication strategy by June Setup of website |  | Update of communication strategy
Achieved
|  | Source | [5 empty] | Assumptions
| Output Indicator 5.2 |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
| Results of multi-event assessment tool show good responses from participants | Planned | 0 | 7 out of 10 people surveyed rated the event as 'good' and higher | 7 out of 10 people surveyed rated the event as 'good' and higher | 7 out of 10 people surveyed rated the event as 'good' and higher | 7 out of 10 people surveyed rated the event as 'good' and higher
Achieved
| Output Indicator 5.3 | Source
Uptake of SET products (including anchor papers, themed papers, comparative analyses) by the global community, including via the media (see KPI 5.3)
|  |  | Baseline | Milestone 1 (2015) | Milestone 2 (2016) | Milestone 3 (2017) | Target (30 June 2018)
|  | Planned | 0 | 1 case | 2 cases | 3 cases | 4 cases
IMPACT WEIGHTING (15%) |  | Achieved
|  | Source | [5 empty] | RISK RATING: Medium

## Smart Guide
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from DFID and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by DFID and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The DFID share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined e.g. DRF, OP, ICF KPIs, MDG indicators
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your SRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
RISK RATING
Risk ratings are recorded as Low, Medium or High and are supported by a robust analysis including a risk matrix.