Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Evidence for Action to Reduce Maternal and Newborn Mortality in Africa (E4A)
Programme Value: £18,220,491.00		Review Date: December 2014
Programme Code: 201512	Start Date: Aug 2011	End Date: March 2016

Summary of Programme Performance

Year	2012	2013	2014 (This review)	2015	2016
Programme Score	A	A	A
Risk Rating	M	M	M

Summary of progress and lessons learnt since last review

Following recommendations from the 2013 annual review, the programme undertook a strategic review of the whole programme in the first half of 2014. This review has resulted in a more focused and strategic programme. The log-frame was revised to become more representative of country ‘asks’ and ‘sub-asks’, and reworded to reflect the greater strategic approach to the programme, with more specifically tailored approaches in each country.

In the latter half of 2014, E4A has adapted to budget cuts from DFID. This has had significant programme implications. Implementing those changes has taken significant time and effort on the part of E4A and DFID, and has led to further log-frame changes.

The E4A team has remained enthusiastic despite these significant changes and important progress has been achieved in most of the countries and across most of the indicators, as this Annual Review demonstrates. In some areas, the programme has exceeded milestones and where milestones have not been met, it has been as a result of external factors (such as Ebola or changes to government policy). However, we acknowledge budget cuts have added risks to the programme reaching its planned outcomes as activities associated with the theory of change have had to be cut or reduced.

At the outcome level, the programme has bespoke tools that measure ‘data for decision making (DDM)’ - that assesses changes in how well health managers use evidence – and ‘politics, power and perception (PPP)’ that assesses political commitment to maternal and neonatal health. In addition the programme has tools to measure quality of care in each country. In every country, progress has been made. Four of the six countries have made progress on both DDM and PPP, and the other 2 have made progress on one but not both of these indicators.

Lessons learnt: while lesson learning between countries is useful, advocacy messages and approaches take on different forms according to specific country windows of opportunities and evolving contexts. There is no one size fits all solution. It was useful to refocus and rethink the E4A strategy midway through the programme to ensure clarity of thought for strategies and the Theory of Change.

The Independent Evaluation (including the policy studies) teams were hired (competitively selected and passed through the Specialist Evaluation and Quality Assurance Service (SEQAS), and interesting findings have started to emerge. Results should help both in programme learning and in testing the Theory of Change.

Summary of recommendations for the next year

1. Sustainability: Opportunities are currently being sought to institutionalise strategies and approaches in local institutions and processes to ensure the end of E4A does not mean an end to benefits achieved through the work of this programme [ACTION: E4A Team]. Progress on this needs to be reviewed in 6 months time and again at the next annual review. [ACTION: DFID ARD MDG Team – June and December 2015]
2. Consolidate: good progress has been achieved so far. This progress has to be sustained and strategies brought together to ensure outcomes are achieved in all countries. Some counties appear to be further advanced than others, and it appears that more work in Malawi is needed to refine their strategy. Outcome results (Data for Decision Making) for Nigeria also need further investigation and from this a refinement of the country strategy. [ACTION: E4A Team]
3. Document evidence: Focus on documenting transparently which pathways to change worked through the Independent Evaluation. [ACTION: E4A and Evaluation Teams]. This will help others in the field of advocacy and MNH to understand what works, when and how – an important contribution to the overall field.

A. Introduction and Context

DevTracker Link to Business Case:	Link
DevTracker Link to Log frame:	Link

Outline of the programme
DFID is providing £17,256,376 over five years to a consortium led by Options (a UK-based international health consultancy), and including a range of technical, academic, and advocacy partner organisations, to implement the Evidence for Action to reduce maternal and newborn mortality in Africa (E4A) programme. The programme period is 2011-2016; following a lengthy inception phase programme implementation began in the second half of 2012. DFID is also supporting an independent evaluation of the programme.

The programme aims to improve maternal and newborn survival through a combined focus on evidence, advocacy, and accountability in six countries (Ethiopia, Ghana, Malawi, Nigeria, Sierra Leone, Tanzania) and regionally focused on the Maternal Death Surveillance and Response Network, Africa Health Budget Network, CARMMA, AfricaHealth Stats and alignment to the Commission on Information and Accountability goals (working with regional and global institutions and partnerships, such as the African Union, WHO, and the Partnership for Maternal, Newborn and Child Health). E4A is designed to result in better maternal and neonatal health services and outcomes by promoting more effective use of evidence to generate political commitment, strengthen accountability, and improve planning and decision-making – working both at country level and to support strengthening of regional and international accountability frameworks.

DFID is the sole funder of this programme, although some additional funding has been secured from the Gates Foundation and Norway to scale up some specific activities developed under this programme.

Context in 2014:
1. Strategic review: Following the 2013 Annual Review (AR), Options agreed to a Strategic Review of the E4A programme. The main results would be:
  1. Tighter country strategies, with clearer documentation of how they apply the Theory of Change.
  2. Clearer expectations internally and among key stakeholders, of what E4A can and will achieve – including in terms of communications strategy and approaches.
  3. A logframe that better reflects country programme approaches and milestones.

Programme cuts: Due to budget realignments within Africa Regional Department, as of 17th July 2014, DFID and Options agreed £3m reduction to the remaining E4A budget, £1.3m in 2014/15 and £1.7m in 2015/16. The contract amendment was signed October 2014. The strategy involved ending three country programmes six months early (Ghana, Sierra Leone, Tanzania); cutting regional activities; cutting capacity development; reducing the geographical reach of sub national activities and identifying tactical cuts to all activities and operations. The proposed strategy for cuts was approved by the Programme Leadership Group in October 2014, and the log-frame revised accordingly.

1. The Ebola crisis in West Africa has significantly affected the E4A programme in Sierra Leone. The country programme has shown good flexibility and adaptability within the country context by:
  1. Keeping maternal health issues on the agenda (e.g. writing a policy brief on budget tracking particularly to see if Ebola money is in fact new rather than a diversion of resources and continuing relationship with the Office of the First Lady, who continues to advocate on gender and maternal health issues)
  2. Contributing to the overall Ebola effort in various ways (e.g. E4A is part of the Social Mobilisation pillar for Ebola nationally, E4A has contributed to global publications on Ebola situation in Sierra Leone)
  3. Adapting the E4A programme to take into account the current situation (e.g. FIT and QUIC assessments adapted to include Ebola component to enable tracking within health facilities, and collaborating with UNFPA and MOHS on qualitative assessment of RMNCH services and health-seeking behaviour in the current context of Ebola).

## B: PERFORMANCE AND CONCLUSIONS

Annual outcome assessment
The overall outcome statement for E4A is ‘More and better, evidence based use of resources for MNH’, with specific country-adapted descriptions for each country. Each country has 2-4 outcome indicators:
- Outcome 1: Use of evidence by national and sub-national health managers and health facility managers in their decision-making (measured by bespoke tool Data for Decision-Making DDM)
- Outcome 2: Political will to improve quality of care and the use of evidence for decision-making (measured by bespoke tool Politics, Power and Perception PPP)
- Outcomes 3 and 4: Country-specific tracer indicators on quality of care (measured by a variety of data collection tools within the countries)

Reporting against the outcome indicators 1 and 2 shows that most countries are on track, with the exception of Nigeria, where the DDM score is much lower than expected (38%, compared to 53% 2014 milestone), and the PPP score is slightly lower than expected (58%, compared to the 65% 2014 milestone) in Tanzania.

We recommend that E4A consider conducting further qualitative research – as they have suggested - to understand the fall in use of data for decision-making (initially thought to be due to high staff turnover at state-level in Nigeria) and in political will (could be due to discrepancies between national and state-level priority making in Tanzania). The follow-up research will allow country teams to focus their efforts to achieve outcomes in the coming year.

For the outcome indicators on quality of care, most countries seem to be well on track for their 2014 milestones. The exceptions are Ethiopia, where under indicator 3, the 2014 milestone (‘regional planning and other resource allocation meetings include discussion of Maternal Death Surveillance and Response (MDSR) data’) has not been achieved. This milestone might have been over-ambitious because it depends on the government moving forward on MDSR fast. We recommend that E4A revisits whether the 2015 milestone is therefore going to be achievable. The other exception was Sierra Leone, where no health facilities were BEmONC compliant when measured earlier in 2014, the November 2014 results are still pending. The 2015 milestone will probably have to be altered, and a reason given if it is not reached (but likely to be Ebola). It is worthwhile for E4A to keep a close watch on Tanzania, which missed the 2014 outcome indicator 3 milestone very slightly, to ensure the 2015 milestone is on track.

Overall output score and description

A - Outputs met expectation

Key lessons
Strategic Review process lessons: The linkage between strategies and approaches to achieving change is key (accountability, advocacy, media use, website, MDR and other data) – so it was useful to rethink how these strategies fit together and form a more coherent whole. Moreover the strategic review articulated the steps to change in achieving logframe indicators and the theory of change. It was also useful to take the process of the strategic review slowly, and at this midway point during the programme, to ensure country-team ownership and involvement in development of log-frame indicators. Lastly, it was good to recognise that while a common approach underpins E4A throughout country programmes, country-specific approaches utilising specific windows of opportunity for advocacy and accountability are much more realistic.

Key actions
- DFID’s advisory team in Africa Regional Department need to ensure E4A maintains its strategic focus.
- We recommend that E4A consider conducting further qualitative research – as they have suggested - to understand the fall in use of data for decision-making scores in Nigeria.

Has the logframe been updated since the last review?

Yes, the logframe was updated twice in 2014. First the logframe was updated following the Strategic Review (completed June 2014), then the logframe was revised due to programmatic budget cuts (completed October 2014). These changes were discussed and approved at the DFID E4A Programme Leadership Group. Contract amendments have been made to align to these changes.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Better information for better results: realising key parts of Commission on Information and Accountability (CoIA) recommendations in 6 countries
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	31%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
1.1 / Ethiopia: Maternal death surveillance and response (MDSR) system coverage: the number of focal regions and woredas implementing MDSR per national guidelines, with meetings occurring as stipulated in the guidelines / Ghana: Use of MNH data for forward planning and resource allocation at district level. / Malawi: Coverage of community maternal death reviews (c-MDRs). / Nigeria, Sierra Leone: Coverage of maternal death reviews (MDRs) / Tanzania: Coverage of maternal and perinatal death reviews (MPDRs)	Only Ghana has a 2014 milestone: / DHMTs in 6 focal districts have considered new MNH evidence at a management meeting	Achieved in 8 focal districts / Over-achieved
1.2 Ethiopia: % of health facilities visited in the last quarter of the project year which are implementing MDSR according to the national guideline / Ghana: Use of maternal death review (MDR) findings to identify and report problems in the system / Malawi, Nigeria, Sierra Leone: Use of maternal death review (MDR) findings. / Tanzania: Use of maternal death review (MPDR) findings	Ethiopia: Supportive supervision visits in all 4 focal regions/cities include the completion of a checklist/guide to establish whether the national guideline is being followed / Ghana: E4A-supported training on MDR feedback delivered to Ghana Health Service staff in 6 focal districts / Malawi: Feedback mechanism operates via quarterly meetings in 6 districts / Sierra Leone: National guideline on strengthening MDR response developed / Tanzania: Training of hospital staff from 8 hospitals in Mara region on how to use MPDR findings (action and response) / Nigeria – no 2014 milestone	Ethiopia: Achieved / Ghana: Training delivered to staff in 12 focal districts. Over-achieved / Malawi: Achieved / Sierra Leone: Not achieved due to Ebola crisis / Tanzania: Not achieved due to MOHSW asking for new MPDR guidelines before any training takes place
1.3 Ethiopia: Use by regional MDSR committees of MDSR data disaggregated by geography / Ghana: Use of disaggregated maternal and newborn data (including indicators from the CoIA list) in progress and performance reviews / Malawi: Use of disaggregated maternal and newborn indicators in progress and performance reviews at district level / Nigeria, Tanzania: Use of disaggregated maternal and newborn indicators from the CoIA list in progress and performance reviews. / Sierra Leone: Availability of disaggregated data on maternal and newborn indicators from the CoIA list	Ethiopia: Regional MDSR committees in 2 focal regions/cities have discussed disaggregated MDSR data at least once / Ghana: Census workshop with MNH stakeholders / Malawi: At least one round of data collection complete for the District Dashboard in all 6 focal districts / Nigeria: MNH scorecards are populated bi-annually, and results discussed by State review team in 1 focal state / Sierra Leone: Set of MNH indicators agreed at national level, including indicators from the CoIA list (the Sierra Leone indicator index) / Tanzania: Disaggregated data used at a 6-monthly review meeting to evaluate progress against the 2013-2015 Mara Strategy	Ethiopia: partially achieved, due to MDSR system being recently set up / Remaining 5 countries all achieved
1.4 Ethiopia: Development of a database integrating data for IDSR (Integrated Disease Surveillance and Response) and MDSR (Maternal Death Surveillance and Response) / Ghana: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions / Malawi: Coverage of mobile phone data capture system to monitor health facility readiness and ability to perform signal functions (QuIC) / Nigeria: Use of MNH evidence to support the development of annual state health sector plan and budgets / Sierra Leone: Availability and accessibility of data on key MNH outcomes / Tanzania: Coverage of QuIC data collection system to monitor health facility readiness and ability to perform signal functions	Ethiopia: Structure of integrated database is agreed and database is ready to be populated / Ghana: Quality of Institutional Care (QuIC) system is used to capture data from 67 health facilities in 16 districts / Malawi: Quality of Institutional Care (QuIC) system is used to capture data from 35 health facilities in 4 districts / Sierra Leone: First round of quality of Institutional Care (QuIC)/QuIC-FIT system is used to capture data from 22 health facilities in 2 focal districts / Tanzania: One round of QuIC data collection completed in at least 50 health facilities in 6 focal districts / Nigeria – no 2014 milestone	Ethiopia: Achieved / Ghana: Data captured from 49 facilities in 12 districts. Partially achieved, due to further permissions to conduct QUIC needed from regional directorates / Malawi: data captured from 10 facilities in 2 districts. Partially achieved, due to initial resistance from one of the regions / Sierra Leone: 40 facilities in 4 districts & Tanzania: 76 facilities in 8 districts. Over-achieved

Key Points
- The four main approaches taken by E4A country teams to increase the use of evidence are: improving coverage of MDSR data, ensuring that MDSR data are used, ensuring that MNH data is disaggregated, packaging MNH data into scorecards to facilitate data for decision-making and trialling a new system of real-time quality of care data collection from facilities by telephone (QUIC).
- These approaches have been used differently in each country according to the specific country context, and mostly look to be gaining progress as expected – with the exception of Tanzania where there is a system bottleneck with approving the MPDR.
- QUIC took longer to be established, but now progress is going well, for example in Tanzania where there are practical examples of change that the QUIC process has prompted in 3 districts.

Summary of responses to issues raised in previous annual reviews (where relevant)
Output 1 indicators and milestones were significantly revised during the Strategic review to become more meaningful and relevant to country asks and sub-asks.

Recommendations
- The Ghana E4A team (indicator 1.1) is conducting monitoring visits with DHMTs to ensure quality evidence is considered in management meetings. This type of quality oversight over whether the information reaching DHMTs and other decision-making bodies is being used, and used appropriately, will be important to consolidate in 2015 to ensure the overall outcome of better use of data for decision-making is being met.
- 2015 will be a key year for ensuring the QUIC approach is adopted long-term by key stakeholders, and the results being actively used to improve quality of facilities.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Political leadership and public momentum
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	28%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
2.1 / Ethiopia: Integration of national MDSR guidelines in training and strategic plans / Ghana: Percentage of MamaYe! press releases that lead to a published article or are featured on radio/TV, without incentive / Malawi: Number of national TV programmes covering MNH issues, and number of district-level broadcasts/ publications covering MNH issues / Nigeria: Number of news articles in a 3-month period making reference to MNH, in newspapers (including online) / Sierra Leone: Percentage of MamaYe! press releases that lead to a published article in at least one newspaper, without incentive / Tanzania: Local media coverage of MNH issues	Ethiopia: Pre-service and in-service training schools in 2 focal regions/cities have had orientation sessions on the MDSR system / Ghana: Ghana’s engaged advocates/activists list includes 30 journalists who have been sensitised to the campaign via training events or individual meetings / Malawi: 10 programmes aired on national TV across the year, which cover MNH issues. District-level journalists publish or broadcast at least 2 MNH stories / quarter / Nigeria: 50% increase in number of news articles (50 articles in total in 2014) / Sierra Leone: Sierra Leone’s engaged advocates/activists list includes 20 journalists who have been sensitised to the campaign via training events or individual meetings / Tanzania: Tanzania’s engaged advocates/activists list includes journalists from at least 19 regions, who have been sensitised to the MamaYe campaign via training events	Ethiopia: Not achieved, groundwork has been done, on track to achieve 2015 milestones / Ghana: 34 journalists sensitised. Over-achieved / Malawi: Achieved / Nigeria: Not achieved (22 articles), partially due to Ebola crisis dominating the news in the latter half of 2014. On track to achieve 2015 milestone. / Sierra Leone: 23 journalists sensitised Over-achieved / Tanzania: 22 journalists from 21 regions Over-achieved
2.2 Engaged activists /advocates	No 2014 milestones
2.3 Accessibility of relevant MNH information and resources for stakeholders	All countries except Ethiopia: Improved functionality of website via updates to structure of evidence pages	Achieved. Qualitative research through a website user assessment was also used to improve website functionality. Proof of increase in functionality with increase hits / month from 1427 in January to 4881 in October for the parent site
2.4 Website visits per month	Website visits / Ghana: 820 / Malawi: 580 / Nigeria: 900 / Sierra Leone: 700 / Tanzania: 830	Over-achieved / Ghana: 856 / Malawi: 584 / Nigeria: 1022 / Sierra Leone: 774 / Tanzania: 835
2.5 Ghana, Nigeria, Sierra Leone: Adoption of MamaYe! campaign by key engaged advocates/activists / Malawi: Number of MamaYe! clubs trained in 6 focal districts, and number of MNH seminars at the Kamuzu College of Nursing / Tanzania: White Ribbon Alliance (Tanzania)’s capacity to influence MNH policy at national level	Malawi: 6 MamaYe clubs trained, and 10 KCN seminars over the period November 2013 – October 2014 / Sierra Leone: Activist engagement package delivered to district-level focal points, CSOs and partner organisations in 2 districts / Tanzania: Formal capacity assessment carried out on WRA Tanzania, which informs institutional and operational capacity-building / Nigeria and Ghana – no 2014 milestone	Malawi: 16 MamaYe clubs trained. 10 KCN seminars held. Overachieved / Sierra Leone and Tanzania: Achieved

Key Points
- E4A’s approach to achieving political leadership and public momentum has included: engaging and mobilising communities to be more aware of MNH issues, and empowering CSOs and citizens to advocate for and take action on MNH. Activities are related to the MamaYe website as well as engaging traditional and social media. This acknowledges that there are a range of ways to reach people in both cities and rural areas in the five African countries. In addition, the large proportion of website visitors from outside Africa also acknowledges the importance of the diaspora in some of these countries in influencing the debate. In Ethiopia, the approach is different and more focused on making sure that the MDSR system is sustainable via engagement with clinical training schools and health sector strategy.
- Milestones for indicator 2.4 have changed dramatically in 2014, and have become much more achievable. This is because the website was up and running for a while, so realistic predictions could be made about what readership could be expected from an MNH country-specific website (the first of its kind in all countries). The revised website numbers remained ambitious, in that each country had an increased target in 2014 on per month website visits as compared to 2013 actual numbers. Lastly, changing indicator 2.3 to measure ‘improved website functionality’ within the logframe has instituted ongoing qualitative review, updates and improvement of the websites.

Summary of responses to issues raised in previous annual reviews (where relevant)
2.5 is a new indicator, introduced during the Strategic Review based on recommendations from the 2013 AR to: (a) be more strategic in the E4A advocacy and communications approach and initiate two-way dialogue based on the platform MamaYe brings and (b) have the logframe reflect better the varying advocacy activities being undertaken in each country. Initial results from 2014 milestones are encouraging.

Recommendations

- Consider sustainability of MamaYe websites when the E4A programme closes. Who is going to host the MamaYe website, update content, upload evidence etc in each country on programme completion? This should be considered within a coherent sustainability strategy for the entire E4A programme in each country.
- Output 2 is also about ‘Political leadership’. Capitalising on upcoming opportunities within Nigeria, Tanzania and Ethiopia with 2015 elections will be key.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Accountability and transparency mechanisms – better oversight and transparency of the provision of MNH services, for better accountability for mothers and their babies
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	31%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 (all countries except Ethiopia) / Ghana: Use of national accountability mechanisms to hold district health managers to account for the status of MNH services in E4A focal districts / Malawi: Multi-sectoral, evidence-based community level accountability mechanisms in place, which include District health sub-committees / Nigeria: National- and State-level accountability mechanism for service delivery / Sierra Leone: Transparency of RCH budget / Tanzania: RMNCH budget advocacy forms key activity for civil society coalition	Ghana – In 8 focal districts, there has been at least one round of data collection using the MNH scorecard mechanism / Malawi – At least one district health sub-committee meeting in 3 focal districts to produce action plans with use of evidence / Nigeria – no 2014 milestone / SL – National health accounts with ability to isolate MNCH spending / Tanzania – Support provided to WRA to increase capacity for budget advocate	Ghana - Achieved (+ results disseminated to communities) / Sierra Leone and Tanzania – also achieved / Malawi - Established in one district – Partially achieved, reasons given include timing of Ministry of Health (MHSP) and release of training materials. Groundwork been done, progress expected in 2015 to achieve 2015 targets on time
3.2 Number of people supported to hold decision-makers to account	Ethiopia – 2,500 / Ghana – 16,000 / Malawi – 10,000 / Nigeria – 18,000 / Sierra Leone – 7,000 / Tanzania – 10,000 / TOTAL = 63,500 / (Using DFID corporately agreed indicator)	Ethiopia – 2,600 / Ghana – 23,453 / Malawi – 20,718 / Nigeria – 20,509 / Sierra Leone – 11,803 / Tanzania – 174,048 / TOTAL = 253,131 / Overall, over-achieved by a factor of 4.
3.3 (only Ethiopia and Ghana) / Ethiopia: Number of health facilities or regions producing MDSR action plans / Ghana: Mechanism to encourage service providers to report their resource and training needs	Ethiopia: At least 1 hospital or health centre in each focal zone/city produces an action plan based on that facility's MDSR data / Ghana: In 1 region (4 districts), teams are allocated to support supervision in districts. They visit at least once every 6 months and make a record of needs	Ethiopia: Achieved / Ghana: Partially achieved (teams have been allocated in 2 districts, but District Directors requested a delay due to time constraints).
3.4 (only Ethiopia) / Ethiopia: Percentage of MDSR recommendations from 2014 action plans which have been implemented	Ethiopia: system in place for monitoring the number and % of recommendations which have been implemented	Ethiopia: Achieved

Key Points
- The E4A approaches to accountability involve setting up MNH budget tracking, action plans, scorecards and sub-national MNH accountability platforms as processes (with the exception of Ethiopia, where establishing MDSR action plans are the key approach). The only country to not achieve its 2014 milestone is Malawi, where progress has been slower than anticipated for several reasons, including delays to relevant activities within the Ministry of Health and the need for more capacity-building work than had been anticipated. This should not hinder achieving 2015 milestones, however. For output 3.3, Ghana partially achieved its 2014 milestone for the same reason. One of E4A’s assumptions for this output is that ‘national and sub-national governments are receptive to transparency of information and budgeting’. E4A has to continue to strike the delicate balance of working with civil society and communities to hold governments to account, whilst also working closely with governments to increase transparency. This is not always an easy balance to strike.
- Indicator 3.2: Significant over-achievement by all countries. Mostly due to teams’ success in engaging with media outlets. Significant high numbers coming from Tanzania and Ghana through spin-offs of MamaYe launch events/clubs. Also Tanzania has had significant success with journalists, including an MOU with the Union of Tanzanian Press Clubs, and an increased focus on quality of reporting based on evidence. Tanzania also has positive country context with increased policy commitments to MNH.

Summary of responses to issues raised in previous annual reviews (where relevant)
From last AR: “Indicator 3.2 shows large numbers of people reached by the programme and ‘supported to hold decision-makers to account’. This indicator is monitored in line with DFID corporate guidance but does not itself capture the extent to which decision-makers are held more accountable for MNH services and outcomes. The strategy for maximising the value of supporting individuals to hold decision makers to account is discussed further in section B. It is recommended that country programmes develop/clarify plans to translate individuals’ engagement with public campaigns into meaningful empowerment to demand quality MNH services (and exert pressure for quality improvement).”

During the E4A strategic review in 2014, the teams explored explored opportunites where decision makers could be held more accountable for MNH outcomes and this has informed the ask’s and sub-asks in each country. For example, E4A country teams have used MamaYe campaign and website to create coalitions (in Ghana), launch events (in Tanzania and Nigeria), and school clubs (in Malawi).

Recommendations
- E4A country teams to continue working with ‘champions’ who can hold decision-makers to account, using existing platforms of MamaYe and coalitions already made who will continue to carry the banner of MamaYe once E4A ends.
- E4A to institutionalise accountability mechanisms within sustainable structures to ensure responsible exit strategies from the programme in 2015 and in 2016.
- In Ethiopia where MDSR is the approach, need to continue to work closely with host institution (WHO) to ensure systems are institutionalised before programme completion.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Better alignment between national and regional MNH initiatives including the realisation of Commission on Information and Accountability (CoIA) goals
Output number per LF		Output 4	Output Score	A+
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Indicator 4.1: Contribution to the CoIA learning process at the global level	‘Evidence, Advocacy and Accountability mid-term lessons learnt brief’ produced by core team, and communicated effectively to level 1 and level 2 partners at global and regional levels	Over achieved / -Presentation to PMNCH colleagues in South Africa / -E4A Nigeria features in IERG 2014 report / -E4A featured in 2014 State of the World’s Midwifery report / -Four articles published in International Journal of Gynaecology and Obstetrics, July 2014. Articles downloaded and viewed significant number of times from US/UK / -Further work to disseminate these articles to African stakeholders in progress
Indicator 4.2: Influence of CARMMA on MNH-relevant decisions made by heads of state and relevant ministries	Launch by CARMMA of regional award scheme to recognise good work in MNH by individuals or organisations in Africa	Achieved / -The ‘Mama Afrika’ award scheme was launched in August 2013, work is ongoing on celebrating nominees / -New African Health Stats website supported by E4A and hosted by AU
Indicator 4.3: Regional and national capacity for implementation of MDSR	Professional MDSR, training and knowledge-sharing network established in conjunction with the MDSR working group, to support scale-up of MDSR regionally. Database of network members established. At least twice a year, updates sent by email on available MDSR resources, training opportunities and available training guidelines based on identified need	Achieved / -The MDSR Action Network’s (launched in April 2013) now has a website (launched May 2014), with average of 500 hits/month since its launch / -Quarterly newsletters sent out to members since Nov 2013, with all relevant information. / -MDSR Action network has also been active in disseminating messages on MDSR events

Key Points
Underlying point: E4A has played a catalyst role in raising influence of CARMMA within the African Union. Dr. Zuma – AU Commission’s Chairperson – has been increasingly involved with E4A around data availability and profiling of maternal health stats and the Mama Afrika award.

Summary of responses to issues raised in previous annual reviews (where relevant)
Following strategic review, new indicators now more relevant to E4A activities.

Recommendations
Moving forward, need to focus on sustainability and institutionalisation of these developments within African institutions. Recognise that it is challenging given programme cuts and limited time/resources left, but examples discussed in AR meeting:
1. Bring more to the fore the experiences of MDSR networks from country-level E4A teams to international fora.
2. Inspire non-E4A countries who are part of the MDSR network to take positive experiences and create MDSR coalitions.
3. Develop sustainable solutions to maintain/use statistics on African Health Stats. E.g. could try continuing linkages with UNFPA, WHO, USAID as key partners to institutionalise these changes. Bring African Union staff into the equation.
4. Involve Tim Stern (DFID’s representation to the AU) on health discussions
5. Work with Chair of FIGO Advisory Group to institutionalise MDRs, with community involvement as key part of that

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Complexities in trying to identify VFM indicators for a programme of this nature was noted in the business case and also echoed in the external review carried out by Health & Education Advice & Resource Team (HEART) in January 2014. Given this scenario five quantifiable VfM measure were recorded in the business case which have not changed for reporting purposes in this annual review.

- Management and administration costs per pound invested (measured by unit costs of flights and per diems and accommodation)
- Extra resources leveraged per pound invested
- Use of evidence by national and sub-national health managers in their decision-making
- Lives saved per pound invested
- Economic cost of maternal lives saved per pound invested

VfM performance compared to the original VfM proposition in the business case

This annual review reports against the first three indicators compared to the first two reported in the last annual review. Reporting on the last two indicators will be done at the end of the programme due to data availability and the nature of their relationship with cost benefit analysis agenda and the premise that the project will enhance the efficiency of pre-existing spend on MNH.

Good progress has been made on all three indicators. On the first indicator a total of £29,443 was saved from the allocated budget.

All Flight Costs	No of Return Flights	Unit Cost	Total Cost
Budget for October 2013 to September 2014	84	£1508	£126,672
Actual cost for the same period	167	£754	£125,611

Accommodation – African City	No of Days	Unit Cost	Total Cost
Budget for October 2013 to September 2014	768	£178	£136,704
Actual cost for the same period	1,570	£69	£108,322

Extra resources were leveraged during this reporting year. The Sharpened One Plan for RMNHC in Tanzania was supported WHO with a commitment of $150,000 for the roll-out of the plan. In Nigeria the Community Health and Research Initiative project was supported by CHR to the tune of £35,000. CHR collaborated with E4A in Kano and Jigawa States training health workers, training and organising advocacy and knowledge management, supporting accountability mechanisms and developing MNH scorecards. E4A’s influence has led to its approaches and models forming a core part of the new DFID funded MNCH2 programme design and implementation.

QUIC, a low-cost approach to capturing simple data on the state of EmONC at facility level was introduced as a pilot in the sub national areas within which E4A was active. Additional funding from NORAD enabled the programme to expand this to all E4A countries.

While we have used the term ‘leverage’, and that examples stated above are additional resources mobilised into this work, we acknowledge this does not strictly meet the definition of leverage by DFID’s Chief Economist, Stefan Dercon (November 2014) as theoretically these resources would be used for other development work. Nonetheless, these are additional resources for maternal and newborn health.

Against the third indicator, the Data Decision Making (DDM) surveys indicated that in the five of the six countries there was an improvement since baseline in the use of MNH evidence by national and sub-national health managers in their decision-making. The most striking increase was seen in Ghana, where the midline score was 70% against a base line of 50% and in Tanzania it was 60% against a baseline of 58%.

Assessment of whether the programme continues to represent value for money
Overall the programme is providing value for money given the progress made in all the outputs and the above three VFM indicators. The budget cuts have reduced the programme outputs, and there are risks to the ability of the programme achieving its overall effectiveness – which could risk the value for money of this programme. This is being monitoried by the E4A and DFID team.

Quality of financial management

The spend profile for 2014/15 has been as expected. At short notice Options financial management was also able to cope with DFID’s call for a budget reduction totalling £3 over two financial years (2014 to 2016). Without the foundation of good financial management Options would not be able to manage the budget reduction so efficiently.

In addition to receiving Option’s annual audited accounts, they have also provide a quarterly financial management report which incorporates the milestones achieved, payment requested for the previous quarter and an overall reconciliation of payments received against the contract value. A further reconciliation is also available in Options annual report which schedules all the milestone payments received from DFID in the reporting period.

Date of last narrative financial/management report	07/11/2014 (4807906)
Date of last audited annual statement	09/04/2014 (4809973)

E: RISK

Overall risk rating: Medium

We assess this programme to remain at medium risk, however, we recognise that risks have increased this year.

1. Budget cuts have affected the implementation of the programme. Activities have had to be reduced or cut and geographical locations reduced. This has had an impact on the outputs of the programme and will reduce the impact of the programme, particularly in the translation of sub-national approaches to inform national policy.
2. It is possible that sustainability of the programme may be compromised, particularly where the programme has less time to develop mechanisms of continuity and build relationships (in particular in the 3 countries where E4A will close early - Ghana, Tanzania and Sierra Leone).
3. Sierra Leone and Ebola – higher risk of achieving MNH outcomes through E4A because of weakened MNH health systems and government staff dedicated to MNH.

Overview of programme risk

The risks are highlighted in the Options E4A annual report 2014

Outstanding actions from risk assessment

Key risks around political and technical commitment are already partly mitigated by the Global Strategy/CoIA (Commission of Information and accountability) process. However as a result of the budget cuts new risks have been identified in Options 2014 annual report. This will need careful planning and coordination in order to put in an effective mitigating strategy.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe

In terms of timescale the project is still expected to close on it its original end date. However it is important to remember that programme activities have been scaled back and the original headline results have been amended accordingly following the budget reduction.

Performance of partnership (s)

DFID and Options have developed a good working relationship. The budget cuts were managed constructively and professionally not only by Options but also by country directors, consortium partners and technical leads. To top this, no issues have been encountered with the performance of the partnership in the running of the programme.

Asset monitoring and control

DFID does not monitor assets but has been provided with a list of assets purchased with the grant in the early years of the programme. No new assets have been purchased in this reporting period.

G: CONDITIONALITY

Update on partnership principles (if relevant)

Not relevant

H: MONITORING & EVALUATION

Evidence and evaluation

Evaluation

Progress:
  1. DFID competitively tendered for a supplier to conduct the Independent Evaluation. The Independent evaluation Inception Period ended in mid-April 2014. A pragmatic and strong Inception Report was submitted to DFID April 2014, then submitted to SEQAS and received an ‘amber’ rating. SEQAS comments were discussed and Inception Report adapted accordingly. The Inception Report and Evaluation Framework were since adapted due to re-budgeting.
  2. Policy studies ongoing under the management of E4A, with the technical oversight of DFID. Good systems established in 2014 (policy study teams, data collection protocols, country-specific research ethics board passed, and data collection ensued), and good communication/interaction with independent evaluation team.
  3. DFID, E4A and independent evaluation team agreed to change the nature of Sierra Leone involvement in evaluation due to the Ebola crisis.

Issues to consider for 2015:
  1. The Independent Evaluation key activities will be implemented in 2015. Monitoring by the E4A Monitoring and Evaluation Committee (MEAC) required to ensure strong communication with policy studies, and strengthening of overall Evaluation Synthesis Component as discussed and agreed.
  2. The sub-national and national level policy study findings have been useful, and seem to be successfully communicated to E4A country teams to ensure learning. Monitoring by MEAC required for 2015, particularly on national-level policy study in Ghana where initial findings seem wanting on quality (lack of depth and context understanding).

Theory of Change
Modifications to the programme design were required following the last Annual Review (2013). E4A and DFID worked together to conduct a Strategic Review (culminating in June 2014). Further details on the changes in the ToC can be seen in the Strategic Review document. Important to highlight are how the ToC changed by:
- Putting Quality of Care at a central impact level (linking it to how E4A would save maternal and newborn lives), instead of as an outcome indicator.
- Revised the Outcome statement to be more aligned to what E4A actually does on better allocation and use of resources, rather than on being ‘decision-makers acting on evidence’.
- Redesigned the outputs to ensure that MamaYe was being reflected as it was being used, namely: as a central tenant underpinning all activities rather than an end to itself.
- Country asks and sub-asks were realigned to reflect and contribute to the log-frame and the revised theory of change.

Following that, significant programme budget cuts had to be made, and there was another programme redesign (culminating in October 2014). Changes to programmatic budget cuts carry several significant risks to the Theory of Change:
- Sustained political change is more challenging. The programme will end early in 3 countries, leaving less time to work with partner organisations who need to continue the work post-E4A, and less time to support building the capacity of government and other stakeholders to ensure that evidence will continue to be used.
- There may be lower level of sub-national to national impact, one of the key assumptions in the ToC, due to a reduction in geographical coverage and shorter time-frame in 3 countries.
- Establishing sustained advocacy momentum is challenging with decreased resources for capacity building and work in less districts.
E4A is managing these risks through strategically targeting certain groups, and leveraging new funding from the Gates Foundation for certain activities in 3 countries. However, the assumptions behind the ToC may need to be reconsidered at programme completion with these increased levels of risk in place.

Monitoring progress throughout the review period

Direct feedback from stakeholders

The programme (and its evaluation) has formal mechanisms for ensuring feedback from stakeholders is directly fed into the implementation of the programme. However, for the purposes of this review, stakeholders were not directly consulted.

Monitoring activities throughout the review period (field visits, reviews, engagements)

DFID have been highly engaged with the core team from E4A due to the strategic review (March-June 2014), followed by the programmatic changes due to budget cuts (latter half of 2014). E4A have responded with log-frame changes and documented changes responsibly. The revisions have often taken significant time and effort on the part of the E4A country teams, E4A core team, and DFID because of close consultation. However, we recognise that the lengthy and resource-intensive process was useful for all parties, especially for the E4A country teams who have clarity and ownership of the log-frame and revised country asks. Normally, these revisions would have been done during Inception Phase, however having a strategic review during this mid-way point has been useful because there are established country teams in place with good understanding of the country context and programme opportunities as well as challenges. Moreover the strategic review enabled a reflection of changes to the political landscape and a more effective response from E4A to this evolving context. No field visits from DFID were conducted during 2014.

Annual Review process

2014 was an intense and challenging year for E4A, including a strategic review and budget cuts, which necessitated a high level of DFID interaction with the E4A team and changes in Theory of Change, log-frame and country work-plans.

The last annual review was conducted by an external consultant. The E4A Programme Leadership Group agreed this Annual Review would be an internally managed review. The SRO for this programme was seconded to the Ebola team during the latter part of 2014. It was therefore agreed that the 2014 Annual Review would not include any country visits, and instead be informed by the log-frame results (QA-ed by the MEAC) plus by a series of ‘Challenge Meetings’. These were 2 hour virtual meetings with each of the 6 E4A countries and one for the regional team. Jane Miller led each of the seven Challenge Meetings, where the 6 E4A country teams plus regional E4A players did a short presentation followed by a series of questions and discussion. Other DFID participants included representatives from ARD, MEAC, policy team and DFID country advisors.

This approach was excellent value for money and provided the opportunity to review the breadth of the programme – providing opportunities for all E4A staff at all levels to participate – as well as a wide range of DFID advisory input. Very useful discussions and debates were had with all teams. One constraint was the audio quality for a couple of the meetings, but overall was considered successful and worth replicating as a way of reviewing multi-country and regional programmes.