Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Low Carbon Support (LCS) Programme
Programme Value: £ 4.500.000		Review Date: 5- 17 January 2015
Programme Code: 203123	Start Date: / 31 January 2013	End Date: / 18 December 2015

Summary of Programme Performance
Year	2013/2014	2014/2015
Programme Score	A+	A
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

There were senior staff changes in the PKPPIM (Pusat Kebijakan Pembiayaan Perubahan Iklim dan Multilateral/ Center for Policy Financing Climate Change and Multilateral) – the main recipient for support under the programme. These changes in PKPPIM leadership have affected progress as new relationships had to be developed between Low Carbon Strategy LCS consultants and their PKPPIM counterparts. Strong working relationships have now been established. The last review was conducted in January 2014.

Progress against logframe
During 2014 , the project used a revised logframe which was approved in December 2013. At the impact level, the project is seeking to expand and deepen the use of Feed in Tariffs for renewable energy and direct more of the government’s budget towards low carbon development. At the goal level it seeks to encourage the Government of Indonesia to reduce the overall level of energy subsidies. The proposed reduction of energy and fuel subsidies proved to be too challenging at the beginning of 2014, but since then, the newly elected government (Oct 2014) has implemented a substantial cut. The new administration’s decision to cut fuel subsidies in late October soon after the inauguration of the new President faced minor opposition. The impact of the subsidy cut has been lessened by the sharp fall in the oil price in late 2014. In addition the re-allocation of funds from subsidies to health and other social spending has been viewed positively both by the market and nationally. In January 2015, subsidies for petrol were completely abolished.

The LCS project focuses on areas that are most likely to produce actual changes in regulations, demonstrable reallocations of the budget towards supporting low carbon development and fiscal policies that support the Government’s own emissions reduction targets. Considerable progress has been made on developing marking and scoring so that allocations for low carbon can be made and then monitored. GoI now needs to increase the funds it allocates so that the overall level of budget allocation increases in future budgets.

In relation to Pusat Investasi Pemerintah / Indonesia Investment Agency (PIP), the programme has helped it complete a legal/institutional review that was conducted in 2013 and finalised in early 2014 – offering advice on a structure to increase the delivery of low carbon investment through the government budget. It now seems unlikely that PIP and Ministry of Finance (MOF) will approve and implement this significant legal/institutional reform package in PIP within the current time frame of the LCS programme. But it forms a substantial basis upon which future reform can be considered.

Summary of recommendations for the next year

The UK Climate Change Unit (UKCCU) and the Ministry of Finance agreed to continue the LCS project until December 2015, and both parties agreed that the project’s activities from April – December 2015 will focus solely on forestry and land-use issues. A clear workplan for the extension needs to be finalised in the very near future.

Several studies and research projects were conducted in 2014. PKPPIM will have to decide which studies can be further developed as future policies in line with the new Minister of Finance’s priorities. It is advised that PKPPIM need to have priority activities in their 2015 workplan, and have a reliable sense of which ones are viable and which ones will potentially over-burden their workloads and human resources.

Ensure that the communication and outreach is fully implemented and embedded in each piece of work. Help PIP deliver substantial investment into the low carbon projects that the programme has been helping PIP to target for investment.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203123/documents/ / Quest no 3719312
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-203123/documents/ / Quest no 4175355

Outline of the programme

Indonesia is vital to the world's efforts in mitigating the impact of climate change. With estimated greenhouse gas emissions of 1.7Gt (billion tons) in 2005, Indonesia has been recognised as amongst the top ten emitters of CO2e. Its emissions under a “Business as Usual” scenario are projected to grow to 2.95Gt CO2e by 2020. Indonesia has the world’s third largest area of tropical forest (after Brazil and the DR Congo), as well as extensive carbon-rich peat lands.

At the United Nations Conference of the Parties (COP) 15 in Copenhagen in December 2009, the President of the Republic of Indonesia committed to reducing emissions by 26% below business as usual projections by 2020 (or up to 41% with international assistance). Indonesia’s National Action Plan in Reducing GHG Emissions (RAN-GRK 2011) estimates that the 26% target on emission reductions amounts to an annual reduction of 0.754Gt CO2e by 2020 over the government’s business as usual projection 2.9Gt CO2e by 2020.

Emission reductions will only be politically and economically sustained if Indonesia is able to move onto a low carbon growth path that generates employment, growth and poverty reduction. The Government of Indonesia’s current target for economic growth is 6.5% per year for 2012 to 2014. The dual achievement of low carbon growth and emission reduction targets will be a huge challenge. A major part of that challenge is the development of viable alternatives to “business as usual” carbon-intensive investment patterns that can genuinely provide prosperity and employment and are supported by Indonesian decision makers.

There is little doubt that responsibility for overall “climate change” policy in Indonesia is complicated and diffuse. Combating climate change comes with the promise of significant donor funding. This means that there is a good deal of competition for leadership between several agencies in this undefined space, in particular between Indonesia’s planning ministry (BAPPENAS), National Council on Climate Change (DNPI) and the Ministry of Environment and Forestry – as well as provincial and district government who implement policy. The UK is attempting to support GoI coordination on climate change through its on-going programme of support to BAPPENAS.

The situation of the Ministry of Finance is in direct contrast to that of supporting institutions that are working in climate change who are still required to secure mandates and budgets, coordinate and reach compromises on areas of responsibility. Both UKCCU and Fiscal Policy Agency agree that support is needed to:
- develop effective fiscal policies;
- engage in broad consultation with multiple stakeholder groups (the dominant tradition is to develop policies in-house, behind closed doors);
- firmly embed political analysis in strategies to achieve change;
- build wide political support for fiscal policy proposals; and
- develop expertise in communications to steer through policy change.

Ultimately, MoF needs support so that it can build its capacity beyond technical analysis towards a comprehensive approach to enable it to build support and constituencies that can help push good fiscal policy proposals through Parliament.

1. The Low Carbon Support to the Ministry of Finance Phase 2 is a two year project prior support to the Ministry of Finance which phase 1 has been successfully completed. This support has developed relationships and built trust between the UK and Indonesia. Past results and the strong relationship with the Fiscal Policy Agency and Indonesia Investment Agency under Ministry of Finance have been the catalyst for the request for broader and deeper assistance on low carbon development.
2. The Low Carbon Support to Ministry of Finance Phase 2 will directly contribute to the low carbon development objectives in HMG’s current Country Business Plan for Indonesia and forthcoming operational plan (2012/13 to 2014/15). It forms part of the UK’s overall commitment to support low carbon development under the International Climate Fund (2011-2015).
3. By the end of the project, we would expect that with UKCCU support energy subsidies will be at least 20% lower than 2012 levels and fundamental reform feed in tariffs for renewable energy will have been implemented. Both these measures would transform the economics of renewable energy in Indonesia and are critical for Indonesia if it is to hit its policy of increasing renewables from 3% of installed capacity to 17% by 2025.
4. The project memorandum with the Government of Indonesia was signed at the end of November 2012. The approval from Secretary of State on the project implementation was given in January 2013. The contract with the Oxford Policy Management Limited (OPML) as the project contractor was issued on the 30th of January 2013.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome of the intervention will be a supportive environment for low carbon investment established in Indonesia. This will be achieved by:
- MoF building stronger external networks and sharing evidence and building consensus on future policies.
- New initiatives launched to support low carbon development, including at the regional level.
- A Government White Paper on Low Carbon Development launched and associated regulations put in place.
- A greater emphasis upon low carbon development within the Indonesia Investment Agency that will leverage private and international finance of at least $300m during the life of this programme.
- MoF having built sufficient political and stakeholder support to enable it to reduce energy and fuel subsidies (by at least 20% over 2012 levels) and fundamentally reform feed in tariffs for renewable energy. Both these measures would transform the economics of renewable energy in Indonesia and are critical for Indonesia if it is to hit its policy of increasing renewables from 3% of installed capacity to 17% by 2025.

For the outcome indicator 1 - which measures on new low carbon incentives and regulations introduced and implemented. Strategic papers in all 3 areas (clean energy, energy efficiency, and green planning/ budgeting) have been completed. All are still at varying phases of gaining PKPPIM / MOF formal acceptance with varying impacts to date on Government / MOF regulations or budget allocations:
- Green Planning and Budgeting Strategy Paper;
- Green Planning and Budgeting inputs to 5 year plan 2015 – 2019 and to Nota Keuangan for 2015 Budget;
- Coherent Fiscal Policy Framework for Renewable Energy;
- Finalization of Coherent Fiscal Policy Framework for Energy Efficiency;
- Development of a Biomass Waste to Energy Financing Scheme;
- Fiscal Policy Instruments for Addressing Wastes in the Oil and Gas Industries;
- Rapid Assessment of Scope for Scaling up the Bio-Diesel Industry;
- Assessment of Viability of Converting Forest Wastes to Bio-Methanol;
- Design of a Financing Scheme to promote Energy Efficiency Investments;
- Fiscal Policy Framework for Land Based / Forestry Sectors;
- Standard Operating Procedures for Geothermal Project Assessment;
- Standard Operation Procedures for Hydro Project Assessment;
- Draft MOF Regulations have been prepared for: (i) Energy Efficiency Financing Facility; and (ii) Biomass waste to energy financing scheme, and are waiting to be formally approved;
- A number of the papers are of a broad strategic nature, e.g. Green Planning and Budgetary Strategy; Coherent Fiscal Policy Framework for Renewable Energy; and (iii) Coherent Fiscal Policy Framework for Energy Efficiency. These will need to be considered over an extended time frame through a number of policy instruments rather than through single regulations; and
- The PIP SOPs for geothermal and hydro possess a form of regulatory status within PIP / MOF.

A challenge for MOF will be translating the policy studies into implementation. Too few of the recommendations for policy change developed under the programme have resulted in policy change- a key task for the project in its last year will be to focus on implementation.

Outcome indicator 2 measures how much funding PIP has allocated to low carbon investment. Until December 2015, PIP has significant resources on hand for funding clean energy / low carbon investments, potentially exceeding US$ 450 million, not to mention the Geothermal Financing Facility and other free balance sheet funds available to PIP. PIP is currently in the advanced stages of processing around seven highly prospective investment financing applications, in the sectors of geothermal, energy efficiency, hydro and bio-mass. No formal approvals / disbursements were achieved in the 2014 calendar year but significant approvals / disbursements are expected in 2015 and 2016 based on the current pipeline being worked on.

PIP funds available have already reached targeted levels from: i) internal free balance sheet resources available to PIP; ii) the geothermal fund. Furthermore an energy efficiency financing scheme is under consideration for 2015.

In 2014, PIP reviewed several loan proposals on renewable energy and green projects from developers. The LCS project has supported PIP in appraising 4 geothermal proposals, 2 hydro power proposals and 1 solar power proposal. On the geothermal proposals, The LCS is supporting the selection process and contracting a Loan Appraisal Firm to review the proposals, a legal firm to provide training including assessment of developers, audited financial reports and company structure as part of a preliminary review process and providing Geothermal in-house consultants.

The hydropower proposal has passed the preliminary process and is currently in the technical due diligence stage. LCS is providing advisory support in creative financing scheme (Novation) assessment for developers to pass PIP's preliminary process. LCS is selecting and contracting a technical expert to provide training for PIP using the developers as a model case to do the technical due diligence.

Overall output score and description

The overall output score is A given that all outputs are achieved.

Key lessons

During 2014, the LCS programme has produced a number of studies and research. Yet much of this work has not resulted in policy changes. Specific key lessons for the programme:

- To focus on research that is of very high priority and has some prospect of resulting in real policy change;
- Coordination with other ministries needs to be given higher priority – this has started to happen under the new Head of PKPPIM, but more needs to be done to include line ministries when polices are being developed to ensure technical consistency and ownership;
- There are limitations to the volume of research and studies that can be reviewed by officials. For the remainder of the programme limited new research should be undertaken – instead the focus should be on implementation of existing studies and only a very small number of new high priority studies with a strong prospect of leading to policy implementation;
- The programme should support PIP to develop applicable regulations that enable it to take risks as otherwise it will be quite difficult to start any project investment with the current limitations on risk appetite;
- Capacity building for PKPPIM and PIP has been in line with the requirement and strengthened both agencies’ capabilities in the climate change sector. There is now no need to have further capacity building activity especially for energy sector over the no-cost extension period – or for any generic climate change training.

Key actions

With the large number of studies and research, the policy reforms require extensive work at senior levels including closer collaboration with line ministries and presentation at the ministerial level. PKPPIM can use the opportunity of preparing a white paper on fiscal policies to utilise the many recommendations and policies developed under the LCS programme to the new minister in Finance.

With support from LCS, PIP needs to re-engage with the relevant agencies within MoF and with other line ministries to seek to review and revise the PMK No 03/2012 on the geothermal fund facility. The points of revision in the draft are:
- Remove the maximum amount of US$ 30 million to be replaced with maximum loan, should be determined based on per project assessment
- To include the work plan as part of the financial assessment (not just the financial capacity), and that PIP can disburse the financing in accordance with the work plan
- Additional mechanism for repayment of loan in 2 cases: if technically in the preliminary stage it was discovered that the project will not yield good output, or if the project is successful
- Clarifying the repayment term that was previously referred to as "financial closing date" to when the borrower draws down the first loan (not to be interpreted as when the borrower get commitment from other lender/investor for the exploitation phase)

The programme has been extended for the period of April-December 2015. The focus of programme activities will be:
- Finalisation of the current studies and research under PKPPIM
- Finalisation of the current geothermal review on the proposal investment under PIP
- Studies and research on the forestry and land based sectors
- Capacity building on the forestry and land based sector
- Coordination and partnership amongst stakeholders and GoI on the forestry and land based sector

Has the logframe been updated since the last review?

The logframe was updated during the last annual review. It has been agreed that the technical working committee will update the logframe once the administration for extended the project is completed (mid February 2015).

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	High quality technical assistance to the Ministry of Finance
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Evidence papers presented and high level policy seminars conducted	Produced at least 8 policy papers with recommendations to be considered by Minister of Finance	14 policy papers been commissioned, 9 strategic papers have been completed and 2 studies and 2 SOP continue into ministerial regulation
Staff trained through UKCCU support	Deliver at least 6 low carbon training events as part of capacity building initiative for PKPPIM including participants from other parts of MoF	5 overseas training events as part of capacity building initiative were conducted under PKPPIM and more than 10 training events in-country as part of the studies and research

Key Points

Output 1 is aimed to improve the technical basis on which policies are formulated and generate policy recommendations that result in real policy change and improve the skills and knowledge of staff who are formulating and implementing the policies

Within PKPPIM there are 14 policy papers that have been commissioned:
- Green Planning and Budgeting Strategy Paper;
- Coherent Fiscal Policy Framework for Renewable Energies;
- Coherent Fiscal Policy Framework for Energy Efficiency;
- Fiscal Policy Framework for Developing Upstream and Downstream Activities for Enhanced Utilisation of Natural Gas;
- Development of a Biomass Waste to Energy Financing Scheme;
- Fiscal Policy Instruments for Addressing Wastes in the Oil and Gas Industries;
- Rapid Assessment of Scope for Scaling up the Bio-Diesel Industry;
- Assessment of Viability of Converting Forest Wastes to Bio-Methanol;
- Design of a Financing Scheme to promote Energy Efficiency Investments;
- Fiscal Review of Carbon Capture and Storage in Oil and Gas;
- Economic Implications of Removal of Fuel Subsidies in Jabodetabek Region;
- Fiscal Policy Framework for Land Based / Forestry Sectors;
- Fiscal Policy Instruments for Addressing Motor Vehicle Emissions; and
- Fiscal Policy Arrangements to Enhanced Commuter Rail Services in Jabodetabek Region.

Within PKPPIM there are 9 policy papers that have been completed between late 2013 and January 2015:
- Green Planning and Budgeting Strategy Paper;
- Coherent Fiscal Policy Framework for Renewable Energies;
- Coherent Fiscal Policy Framework for Energy Efficiency;
- Development of a Biomass Waste to Energy Financing Scheme;
- Fiscal Policy Instruments for Addressing Wastes in the Oil and Gas Industries;
- Rapid Assessment of Scope for Scaling up the Bio-Diesel Industry;
- Assessment of Viability of Converting Forest Wastes to Bio-Methanol;
- Design of a Financing Scheme to promote Energy Efficiency Investments; and
- Fiscal Policy Framework for Land Based / Forestry Sectors;

There are several studies/policy papers which have been translated into a ministerial regulation:
- Draft MOF Regulations have been prepared for: (i) Energy Efficiency Financing Facility; and (ii) Biomass waste to energy financing scheme, and are waiting to be formally approved; and
- A number of the papers are of a broad strategic nature, e.g. Green Planning and Budgetary Strategy; Coherent Fiscal Policy Framework for Renewable Energy; and (iii) Coherent Fiscal Policy Framework for Energy Efficiency. These will need to be considered over an extended time frame through a number of policy instruments rather than through single regulations; and
- The PIP SOPs for geothermal and hydro possess a form of regulatory status within PIP / MOF.

Capacity building is not limited to formal training events but includes job support from the longer term LCS team; close collaboration with short term consultants in completion of particular assignments; and the convening of regular policy related seminars/ Focus Group Discussion (FGD)s etc. in line with the work plan. Around 18 policy related events such as workshops / FGDs (all of which contained a capacity building component) were held during 2014 with total attendance of 536 participants, where significant proportion of the participants came from external stakeholders of PKPPIM and PIP.

As part of the Green Planning budgeting activities, a series of low carbon, green planning and budgeting and sustainable development workshops have been conducted (7 capacity building workshops between December 2013-mid 2014)

For 2015, two further courses for PKPPIM have been planned but subject to final negotiations and contracting, namely: (a) course on economic modelling to be convened by University of Indonesia (approximately 25 participants mainly from PKPPIM and other parts of MOF); and (b) a course in Economic Techniques for Climate Change Analysis which is under discussion.

PKPPIM Capacity Building Activities 2014

Summary of responses to issues raised in previous annual reviews (where relevant)

Ensuring timely and high quality advice and support provided by the LCS consultants was raised in the previous annual reviews. As follow up the LCS consultant’s services are pro-actively discussed with the MOF and constructive feedback is requested from MOF.

Recommendations

The project under output 1 has met expectations and is on track, however, given the number of studies/research conducted, there are several studies/research that need further review and final approval from PKPPIM before they can be published or socialised amongst stakeholders. Follow up and further attention is needed to ensure that all studies and research are summarised in order to be able to produce a white paper as a resource for the Minister of Finance in reviewing RE and climate change issues.

MOF and the LCS team need to focus on finalising and socialising the remaining work. An exercise on reviewing all recent work had been undertaken and is needed to identify policy reform areas. In order to gather as many inputs to the report as possible, Director Generals in Ministry of Finance needed to be consulted on their priorities for reform.

The Green Planning Budgeting Report is in the final stage of approval (a foreword from the Minister of Finance is being finalised). The target date for completion and release of the report is aimed for end of January 2015. It is considered that a small event sometime in mid-February 2015 will be used for release and promotion of the strategy.

24 staff from the Ministry of Finance, Ministry of Energy and Ministry of Industry and PIP have been facilitated to attend external training courses, relevant conferences and study trips. There is a necessity for clear action plans after each study trip/research completed on how the capacity building is in line with priority work and workplan of PKPPIM to be discussed at the beginning of the year. It is also noted that any capacity building programme should be in line with log-frame and project purposes.

Output Title	Wider stakeholder input to MoF low carbon policy making.
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Numbers of outreach events	Undertaken at least 4 formal outreach events	41 outreach activities were conducted including : / 32 workshops /FGDs / small policy publications / 5 promotions linked to studies / publications / 2 international study tours and / 2 communications training events / The 41 outreach activities closely related to events / activities undertaken to support the main output 1 and 3 supporting PKPPIM and PIP respectively
Numbers of publications by PKPPIM and PIP	Issued at least 4 low carbon development publications	9 publications issued by PKPPIM.

Key Points

Under output 2, the project aims to encourage and support the Ministry of Finance to consult with wider stakeholders to ensure the policies gain support and insight from other key sources (wider government, academia, private sector, parliament , NGOs, etc).

During 2014, within PKPPIM 9 policy papers were completed and are ready for publication[1]:
[1] Note those marked with (*) are essentially ready for publication but await final PKPPIM approval / clearance to publish
- Green Planning and Budgeting Strategy Paper*;
- Coherent Fiscal Policy Framework for Renewable Energies*;
- Coherent Fiscal Policy Framework for Energy Efficiency*;
- Development of a Biomass Waste to Energy Financing Scheme;
- Fiscal Policy Instruments for Addressing Wastes in the Oil and Gas Industries*;
- Rapid Assessment of Scope for Scaling up the Bio-Diesel Industry;
- Assessment of Viability of Converting Forest Wastes to Bio-Methanol*;
- Design of a Financing Scheme to Promote Energy Efficiency Investments*; and
- Fiscal Policy Framework for Land Based / Forestry Sectors*;

Papers completed for PIP were of technical and internal / confidential nature and not intended for publication. The current Edelman communications contract in PIP is producing PIP promotional materials for their website and for external promotional campaigns / publication. The Edelman contract which commenced work in October 2014 has a strong emphasis on enhancing external communications and marketing of PIP.

For most PKPPIM reports distribution has remained limited to a relatively narrow list of close stakeholders, many are awaiting PKPPIM clearance of particular reports for broader circulation. In most cases circulation has included:
- BKF in MOF;
- DG Budgets in MOF;
- DG Fiscal Balance in MOF;
- DG Treasury in MOF;
- Ministry of Energy and Mineral Resources;
- Ministry of Environment;
- Ministry of Forests;
- Ministry of Industry;
- Ministry of Agriculture;
- Ministry of Transport;
- Bappenas;
- Selected Development Partners;
- Selected Private Sector Developers; and
- Selected Industry Associations.

In a small number of cases, reports have also been placed on the BKF website following earlier PKPPIM approval to do so: (i) Rapid Assessment of the Bio-Diesel Industry; and (ii) Bio-mass Waste to Energy Financing Scheme. Furthermore a summary of the Green Planning and Budgeting Paper was successfully presented to a large audience at a side event at the December 2014 UN Cliamte Change Convention, COP meeting in Peru.

A wider plan for broader circulation of reports has been prepared by the LCS Communications Consultant and will be implemented on a case by case basis as PKPPIM approves the release of particular reports.

Summary of responses to issues raised in previous annual reviews (where relevant)

The communication and outreach was initially designed by the consortium’s partners in the first few months of the project. During the year 1, the communication and outreach have been embedded in relevant activities rather than being driven by an over-arching communication strategy. To ensure focus and structure of the programme, the steering committee agreed to have a communication strategy which not only focuses on the outreach associated with technical policy but also on capacity building for PKPPIM and PIP in communications.

As an action to the previous annual review, a communication specialist was hired with the main focus on communication and outreach activity.

Recommendations

The project needs to fully use the communication specialist sitting in Ministry of Finance. It is noted that it required some time to get the communication specialist in place and even more time is needed to really use the specialist expertise on the board.

The communications component continues to be slow in implementation but it remains important to spread the results of different studies etc. The work done will not be of optimum benefit if the results are not spread widely, including initially in MOF – including Fiscal Policy Agency, DG Budgets; DG Fiscal Balance; and DG Treasury. It is recognized that there are constraints on communications work pending the completion and clearance of particular pieces of work.

The Donor Partner (DP) coordination meeting which was conducted twice in 2013 was not conducted at all at 2014. However, in September 2014 a consultation meeting was organized between LCS consultants and AusAID, GIZ, UNDP, GGGI, World Bank and CPI. Further coordination meeting with DPs is required to avoid overlapping on the support as well as a tool for sharing any project outputs and success story.

Output Title	Low carbon investment objectives fully incorporated into the operations of the Indonesia Investment Authority (PIP)
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	50%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Standard Operating Procedures (SOP) established for low carbon development	Elaborated and finalized the SOP for one additional low carbon sector (e.g. energy efficiency, biomass)	3 SOP are elaborated and under finalisation. / SOP for geothermal project assessment (under finalisation January 2015) / SOP for Hydro project assessment (under finalisation January 2015) / Generic Operating Procedure for processing investment applications (due March 2015) / Support to preparation of a Bio-mass SOP manual (led by USAID)
Implementation of PIP’s institutional reform and capacity strengthening	Capacity strengthened through 6 training events	7 trainings / events both in Indonesia and overseas were conducted during 2014

Key Points

Under the output 3, the project aims to develop SOP for PIP to support low carbon investment (renewable energy and energy efficiency). It is also agreed that the project will support PIP’s institutional reform and capacity building for PIP staff with particular emphasis upon being able to finance renewable energy and energy efficiency investments.

Direct LCS support for Manuals SOPs / developing organisational capacities is still likely to be limited to: (i) revisions to the hydro manual (with work having commenced in October 2014 under Entec who will also test the revised manual in relation to a new project which is currently undergoing appraisal) and (ii) revisions to the geothermal manual (work contracted and well underway as of 30 September 2014).

Similar with PKPPIM, the capacity building pursued by LCS for PIP is not limited to the formal training events but included the job support from the longer term LCS team; on-going annual planning support; close collaboration with short term consultant and in-house training / event for PIP was participated by PIP staff and other line ministries.

PIP capacity development and institutional strengthening strategy to some extent awaits decisions on institutional reform before more holistic approaches to capacity building / institutional strengthening can be finalised. A significant number of LCS supported ad hoc training events have been run in 2014 in house, including: (i) energy efficiency financial model; (ii) cash flow projections; and (iii) Clean energy, United Kingdom study tours. Implementation of particular training and staff development events occurred between May 2014 and January 2015. Some 8 specific training workshops have now been contracted around the following key subject themes: (i) Communications; (ii) Negotiations; (iii) Legal Skills; (iv) Business Development; and (v) Risk Assessment and Management. The first course was held in May with the remainder spread between May 2014 and early 2015. Three of the 8 courses were completed in the June and September 2014 quarters with five courses remaining for completion at 30 September 2014 (one in October; one in November, with the remaining three in December / early 2015).

In September 2014, LCS supported a comparative study in the United Kingdom for PIP and MOF which focused on institutions financing clean investment, including: (i) Climate Bonds Initiative; (ii) European Development Bank; (iii) Green Investment Bank; (iv) Department of Business Innovation and Skills; (v) Bank of America / Merrill Lynch; (vi) Climate Market and Investment Association; (vii) Department of Energy and Climate Change; (viii) WRAP; and (ix) Salford City Council. A benchmarking review report was concluded at the end of the visit with the visit assessed as very valuable by the PIP management. In addition a benchmarking review has been undertaken of procedures of other investment institutions in Indonesia.

Training / event for PIP was participated by PIP staff and other line ministries.

As detailed above seven (7) specific capacity building training events were convened for PIP in the reporting period covering some 137 participants.

PIP has significant resources on hand for funding clean energy / low carbon investments, potentially in excess of US$ 450 million, bearing in mind the Geothermal Financing Facility and other free balance sheet funds available to PIP. PIP is currently in advanced stages of processing around ten highly prospective investment financing applications, including several each in the sectors of geothermal, energy efficiency, hydro; and bio-mass. No formal approvals / disbursements were achieved in the 2014 calendar year but significant approvals / disbursements are expected in 2015 and 2016 based on the current pipeline being worked on.

One hydro power project located in Bengkulu province, is at approval stage. It has passed PIP's preliminary process. PIP is currently doing the technical due diligence and already presented the project to the Management. LCS Involvement: LCS is providing advisory support in creative financing scheme (Novation) assessment in order to pass PIP's preliminary process. LCS is selecting and contracting a technical expert to provide training for PIP using developer as model case to do the technical due diligence.

There are 6 projects pipeline which are now under discussion and supported by LCS project.
Geothermal project
Location: Banten, West Java
Status: Passed PIP's preliminary review and currently being appraised by Loan Appraisal Firm
LCS Involvement: LCS Advisory support the promotor team in conducting meetings with the developer. LCS is providing Geothermal in-house consultant and supporting the selection process and contracting Loan Appraisal Firm to review the proposal in detail.
Geothermal project
Location: Ijen, Central Java
Status: Processed by PIP for the preliminary review
LCS Involvement: LCS Advisory support the promotor team in conducting meetings with the client to convince them to apply to PIP. LCS is providing Geothermal in-house consultant, supporting the contracting of legal firm to provide training including assessment of developer audited financial report and company structure as part of preliminary review process.
Geothermal project
Location: Bandung, West Java
Status: Processed by PIP for the preliminary review
LCS Involvement: LCS Advisory support the promotor team in conducting meetings with the ?, providing Geothermal in-house consultant and supporting the contracting of legal firm to provide training including assessment of parental company structure and its eligibility to pass PIP's preliminary process.
Geothermal project
Location: Tangerang, West Java
Status: Processed by PIP for the preliminary review
LCS Involvement: LCS Advisory support the promotor team in conducting meetings and providing Geothermal in-house consultant.
Hydro Power project
Location: Sukabumi, West Java
Status: has passed PIP's preliminary process. PIP is currently doing the technical due diligence and already presented the project to the Management.
LCS Involvement: LCS is providing advisory support in convincing developer to restructure their project so that it can pass PIP's preliminary process. LCS is selecting and contracting a technical expert to provide training for PIP using developer as model case to do the technical due diligence.
Solar PV project
Location: Bandung, West Java
Status: developer is currently in PIP's preliminary process
LCS Involvement: LCS is providing advisory support on documents needed and how to do initial review for Solar PV Project (because PIP does not have the manual yet). LCS also provides advisory support in potential co-financing with the French development Bank AFD.

Summary of responses to issues raised in previous annual reviews (where relevant)

The LCS project has invested considerable efforts and expertise to work with PIP on a first SOP for mini-hydro. An initial version of the SOP has been extensively tested on a real project and it is now in the process of being revised for wider applicability. It is expected that the two mini hydro power projects would, after testing with the SOPs, be ready for financing. This is still not the case and PIP needs to consider further whether this particular project is suitable to be the first mini-hydro project supported by PIP.

Support on institutional reform of PIP focused on low carbon / green financing areas. Further follow up on legal clarification/opinion in relation to: i) “no loss” provisions in the PIP regulatory framework including issues of mandatory versus non-directed investments; and (ii) the legal scope for PIP to undertake equity investments. Further work, mainly of a legal nature, may still be requested later on once PIP and MOF accept some of: (i) regulatory clarifications under existing status – no losses, mandatory provisions, SOPs etc.; and (ii) intermediate term formation of a subsidiary PT Company to give focus to green financing initiatives; and (iii) longer term restructuring to a full State Owned Enterprise (PT Persero status). It was also expected that a decision on future PIP would be finalised in 2014 especially related to ‘no loss’ provisions in the PIP regulatory framework and the legal scope for PIP to undertake equity investment. But due to the election and changing new government this issue was pending and will be discussed in 2015.

Recommendations

Final design of the Revolving Fund (now referred to as a Financing Facility) still awaits MOF final decision making and approval, and preparation of MOF Regulations that set out the rules of operations. LCS has provided technical support to PKPPIM in the preparation of the MOF Regulations. A clear step on the energy efficiency financing facility needs to be presented to the minister in order for PIP to start designing the nature of the scheme.

In order to secure the geothermal investment, a discussion needs to be started with relevant agency/unit within MOF and other line ministries in relation to the revision of PMK no 03/2012 on geothermal fund facility, management and the use of the funds as with the current PMK.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers to the programme are the technical consultancy inputs and support to Ministry of Finance through long-term and short-term consultancy appointments.

The total cost spent during 2014 is as follows:
Core budget	Special fund
Fees - Long-term expenditure	£564.675.2	£248,296
Fees – Short-term expenditure	£408,455	£ 33,375
Reimbursable cost	£ 69,357.6	£163,583.1
Total	£1,487,741.8

The project has succeeded in providing a large number of highly qualified consultants. All of the work results have been regarded as high quality, with the exception of one deliverable: reviewing existing solar PV fiscal incentives and developing proposals on fiscal reforms to support solar. The objective of the solar fiscal incentives review is to develop appropriate fiscal reforms and to feed these into the broader renewable energy strategy. Completion was initially due by late November 2013 but finalisation of the study was long delayed awaiting further development of the auction based system for solar feed in tariffs (first auctions were held in December 2013 but were not well supported and subsequent auctions have been problematic). An initial outreach focus group discussion event was held in October 2013 allowing consultation with key stakeholders on preliminary study findings and issues with a final focus group discussion held in July 2014. Following the final FGD and despite numerous follow ups and warnings the consultant was unable to prepare a draft final report in a timely fashion and as a result the contract was cancelled by late in the September quarter.

The project has been successful in securing Indonesian expertise. This is important as the Indonesian consultants have better knowledge of the current law and fiscal policy and have a strong network within the line ministries.

The UK government agreed to continue support in Indonesia on the forestry and land base sector. The discussion on the no cost extension until December 2015 with specific activities on forestry and land based sector was finally agreed in November 2014.

VfM performance compared to the original VfM proposition in the business case

According to the projections as of end of December 2014, the project is expected to meet forecast.

Any work that has to be delivered outside the OPML–led consortium is always subject to competitive tender with at least 3 bidders and a transparent discussion and negotiation on the fee rates.

In December 2014, OPML requested to raise the limit for getting 3 quotes. Currently OPML should get three quotes for purchases over £100 and they would like to raise the limit to £200. However due to the success of on-going procedure and the smaller activities during extension, UKCCU rejected the request and kept the £100 as a minimum threshold.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money by having at least three quotations and competitive tender for any procurement / purchases above £100. The limit was agreed during the Steering Committee meeting as part of programme governance and accountability. Records for the tenders and evaluations are kept by OPML local and UK office.

The programme was audited for fiscal year 8 February 2013 to 31 March 2014 by Paul Hadiwinata audit firm, and the final audit statement result was unqualified. It is planned to have another financial audit review in 2015.

In 2014, there was a requirement to shift resources from the component covering the special fund to the short term consultancy budget to allow consultancy related expenditures on outreach and communication to be properly recorded under the special fund output.

Quality of financial management

A financial report is submitted on a quarterly basis to UKCCU. In line with government regulation, MoF with support from OPML also submitted a regular BAST (financial report) to the Treasury Division at MoF. The BAST is signed by PKPPIM as the lead partner and Head of UKCCU.

Date of last narrative financial report	1-31 December 2014
Date of last audited annual statement	8 February 2013 to 31 March 2014

E: RISK (½ page)

Overall risk rating: Low/Medium/High
The overall risk rating assigned to Business Case was Medium and this has not changed
Output 1: Medium
Output 2: Medium
Output 3: Medium
Overview of programme risk
Risk	Mitigation measures
Risk of no influence, all the capacity building and advice provided is neither used nor has any impact on policy.	The Ministry of Finance has requested this support from the UK as a fellow G20 country. / The governance arrangements specifically allow MoF to determine the detailed work programmes of the technical assistance and to respond directly to the requirements of Ministers and senior leaders in the Ministry of Finance. / The UKCCU will be a member of the Steering Committee and will be in regular contact with the Fiscal Policy Office. If advice and support provided are judged to be ineffective then measures will be taken to review design and or scale-down support. / Evidence from existing support to MoF suggests that provided advice is delivered in accordance with MoF requirements, and will be effective in supporting reform and policy change.
Risk of corruption	The UKCCU conducted a fraud and corruption session at MoF inviting the consultants and shared DFID fraud and corruption policies. The annual audit been agreed with the service provider. The first project audit report underlines the unqualified audit opinion.
Risk of underspend	There is considerable risk of underspending in Indonesia. Programmes and projects are often delayed. In designing this intervention, the UKCCU has ensured that there will be adequate management and administrative capacity in the programme so that its activities can be delivered on time and to budget.

Outstanding actions from risk assessment

N/A
F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme was delivered against the planned timeframe, however, it required a time extension in order to fully complete the ongoing study and research both at PKPPIM and PIP, start the transition on forestry and land base and allocate programme funds while maintaining programme quality and coordination. It is currently anticipated that programme funds will be expended in December 2015.

Performance of partnership (s)

Partnership with Ministry of Finance started in 2010 with Phase 1 and continued with Phase 2. There are a number of ways in which UKCCU regularly monitors the project: through attending the project workshops and events, technical working committee meetings, spot check review and also regular Steering Committee meetings.

Asset monitoring and control

LCS maintains the asset register list both for PKPPIM and PIP. The latest asset register list is retained at the LCS office.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

The underpinning logic for the theory of change of the project still remains the same:

Starting point

- Low carbon development is not happening quickly enough in Indonesia because the policies that would encourage this to happen are either not in place or if they are in place, they are weak and do not create strong enough incentives.
- In the climate change arena, Indonesia, not unlike a lot of countries, has confused and conflicting mandates for different institutions.[1]
- The Ministry of Finance is by far and away the most important ministry in setting the framework and incentives for low carbon development which other actors then respond to.
- But the Ministry of Finance has limited capacity and resources to push through policy reforms. In particular it needs to be more connected with outside stakeholders, it needs to use more evidence and to build support for its policies across other ministries and with parliament.

Change needed

- More evidence, more outreach, more input from external experts would enable the Ministry of Finance to identify and develop economic and fiscal strategies to reduce emissions and promote a more efficient use of Indonesia’s resources for sustainable development.
- For any policy change to be successful it needs to be properly researched and have a solid evidence base.
- Wider stakeholders (other ministries, think-tanks, politicians) need to be involved in policy formulation from the start, and for this to happen the Ministry of Finance needs to open-up its policy making process more than it has traditionally done.
- Policy needs to be disseminated properly to other ministries and agencies, it needs champions and supporters outside government.
- Policy, especially when it is in very sensitive areas, needs to have very strong ministry ownership and or involvement.
- Communication needs to be improved so that wide support can be gained.

However, the context in which investment decisions are being made have changed. The fluctuation of the currency and a worsening macro-economic environment have all increased risk levels for investment in Indonesia, particularly for foreign investors. These conditions have also increased the cost of investment for the Government of Indonesia and domestic investors, particularly when foreign currency based loan and imported materials are used.

Monitoring progress throughout the review period

OPML delivers quarterly programme and financial reports to UKCCU. In addition, the technical working committee meets every month and the Steering Committee meeting is conducted on a quarterly basis.

Annual Review process

The review was performed by Suriany Ida from UKCCU through review of project documentation, all project partners plus a number of external stakeholders including Bapak Made (DJ State Budget), Bapak Yono Reksoprodjo (Kadin – Chamber of Commerce), Bapak Dadan Kusdiana (Director of Bio-energy ESDM), Bapak Dwi Herteddy (Ministry of Agriculture), questionnaire discussion with OPML team, and discussion with PKPPIM and PIP which was conducted from 5-15 January 2015.