## A1 Goal, Purpose, Risk
Annual Review
ARIES Project Code | 201551
ARIES Project Description
A1: Goal, Purpose, Risk
Goal
Goal statement | Achievement of MDGs 2 and 3 - universal primary education, and gender parity in primary and secondary schools
Indicator 1 | Net & Gross Enrolment Ratios (NER and GER) in primary education (DFID Standard Indicator, MDG 2 Indicator 6, and WB core indicator)
Milestone for this review (if any) | 83% NER, 114% GER (in 2010)
What progress has been made in the period covered by this review? | NER up from 79% in 2008 to 83% in 2009 (from annual Welfare Monitoring Surveys); but 2010 WMS not yet available. GER static at 115% in 2009 and in 2010 (from EMIS reports). The Education Sector Performance Report 2010 suggests that more girls are starting school at the right age. This bodes well for efforts to avoid girls reaching puberty in primary education when many tend to absent themselves from school or drop out altogether. Increase in total enrolment from 3.67m in 2009 to 3.87m in 2010 (200,000 more children in school). Malawi was substantially below the SACMEQ average for both reading and mathematics in 2007(as in 2000) although 2007 scores showed a slight improvement on 2000, especially in mathematics )
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | Ratio of boys to girls in primary/secondary education
Milestone for this review (if any) | 100% Primary, 80% Secondary (in 2010)
What progress has been made in the period covered by this review? | Primary target achieved: 101% (1,942,924 girls, 1,925,719 boys). Secondary almost achieved: 79% (EMIS 2010)
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3
Milestone for this review (if any)
What progress has been made in the period covered by this review?
What evidence is there of progress made in the period covered by this review towards the Goal-level Target(s)? | Overall, more girls in primary school than boys. Near equal number of girls to boys in the first seven years of primary school. 38% survived to Std 8; 62% (55,421girls) pass the Primary School Leaving Certificate Examination (PSLCE) and 56% progress to secondary school (EMIS) compared to 40% in previous year. Over 1200 Mother groups to date established and attached to schools to provide support and counselling to adolescent girls and to promote girls' education in their communities. Over 4,000 girls received bursaries for secondary school (4% coverage). Construction of 7 girls’ hostels in ‘day’ secondary schools is continuing.
Goal Recommendation 1 | With NER targets achieved, important to start focussing more on learning assessment and achievement, and on stronger measures to accelerate transition to secondary school, especially for girls.
Goal Action Point 1 | DFID working with other DPs to support the MoEST to develop a credible system for setting and measuring literacy and numeracy standards, at least for Standards 1 to 4, and for extending gender parity up to standard 8 and into secondary school.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Goal Recommendation 2
Goal Recommendation 3
Goal Action Point 2
Goal Action Point 3
Purpose
Project Purpose | The Government of Malawi and Development Partners effectively and efficiently implement the ESIP
Indicator 1 | % of GoM discretionary recurrent budget allocated to education
Milestone for this review (if any) | 20%
What progress has been made in the period covered by this review? | Achieved. Government of Malawi met 2010/11 Budget commitments, 21% (excluding external grants) of the recurrent budget was allocated to education. DFID disbursed first £7m instalment in July 2010, and £4.67m of 2nd instalment (out of £7m) in line with progress made on 6 out of 9 key reforms specified in the ESIP. Disbursements from other JFA partners are: UNICEF $250,000 and Germany €5.5 mn. With a Head of Procurement appointed (a condition for the World Bank's disbursement), WB are now able to process funding requests for FTI and IDA funds. Education Sector Performance Report produced for the first time this year prior to the Joint Sector Review (JSR) and spelt out all the available evidence on various agreed monitoring indicators.
If Indicator 2 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 2 | % of the education budget devoted to primary education
Milestone for this review (if any) | 50% (in 2010/11)
What progress has been made in the period covered by this review? | Achieved. 56% of education budget allocated to primary. Supplementary budget of MK2.2bn approved by parliament, Feb 2011; the bulk of this will go to primary school expenditures such as classroom construction, School Improvement Grants (SIGs) and construction of Phalombe TTC.
If Indicator 3 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 3 | % of funding to the recurrent education budget released by MoF to MoEST within year
Milestone for this review (if any) | 80%
What progress has been made in the period covered by this review? | Overall, 48.5% (MK 22.26bn ) of 2010/11 budget released by Treasury by Feb. 2011. 30% of development activity funded due to slow progress. Infrastructure payments through Treasury. JFA eligible expenditures likely to be achieved. 80% budget execution likely to be achieved in 2010/11, but audit report not due until Dec. 2011. (source: MoEST Quarterly financial report).
If Indicator 4 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 4 | Pupil: Teacher Ratio (PTR) in primary schools, Student: Teacher Ratio (STR) in secondary schools
Milestone for this review (if any) | PTR 76:1, STR 28:1 (in 2009/10)
What progress has been made in the period covered by this review? | Not achieved. PTR 80:1 and STR 22:1 (EMIS 2010). Enrolment is inflated by repetition. Recruitment of teachers in training has more than doubled. Open and Distance Learning programme introduced and up to 4,000 recruited in 2010. 1000 teaching assistants recruited. 6,000 more secondary school leavers are currently being recruited as student teachers, to be trained through distance learning. Teacher deployment is now based on PTRs. Pensions Bill may cause many teachers to retire early.
If Indicator 5 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 5
Milestone for this review (if any)
What progress has been made in the period covered by this review?
If Indicator 6 is to be reported against, click on the '+' sign to the left of this worksheet
Indicator 6
Milestone for this review (if any)
What progress has been made in the period covered by this review?
Are Purpose Assumptions being realised? If so, to what degree, and what has been the effect on the project? | Yes, to a large extent. This has been achieved through Development Partners, particularly DFID, holding Government of Malawi to account. Financial management and procurement improving. Financial management quarterly reports produced. A police case involving sale of government textbooks in the open market is being investigated.
What evidence is there that achieving the Purpose is contributing to the realisation of the Goal? If it is doing so, to what degree? | Collaboration between DPs and government has significantly improved the planning and quality of reporting on progress. For the first time this year, the education sector produced a Performance Report. Quarterly financial reports have been regular and of good quality. Technical Working Groups are meeting more frequently and meetings becoming more focussed due to the co-leadership of DPs and MoEST. Sector Working Group meetings for the first two quarters in 2010/11 were held. MoEST has struggled to get discussion and reporting at SWG to focus on high level issues and on progress and results. DPs and MoEST continue to work closely to ensure that efforts by the SWAP Secretariat to orient the districts to SWAP continue and build a capacity at the 'frontline' to deliver. Critical policies on girls education, Teacher management and development; on reducing repetition, accelerating construction to be reviewd/strengthened/approved as required. Mutual accountability between Ministry of Finance and MoEST on the one hand and between DPs and MOEST on the other needs to improve.
What is the evidence that the likely achievement of the Purpose can be attributed to progress made in delivering the Outputs in the period covered by this review? | Better co-ordination between donors and MOEST has strengthened focus on Education Sector Plan (ESIP) priority actions. Greater adherence to agreed benchmarks and triggers for funding. DFID disbursements have been performance based. World Bank scrutiny of construction contracts is helping improve the contracting process. Joint Sector Review (JSR) process, including quarterly reports and regular meetings is increasing the momentum for reform and tangible results. EIMU and ADB merger agreed and implementation underway. This will increase EIMU's capacity to deliver results. Guidelines on implementation of School Improvement Grants(SIGs) finalised. DFID pilot on use of SIGs demonstrated that SIGs generate stronger community participation and local commitment and allow teachers to be more accountable to parents and to the community.
Purpose Recommendation 1 | DFID to continue to use a performance based approach for disbursements.
Purpose Action Point 1 | DFID working with other DPs to continue to reinforce mutual accountability for performance from both donors and the MOEST.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Purpose Recommendation 2
Purpose Recommendation 3
Purpose Action Point 2
Purpose Action Point 3
Project Purpose Score | 2 | 2.35
Purpose Justification
Risk
Project Risk Rating or latest Overall Risk Score. | High
Based on the review, does the Project Risk Rating need revision? | No
If Yes, why is this?
If new risks have emerged, click the '+' box on the left-hand side and list them in the appropriate boxes.
* High Impact / High Probability
* High Impact / Medium Probability
* High Impact / Low Probability
* Medium Impact / High Probability
* Medium Impact / Medium Probability
* Medium Impact / Low Probability
* Low Impact / High Probability
* Low Impact / Medium Probability
* Low Impact / Low Probability
What is being done, or will need to be done, to manage or monitor these new Risks?
Risk Recommendation 1 | Filling vacant posts alone will not give MoEST the capacity it needs. MoEST needs to continue to strengthen staffing and capacity and Director-level ability to manage change and drive reform. MoEST has recently appointed a new Director of Planning, Head of Procurement, HR Controller and Operations Manager for Education Infrastructure Management Unit (EIMU). Three new TAs - for procurement, HR, and M & E have also been recruited. MoEST to optimise the capacity and skills of all these to deliver better results, and to reduce the inherent risks.
Risk Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Risk Recommendation 2
Risk Recommendation 3
Risk Action Point 2
Risk Action Point 3
Logframe, DSOs, Cross-Cutting Markers
Logframe revised/needs revision? | Yes
If Yes, why was/is this? | More recent baseline data became available in the early stages of the programme, and two errors in the logframe were found after it had been approved.
Logframe Recommendation 1
Logframe Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Logframe Recommendation 2
Logframe Recommendation 3
Logframe Action Point 2
Logframe Action Point 3
DSOs revised/need revision? | No
If Yes, why was/is this?
DSO Recommendation 1
DSO Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
DSO Recommendation 2
DSO Recommendation 3
DSO Action Point 2
DSO Action Point 3
Cross-Cutting Markers revised/need revision? | No
If Yes, why was/is this?
CCM Recommendation 1
CCM Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
CCM Recommendation 2
CCM Recommendation 3
CCM Action Point 2
CCM Action Point 3

## A2 Outputs 1-5
A2: Outputs 1-5
Output 1 |  | Expanded and more equitable access to each level of education
Impact Weight revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) |  | 35%
Risk revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Risk |  | High | 1
0.35
DFID Share revised/needs revision? |  | No
If Yes, why was/is this? |  |  | 1
Original or Revised DFID Share |  | 6.5% | 2
3
Indicator 1 (leave blank if standard indicator) |  | Additional number of primary school classrooms constructed or rehabilitated per year and unit cost of classrooms | 4
Is this a Standard Indicator? |  | Yes | 5
Select standard indicator from drop down list |  | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) |  | 500+ classrooms, at <£11,000 each | 0
Progress made in the period covered by this review, including numbers. |  | Unit costs target achieved. EIMU's unit costs of $14,500 (£9,000) per classroom compare favourably with others (UNICEF - $14,500, Save the Children - $17,750). Classroom construction targets not achieved. Only 42% of contracts awarded in April 2010 by EIMU for classrooms and related infrastructure were completed by 31 December. 104 out of 284 classrooms completed. Overall 544 classrooms constructed in the sector plus 52 constructed by communities and funded through the GoM Local Development Fund (LDF). Classroom: pupil ratio 1:101, an improvement from 1:116 in 2009 (EMIS 2010). A new school mapping exercise is being commissioned to make classroom construction and school location more needs-based.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) |  | Survival Rate to Grade 5 (proportion of pupils starting grade 1 who reach 5, by sex)
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | male 55%, female 53% in 2009/10 (revised logframe milestones, from CABS PAF)
Progress made in the period covered by this review, including numbers |  | Not achieved; but trend is improving consistently Survival rate to Standard 5 and 8 reported to have improved to 72% and 49% respectively ( EMIS 2010) up from from 65% and 39% in 2009. We have doubts about this scale of improvements. Education statistics 2009 erroneously reported a survival rate for girls of almost 74% (Std 5) and 49% (std 8); The 2010 CABS review revised these downwards to 51% ( std 8) and 23% (std 8) and set targets at 53% (std 5) and 25% (std 8) for the next CABS reporting deadline of Feb 2011. There was agreement that cohort analysis would be the methodology for calculating this indicator for 2010 on the same basis as was redone for 2009 in order to show a consistent change over time. DFID will be working with the government to do further analysis of the governmernt data and confirm these with reality checks through school visits. Girl drop out rate of 23% compared to 7.5% for boys is a decline on last year's 16%. GoM has approved a policy requiring every primary school to establish Mother groups to support, counsel and keep girls in school. Over 1200 Mother Groups have been established (source: Education Sector Performance Report 2010). In one district (Dedza), Mother groups were able to track and get 351 drop outs to return to school.upwards.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) |  | Transition Rate from primary to secondary school (m/f) and actual difference between number of boys and of girls in Standard 8
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | Male 35% Female 38%
Progress made in the period covered by this review, including numbers |  | Actual difference (gender gap) of 11,908 shows an improving trend (reduced from 20,602 in 2008 and 18,366 in 2009).
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 1 |  | 3 | 0.5
Impact Weighted Score |  | 17.5 | 0.175
Justification for the Score |  | Milestones and targets only partially met.
Output 1 Recommendation 1 |  | Need to investigate why transition rates are projected to fall slightly year on year.
Output 1 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 1 Recommendation 2 |  | Need to assess the proposed strategy for reducing repetition and review as appropriate. Analyse further government's willingness to implement the repetition policy in order to determine how else we might approach reducing repetition.
Output 1 Recommendation 3
Output 1 Action Point 2 |  | DFID to analyse government's willingness to implement the repetition policy in order to determine how else we might approach reducing repetition
Output 1 Action Point 3 |  | Encourage government to set an ambitious but realistic classroom target ( bearing in mind potential constraints such as availability of building supplies, fuel and capacity of EIMU to provide regular oversight on construction)
If Output 2 is required, click on the '+' sign to the left of this worksheet
Output 2 | Improved quality and relevance with effective learning | Improved quality and relevance of education, with effective learning.
Impact Weight revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) |  | 35%
Risk revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Risk |  | High | 1
0.35
DFID Share revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised DFID Share |  | 6.5%
Indicator 1 (leave blank if standard indicator) |  | Number of primary school teachers trained per year (national total +number attributable to DFID)
Is this a Standard Indicator? |  | Yes
Select standard indicator from drop down list |  | 1. Number of teachers trained | 0
Milestone for this review (including number, if any) |  | 4,000 in 2009/10 (300 attributable to DFID)
Progress made in the period covered by this review, including numbers |  | Achieved. 3,456 graduated from TTCs, (45% of them female); 4,419 currently in training in TTCs and another 4,000 being trained through Open and Distance Learning (ODL), of whom 36% are females (Source: Department for Teacher Education - DTED). A shortlist completed for recruitment of a second cohort of 6,000. Rural teachers allowance introduced. GoM secured funding for construction of 4 new TTCs for primary school teachers and one for secondary teachers; 1,000 Teaching assistants recruited. Some delays in payment of teacher salaries. 48,963 primary school teachers in the year under review - 40% of them female (source: HRMD - Human Resource Management Department, EMIS, DTED). A teacher projection study being planned (to recommend how to track attrition, actual numbers working, numbers leaving public service and the profession). Speed of teacher deployment after training needs to improve.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) |  | Primary school completion rate (PCR), (= Standard 8 enrolment, minus repeaters, as % of 13 year-old population)
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | 38% based on Country Status Report (in original logframe) and 56%m/47%f ased on EMIS and population census data (in revised logframe).
Progress made in the period covered by this review, including numbers |  | Impossible to assess progress in the absence of population projections by single year of age.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) |  | % pass rate in Primary School Leaving Certificate Examination (PSLCE), and Malawi School Certificate Examination (MSCE)
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | PSLCE 70%, MSCE 38%
Progress made in the period covered by this review, including numbers |  | Partially met. Overall PSLCE pass rate 69% (EMIS 2009), MSCE - 53%. Almost 62% ( 55,421girls) passed the Primary School Leaving Certificate Examination (PSLCE ); compared to 74% of boys (82,426boys). 46.5% (13,604) of girls passed the Malawi School Certificate of Education (MSCE) compared to 58% (23,017) for boys. This is an increase from almost 31% MSCE pass rate for girls and 44% for boys. (EMIS 2010)
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 2 |  | 2 | 0.75
Impact Weighted Score |  | 26.25 | 0.2625
Justification for the Score
Output 2 Recommendation 1 |  | Measures to tackle the large class sizes (besides training more teachers) as well as an effective system for measuring national literacy and numeracy standards need to be agreed urgently.
Output 2 Action Point 1 |  | DFID to work with development partners particularly UNICEF ( who are supporting the MOEST on developing a National system to measure literacy and numeracy) to get momentum and clear decisions on taking this forward.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 2 Recommendation 2 |  | DFID to work through DPs to get a stronger commitment and action from the sector particularly MoEST on achieving parity in Std 8, and more girls advancing to secondary.
Output 2 Recommendation 3 |  | Need to investigate the poor performance of girls in PSLCE & MSCE ( considering they learn in relatively small class sizes compared to earlier classes)
Output 2 Action Point 2 |  | DFID to use its new girls education programmes to leverage more support and focus on need to accelerate specfic measures to keep girls in school.
Output 2 Action Point 3 |  | DFID to track teacher/pupil ratio (+ numbers) across grades, and over time, (in addition to teachers ever trained).
If Output 3 is required, click on the '+' sign to the left of this worksheet
Output 3 |  | Improved governance and management of the system with more efficient service delivery
Impact Weight revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Impact Weight (%) |  | 30%
Risk revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised Risk |  | High | 1
0.3
DFID Share revised/needs revision? |  | No
If Yes, why was/is this?
Original or Revised DFID Share |  | 6.5%
Indicator 1 (leave blank if standard indicator) |  | Repetition and dropout rates in primary schools (weighted means across all 8 grades)
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | Repetition: 16%; drop out: 12% in 2009/10 (from revised logframe)
Progress made in the period covered by this review, including numbers |  | Partly achieved. Overall repetition rate is 15%. Repetition rates for girls (14.9%) in Std 8 are slightly lower than for boys (15.4%). Drop out milestone not achieved. Almost one in 4 girls drops out of Std 8 ( 23%) compared to only 7.4% for boys (EMIS 2010). Guidelines on measures needed to control repetition and to reduce class sizes have been drafted for implementation at the start of the 2011/12 school year, . The Accountant General has granted approval for every primary school to have its own bank account.
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator) |  | Unit costs in MK (and as % of GDP pc) by level of education. ('unit cost' means public recurrent expenditure per student)
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | Primary MK3,500 (10%), Secondary MK30,000 (83%), University MK700,000 (1900%) in 2009/10
Progress made in the period covered by this review, including numbers |  | Breakdown of expenditure by sub-sector is not available so unit costs cannot be calculated. Milestone probably not achieved. Poor progress. Accelerating access to University education is likely to continue to be a priority for the government. A new Principal Secretary has been appointed and a Higher Education Council established. With six new universities proposed (to be funded from the national budget) the threat to the commitment to the primary education allocation is present. GoM promised university students that fees will not be increased. Public University Students Loan Trust (PUSLT) abolished and student loans now administered by Malawi Savings Bank. WB leading study on policy options in higher education, including financing options.
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator) |  | Timing of approval of annual work programme, education sector budget and procurement plan
Is this a Standard Indicator? |  | No
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any) |  | All three by 30/09/2010
Progress made in the period covered by this review, including numbers |  | Achieved. Revised PoW 30/08/10, Education Sector Budget 30/07/10, Procurement Plan 30/03/10. Procurement Technical Assistant (TA) recruited. The education SWAp MoU and the Joint Financing Arrangement (JFA) require the GoM to produce quarterly reports on progress, finance and procurement. Such reports are being produced but need to improve to inform high level decision making on accelerating reform. Terms of reference for the financial and procurement audit have been drafted and are being finalised, under the supervision of the World Bank. Regular audits and Public Expenditure Tracking Surveys will be undertaken to ensure transparency and accountability in the face of fiduciary risks. Sequencing of timelines for production of 3 docs to be revised. For example POW dates to be earlier to inform the procurement plan.
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 3 |  | 2 | 0.75
Impact Weighted Score |  | 22.5 | 0.225
Justification for the Score |  | Two of the three targets not clearly achieved.
Output 3 Recommendation 1 |  | DFID to work with JFA partners and MoEST to ensure that key financial planning, budgeting, procurement and reporting documents are produced within agreed time lines and of good quality.
Output 3 Action Point 1 |  | DFID to work with other DPs and through TWGs and TAs to ensure next quarterly reports (especially the Progress and Procurement sections) and proceedings of the next Sector Working Group tackle the critical issues.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 3 Recommendation 2 |  | Need to launch a public education campaign on reducing repetition and class sizes to communicate positive messages, reassure parents that their children's education will not suffer, and to help manage any political risks associated with introducing such a policy.
Output 3 Recommendation 3
Output 3 Action Point 2 |  | DFID to work with other DPs and through the Communications Systems task force to get some high level decision on this, recruit a consultant to design and launch a campaign by August 2011 ahead of the introduction of the new policy in September.
Output 3 Action Point 3 |  | Repetition as an efficiency measure; DFID to use its co-leadership of the Basic Education TWG to get repetition guidelines finalised and implemented in school year starting September 2011;
If Output 4 is required, click on the '+' sign to the left of this worksheet
Output 4
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 4 |  |  | 0
Impact Weighted Score |  | 0 | 0
Justification for the Score
Output 4 Recommendation 1
Output 4 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 4 Recommendation 2
Output 4 Recommendation 3
Output 4 Action Point 2
Output 4 Action Point 3
If Output 5 is required, click on the '+' sign to the left of this worksheet
Output 5
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  |  | 0
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list |  | 2. Number of classrooms constructed or rehabilitated | 0
Milestone for this review (including number, if any) |  | what you started out to achieve - target for that year
Progress made in the period covered by this review, including numbers |  | quantity actually delivered
Output Performance for Output 5 |  |  | 0
Impact Weighted Score |  | 0 | 0
Justification for the Score
Output 5 Recommendation 1
Output 5 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 5 Recommendation 2
Output 5 Recommendation 3
Output 5 Action Point 2
Output 5 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## A2 Outputs 6-10
A3: Outputs 6-10
If Output 6 is required, click on the '+' sign to the left of this worksheet
Output 6
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 6 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 6 Recommendation 1
Output 6 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 6 Recommendation 2
Output 6 Recommendation 3
Output 6 Action Point 2
Output 6 Action Point 3
If Output 7 is required, click on the '+' sign to the left of this worksheet
Output 7
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 7 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 7 Recommendation 1
Output 7 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 7 Recommendation 2
Output 7 Recommendation 3
Output 7 Action Point 2
Output 7 Action Point 3
If Output 8 is required, click on the '+' sign to the left of this worksheet
Output 8
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 8 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 8 Recommendation 1
Output 8 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 8 Recommendation 2
Output 8 Recommendation 3
Output 8 Action Point 2
Output 8 Action Point 3
If Output 9 is required, click on the '+' sign to the left of this worksheet
Output 9
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 9 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 9 Recommendation 1
Output 9 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 9 Recommendation 2
Output 9 Recommendation 3
Output 9 Action Point 2
Output 9 Action Point 3
If Output 10 is required, click on the '+' sign to the left of this worksheet
Output 10
Impact Weight revised/needs revision?
If Yes, why was/is this?
Original or Revised Impact Weight (%)
Risk revised/needs revision?
If Yes, why was/is this?
Original or Revised Risk |  | 0
0
DFID Share revised/needs revision?
If Yes, why was/is this?
Original or Revised DFID Share
Indicator 1 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 2 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 2 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 3 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 3 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 4 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 4 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 5 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 5 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
If Indicator 6 is required for this Output, click on the '+' sign to the left of this worksheet
Indicator 6 (leave blank if standard indicator)
Is this a Standard Indicator?
Select standard indicator from drop down list
Milestone for this review (including number, if any)
Progress made in the period covered by this review, including numbers
Output Performance for Output 10 |  | 0
Impact Weighted Score | 0 | 0
Justification for the Score
Output 10 Recommendation 1
Output 10 Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Output 10 Recommendation 2
Output 10 Recommendation 3
Output 10 Action Point 2
Output 10 Action Point 3
1. Number of teachers trained
2. Number of classrooms constructed or rehabilitated
3. Number of health professionals trained
4. Number of one year olds vaccinated against measles
5. Number of insecticide treated bed nets distributed
6. Number of people with advanced HIV infection receiving ARVs
7. Number of condoms distributed
8. Number households provided with new/improved drinking water sources
9. Number of new/improved sanitation facilities provided
10. Total length of roads built or upgraded
11. Total length of roads maintained or rehabilitated
12. Number of households provided with new/improved access to basic electricity supply
13. Number of people directly assisted by food security programmes
14. Number of people directly assisted by social assistance programmes

## B Project Scoring
B: Project Scoring
20 | 2011-03-22
Impact Weighting (must = 100) | 100%
Total Impact Score | 66.25 | 0.6625
Output Risk | High | 1
Method of Scoring: Sources of Information
Using the drop-down menu for each box, enter "X" for each Source of Information used in the review.
Quantitative data from national systems | X
Quantitative data from project/programme study | X
Government assessment
Joint donor review | X
Independent consultant review
DFID staff review | X
Scoring Responsibility: Partners Involved
Using the drop-down menu for each box, enter "X" to indicate Partners Involved in the review.
National Government partner | X
National non-Government partner
Independent consultant | X
Donor partners | X
DFID staff | X
Donor partners | GIZ; CIDA
Comment here on the Method of Scoring and Scoring Responsibility.
Scoring Recommendation 1
Scoring Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Scoring Recommendation 2
Scoring Recommendation 3
Scoring Action Point 2
Scoring Action Point 3

## C Knowledge & Evidence
C: Knowledge Sharing and Evidence
Lesson category
1. Working with partners | DFID logframes provide a good basis for dialogue around results.
Working with Partners Recommendation 1 | The original and revised logframes for MESRP should be shared with MoEST and donor partners to focus their attention on results, and on quantification wherever possible.
Working with Partners Action Point 1 | DFID Education Advisers to follow up with key individuals in MoF, MoEST and other agencies.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Working with Partners Recommendation 2
Working with Partners Recommendation 3
Working with Partners Action Point 2 | DFID to continue to make disbursements conditional on performance on targets
Working with Partners Action Point 3
2. Best Practice / Innovation | Setting spending targets and reform commitments have been useful moves towards results-based financing.
Best Practice / Innovation Recommendation 1 | Investigate whether incentives and bonuses for good performance are more or less effective than sanctions for poor performance.
Best Practice / Innovation Action Point 1 | Pursue with others in DFID and in other agencies.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Best Practice / Innovation Recommendation 2
Best Practice / Innovation Recommendation 3
Best Practice / Innovation Action Point 2
Best Practice / Innovation Action Point 3
3. Project Management | Programme management is a shared responsibility of programme managers and professional advisers
Project Management Recommendation 1 | Annual Reviews such as this one should be jointly carried out and owned by DFID programme managers and professional advisers.
Project Management Action Point 1 | Create a team of managers and advisers to carry out next year's review.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Project Management Recommendation 2
Project Management Recommendation 3
Project Management Action Point 2
Project Management Action Point 3
Other Comments
If appropriate, comment on the effectiveness of the institutional relationships created or enhanced by the project, e.g., comment on processes and how relationships have evolved. | This DFID programme is part of the wider SWAp (sector-wide approach) in the education sector. The structures of the 'E-SWAp' are still emerging and are heavy consumers of DFID staff time but seem to be more effective than the previous relatively ad hoc structures and procedures, which were fragmented and differentiated.
Key issues, points of information or additional comments that may be useful for this or other project teams.
Other Recommendation 1
Other Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Other Recommendation 2
Other Recommendation 3
Other Action Point 2
Other Action Point 3
Evidence: Key documents
Quest No.
Education Sector Performance Report
Education Management Information System 2010
Education Management Information System 2009
Quarterly Financial reports
Malawi Education Sector Reform, Programme Memorandum 2010
Evidence Recommendation 1 | Financial reports should focus more on unit costs to provide a better basis for assessment of cost-effectiveness.
Evidence Action Point 1 | DFID staff to pursue unit cost data with budget unit and with Director of Finance in MoEST.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Evidence Recommendation 2
Evidence Recommendation 3
Evidence Action Point 2
Evidence Action Point 3

## D Conditionality Sustainability
D: Conditionality and Sustainability
Conditionality
If conditions are attached to this project, was disbursement suspended during the review period because of the conditions? | Yes
If Yes, what was the cause? | The second half of the total disbursement for the year was at first delayed and then partially withheld. The cause was the assessment that progress was satisfactory on only two thirds of the indicators used for monitoring progress on the nine key elements of the reform agenda in the Education Sector Implementation Plan.
Date Suspended (dd/mm/yyyy)? | 2011-02-25
What were the consequences? | Malawi has lost £2.33m of the committed British aid under this programme in 2010/11.
Conditionality Recommendation 1
Conditionality Action Point 1
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Conditionality Recommendation 2
Conditionality Recommendation 3
Conditionality Action Point 2
Conditionality Action Point 3
Sustainability
Comment on how likely is it that the benefits arising from this project will be sustained after the end of project. | If the programme succeeds to any significant extent, it is likely that the benefits arising, particularly the efficiency gains, will be sustained in the longer term.
Sustainability Recommendation 1
Sustainability Action Point 1 | DFID to work with DP group to support the change management process in the MoEST itself and the MoEST's leadership of the SWAP to ensure ownership of reform is sustained.
If more Recommendations or Action Points need to be identified, click the '+' box on the left-hand side.
Sustainability Recommendation 2
Sustainability Recommendation 3
Sustainability Action Point 2 | DFID in partnership with other DPs to engage with Communications systems task force and with UNICEF ( as co-chair of the task force) on strengthening use of public media to get public support and understanding of reform in the sector.
Sustainability Action Point 3 | DFID working with other DPs to emphasise through TWGs and meetings with directors on importance of MoEST optimising TA capacity and implementing the capacity development strategy quickly.

## E Recommendations & Actions
E: Recommendations and Action Points
Recommendations |  | Person / team who will action the recommendation
A1: Goal
R1 | With NER targets achieved, important to start focussing more on learning assessment and achievement, and on stronger measures to accelerate transition to secondary school, especially for girls. | Don & vera
R2 | 0
R3 | 0
A1: Purpose
R1 | #REF!
R2 | 0
R3 | 0
A1: Risk
R1 | Filling vacant posts alone will not give MoEST the capacity it needs. MoEST needs to continue to strengthen staffing and capacity and Director-level ability to manage change and drive reform. MoEST has recently appointed a new Director of Planning, Head of Procurement, HR Controller and Operations Manager for Education Infrastructure Management Unit (EIMU). Three new TAs - for procurement, HR, and M & E have also been recruited. MoEST to optimise the capacity and skills of all these to deliver better results, and to reduce the inherent risks. | Don
R2 | 0
R3 | 0
A1: Logframe
R1 | 0
R2 | 0
R3 | 0
A1: DSOs
R1 | 0
R2 | 0
R3 | 0
A1: Cross-Cutting Markers
R1 | 0
R2 | 0
R3 | 0
A2: Outputs
R1.1 | Need to investigate why transition rates are projected to fall slightly year on year. | Vera & Don
R1.2 | Need to assess the proposed strategy for reducing repetition and review as appropriate. Analyse further government's willingness to implement the repetition policy in order to determine how else we might approach reducing repetition. | Don & Vera
R1.3 | 0
R2.1 | Measures to tackle the large class sizes (besides training more teachers) as well as an effective system for measuring national literacy and numeracy standards need to be agreed urgently. | Don
R2.2 | DFID to work through DPs to get a stronger commitment and action from the sector particularly MoEST on achieving parity in Std 8, and more girls advancing to secondary. | Vera
R2.3 | Need to investigate the poor performance of girls in PSLCE & MSCE ( considering they learn in relatively small class sizes compared to earlier classes) | vera
R3.1 | DFID to work with JFA partners and MoEST to ensure that key financial planning, budgeting, procurement and reporting documents are produced within agreed time lines and of good quality. | Don
R3.2 | Need to launch a public education campaign on reducing repetition and class sizes to communicate positive messages, reassure parents that their children's education will not suffer, and to help manage any political risks associated with introducing such a policy. | Andrew
R3.3 | 0 | Don
R4.1 | 0
R4.2 | 0
R4.3 | 0
R5.1 | 0
R5.2 | 0
R5.3 | 0
R6.1 | 0
R6.2 | 0
R6.3 | 0
R7.1 | 0
R7.2 | 0
R7.3 | 0
R8.1 | 0
R8.2 | 0
R8.3 | 0
R9.1 | 0
R9.2 | 0
R9.3 | 0
R10.1 | 0
R10.2 | 0
R10.3 | 0
B: Scoring
R1 | 0
R2 | 0
R3 | 0
C: Knowledge Sharing
Working with Partners
R1 | The original and revised logframes for MESRP should be shared with MoEST and donor partners to focus their attention on results, and on quantification wherever possible. | Don
R2 | 0
R3 | 0
Best Practice / Innovation
R1 | Investigate whether incentives and bonuses for good performance are more or less effective than sanctions for poor performance. | Don
R2 | 0
R3 | 0
Project Management
R1 | Annual Reviews such as this one should be jointly carried out and owned by DFID programme managers and professional advisers. | Andrew
R2 | 0
R3 | 0
C: Other Comments
R1 | 0
R2 | 0
R3 | 0
C: Evidence
R1 | Financial reports should focus more on unit costs to provide a better basis for assessment of cost-effectiveness. | Don
R2 | 0
R3 | 0
D: Conditionality
R1 | 0
R2 | 0
R3 | 0
D: Sustainability
R1 | 0
R2 | 0
R3 | 0
Additional Recommendations arising
R1
R2
R3
Action Points |  | Person / team who will lead on the Action Point
A1: Goal
AP1.1 | DFID working with other DPs to support the MoEST to develop a credible system for setting and measuring literacy and numeracy standards, at least for Standards 1 to 4, and for extending gender parity up to standard 8 and into secondary school. | Vera & Don
AP1.2 | 0
AP1.3 | 0
A1: Purpose
AP1.1 | DFID to continue to use a performance based approach for disbursements. | Don & Sarah
AP1.2 | 0
AP1.3 | 0
A1: Risk
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Logframe
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: DSOs
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A1: Cross-Cutting Markers
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
A2: Outputs
AP1.1 | 0
AP1.2 | DFID to analyse government's willingness to implement the repetition policy in order to determine how else we might approach reducing repetition
AP1.3 | Encourage government to set an ambitious but realistic classroom target ( bearing in mind potential constraints such as availability of building supplies, fuel and capacity of EIMU to provide regular oversight on construction)
AP2.1 | DFID to work with development partners particularly UNICEF ( who are supporting the MOEST on developing a National system to measure literacy and numeracy) to get momentum and clear decisions on taking this forward. | Don & Vera
AP2.2 | DFID to use its new girls education programmes to leverage more support and focus on need to accelerate specfic measures to keep girls in school. | Vera
AP2.3 | DFID to track teacher/pupil ratio (+ numbers) across grades, and over time, (in addition to teachers ever trained). | Vera
AP3.1 | DFID to work with other DPs and through TWGs and TAs to ensure next quarterly reports (especially the Progress and Procurement sections) and proceedings of the next Sector Working Group tackle the critical issues. | Don
AP3.2 | DFID to work with other DPs and through the Communications Systems task force to get some high level decision on this, recruit a consultant to design and launch a campaign by August 2011 ahead of the introduction of the new policy in September. | Andrew
AP3.3 | Repetition as an efficiency measure; DFID to use its co-leadership of the Basic Education TWG to get repetition guidelines finalised and implemented in school year starting September 2011;
AP4.1 | 0
AP4.2 | 0
AP4.3 | 0
AP5.1 | 0
AP5.2 | 0
AP5.3 | 0
AP6.1 | 0
AP6.2 | 0
AP6.3 | 0
AP7.1 | 0
AP7.2 | 0
AP7.3 | 0
AP8.1 | 0
AP8.2 | 0
AP8.3 | 0
AP9.1 | 0
AP9.2 | 0
AP9.3 | 0
AP10.1 | 0
AP10.2 | 0
AP10.3 | 0
B: Scoring
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Knowledge Sharing
Working with Partners
AP1.1 | DFID Education Advisers to follow up with key individuals in MoF, MoEST and other agencies. | Don and Vera
AP1.2 | DFID to continue to make disbursements conditional on performance on targets
AP1.3 | 0
Best Practice / Innovation
AP1.1 | Pursue with others in DFID and in other agencies. | Don and Vera
AP1.2 | 0
AP1.3 | 0
Project Management
AP1.1 | Create a team of managers and advisers to carry out next year's review. | Andrew
AP1.2 | 0
AP1.3 | 0
C: Other Comments
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
C: Evidence
AP1.1 | DFID staff to pursue unit cost data with budget unit and with Director of Finance in MoEST. | Don
AP1.2 | 0
AP1.3 | 0
D: Conditionality
AP1.1 | 0
AP1.2 | 0
AP1.3 | 0
D: Sustainability
AP1.1 | DFID to work with DP group to support the change management process in the MoEST itself and the MoEST's leadership of the SWAP to ensure ownership of reform is sustained. | Don & vera
AP1.2 | DFID in partnership with other DPs to engage with Communications systems task force and with UNICEF ( as co-chair of the task force) on strengthening use of public media to get public support and understanding of reform in the sector. | Andrew & Vera
AP1.3 | DFID working with other DPs to emphasise through TWGs and meetings with directors on importance of MoEST optimising TA capacity and implementing the capacity development strategy quickly. | Don & Vera
Additional Action Points arising
AP1.1
AP1.2
AP1.3