Type of Review: Annual Review

Project Title: Malawi Education Sector Reform Programme (MESRP)

Date started:	March 2010	Date review undertaken: July 2013

Instructions to help complete this template: / Before commencing the annual review you should have to hand: / the Business Case or earlier project documentation. / the Logframe / the detailed guidance (How to Note)- Reviewing and Scoring Projects / the most recent annual review (where appropriate) and other related monitoring reports / key data from ARIES, including the risk rating / the separate project scoring calculation sheet (pending access to ARIES) / You should assess and rate the individual outputs using the following rating scale and description. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores: / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Introduction and Context

What support is the UK providing?
The Malawi Education Sector Reform Programme (MESRP) is DFID’s £50 million programme to support transformational change in Malawi’s education sector (2010 - 2013) as part of a £200 million donor pooled fund in a Sector-Wide Approach (SWAp). DFID has disbursed £42 million over three years as pooled and earmarked Sector Budget Support (SBS) to the Ministry of Education, Science and Technology, £5 million over three years for improving domestic accountability and sector governance and a £3 million provided to the MOEST to further construction of classrooms began under the Education Sector Support Programme (ESSP) which preceded MESRP

What are the expected results?
Four major donors (Germany, UK, World Bank, and the Global Partnership for Education) are pooling funds in a Sector-Wide Approach (SWAp) to support implementation of the ESIP (Education Sector Implementation Plan), which aimed to achieve the following results by June 2013: / Over 2,000 primary school classrooms constructed or rehabilitated. / Over 16,000 new primary teachers trained. / Equal numbers of girls and boys in Form 1 of secondary school. / Repetition falling from 20% of all pupils in school to 5%. / The overall Pupil: Teacher Ratio (PTR) falling from 78:1 to 62:1. / All 6,000 primary schools supported by direct grants. / Intended outputs were: / Expanded and more equitable access to primary education / Indicators: / % of planned school buildings completed annually and unit classroom costs / Survival rate to grade 5 disaggregated by gender / Difference between number of boys and girls at grade 8 / Number of children supported by DFID in primary education (DRF indicator) / Improved quality and relevance of education, with effective learning / Indicators: / Number of primary school teachers trained and hired / Primary school completion rate and number of children completing primary education supported by DFID (DRF indicator) / % pass rates Primary School Leaving Certificate Examination (PSLCE) / % pass rates Malawi [Secondary] School Certificate Examination (MSCE) and number of children supported by DFID in lower secondary (DRF indicator) / Improved governance and management of the system with more efficient service delivery / Indicators: / Repetition and dropout rates in primary school / Unit costs, in MK by level of education / Timing of approval of the annual POWs, education sector budget, and procurement plan

What is the context in which UK support is provided?
The Malawi 2009 MDG Report indicated that MDGs 2 and 3 are “unlikely to be met”. The Net Enrolment Ratio was 83% (2010, Welfare Monitoring Survey) and projected to reach 88% by 2015. Gender parity has been achieved to primary standard 5 but not in secondary schools, where the ratio of girls to boys was 0.9:1. The overall primary school completion rate rose from 26% in 2005 to 35% in 2009, but was still far too low. More than 600,000 primary school-age children were not enrolled in school, while 698,000 children enrolled in primary school in 2008 were repeating the same grade. Gender and regional disparities persist, and the quality of teaching and learning in primary schools is generally low. / The Malawi Education Country Status Report (CSR, World Bank, 2009) analysed equity and efficiency of resource allocations and proposed reforms in policy and practice. It formed the basis for the assessment of priorities and resource allocations in the Education Sector Implementation Plan, the medium-term national plan, translating the vision of the NESP into operational terms. / Government and donors agreed that fundamental changes in policy and practice were required to bring about transformation in the education sector. However, given poor prospects for achieving the MDGs in education, and with only 44% of the Government budget allocated to primary education and much spend poorly targeted, GoM and donors recognised that ‘business as usual’ could not continue. Primary education needed to be better financed, and resources allocated more equitably between districts, income groups, and learners at different levels of the system. Resources needed to be used more efficiently, to avoid the losses involved in high rates of grade repetition and school dropout. / Government and donors agreed that the most urgent reform was to reduce class sizes. This required more teachers; more permanent classrooms; stricter control of repetition; and the use of classrooms for two shifts each day. The recruitment of additional, auxiliary teachers, and their training on-the-job by distance learning, will act to kick-start the process. To implement these priority actions, MoEST, Ministry of Finance, and donors would pool funds through government systems, under the Joint Financing Arrangement. / The education SWAp would enhance mutual accountability (GoM, donors and civil society) and internal accountability (MoEST and MoF). By using government systems and stimulating better coordination between government and donors, it would reduce transaction costs with substantial efficiency gains in programme management and reporting. / DFID would continue to engage with civil society as well as Government, particularly in holding government accountable for the use of public funds and teachers accountable to parents in local communities. DFID support for increased accountability through civil society would include NGOs, the media, churches and the teachers union. DFID will also work with the Parliamentary Committee on Education.

## Section A: Detailed Output Scoring

Output 1: Expanded and more equitable access to each level of education
Output 1 score and performance description: B (Outputs moderately did not meet expectation) / Indicator 1.1: Number of primary school classrooms constructed or rehabilitated per year, and unit cost of classrooms. Milestone for 2011/12: 500+ classrooms (DFID’s 10%); unit cost <£13,000. / Classroom construction was a challenge at the beginning of the review period. The Education Infrastructure Management Unit (EIMU) is short-staffed and Government of Malawi (GoM) payment and procurement procedures caused delays in awarding contracts and paying contractors. In the period 288 new classrooms were completed (by the end of 2012) out of a target of more than 500 planned although contracts for the construction of an additional 502 classrooms were awarded. / However in response to this to increase the scale and pace of classroom construction the GoM decided to use the Local Development Fund (LDF) which had demonstrated capacity to build school infrastructure quickly to construct more classrooms. The LDF built 1,220 classrooms, 201 teacher houses and 407 VIP latrines. The other key actor in construction, UNICEF, completed 156 classrooms, rehabilitated 6, built 50 teachers houses and 26 pit latrines bringing the number of classrooms built over the period to a total of 1670. 167 classrooms (10%) of these are attributed to DFID missing the target of 500+ in the logframe. This output did not meet expectation / Unit costs varied among these players. EIMU constructed at double classroom block at a unit cost of MK19, 034,847.01 (£37,041.87), more than the milestone. The 49% devaluation of the kwacha in mid-2012 dramatically increased the price of construction materials by between 80% and 90%.. UNICEF’s unit cost was £22,349.50 again significantly higher than the milestone. By contrast the average unit cost of a school block constructed by LDF was MK6.7 million (£13,037.9) just above the milestone target of £13,000. The latter can be achieved through community contributions thereby keeping the costs of material and some labour down. The quality of LDF constructed classrooms is generally agreed to be much lower than those constructed by government EIMU or UNICEF. There is a trade off in that the environmental impact is greater due to the use of burnt bricks at community level. LDF is trialling SBS blocks as a way to negate the environmental impact. / Indicator 1.2: Survival Rate to Grade 5 (proportion of pupils starting grade 1 who reach grade 5, by sex). Milestone for 2011/12: male 56%, female 56%. / Education Statistics 2012 data indicates that the milestones in this indicator have been surpassed. Survival rate for Standard 5 in 2012 was 58% for boys and 59% for girls. Although the indicator has performed well against the targets set in the logframe there has been a marked drop in the survival rates recorded in the 2011 EMIS. , there has been a 23% and 21% drop for boys and girls respectively from the 2010/2011 survival rates. The reduction can be accounted for in two ways. Firstly it seems that the EMIS data from 2012 is more accurate than EMIS 2011 (and any EMIS prior) as data is now collected at district level through DEMIS rather than just centrally as it was before. The reality is probably that the previous EMIS figures were overstated due to poor collection methods and the current are more realistic. Secondly it is possible that the economic downturn had an effect on the numbers of children in school as families struggled to cope financially. DFID will explore more fully with the MOEST the likely reasons for this. / Indicator 1.3: Transition Rate from primary to secondary school (male/female), and actual difference between the numbers of boys and of girls in Standard 8. Milestone for 2011/12: male 33%, female 36%, and gender gap of less than 16,000 in Standard 8. / EMIS 2012 data indicates that the milestone on transitional rates has been significantly exceeded. The transition rates for primary to secondary school are 69.4% and 54.2% for boys and girls respectively. However there were 17,304 more boys than girls in standard 8 in 2012 moderately missing the log frame milestone of less than 16,000. / Progress against expected results: / With the expansion classroom construction via LDF, there has been significant progress in construction and rehabilitation of primary school infrastructure and the target has been significantly exceeded although the unit cost of constructing a classroom block rose due to the increased cost of building materials fuelled by devaluation and scarcity of the commodities since the mid-2011. Though the milestone for survival to standard five has been exceeded there continues to be more boys than girls surviving to standard 8. / Recommendations: / DFID should maintain pressure within the education SWAp and amongst pooled partners to prioritise primary school classroom construction, particularly completion of those contracts which are outstanding through EIMU. However, as around 50% of primary school graduates in Malawi cannot be accommodated in existing secondary schools (EMIS 2012) DFID should also consider the need to expand secondary access. Expanding the number of secondary school classrooms is an increasing priority if the transition rate from primary to secondary is to rise. / DFID should support the recent involvement of the Local Development Fund (LDF) in decentralised classroom construction and work with the Directorate of planning in MOEST and with the Infrastructure Technical working group to agree a model of accelerating construction of good quality primary classrooms. The MoEST have indicated they are already in the process of redefining EIMU’s role to that of an oversight body. Given the limitations EIMU have experienced in actually constructing classrooms over the last three years DFID would support such a move. / DFID, together with pooled partners, should support further analysis around the LDF approach, with a focus on understanding the value for money offered by LDF in relation to the quality and durability of classrooms to ensure that short term savings do not hide longer term costs (i.e. if the classrooms have a much shorter life span). Moreover, as LDF classrooms are made from community contributions in the form of burnt bricks the analysis needs to include how environmental concerns might be addressed in any scaled up school infrastructure construction by LDF. LDF is currently trialling stabilised soil bricks (SSBs) in 100 communities; DFID together with MoEST should closely monitor this.
Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk rating: High / Revised since last Annual Review? No

Output 2: Improved quality and relevance of education, with effective learning
Output 2 score and performance description: A+ (Outputs moderately exceeded expectation) / Indicator 2.1: Number of primary school teachers trained per year (national total, plus number attributable to DFID). (This is a DFID ‘Standard Indicator’.) Milestone for 2011/12: 4,800 teachers (475 attributable to DFID). / 4,360 student teachers were enrolled in the residential Initial Primary Teacher Education (IPTE) programme in Teacher Training Colleges in 2011/12 (Education Sector Progress Report for the Quarter ending 31st March, 2013 p.41). In addition, another 3,567 trainee teachers graduated through the Open and Distance Learning (ODL) IPTE programme in 2012 of which 1380 (39%) were female. Overall a total of 7,927 teachers have been trained substantially exceeding the milestone. / The introduction of the ODL programme has been a major success over the last two years nearly doubling the number of teachers trained per year. Many stakeholders in the sector consider this to be the area where the pooled fund has had the most significant impact at a classroom level. As a result, the overall Pupil: Teacher Ratio (PTR) has been gradually falling from 81:1 in 2009 to 76:1 2011 and 74:1 in 2012. Randomised control trials undertaken by the World Bank in Malawi reveal very little difference in the quality of teaching provided by graduates of ODL compared with those from the conventional IPTE. This suggests that the ODL model may offer better value for money as well as enabling the more rapid deployment of teachers to classrooms (around 4,000/year) as the model deploys the trainees and trains them on the job. The Government Department of Human Resources has created posts for promotion of primary school teachers in a new establishment. Filling of those posts is planned for the 2012/13 financial year including 7674 posts for IPTE and ODL graduates. Nevertheless, supervision and support to classroom-based trainee teachers remains a major challenge as does the lack of teachers’ houses. All stakeholders consulted in the course of this review emphasised the importance and motivational effect of teachers’ houses to the deployment of teachers to more remote rural areas where they are most needed. In the year under review, the pooled fund through EIMU started the construction of 31 teachers’ houses and completed 26 and LDF completed 201. It should also be noted however that the ODL model employs trainee teachers’ in their own communities thereby obviating the need for additional houses. / More broadly, evidence on the improved quality and relevance of education is mixed. The distribution of teaching and learning materials is widely acknowledged to have been poor within the first year of the SWAp but has improved dramatically over the reporting period. 9 million standard 3-8 textbooks were procured in 2011-12, and arrived in the country in January 2013. Delivery has been completed in the central and southern regions and is due to finish in the north soon. Meanwhile the procurement of 7million standard 1-3 textbooks and 10million standard 3-7 books has started. In addition 60,000 registers were printed and dispatched to primary schools. 56 million exercise books, 300,000 slates and 8million pencils were procured. Under the CBE programme 38,800 books, 10,080 facilitators’ guides have been distributed to 600 CBE centres and 50 motor cycles provided to CBE supervisors nation-wide. In the current financial year (2012/13) the same amounts are being procured for the new 1200 centres. Under Secondary education teaching and learning materials which include 313,000 textbooks, 20,000 chairs and 20,000 desks have been procured and distributed. In the current financial year 15,000 single-seater desks and chairs as well as 230,540 textbooks and 8000 mattresses are being procured. / In terms of improving the quality and relevance of education, the school grants under the Primary School Improvement Programme (PSIP) are widely regarded as a significant success story. Initial reports suggest these grants are reaching schools and being utilised for their correct purpose. In 2011/2012, 2,228 schools received School Improvement Grants (SIGs) out of the annual target of 5,500 schools. Another 3,069 schools in the 12 PSIP districts received Direct Support to Schools’ grants. (Education Sector Performance Report – 2011/12). 846 senior staff members and 1,323 schools were trained twice in School Improvement planning to increase their role in school procurement, financial management and national strategy for community participation out of the ESIP target of 1,500 schools. . The MoEST will scale up to the remaining 10 districts whilst also doubling the amount of the grant in the 2013/14 budget. The use and efficacy of these grants will be further tested through both the Fiduciary Risk Assessment (FRA) that DFID is currently undertaking and the Public Expenditure Tracking Survey (PETS) which DFID will support the World Bank to undertake later in 2013. Both studies will look at how funding is protected as it trickles down to the local level and any challenges that need to be addressed to maximise resources including the impact at school level. / In terms of measuring learning outcomes USAID has conducted two rounds of its Early Grade Reading Assessment (EGRA) in Malawi in both 2010 and 2011 and plans to continue on an annual basis. MoEST is keen to adopt this as a measure of learning outcomes and there is potential for a scale up in the future. / Indicator 2.2: Primary school completion rate (PCR), (= Standard 8 enrolment, minus repeaters, as % of 13 year-old population). (This is a World Bank ‘Core Indicator’.) Milestones for 2011/12: male 58%, female 51%. / The figures for 2012 suggest that the total primary completion rate is 59% with 65% male and 54% female thereby exceeding the original target. These figures need to be interpreted with caution however as the last reliable census data was collected in 2008. If we assume a population increase of 10% since 2008 (on the basis of the projections from the 2008 census) the picture worsens with a 54% total PCR, 59% male (still slightly exceeding target) but only 49% female (slightly below target). In the absence of accurate census data a reliable figure cannot be quoted for the PCR. / Indicator 2.3: % pass rates in Primary School Leaving Certificate Examination (PSLCE), and Malawi School Certificate Examination (MSCE). Milestones: 70% in PSLCE, 40% in MSCE. / A total of 205,739 pupils comprising 111,419 boys and 94, 320 girls sat for 2011/12 Primary School Leaving Certificate Examinations; 141,646 pupils passed comprising 83,396 boys and 58,250 girls representing 68.9% pass rate for PSLCE, 75% for boys and 62% for girls. Although boys exceeded the target, girls are still underperforming. A total of 102,688 students comprising 58,745 boys and 43,943 girls sat for the 2011/12 Malawi School Certificate of Education (MSCE). 56,246 passed comprising 34,912 boys (59%) and 21,334 girls (49%) representing 55% pass rate overall. Although a large difference remains between the pass rate for boys and girls, at least at MSCE level both outstripped the target of 40%. / Progress against expected results: Overall progress has dramatically exceeded targets in the key area of teacher training with greater numbers than ever before gaining teaching qualifications through the parallel systems of IPTE and ODL. These gains have been translated into the classroom as demonstrated by the falling Pupil Teacher Ratios. Progress in other areas has been more muted. There has been considerable effort made to address shortages of teaching and learning materials (TLMs) and this should be evident in the coming school year (13/14). There has also been effort made to measure learning outcomes before the formal Grade 8 exams (PSLCE) in order to make more targeted inputs in the early grades. Pass rates for both the primary and secondary examinations have exceeded targets although the performance of girls remains a concern. DFID’s Keeping Girls In School (KGIS) programme, a £37.5m investment in girls’ education, complements MESRP through a combination of incentives such as cash transfers, secondary school bursaries, and interventions that tackle the factors that cause girls to drop out.
Recommendations: DFID and pooled partners to work with government to ensure adequate funding is allocated in the budget to to ensure newly trained teachers can be absorbed by the system and placed where they are most needed. DFID needs to actively participate in discussions between DPs and MOEST on how best to address the issue of teacher housing These discussions could consider for example provision of a number of smaller houses to accommodate single teachers. Currently a three bedroom teacher’s house is constructed at a unit cost of £33,108.73 (EIMU data). This unit cost would significantly reduce if the smaller teacher’s house model is adopted. / Regarding learning outcomes neither PSLCE nor MSCE are reliable measures in the early grades as many children will have dropped out before reaching these formal examinations. Therefore in future DFID programme other indicators of quality should be used.. The Early Grade Reading Assessment (EGRA) and Early Grade Maths Assessment (EGMA) undertaken by USAID in 2010 and 2011 should provide better measures of achievement on a pedagogically useful and internationally comparative basis. This has been adopted by the MoEST in the ESIP II draft document. / Impact Weighting (%): 35% / Revised since last Annual Review? No / Risk rating: High / Revised since last Annual Review? No

Output 3: Improved governance and management of the system, with more efficient service delivery
Output 3 score and performance description: A - Outputs met expectation / Indicator 3.1: Repetition and dropout rates in primary schools. Milestones for 2011/12: repetition 12% and dropout 10%. / Repetition rate for 2011/2012 is 18.8 % indicating an increase from 16.7% in 2010/11 and missing the target of 12% in the logframe. Dropout rate slightly increased from 9.9 % in 2010/2011 to 10.2% in 2011/2012 slightly missing the 10% target in the revised logframe (ESPR 2011/12). As with the survival rates mentioned above it is unclear at this point whether increased drop out is as a result of the worsening economic situation in Malawi over the period (in times of economic stress families with low disposable incomes are more likely to take children out of school due as the costs of sending them and the opportunity costs of them not working become too much to bear) or better data collection and reporting or a combination of the two. It is clear that further support needs to be given to MoEST to improve EMIS so we can be certain of the reliability of data. There is discussion amongst DPs about how best to do this and UNESCO’s International Institute for Education Planning (IIEP visited Malawi in August 2012 and have shown interest. DFID will consider how best we can add support the strengthening of EMIS in the next round of education support. / Indicator 3.2: Unit costs (in Malawi Kwacha, and as a percentage of GDP per capita) by level of education, with 'unit cost' meaning public recurrent expenditure per student per year. MK 4,400 (12%) Primary, MK 20,000 (55%) Secondary and MK 400,000 (1,100%) University / The data shows that the unit cost rose in 2012 to MWK 6,244 at primary level and MWK 28,206 at secondary level above targets in the logframe. At the time of this review, there was no information on unit costs for university education and what percentages primary and secondary education unit costs are of the GDP. However, the increase in expenditure at the primary level is particularly welcome as this was recognised as being too low and contributed to the inequalities in the system. University fees at MK55, 000continues to be unacceptably higher than primary and secondary perpetuating the inequity in the system. Although this is an increase from MK24000, it hardly reduces the enormous subsidy that the government provides to the sub sector. More work clearly needs to be done to reduce inequality and increase the expenditure at the lower levels of education, particularly in the lower grades. DFID is working with all stakeholders to support this agenda. / Indicator 3.3: Timing of approval of the annual work programme, education sector budget, and the procurement plan. Milestone for 2011/12: all three approved by 30-7-12. / This milestone was partially achieved; two of the three key documents were in place on time. The ESPR 2011/12 indicates that the procurement plan was updated in March 2012 aimed at both clearing the backlog in procurement, and in setting new and realistic targets. However, the procurement and delivery of many goods and services that were planned for 2011/12 delivery, especially TLMs, were actually procured in the 2012/13 year. The education sector supplementary budget was presented to parliament in February and approved in March 2012. / Capacity building has been enforced through regular training in activity based budgeting, financial management and procurement. During the budgeting workshops staff from all cost centres are trained in Medium Expenditure planning since three year rolling programmes of work (POW) have to be compiled and costed. POWs draw directly on the ESIP and Procurement workshops are combined with budgeting workshops since POWs are linked to the procurement plan. The activity based budget in turn is linked directly to the POW to ensure the implementation of the ESIP/NESP and in order to align budgeting to sector priorities. Workshops on financial risk management have been carried out. / In the course of the decentralization of payment processing away from HQ to the central regions 20 officers have been trained to master the Integrated Financial Management Information System.
Progress against expected results: / All stakeholders interviewed for the annual review agreed that governance and management of the education sector has improved dramatically through the SWAp and pool fund structures. “With the pool fund, the education landscape in Malawi is transforming” (Director Basic Education). Technical Working Groups and the Sector Working Group are meeting on a quarterly basis, albeit focussed on activity implementation rather than progress towards targets and results. MoEST staff report great satisfaction with the pool fund - “with the pool fund the Ministry can spell out its priorities” - and with the predictability of fund flows. Budget execution has also improved. Key to improved management in MoEST has been the filling of almost all senior posts. At the same time, frustration appears to be growing at the constraints imposed by development partners through the eligible expenditures outlined in the Joint Financing Agreement. / Despite these positive developments, challenges remain. DPs continue to operate different disbursement triggers for the pool fund which both defies the purpose of the instrument and undermines the ability of DPs to influence policy. The Chair of the DP Group commented on the scope to improve the alignment of external resources to the national education plan and to better capture DP resources on budget. / Repetition rates have not improved and although unit costs seem to have risen, the net value of these amount could be lower (bearing in mind the impact of 49% devaluation) / Recommendations: DFID should work in the coming months to explore the potential for the development of a small number of mutually agreed pool fund disbursement triggers; and as Co-Chair of the Donor Group to support MoEST (to ensure the next Joint Sector Review and budget review meetings are more focussed on assessing results achieved rather than activities implemented. / DFID working with other DPs to instigate a discussion with MOEST on how to tackle repetition, make expenditures at different levels of education more equitable. / Impact Weighting (%): 30% / Revised since last Annual Review? No / Risk rating: High / Revised since last Annual Review? No

## Section B: Results and Value for Money.

1. Progress and results
1.1 Has the logframe been updated since last review? No / The original log-fame was approved, as Annex A to the Programme Memorandum, in January 2010. When errors in the baseline data were found, and more appropriate 2009 data became available, the logframe was revised in June 2010, and again in October 2010. The latest of these versions is used in this Annual Review. / 1.2 Overall Output Score & Description: A+ (Outputs moderately exceeded expectation) / 1.3 Direct feedback from beneficiaries / ‘Beneficiaries’ of this project are primarily the Ministry of Education, Science and Technology (MoEST) of the Government of Malawi, and indirectly the children of Malawi and their parents. Direct feedback was sought from key officials in the MoEST as well as all major pooled and discrete donors. Field visits were undertaken to three schools during the course of the review. Indirect feedback from beneficiaries is available in the quarterly SWAp progress reports and in the annual performance reports produced by MoEST. The overwhelming feedback was positive from those interviewed with general consensus that the move from projectised funding to a SWAp had helped build capacity at MoEST. There was also consensus that improvements in service delivery are slowly being felt particularly as more textbooks and teachers are arriving in classrooms and more money is flowing directly to schools through improvement grants. The increased autonomy that the latter brings was widely praised by MoEST officials and the head teachers consulted with.
1.4 Summary of overall progress / In conclusion seven of the milestones on the nine indicators have been fully achieved, one partially achieved (3.3) and one has not been achieved (3.1). There has been marked improvement over the past year in the speed of classroom construction, the numbers of teacher’s trained, the numbers of children transitioning to secondary education, services for out of school children through Complementary Basic Education, the numbers of schools receiving and utilising school grants, measuring learning outcomes and management of the education SWAp.
1.5 Key challenges / Although the pace of reform is increasing challenges remain in the form of translating the inputs into measurable learning gains for school children in Malawi. Learning outcomes remain low as the 2010 and 2011 EGRAs attest to. 97.1% of Standard 2 learners and 69.3% of learners in Standard 4 are unable to answer a single comprehension question correctly. Drop out and repetition rates are persistent problems no doubt exacerbated by the high pupil to teacher ratios in the early grades. As PTR is calculated as an average over the eight primary grades the figures mask the reality that the average PTR in grade 1 in 2012 was 153 compared to 42 in grade 8. Inequalities also remain within the system with expenditure at tertiary level 169.5 times that of primary level. Finally challenges remain in raising levels of girls’ attainment at all levels of education despite having achieved 1:1 gender parity up to grade 5.
1.6 Annual Outcome Assessment / The goal of the Malawi Education Sector Reform Programme (MESRP) is the achievement of MDGs 2 and 3 – universal primary education, and gender parity in primary and secondary school enrolment. This last year has seen further progress towards equal numbers of boys and girls being enrolled in school, in successively higher grades. But the country is still far from achieving universal enrolment in primary education. The Net Enrolment Ratio listed in the 2012 EMIS is 112% which cannot be the case as by definition the NER cannot be over 100%. This also puts into question the validity and credibility of EMIS data. The primary school completion rate is estimated at between 54% and 59% but again the lack of census data mean it is difficult to supply accurate figures. Meanwhile, there are 770,000 repeaters in primary schools, occupying the places that should be taken by the 600,000 children aged 6-13 who are out-of-school, mostly having started in Standard One but having dropped out along the way. That said, great strides have been made in addressing the educational needs of out-of-school children through Complementary Basic Education centres which now total over 600 nationwide. The accelerated programme has been held up as a model for use across the region.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Yes / Over £46 million of the committed £50 million for this programme had been disbursed by June 2013 representing 93% of the approved commitment spent for the duration of the project. An extension is being sought to allow DFID an additional year in which to continue SBS whilst at the same time investigating areas of good and poor performance in order to target the MESRP successor programme to build on what is working well, address critical gaps and achieve improvements in learning outcomes. / 2.2 Key cost drivers / The programme design identified construction costs as being the key area which could drive costs during implementation. As a result of the devaluation of the kwacha and the lack of availability of Forex construction costs rose significantly over the period which had an effect on classroom construction through EIMU. As a result many contractors were unable to complete construction and a total of 208 classrooms went unfinished and contracts lapsed. The present position is that the MoEST is working to resolve the impasse with contractors and expects the sites to be completed within the next six (by December, 2013) months. If the extension to MESRP is granted DFID has set the completion of the outstanding classrooms as a trigger for the release of funds. / However classroom construction managed to exceed targets through the use of the Local Development Fund which uses local contributions (in the form of bricks and labour) and has unit costs much lower than those of EIMU constructed classrooms. / 2.3 Is the project on-track against original timescale: Yes / The project was approved by the DFID Minister of State in the UK in January 2010. The first disbursement, a £3 million bridging grant, was made in March 2010 to complete classrooms under the previous education programme.. £11.7m was disbursed in 10/11 (£2.33m held back from government due to poor performance on three of nine reform agendas) and £14m was disbursed in 2011/12 We are seeking a 12 month extension to the programme to include another year of SBS and research and analysis that will give us the critical information and understanding that will inform the design of any successor programme to MESRP.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project / Since the start of the education SWAp in March 2010 there has been increasing recognition that MoEST and DPs needed to have a clearer focus on the measurement of learning outcomes (rather than solely inputs). In addition it was realised that the summative assessments at the end of primary (PSLCE) and secondary (MSCE) are not the best ways of measuring learning, particularly in a context where a large proportion of the initial school population will already have dropped out by grade 8. Measuring learning outcomes was itself a priority area in the Education Sector Implementation Plan and good progress has been made in this area through USAID’s EGRA in 2010 and 2011. However the USAID sample size is limited (1000 in 2010 and 3000 children in 2011 respectively from a primary school population of over 4 million). Whilst DFID welcomes the use of EGRA, we will also look into the possibility of conducting broader scale community led assessments of learning in future programmes both in order to have a measure of learning whilst also building demand-side accountability. Additionally, DFID will work with MOEST and DPs to critically examine how we can better ensure inputs translate into increased learning outcomes and improved results especially as we design a successor programme our upcoming education programmes in Malawi. / 3.2 Where an evaluation is planned, what progress has been made? / The programme document for MESRP provides for regular monitoring and evaluation of progress, but not for a specific impact evaluation. An independent review of the progress of ESIP was undertaken in mid-2012 (funded by GIZ) on behalf of MoEST and DPs and, in line with DFID’s findings in this Annual Review was positive on the progress of the SWAp and increased capacity of MoEST to deliver but less so on the learning outcomes. The Education Sector Implementation Plan (ESIP) period expires in June 2013, and the design of next phase, ESIP II, is nearing completion by MoEST (with extensive involvement of DPs including DFID). / In addition there have been three sector wide appraisals (one undertaken annually). Individual donors have also undertaken small scale evaluations of specific parts of the programme in line with their strategic priorities (e.g. the World Bank has looked at the performance of the school grants, Open and Distance Learning model for teacher training, construction through LDF, JICA has undertaken a study of the modality of delivering secondary education, USAID on the literacy rates through EGRA, KfW on the infrastructure through EIMU, UNICEF on the impact of the SWAp on girls education). Therefore the need for another evaluation is low. / What is needed however is a more in-depth analysis of why the sector performed well or poorly in certain areas combined with an analysis of the formal and informal rules of the sector which enable or hinder progress. This will be commissioned by DFID over the course of the extension through a sector wide Political Economy Analysis and Public Expenditure Tracking Survey.

4. Risk
4.1 Output Risk Rating: High / 4.2 Assessment of the risk level / The risk rating remains high, given the economic context and the scale of the education sector in Malawi. Fiduciary risk with regard to budget credibility is assessed by the national FRA to be substantial. Expenditure performance in comparison to original budgets at disaggregated levels of expenditure continues to be weak. Fiduciary risk with regard to comprehensiveness and transparency of budgeting is assessed by the national FRA to be on the higher end of moderate. There are weaknesses with regard to the reporting of budget plans and activities of sub vented education institutions. / A Fiduciary Risk Assessment of the sector is currently underway and DFID will take the findings into account as going forward.
Risk of funds not being used as intended / The World Bank, in its role as Supervising Entity for the Global Partnership for Education (previously known as the Fast Track Initiative), exercises fiduciary oversight of the pooled fund on behalf of DFID and the other donor agencies. Two independent financial audits have been undertaken on the SWAp by Pricewaterhouse Coopers. The latest showed considerable improvement on the first; evidence of increasing capacity within MoEST. All of the pooled funds were accounted for and a much broader sample undertaken. A procurement audit is currently underway with the results expected later this year. DFID, together with the World Bank, will keep a close eye on both processes and continue to monitor risks through our presence in the Technical Working Groups and as Co-Chair of the DP group. / 4.4 Climate and Environment Risk / The most significant environmental risks are those related to the construction of school infrastructure. The Ministry’s Education Infrastructure Management Unit (EIMU), which DFID supported from 2008-11, has insisted that contractors use stabilised soil blocks (SSBs) rather than burnt bricks. However the LDF is now undertaking the majority of classroom construction which has environmental implications as they use burnt bricks prepared by local communities for construction. However they are currently trialling the use of SSBs in 100 locations with the intention of extending the use of SSBs countrywide. This will drastically reduce the environmental impacts of primary construction. The World Bank exercises close environmental scrutiny over all construction financed through the Ed.SWAp pooled fund and conducts regular site monitoring to this end.

5. Value for Money
5.1 Performance on VfM measures / Economy - Malawi has one of the lowest unit costs for primary education per child per annum in the countries DFID supports. However as Malawi moves towards a ratio of 1 textbook per child DFID expects costs to increase here and accepts this is a necessary increase in order to increase quality. Costs of classrooms are above average for DFID supported countries however new approaches, such as community construction through the Local Development Fund, have led to substantial cost savings. Further investigation is underway to ensure these savings will hold in the long term in regards the durability of LDF construction. / Efficiency – Survival rates and primary completion rates in Malawi are low which compromises the efficiency of the system. DFID is working closely with other DPs and MoEST to better understand how to tackle these inefficiencies and ensure that adequate inputs such as classrooms, teachers and teaching and learning materials are provided at reasonable costs. / Effectiveness- Learning outcomes are also low though progress is being made and learning is being consistently tracked for the first time in Malawi. DFID will continue to support a growing emphasis on learning outcomes whilst also investigating what more we and others can do to support this process. / 5.2 Commercial Improvement and Value for Money / The World Bank is leading for DFID and other Development Partners on procurement and financial oversight. A financial improvement plan is in place, with supervision and training, to improve practice and performance. A procurement audit is currently underway for the first time since the SWAp began and the results expected later in the year. DPs have noted dramatic improvements in the speed and scale of procurement since late 2012 through a combination of staff changes and increased focus on procurement within MoEST. DFID will work closely with the World Bank to ensure these positive changes continue and the procurement plans are realised. / 5.3 Role of project partners ; / The key partner for MESRP is the MOEST who are responsible for settling policy and ensuring delivery of basic services. Other partners are those in the Pooled Fund- World Bank, Germany, and Global Partnership for Education (GPE) all of whom are interested in managing fiduciary risks and improved financial management. There has been increasing harmonisation amongst DPs in recognition of the fact the better alignment should improve results in the sector. DFID is currently Co-Chair of the DPs group in conjunction with UNICEF as the Chair. Through this role DFID is pushing the harmonisation agenda and is receiving positive feedback form all stakeholders (pooled and discrete funders as well as MoEST). Plans are afoot to increase harmonisation of disbursements through ESIP II and DFID will continue to push for this to improve aid effectiveness. / There are also several discrete funders, the main ones being USAID, UNICEF and GIZ who contribute significant funds and technical assistance to the sector and to the MOEST. DFID is seeing increased engagement between MOEST and DPs ( in particular poled partners) and discrete partners. / 5.4 Does the project still represent Value for Money : Yes / The investment continues to represent value for money as it is a systems approach and provides benefits wider than directly measured in the logframe such as helping pool resources together, taking a sector wide priorities. and enhances state government ownership and state legitimacy. It strengthens the delivery system in addition to achieving concrete deliverables such as classrooms, teachers and textbooks. A SWAP approach also presents the best opportunity for improving learning outcomes. Together with DFID’s Keeping Girls in School programme and the construction of Phalombe Teacher Training College SBS is enabling DFID simultaneously to focus on the broader supply side issues facing the education sector as well as tackling critical problems such as girls education which should help improve gender parity at primary and secondary level.

6. Conditionality
6.1 Update on specific conditions / Prior to approval of DFID’s programme, a set of benchmarks were negotiated and agreed to serve as triggers for release of the £7 million in July and £7 million in December of government year. The July disbursement is triggered by Government of Malawi meeting two key budget commitments: (i) At least 20% of the recurrent Government budget allocated and spent on education, each year from 2010/11, with donor funds for education additional to the spending from domestic revenues: (ii) At least 60% of the education budget goes to primary education: and (iii) an additional trigger of 90% of budgeted funds for education released by Treasury (Ministry of Finance) and actually spent within the financial year. These main two triggers were met in 2011/12.

7. Conclusions and actions
Overall the project has scored an A in recognition of meeting (and in many cases exceeding targets) in seven out of nine indicators. It is clear that the pool fund and SWAp structures are an enormous improvement on the standalone project modalities that predominated before. There was widespread consensus among interviewees for the annual review that the structures work and that they enable reasonably effective dialogue to take place in the sector. This said, as recognised by a number of development partners, there is considerable scope for much improved coordination and collaboration among the development partners. / ESIP II offers an opportunity to redefine and agree key priorities in the sector and there is scope to develop a roadmap for improving aid effectiveness. It also offers an opportunity to strengthen the focus on what and how children are learning in addition to continued delivery of critical inputs and facilities such as classrooms, teachers, teaching and learning materials. At the same time, as the MoEST gains confidence in its leadership, it is to be expected that it may want to understand how the pool fund can evolve and this should be encouraged. / Irrespective of the WB’s role in fiduciary risk monitoring, DFID Malawi should consider its own emphasis on monitoring and managing pool fund risks. The most recent FRA (2011) shows substantial risk across all assessment areas except one. An updated FRA is currently underway and a Financial Management Improvement Plan in place, agreed with DPs and MoEST. A procurement audit is underway and will be subject to the scrutiny of all pool fund partners so that areas of weakness can be identified and appropriate measures taken. With many bilateral donors now adopting a “zero tolerance” approach to fraud and corruption, even relatively minor fraud or financial mis-management could have a devastating impact on the education pool fund leading to the withdrawal of funds. Learning from the DFID Kenya education programme fraud alongside a robust approach to risk and financial management in the pool fund, DFID Malawi will consider in the MESRP successor programme spreading risk by programming some resources outside of the pool fund.

8. Review Process
This Annual Review was conducted in-house by DFID Malawi staff, The review team also included Education Advisers and Programme Managers from the Human Development Team with support from Sandra Barton, Education Adviser, DFID Kenya ( Over the period 27/05/13 – 31/05/13,) / The report was reviewed by the DFID Malawi HDT Team Leader and the Programme Board and approved by the Deputy Head of Office of DFID Malawi.