Annual Review - Summary Sheet

Title: Assets to Adolescent Girl’s Programme (SPRING)
Programme Value: £16,436,037		Review Date: 17/12/2018
Programme Code: 203375	Start Date: 17/12/2013	End Date: 31/03/2022

Summary of Programme Performance
Year	2014	2015	2016	2017	2018
Programme Score	A	A	A+	A	A+
Risk Rating	High	High	High	High	High

DevTracker Link to Business Case:	Business Case
DevTracker Link to Log frame:	Logframe

A. Summary and Overview

Description of programme

SPRING has worked with 75 businesses in nine countries, attracting $9.8m[1] of investment and has reached 589,994[2] adolescent girls and women.
[1] This is comprised of both grant financing and commercial investment
[2] 515,680 came from one business in Tanzania and the 74,314 came from the other SPRING businesses.

The SPRING programme works as a business accelerator. It identifies ventures in low income countries with products and services that can improve the lives of girls and provide support to these businesses to enable them to reach girls at scale. The support provided includes funding but also access to mentors, expertise and peer-to-peer learning to help drive their business models forward. The businesses supported by SPRING will have products that help girls to learn, earn, save, and stay safe. SPRING is funded by DFID, DFAT, and USAID (and, formerly, Nike Foundation). To date SPRING has supported 75 businesses across four Cohorts in nine countries between East Africa and South Asia. SPRING has supported these businesses to attract investment and reach adolescent girls and women through their SPRING prototype (goods and services) either as part of the value chain or as end users.

Three cohorts of businesses have completed the SPRING programme, with the end of Cohort 4 events planned in early 2019. SPRING has also provided support to businesses to attract investment. The next year will see SPRING focus on monitoring and evaluation (M&E). This phase will evaluate business performance, and the impact of businesses on adolescent girls and women after leaving SPRING.

The economic empowerment of girls and women is a strategic priority. DFID’s Business Plan (2011-15) highlights the critical role of wealth creation and gender equality in poverty reduction. DFID’s Strategic Vision for Gender Equality highlights women’s economic empowerment (especially access to assets) as crucial to gender equality. The Economic Development Strategic Framework also emphasises improved access to markets, finance, property and employment opportunities for girls and women.

Summary supporting narrative for the overall score in this review

SPRING continues to deliver, and has exceeded all the logframe milestones. SPRING has demonstrated continuous improvement in programme delivery. This has resulted in a streamlined business selection process, increased quality of training for the businesses and effective management of resources.

SPRING has established itself as a unique business accelerator programme; not only in its focus to support businesses to provide products and services for adolescent girls, but also in the hands-on, tailored support provided to businesses. Through its learnings, SPRING has developed a greater understanding of the types of businesses and business models which are most likely to benefit from the accelerator, allowing SPRING to maximise impact and generate efficiencies in delivery.

Over the last year SPRING has increased its effort to support businesses to attract outside investment. This was made possible by the introduction in April 2018 of additional activities which consist of a Go-To-Market Business Assistance Fund (BAF) and Capital Raising Support. These were offered to selected SPRING businesses to advance their prototypes and attract investment. It is intended that this additional support to businesses should attract debt and equity investments from more traditional investors alongside grant financing. This Annual Review has considered SPRING’s performance and portfolio; drawing on specific interviews held with beneficiaries in Nepal and Myanmar.

Recommendations for the year ahead:

SPRING (in collaboration with the M&E partner) should seek to strengthen the businesses’ ability to collect and verify disaggregated data on the impact to adolescent girls- in terms of direct and indirect impact (as defined within the SPRING programme documents) and where possible by income, to better understand the girls reached.

SPRING should develop a clear justification for the type of knowledge products produced, detailing the intended audience and expected impact. This should consider resource availability and cost effectiveness within the coming year. This will help better share the lessons from SPRING.

In order to understand the effect SPRING has on the wider economy, SPRING’s M&E partner should review the programme’s wider impact on the markets the businesses operate in. This should be included in the M&E strategy to be finalised this year.

SPRING should develop a strategy to create an alumni network within the next 6 months. SPRING should form collaborations within the cohorts, especially where there is a crossover between markets, users or products, to strengthen business sustainability and share lessons and therefore improve girl impact.

The programme is a hands-on resource intensive accelerator. SPRING should establish which activities are crucial to having girl impact and therefore mandatory, and which are desirable.

SPRING’s M&E partner should consider comparing SPRING to other accelerators before the next annual review to inform what elements would be best adopted by other programmes in DFID.

## B: DETAILED OUTPUT SCORING

Output Title	SPRING participants reach adolescent girls
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Cumulative number of businesses that launch prototypes designed to reach and benefit adolescent girls through products, services or business models.	39 / (89% of C1, 60% of C2, and 68% of C3)	43 (94% of C1, 72% of C2, and 68% of C3)

Provide supporting narrative for the score

SPRING has exceeded the targets under this output and progress against this indicator has been strong. This indicator tracks the number of businesses that have launched prototypes which are designed to benefit adolescent girls. This indicator has been amended since the 2017 Annual Review to focus on prototype launch as opposed to increased girl reach which is captured elsewhere in the programme logframe. The indicator has also been amended away from “employability” of adolescent girls and women to adolescent girls and women in “business operations”. Of the businesses which sought to generate employment opportunities for girls in the value chain, it was found that a tension existed between continued education and employment in some cases.

SPRING supports cohorts to launch prototypes primarily by:

- Providing technical design and development support during the bootcamps
- Conducting research to inform prototype launch
- Releasing Prototype Development Funds (PDF) to businesses.

Measured at outcome level – SPRING has reached nearly 600,000 girls through the prototypes launched by SPRING businesses. The figures below show the breakdown of the adolescent girls and women reached, whether they are end user to value chain, and what the business helped the girls do better.

Businesses in the earlier cohorts, who have had the benefit of support from SPRING over a longer period of time, have been more successful in launching their prototype. Business selection has also improved over time which has allowed businesses in later cohorts to be better positioned to launch. By the end of August 2018, 16 additional businesses had launched their SPRING prototypes, adding to the total of 43 businesses. This is made up of three businesses from Cohort 2 and 13 from Cohort 3.

For Cohort 3, Prototype Development Funds (PDF) were allocated and disbursed after Bootcamp 2 in September 2017. All businesses that launched in 2017-2018 relied on SPRING to fund their launch. The two businesses that did not receive prototype funding are not expected to launch. Like Cohort 2, a subset of businesses benefited from small grants (ranging from £1,000-£7,000) in addition to research support, enabling them to test their prototypes with real user feedback.

When reviewing launch dates across cohorts 1-3, it is clear that the time it takes to launch a prototype has increased significantly. The increase time taken for prototype launch within a set period is noted in 94% prototype launch by end of cohort in C1 to 47% by the same time in C3. Simultaneously the viability of prototypes launched has increased, with 92% of Cohort 2 prototypes still in market after two years compared with 76% of those for Cohort 1. These improvements have been the result of substantial revisions to the SPRING programme design.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges, in order of priority:

It was found that for some businesses, whilst impact on girls was the original intention, (e.g. R&D Innovation - Nepal), it was recognised that girls may not be a suitable direct audience for the prototype. This meant the focus of the SPRING prototype shifted to girls as an indirect beneficiary. SPRING reporting to DFID does not make clear how it is accounting for girls reached especially where girls are indirect beneficiaries.

In addition to receiving funding, factors such as changes in a company’s structure, product revisions or market constraints affected the likelihood and timing of prototype launch.

Although each year SPRING has refined the processes for PDF allocation there is still a delay between businesses applying funds and them being released. As Cohort 4 is nearing completion such delays reduce the overall SPRING support to launch the prototype successfully, as well as potential loss of momentum following the bootcamp.

Key recommendations, in order of priority:

For those businesses identified as having an indirect impact on girls, SPRING should better communicate to businesses a clear understanding on how indirect impact data is collected, verified and reported on and where possible broken down by income. This should be completed over the next year as part of the M&E strategy.

In some cases, SPRING has created collaborations between businesses such as 1) Build-up Nepal and Doh Eain and 2) R&D, Smart Panni and Build-up Nepal. These collaborations could be very successful in improving the sustainability of business prototypes and increase market presence which could lead to enhanced impact on girls. Over the next year SPRING should actively consider establishing collaborations where possible and have a method to support them. This could also form part of the offer to SPRING alumni.

Cohort 4 is SPRING’s last cohort therefore, it is recommended SPRING captures lessons learned in the legacy plan next year to maximise the dissemination of lessons to the wider eco-system and DFID.

Going forwards SPRING should collaborate with its M&E partner closely to understand what makes businesses able to sustain prototypes as part of the business and continue to reach girls.

- SPRING should compare their performance, added value and effectiveness in terms of value for money (VfM) and impact against other business accelerators to capture stand-out features.
Output Title	SPRING participants improve their investor-readiness
Output number per LF		2	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number (% in brackets) of participants who have improved their investment readiness.	18	20 / (22% C1, 50% C2, 37% C3)

Provide supporting narrative for the score

The targets under this output have been met. This indicator measures the number of businesses with improved investor readiness. It is important to note that not every business within SPRING will ultimately seek external investment in order to grow financially; as such this indicator only considers one form of financial growth.
Case study:

Over the past year, seven businesses (all within Cohort 3) have improved their investment readiness, bringing the total to 20 businesses to date. In order to measure investor readiness, SPRING has developed a scoring mechanism to ascertain the degree of readiness for each business. This includes things like the existence of a pitch deck.

While some businesses from previous cohorts (such as Fightback, Smart Paani, R&D and Sehat Kahani) have continued to receive investment readiness support in the past year, these businesses were all counted previously, and are therefore not eligible to be counted again. In addition, some businesses were not included as they were not identified by SPRING as contributing to this output and were not given a baseline score. These business from Cohort 3 have since received investment readiness support and are likely to have improved their readiness since the start of SPRING.

Key changes made in the past year to SPRING’s investment readiness offerings included:

1. Appointing Regional Investment Managers in both South Asia and East Africa, and
2. Greater availability of support for paid services for a select group of high-potential businesses (and therefore less reliance on pro-bono and low-bono support)

SPRING provides investment readiness support primarily through the country manager role. In some cases, the country manager has built close ties with businesses from previous cohorts. These relationships are maintained after businesses graduate from SPRING and in some cases they continue to receive occasional ad-hoc support from the country managers. This demonstrates the importance of the country manager’s role, but also the degree of tailored, flexible support received by the businesses.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges, in order of priority:

The investment climate appears more mature in East Africa compared to South Asia. However, the South Asia SPRING businesses are readier for investment and their fundraising timeline is better aligned to the programme delivery. Cohort 1 (East Africa) reflects the greatest amount of SPRING’s total attributable investment to date, but Cohort 3 (East Africa) is on track to outperform its previous counterparts. SPRING attributes Cohort 3’s enhanced performance on investment to 1) an improved programme selection process, and 2) more tailored support.

SPRING has also found that more mainstream investment occurred following the grant funding provided through the programme. This demonstrates the importance of the support SPRING provides on capital sequencing and capacity building for social ventures.

Key recommendations, in order of priority:

SPRING’s M&E partner should continue to focus on the businesses seeking external investment to demonstrate success, but could develop a way to recognise the overall financial growth of a business. This should form part of the M&E strategy before the next annual review.

SPRING has developed an investment readiness checklist which evaluates each business, in each set of scorecards there are several instances where scores are given without a narrative explanation for the score. One business scored 20 (out of a maximum of 22) with no justification provided for any score. A lack of recorded evidence makes it hard for SPRING to account for the scores it awards the businesses. SPRING should support the scores with narrative evidence for each of the current businesses over the next 6 months.

The programme should consider greater monitoring of investment readiness support and how it can contribute to longer-term business growth and sustainability and therefore, girl reach.

Country managers often continue to support businesses following their graduation from SPRING. There is a risk that businesses in later cohorts may receive less than previous cohorts. This may mean a drop in results achieved if country managers do not manage their time appropriately. SPRING should establish mechanisms to support country manager’s time management between businesses, and if needed define a clear support cut-off point over.

SPRING should monitor improvement in investment readiness post-cohort for those receiving support through the additional activities, whilst recognising that those seeking investment readiness later may not benefit equally from the same regular country manager support.

Whilst the calibre of the team is strong, SPRING’s continued delivery is at risk should country or investor managers leave the programme. Much of SPRING’s success is due to an individual’s professional network and relationships. SPRING should look to mitigate against risks, by developing a contacts database, filterable by country and sectors. SPRING should also ensure there is a clear handover process in place. This should be done over the next 6 months.

Output Title	Participants benefit from Human Centred Design (HCD) and other forms of SPRING TA to improve business viability and develop products and services benefiting girls
Output number per LF		3	Output Score	A+
Impact weighting (%):		25%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
3.1 Number (% in brackets) of participants who report satisfaction with the HCD and other technical assistance provided through SPRING.	45 (100% in C1, 78% in C2 and 70% in C3)	48 / 100% C1 78% C2 84% C3
3.2 Number (% in brackets) of participants who use HCD to refine their business model, product or service to meet the needs of target girls.	44 (89% in C1, 75% in C2 and C3) – see Document ‘Summary of TOC and Logframe changes’ for rationale for each of these	49 / (89% in C1 / 78% in C2 100% in C3)

Provide supporting narrative for the score

This year, targets under this output have exceeded expectations. Scoring against Output Indicator 3.1 is based on responses to surveys and interviews conducted by evaluation partner Coffey International at the end of cohort event. All of the Cohort 3 survey respondents indicated that they were ‘satisfied’ (56%) or ‘very satisfied’ (44%) overall, with the technical assistance provided by SPRING. The programme is well received, with many businesses stating they would not have reached the same business understanding and maturity without SPRING. Additionally, from those businesses interviewed many expressed satisfaction in SPRING’s unique “hands-on approach” and quality of tailored technical assistance provided.

Output Indicator 3.2, which measures the number of businesses who used human centred design (the approach used by the SPRING) to refine their business model. SPRING has achieved this output with 49 participants providing evidence that shows they have adopted Human Centred Design (HCD) to further refine their business model.

As SPRING is an experimental programme, the programme delivery and type of businesses selected for each cohort has evolved, particularly during the last Annual Review period. Cohort 1’s portfolio largely consisted of younger social enterprises, which were deemed as too early-stage to be able to effectively achieve girl impact. As a result, Cohort 2 included more mature businesses, however, the lack of entrepreneur engagement and business flexibility responded less well to the SPRING model. Through this process SPRING has been able to clearly define the type and scale of business which will benefit the most from participating in the SPRING accelerator. The changing focus between the cohorts is reflected in the businesses reported satisfaction as well as an improvement in the number of businesses refining their business model. All of Cohort 3 businesses used human centred design to refine their prototype.

SPRING has also made improvements in the accelerator curriculum. These include: a new bootcamp modules (marketing/messaging, pitch/storytelling, country-specific girl insights), engaging specialists on messaging, and introducing a ‘Bootcamp 0’ for select businesses.

Feedback from businesses has been frank and honest and is confidential. This means that businesses are not overreporting satisfaction because they think it will affect their funding allocation. SPRING also confirmed that satisfaction is scored after funds are awarded. Although this could mean partners who do not receive the PDF funding are less likely to complete the survey.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges, in order of priority:

A key challenge to the model is the participants ability to encourage other parts of the business to adopt the HCD approach and if they were to leave their business the knowledge built up through the SPRING programme could be lost.

The programme has trained moderators on HCD research in the SPRING countries. SPRING considers this training to have already provided VfM as moderators can put this training to use locally. However, HCD is still considered innovative and the demand for future HCD research may be limited.

Key recommendations, in order of priority:

It is recommended that the M&E phase tracks whether the local moderators have continued to implement HCD research and whether it is believed to have an impact on the success of products and services in the wider ecosystem as a result. This should be considered by the M&E Partner over the next six months.

SPRING should synthesise key lessons from conducting HCD research (and engaging local moderators/stakeholders) and incorporate these into the final report for future programmes to benefit from SPRING’s experience over the coming year.

SPRING seeks to provide innovative solutions to adolescent girls who remain an underserved market. In developing the M&E strategy, SPRING should consider measuring the secondary impact SPRING has had on local markets and whether competitors have also entered the same market as a result of the SPRING prototypes. This should be done over the next 6 months.

Output Title	Ecosystem stimulation for products and services benefitting adolescent girls.
Output number per LF		4	Output Score	A
Impact weighting (%):		25%	Impact weighting % revised since last AR?	0%

Indicator(s)	Milestones	Progress
4.1 Number of communications products with evidence and/or lessons learned produced and disseminated by implementing partner.	26	31
4.2 Amount of value-add (in-kind and cash) contributions raised by SPRING implementing partner	N/A	£1,103,922

Provide supporting narrative for the score

This output has met targets for this year. SPRING has demonstrated a clear method of capturing and implementing lessons learnt in the programme. The focus of Output Indicator 4.1 is to measure the increase in knowledge and understanding of how to support the development of goods and services for adolescent girls using SPRING-like accelerator models. Over the last reporting period, SPRING has developed a legacy plan primarily aimed at investors and donors. The plan has three key knowledge sharing outcomes:

    - Lessons from the SPRING model,
    - Lessons from the Human Centered Design approach,
    - Lessons from focusing on girls as end-users.

During the reporting period, SPRING has produced 13 knowledge products through participation in global and local conferences and by hosting events, producing videos as well as publishing articles and blogs.

SPRING also raises funds through in-kind contributions and cash, this is captured under output indicator 4.2. Whilst there is no set milestone this year, SPRING continues to benefit from in-kind support of corporate partners such as Hogan Lovells and Deutsche Bank. At the point of reporting, the programme has now met and exceeded its August 2017 milestone target of £750,000 by 47%. The majority (90%) of the amount raised to date has been through in-kind/pro-bono support and 9% through negotiated savings/low bono support.

Lessons identified this year, and recommendations for the year ahead linked to this output

Key challenges, in order of priority:

SPRING’s knowledge products can vary from an online blog to a large-scale event. These count towards the indicator target equally even though some will have a much greater impact than others. In addition, SPRING does not consider VfM in terms of resource input and impact when deciding which knowledge product to develop.

SPRING’s reported figure against output 4.2 met its target last year and therefore has not increased this year. It has been suggested that hitting these targets early allowed SPRING to pursue more innovative business in Cohort 4. DFID should balance targets which push partners to deliver the best VfM, while allowing them to focus equally on the development impact of the programme.

Key recommendations, in order of priority:

During the next reporting period SPRING should focus on knowledge capturing and dissemination. Indicator 4.1 provides only numerical targets to SPRING and does not define type of knowledge products required or target audience. SPRING should develop the legacy plan with reference to intended impact, available resources and VfM of each knowledge product.

SPRING should develop methods of tracking the impact of knowledge product to refine the delivery of the legacy plan; this could be in terms of number of views, subsequent meetings or follow-up.

The focus for the SPRING legacy plan is currently to demonstrate to investors and donors the viability of girls and women as end users. However, SPRING should consider targeting these knowledge products to social-enterprises to demonstrate the potential impact of reaching women and girls.

The SPRING alumni could play a key role in the proliferation of products and services for adolescent girls. As SPRING alumni continue to build their networks and sell the value for designing for adolescent girls, they may benefit from training in how to communicate and encourage other businesses to consider a similar route to market.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

The SPRING theory of change is presented below, with major changes from last year highlighted in red. Note that the theory of change itself has not changed; rather, the visual has been refined to better reflect what the programme is doing to achieve impact.

More details have been added to the inputs:

- At the programmatic level, the revised theory now highlights the components offered to each SPRING business;
- At the enterprise level, more details have been added to reflect the customised accelerator experience that has evolved over the lifetime of the programme. Under outputs, the launch of prototypes has been added to emphasise how businesses directly benefit from SPRING assistance, and avoid duplication with the outcome level focus on girl access.

Reflecting on feedback from the last AR, there is now a greater emphasis on sustainability. This demonstrates that SPRING not only catalyses the empowerment of girls over the long-term, but that businesses are also continuing to scale or maintain SPRING solutions for girls over time (and see the value of investing in girls and develop new solutions for them).

SPRING is on track to contribute to all outcomes and outputs, and it will spend this year focusing on consolidating the girl impact evidence base through its legacy plan. The programme appears on track to achieve its impact, and findings from SPRING M&E’s long-term evaluation programme will show whether girl beneficiaries improved outcomes linked to economic empowerment.

Major changes to the logframe in the past year

In February 2018, a revised logframe was finalised as a result of the 2017 Annual Review recommendations. Output 1 was reworded to “Cumulative number (% in brackets) of businesses that launch prototypes designed to reach and benefit adolescent girls through products, services or business models” (from “Cumulative number of participants that increase the number of girls reached with products and services or increase the number of girls involved in business operations). The new wording prevents duplication with the Outcome level indicator measuring “girls accessing SPRING products and services”. In practice, for girls to access products and services, businesses must first launch a SPRING prototype. Therefore, this change better aligns this indicator to the output level, while still maintaining an outcome level indicator that focuses on girl reach (Outcome Indicator 2).

Milestones under Output 2, Output 3.1 and Output Indicator 4.1 have increased to accommodate better than expected performance in previous years under these cumulative targets. Output Indicator 3.2 (“Cumulative number (% in brackets) of participants who use HCD to refines their business model, product or service to meet the needs of target girls”) was reduced as a smaller number of businesses than anticipated signed up to cohort 3.

Proposed changes to the logframe as a result of this review

There are no further changes planned to the logframe.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Economy (minimising input cost)
1. Contributions raised by SPRING through in-kind equivalent conditions (GBP)	£1,103,922 / This is addressed under output indicator 4.2.
2. Cumulative cost savings (GBP)	£104,514 / No change from last year.
Efficiency (conversion of inputs to outputs)
1. Percentage (%) of milestone deliverables met on time	To date, the programme has delivered 100% of its milestones on time. This has been achieved for another consecutive year.
2. Management costs as % of total costs	6.89% / This continues a downward trend from last year (7.18%) and the previous year (9%). SPRING has achieved this through active negotiation on rates (e.g. through a reduction in rental costs). The organisation is achieving economies of scale as it moves into final cohorts, and the fixed costs of the business become a lower share overall.
Effectiveness
1. Cost (GBP) per business compared with value delivered per business services	£21,842.74 per business / This is a slightly higher cost than last year (£17,456) primarily due to higher cost for bootcamps located in a different region.
2. Cost (in GBP) per girl reached	£23.99 / SPRING has achieved an impressive reduction in cost per girl reached over the past 12 months, declining from £542 (2016) to £318 (2017) to £23.99 (2018) as a cumulative total of girls reached and spend to date. / As per last year’s Annual Review recommendation, SPRING has provided additional perspective on the cost effectiveness of reaching girls by type of intervention (below). This demonstrates significantly higher cost in reaching girls through an “earn” intervention (i.e. in the value chain or with productive assets) while the average across other intervention categories is much lower, even when the outlier business of Ubongo excluded. / Earn interventions: £1764 per girl / All others: / £18 per girl with Ubongo. / £151 per girl without Ubongo included.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

The implementing partner has demonstrated numerous examples of where they have been able to minimise overheads, and have worked with businesses to ensure they are sustainable after SPRING’s involvement ends, and thus ensures the cost per beneficiary is low. Clearly, the programme is good VfM, with an overall average cost of £23.99 per girl reached. Splitting this by intervention demonstrates that, as would be expected, the interventions that have deeper impacts on girls cost more. Even these can be classed as good value investments, given the potential transformative impact they can have on girls.

The programme should continue to ensure that the lessons learned from all the different types of intervention are shared with DFID and other stakeholders. This stage will bring extra value to the programme that will impact the wider portfolio.

E: RISK

Overall risk rating: High and mitigation

SPRING is a high-risk programme. It has been explicitly designed to test assumptions and build evidence in an area where the evidence base is weak. The evidence on women’s access to and ownership of assets is clear in terms of development benefits, but evidence on adolescent girls is still not readily available. Moreover, using a private sector development approach to improve girls’ lives and help them learn, earn, save and stay safe is a novel approach. Rigorous M&E, and continuous focus on research are critical to the success of this initiative, given the experimental nature of programme design and the weak evidence base on interventions that work at scale to increase girl’s access to assets. Risks have been identified at programme delivery, output and outcome level as detailed below.

As SPRING moves from the current delivery phase to an M&E phase the risk register should be revisited to reflect risks relating to quality and data availability. Additionally, following the ending of the country manager’s contract, SPRING should consider a risk due to lack of in-country presence and potential loss of relationship with the businesses.

Overview of programme risk

Risk	Gross Risk	Mitigating Action	Residual Risk	Owner
Category: External Context
Security risks in countries of operation prevent programme from delivering objectives	Major	Regular security reviews and training for staff and country managers for SPRING. DFID to regularly update team on changes to duty of care risk assessments. DFID has liaised with the country office and undertook enhanced due iligence for Burma.	Moderate	Palladium
Macroeconomic risks – effect on grantee businesses and potential investors of domestic policy changes in target countries, exchange rate volatilities and policy changes in donor countries.	Moderate	Palladium will monitor these exogenous factors with the support of our country managers who have local intelligence in each country. They will identify opportunities to impact policy platforms to lobby for change as required.	Moderate	Palladium
Category: Safeguarding
Poor safeguarding of girls - Activities to directly engage adolescent girls in the programme are not implemented in a safe and appropriate way	Severe	Palladium have a Girls Safeguarding Advisor in place to oversee the implementation of the SPRING girls’ safeguarding policy including a Code of Conduct and a set of minimum standards to ensure that girls are kept safe. The Code of Conduct details a comprehensive set of policies, protocols, and reporting mechanisms which builds on Palladium’s global policy. Training to businesses is provided at bootcamp prior to signing their Grant Agreements. Grantees are subject to the same requirements as staff, subcontractors and consultants as detailed above. In addition, Grantees are required to commit to developing and implementing a girl safeguarding plan which will enable their own business to avoid or reduce risk to girls from business operations, products, and services.	Moderate	Palladium
Category: Delivery
Grantee Businesses are unable to reach girls with low incomes in a commercially viable way and there is limited traction of new-market based approach to reaching girls	Severe	Businesses are selected on the basis of having a pro-poor impact product or service. The evaluation team will continue to record estimates on the number of girls reached by each business that are considered BoP to ensure the pro-poor aspect of SPRING is captured in Impact Evaluations. All SPRING research and technical assistance provide at bootcamp, HCD research and throughout the programme focuses on testing commercially viable ways to reach girls.	Major	n/a – this is an inherent risk of the programme’s experimental design.
Grantee Business models are not commercially viable, or cannot attract sufficient investor interest in markets where investors are active	Severe	Accelerator activities – bootcamp, TA, mentors - are targeted at enabling relevant businesses to be investment ready. For some earlier stage businesses, this journey will take longer due to need to build capacity and generation of revenue. The Investment Director will be leading the investment process alongside the country managers and identifying the businesses to focus on for investment based on feasibility and readiness. Other activities include 1) a go-to market business assistance fund (BAF) which provides additional TA to selected businesses to unlock greater commercial success and 2) capital risk ranging from basic finical support to attend impact investment conferences to end to end support for capital raising.	Major	SPRING team
Lack of mentors for businesses – quality and quantity	Moderate	SPRING is revisiting their mentoring strategy based on feedback from entrepreneurs and mentors on time commitments. They are looking into other approaches such as sector-specific coaches and mentoring being part of the pro-bono support delivered through corporate partnerships.	Moderate	SPRING team
Timeliness of delivery – delays in implementation	Moderate	The programme is currently delivering to agreed timeframes as set out in programme ToRs. Timelines to be shared with all programme staff well in advance to facilitate planning.	Minor	Palladium
Lack of adequate communication budget, flexibility, or focus of SPRING at global level reduces effectiveness of outreach for the “ecosystem development” aspect of the programme.	Major	Develop a clear and measurable strategy to build awareness of SPRING with relevant audiences within and beyond specific focus countries. SPRING and donors needs to agree a dissemination plan for knowledge products, DFID SRO to facilitate donor alignment and rapid turnaround on communications activities approach.	Moderate	SPRING team
Category: Operational
DFID lacks admin and FLD resources to manage SPRING effectively	Severe	SPRING is now entering its fourth year of delivery and the time commitment required for detailed programme management is substantially reduced compared to earlier years.	Moderate	EIGT team leader
Poor succession management and handovers with DFID staff turnover	Major	DFID SRO will ensure the delivery plan is kept up to date and sufficiently detailed and the new programme manager is up to speed on the programme and all processes. EIGT team leader and GRD corporate team to ensure timely recruitment process in the case of staff turnover.	Minor	DFID SRO
Inefficient use of programme resources, especially staff time, as a result of weak programme management	Moderate	The team have successfully completed a restructure in 2016, with a new team leader and team in London. The recruitment of country managers and regional coordinators across South Asia and East Africa is also complete. Strong programme management systems are in place.	Minor	DFID SRO
Lack of alignment between SPRING donors	Major	This is a risk to manage particularly with the addition of a further donor to SPRING, so four donor organisations to coordinate across. The donors will aim to meet in person once a year to align on programme objectives and theories of change and have a programme update call at minimum once a quarter with the SPRING team leader. Clear responsibility on major programme activities such as selection and knowledge products will also help to mitigate this risk.	Moderate	DFID SRO
Category: Fiduciary
Fraud or corruption within the Programme team	Minor	Palladium maintains a ‘zero-tolerance’ approach to corruption which will be contained in all staff contracts. Palladium has robust procedures to tackle corruption, including clear procedures for whistle-blowing that safeguard staff who report malpractice. The programme will be subjected to internal and external audits.	Minor	Palladium
Misuse of money by grantee businesses	Moderate	Thorough due diligence conducted for businesses prior to confirming their participation in the programme. Ongoing monitoring by country managers to ensure appropriate use of funds. Grant agreements specify use of funds, funds are disbursed on condition of agreed milestones being met. We will also introduce a post-grant field visit by country managers for additional validation.	Minor	Palladium
Category: Reputational
Criticism directed at the programme due to negative sentiment in UK on aid and Nike's involvement in programme – e.g because of South Asia / garment industry.	Major	Quarterly review of all programme communications plans, agreed approvals matrix developed for all programme communication. Alignment with all donors on programme key messages.	Moderate	DFID SRO
Programme attracts criticism for poor VfM	Moderate	Programme team and independent M&E team have developed a comprehensive framework for monitoring VfM. Agreed VFM indicators are reported in each SPRING Annual Review.	Minor	SPRING team

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

As of 25 October 2018, DFID had spent £11,399,050 of the programme budget in total. In financial year 17/18, £3,460,528 was spent. From the start of this financial year to end October 2018, £1,037,066 has been spent, with a total of £2,759,516 forecast for 18/19 (£1,722,450 remaining).

Of the total spend to date, 30.84% (£4,360,457.52) has been on long- and short-term personnel fees. This is the key cost driver of SPRING, along with programme activities, which accounts for 30.24% (£4275,398.54) of the spend to date – making up over 60% of the spend between them. These figures relate to spend for the SPRING programme, and therefore include spending of funds from other donors.

DFID’s forecast for this year is set to increase as DFID has agreed to cover the financial shortfall that arose from another donor reducing their contribution. This increase is within the overall approved budget that was set out in the original business case and within DFID’s limit as set out in the DCA. The increase has been approved, and the changes to the financial forecast are being calculated with the SPRING finance team. Palladium has been responsive in working with DFID to reprofile spend for this year.

Financial management and reporting

Palladium completes annual risk assessments for each project, which cover financial and operational risks and processes. The last SPRING assessment took place in July 2018. The findings did not highlight any serious risks.

Palladium provides regular progress reports on a quarterly basis (December, March, June, September) – the March and September reports have more substantial financial reporting. These are all submitted in good time for DFID to comment before they are finalised.

Palladium is conscious of DFID forecasting variance targets and maintains a best-practice variance tolerance benchmark between forecasting and actuals of 5%. In the 2014/2015 Annual Report SPRING set a long-term internal goal to reduce their variance tolerance to 2%. This year, over the Annual Review period, forecasting has been generally robust, with an average variance between forecast and actual spend of +/-9% per month, and an overall variance of just -0.01%. They achieved a sub-5% variance for 6 months, of which 2 months were sub-2% variance, over the Annual Review period.

There was a delay in sharing the latest external audit report, which was finalised in July but not shared with DFID until November. The report’s findings are generally fine, but note some human or reporting errors. Palladium has accepted the auditor’s recommendations to improve its financial accounting.

SPRING maintains a full asset register between the London, Nairobi and Kathmandu offices, with items are appropriately tagged and stored in secure locations.

Contract management

Palladium and Coffey are both key suppliers for DFID, and a strategic relationship management (SRM) scorecard was completed for both in this reporting period. Both partners adhere to the Supply Partner Code and a very responsive to DFID’s compliance requirements.

Palladium scored 76.5, putting it in the ‘exceeding performance’ category. Palladium often exceeds requirements on nearly all of the metrics, with ‘Partnership, innovation and improvement’ the only area where the score is slightly lower. Palladium have shown responsiveness to feedback and are collaborating well with other organisations.

Coffey overall scored a 67.5, sitting squarely under ‘good performance’. The quality of deliverables, and risk and compliance procedures are its strongest areas, whereas adherence to schedule is their weakest (though still ‘satisfactory’).

G: MONITORING, EVIDENCE & LEARNING

SPRING an innovative accelerator programme, which aims to demonstrate the viability of adolescent girls as a target market for products and services. In order to demonstrate this viability, monitoring, evaluation and learning is a significant embedded aspect within SPRING.

As SPRING draws its delivery phase to a conclusion, efforts have increased over the last reporting year to prepare for the M&E phase. This phase will commence during the next annual review period.

Monitoring

Currently monitoring and evaluation is achieved through an internal team in the SPRING implementing partner with further M&E provided by an independent M&E partner, Coffey. Alongside SPRING’s continuous data collection, Coffey performs data spot checks to highlight performance, data gaps and recommendations.

Monitoring of the programme is performed continuously through varying levels during the programme. During the nine-month accelerator country managers are in regular contact with most businesses on at least a weekly basis. SPRING’s M&E team perform on-going M&E activities. Finally, monitoring is also achieved through the independent monitoring and evaluation body, Coffey, who produce the following reports:

- Cohort Business Performance Evaluation (BPE) Reports
- Cohort Programme Performance Evaluation (PPE) Reports
- Surveys at key programme stages for each cohort (bootcamps, end of cohort)
- Interview and Key Performance Indicator Analysis

During the reporting year the donors and Coffey agreed to develop a Sustainability Report, with the aim to follow the performance of the businesses on completion of the SPRING accelerator programme.

The SPRING M&E system relies on country managers to play a significant role in ensuring that businesses report data and do so accurately. As SPRING winds down, the role of the country managers scaling down may mean there may be risks in the quality of data reported. Risk mitigation to such a gap in frequency and potential reduction in data verification should be considered in SPRING’s M&E strategy for the coming year.

Evidence

During the Annual Review businesses were asked to discuss their data collection methodologies. In most part businesses presented an appropriate methodology for data collection, and were able to sufficiently explain any assumptions made.

SPRING relies heavily on the direct data collected by businesses and during the boot camp businesses are trained in data collection. However, discrepancies exist between the assumptions made by each business in data collection, and the level of direct access to adolescent girls varies.

Whilst SPRING maintains a strong distinction between indirect and direct impact on girls, this was seen often as an area open to misinterpretation outside of the core M&E team. As much of SPRING’s data relies on the business’ ability to collect and interpret data, it is recommended that further effort is given to clarify to the businesses the distinction between direct and indirect impact on girls.

It is important to note that the M&E partner has highlighted risks identified through the spot checks, especially around the indicator related to data on girls. For example, the risk of double counting or counting girls outside of the 10-19 age range. It is recommended that the degree of risk is considered and updated in the risk registers as appropriate. Some businesses are not systematically collecting disaggregated data on the gender or age of their clients and rely on estimations. It is recommended that the M&E teams continue to coordinate to find ways to improve the quality of data and encourage businesses, where possible, to add features to their data collection model, for instance mobile applications, to ask for client’s or beneficiaries’ gender, age range and household income.

A continued recommendation from the previous year is that SPRING should consider how it can support businesses in incentivising partners and stakeholders to contribute to data collection. SPRING could provide clearer guidelines and checks for businesses to make sure that those collecting data know how and when to securely delete personal information, such as phone numbers and photographs.

While the implementing partner has developed an investment readiness checklist with criteria on which to evaluate each business, in each set of scorecards there are several instances where scores are given without a narrative explanation for the score. One business scored 20 (out of a maximum of 22) with no justification provided for any score. A lack of recorded evidence makes it hard for SPRING to account for the scores it awards the businesses. As improvement in investment readiness is one of the logframe targets (Output 2.1), a lack of evidence justifying SPRING’s judgement undermines the credibility of the programme’s results.

Learning

Through the continued trials and improvements between each cohort SPRING has shown that internally it is able to capture lessons learned. However, as the core implementing activities in SPRING draw to a close, SPRING begins to prioritise capturing lessons learned for wider dissemination. The key document SPRING is developing as part of the process, and as discussed under Output Indicator 4.1, is the Legacy Plan which focuses on communicating to donors and investors opportunities to learn from, adapt and incorporate the SPRING model.

As most of the remaining life of SPRING will be M&E, this Annual Review has tried to focus on relevant M&E recommendations for implementation. These recommendations have been provided through the indicator sections of this review.

SPRING is effectively using its professional relationships to help amplify and apply lessons learnt. For example, in collaboration with FHI Ventures, SPRING co-authored a chapter in the next edition of the INGO Impact Investing Network Report, highlighting unique insights from SPRING. Furthermore, SPRING’s knowledge dissemination strategy (Legacy Plan) – has been set up to help others to learn from, adapt and incorporate the SPRING model.

SPRING has collaborated with other projects in DFID: in November 2017, SPRING spoke at a conference in Mozambique hosted by the DFID-funded female economic empowerment programme MUVA (Ligada), presenting on the SPRING model to a group of local stakeholders. The MUVA team were keen to learn more about SPRING’s experience of the programme pivoting away from focusing on businesses engaging girls in the value chain (in Cohort 1), in favour of businesses benefitting girls as end users, trainees, and indirect beneficiaries in later cohorts. The MUVA team attended the Cohort 3 end of cohort event, and SPRING is now helping MUVA to design a pilot programme, using learning from SPRING to test an adapted version of the accelerator model in the Mozambican context. SPRING produced a blog series about this collaboration - and more knowledge products are expected to follow.

Outside of DFID, SPRING has also worked with the ‘Align’ platform, a Gates-funded gender norms project, that is hosted by the Overseas Development Institute. Align focuses on building a community of practice and platform to share and learn about how to shift discriminatory gender norms for girls and young women. SPRING developed a feature for the platform, showcasing several SPRING businesses and the role they play in helping to shift discriminatory gender norms. While a main audience for the platform is the international development community, it is hoped that the SPRING feature will contribute to shifting perceptions about the importance of engaging businesses (and investors) in striving for gender equity.

It is understood that SPRING’s internal M&E team will be reviewing the M&E strategy for the final phase. Clear transparency and collaboration between the two partners will enhance the likelihood of a successful transition into the M&E phase of SPRING.
Progress on recommendations from previous reviews

2017 Recommendation	Progress
1. As part of SPRING’s new focus on providing a minimum viable product, they should consider developing strategies that differentiate on whether the product is likely to be commercially sustainable or whether it will require government, donor or other forms of grant financing.	This recommendation fundamentally relates to the level of flexibility SPRING is able to offer businesses to allow for diverse, tailored support to be provided. A clear example of where SPRING has developed differing strategies depending on the business need is the methodologies of providing investment readiness support as detailed further in Output Indicator 2. / In Version 4.0 of SPRING’s Theory of Change (revised since the 2017 Annual Review), SPRING has reflected on how differentiated support results in a customized accelerator experience for each business. While some components of support are the same across all businesses (e.g. bootcamp modules), other components are tailored and delivered based on the needs and potential (including commercial as well as girl impact potential) of that business and its SPRING prototype. The more customized elements of support include not only PDF funding (which is needs-based and aimed at developing a ‘minimum viable product’ to test in market), but also tailored support for investment readiness and other subsequent funding.
2. To encourage strong performance by country managers, SPRING should report on the cost per beneficiary by country.	After consultation between the SPRING implementing partners and donors it was agreed that a level of data disaggregation as proposed by this recommendation would firstly not be appropriate for SPRING, nor is it likely to directly enhance the country manager’s performance. During the 2018 Annual Review it was noted that the country manager’s performance is central to the success of each cohort and that their performance was already strong, with the current indicators being sufficient drivers for the country managers. / Furthermore, accounting for impact purely in terms of cost per beneficiary would not reflect the differing levels of impact each business has; with some businesses having a prolonged and pronounced impact on the lives of adolescent girls and other businesses reaching more girls, but with a lesser degree of impact. Therefore, SPRING continues to address VfM at a portfolio level. SPRING’s current performance in terms of VfM is detailed further in Section D. / The number of girls that can be reached within a given country is determined by the selection of businesses (a process which engages the entire SPRING consortium) and, subsequently, by the nature of the business’s SPRING prototypes. Although only girl reach is measured at outcome level of the SPRING logframe, depth of impact is also an important factor for SPRING. This sometimes results in selecting businesses and developing prototypes with higher potential for greater depth of impact and lower reach potential. / Since country managers have little influence over girl reach within a given country, SPRING has not used cost per girl reached per country as a performance indicator.
3. To reflect that it is much more difficult to involve adolescent girls in supply chains or provide access to physical assets than provide them with one-off training or a non-durable good, cost per beneficiary should be split by type of end user.	As indicated above, SPRING has not calculated the cost per girl beneficiary as a performance measure. SPRING has, however, disaggregated and analyzed beneficiary data to reflect this recommendation. For businesses providing girls with opportunities to earn (either directly via the value chain or by offering productive assets), the average number of girls reached per business is 175, whereas for businesses providing products and services (including non-durable goods) that help girls learn, save and/or stay safe/be healthy, the average is 2340[3] girls reached per business. SPRING recognizes that there is often a tradeoff between breadth and depth of girl impact, and have endeavored to select a mix of businesses with high girl reach potential and high impact depth potential in Cohorts 2-4, with a greater focus on businesses and prototypes reaching girls as end users, trainees, or indirect beneficiaries (versus through the value chain).
4. Given that a number of businesses have met the criteria for output 1 while generating low levels of revenue, an absolute minimum threshold should be set for increasing sales by 20%. This number should reflect the level of grant resources received	Following this recommendation relating to Outcome Indicator 3, SPRING explored a range of alternatives for evidence gathering against the indicator, including introducing an absolute minimum threshold for businesses starting from zero revenue. SPRING ultimately agreed with donors that while the indicator may be imperfect, a consistent counting approach will remain for all businesses going forward, regardless of their starting revenues or PDF award (the same approach used to date), and will conduct additional analysis/disaggregation of revenue data to provide greater insight on business performance (and sustainability of business performance) as it relates to SPRING/SPRING prototypes.
5. If SPRING is to target more mature businesses, it should provide strong rationale of the additionality that their support provides for these firms.	SPRING is an experimental, flexible business accelerator, adjusting each cohort through applying previous lessons learned. In Cohort 2 SPRING consisted of six mature businesses of 18 in total, the findings from this cohort highlighted that mature businesses would not benefit as greatly from the accelerator, as such SPRING has since moved away from purposefully selecting mature-stage businesses, prioritising other factors such as commitment of leadership, innovativeness, and girl impact potential. Cohort 4 is comprised entirely of early and growth-stage businesses; therefore, this recommendation has become redundant.
6. A business’ overall sustainability should take priority over training moderators for the future. Where a local moderator does not meet a minimum-standard, SPRING should find alternative support.	This recommendation originated due to a highlighted lack of local moderator’s availability with experience in human centred design and research; a fundamental concept of the SPRING accelerator. Due to the importance of the human centred design and need for local culture and language appreciation SPRING decided to train local moderators following Cohort 3. / As a result, the research process received very positive reviews from Cohort 4 businesses and SPRING consortium. The improved delivery of the research component has resulted in stronger prototype development, but also could lead to a retained local capacity for future businesses.
7. Donors should support SPRING in translating their insights into digestible knowledge products. It appears unlikely that these products will suit the needs of both the donor community and the wider populace: therefore, there should be strong consideration of splitting outcome indicator 4.1 into more specific targets.	In the past year, SPRING has refined its strategic communications plan, which entailed segmenting target audiences for knowledge products, identifying information gaps and outlining 3 priority “knowledge tracks” (or areas of focus in documenting lessons learnt and sharing). Each of these knowledge tracks targets primary and secondary audiences through a variety of channels, with specific knowledge products/activities aimed at key audiences. Since SPRING has addressed this recommendation in part through its communications strategy, it was decided with the donors that it was not necessary to split the output indicator into more specific targets, as this would complicate the logframe without adding clear value to the programme. SPRING’s performance against knowledge products is discussed further under Output Indicator 4.1.
8. The relevance of the VfM indicator ‘cost per business’ compared with ‘value per business’ should be considered for next year’s Annual Review.	SPRING has a VfM framework and separately tracks ‘cost per business’ as the amount of grants (including research, PDFs, BAFs, etc.) which does not include in-kind resources provided from experts/partners across the consortium. ‘Value per business’ is interpreted as the number of girls reached (aka breadth) per business which is tracked in SPRING’s logframe. However, comparing these two in the VfM framework does not provide conclusive analysis as the depth of girl impact is also an important factor (as stated above in response to recommendation #2) in determining value.
[3] Ubongo’s beneficiaries, totalling more than 500,000, fit into this category, but have been excluded from this analysis, as they are an outlier.