Business Case

Summary Sheet

Title: Health Transitions- To Improve Reproductive Maternal and Child Health (RMCH) Outcomes in Mozambique
Project Purpose: / To provide technical and financial support to the different functions of the health sector in Mozambique to improve results in reproductive and maternal health
Programme Value: £34 million		Country/ Region: Mozambique / West and Southern Africa
Project Code:	Start Date:2016/17	End Date:2019/2020
Overall programme risk rating:	Medium
Quest Number:

Table of Contents
Intervention summary	3
Strategic Case	4
Appraisal Case	10
Theory of Change ………………………………………………………………………………………………...18

Commerical Case …………………………………………………………………………………………………28
Financial Case	30
Management Case	33
Risk Matrix …………………………………………………………………………………………..…...………37

Appendix 1: Programme Logframe

----------------------------------------------------------------------------------------------------------------------
GLOSSARY

CA – Convening Agent
CHAI –Clinton Health Access Initiative
CMPs- Centrally Managed Programmes
CPR – Contraceptive Prevalence Rate
DALY – Disability Adjusted Life Years
FM – Fund Manager
GAVI – the Vaccine Alliance
GFATM – Global Fund to combat AIDS, TB and Malaria
GFF – Global Financing Facility
GoM – Government of Mozambique
Ministry of Health – Ministry of Health
OJEU – Official Journal of the European Union
PCD –Procurement and Commercial Department
PES – Annual Estrategic Plan of the Health Sector
PFM – Public Financial Management
PSI – Population Services International
REPRODUCTIVE AND MATERNAL HEALTH – Reproductive and Maternal Health –short for sexual reproductive, maternal, neonatal, child and adolescent health in this business case
RMNCH – Reproductive, Maternal, Neonatal and Child Health
SAA- Standard Administrative Agreement
SDG – Sustainable Development Goal
SENIOR RESPONSIBLE OWNER – Senior Responsible Owner
UNA- United Nations Agencies
UNFPA – United Nations Population Fund
UNICEF – United Nations Childrens’s Fund
VfM – Value for Money
WHO – World Health Organisation

Intervention Summary

What support will the UK provide?
The UK will provide £34 million over 4 years to strengthen how the health sector in Mozambique functions and enable up to 4 million Mozambicans (20% of the rural population) to access quality reproductive and maternal health services. Maternal health indicators have been used internationally to indicate how well the health system is functioning. The reason for this is that different parts of the health system such as resources (health professionals and medicines), the management of these resources and the delivery of health services all need to work together for reproductive and maternal health indicators to improve. This business case will therefore focus on improving reproductive and maternal health indicators so that we can know to what extent our support is strengthening the health system.

The programme will increase the number of new users of contraceptives in Mozambique, by a 20% and contribute to the Manifesto Commitments on family planning. It will also contribute to achieving three of the United Nation’s 17 Sustainable Development Goals to end poverty by 2030: good health and well-being to ensure health lives, gender equality and empowering women and girls and reducing inequality within and among countries. This programme will be compliant with two of the four UK Aid strategies on tackling extreme poverty and strengthening resilience and response to crises.

The programme will consist of two inter-locking components:
(i) £23.5 million for technical and financial support to strengthen the health system. These will support decision making and management at the central level in the Ministry of Health and the delivery of services at the sub-national level in the provinces. Up to four provinces, each with different health system challenges will be selected. This component of the programme will build on the lessons from a recently ended programme funded by DFID, where three United Nations agencies (UNFPA, WHO and UNICEF) worked together to improve results in reproductive and maternal health in 14 countries including Mozambique.

The technical assistance will consist of placing qualified staff including UK technical experts to support health professionals in their day to day work. At central level this support will help the Ministry of Health to improve the management and distribution of their scarce resources. As a result, the Ministry of Health will prioritise interventions that have been proven to be low cost and deliver results. At the sub-national level the technical support will improve the quality of services delivered to in health facilities.

Funds will be channelled to the three UN agencies, who will in turn pay suppliers and contractors of the Ministry of Health and provincial health authorities for medicines, infrastructure such as water and electricity and medical equipment. No funds will be channelled directly through Government systems, in complying with the UK Government policy in Mozambique.

(ii) £7.5 million for technical and financial support to family planning. This component will use communication approaches to get influential community members such as community and religious leaders to support the use of birth control for women and adolescent girls. Communication messages will be adjusted to the social context and practices in the target provinces. This component will be delivered through a service provider, contracted through a tendering process.

An additional £3.3 million will be used to improve the coordination and coherence of all UK investments in the health sector, and capturing lessons from the implementation of the programme. DFID will appoint a Programme Coordinator who will be responsible for supporting the three UN agencies to work together, and make sure that where possible all UK investments in the health sector are coordinated.The UK investments in the health sector in Mozambique are bigger than this proposed bilateral programme. DFID Mozambique will make sure that there is increased coordination across these programmes, wherever possible.

The proposed programme will also lay the ground work for the Global Financing Facility (GFF) in Mozambique. This centrally funded mechanism aims to increase the geographical coverage of reproductive and maternal health services in Mozambique. Mozambique is eligible to apply for the second round of the Global Financing Facility from July 2017. However, our technical assessments indicate that the country is unlikely to meet the conditions to access funding from the Facility within the next two to three years. This programme will therefore provide technical support for the Ministry of Health to fulfil the Facility’s requirements. It will also demonstrate how the Facility could work in Mozambique. A break clause at the end of the third year will enable DFID to decide if we should transition to the Global Financing Facility and phase out our bilateral support or if the programme should continue alongside the Global Financing Facility. The Global Financing Facility offers a potential exit for DFID because if it is successful, DFID support will no longer be required after the year 2019.

Why is UK support required?
13 women die during childbirth in Mozambique, the second highest rate in Southern Africa. The Maternal mortality ratio has remained high and unchanged, over the last decade. This is symptomatic of wider problems with the health system including: social barriers such as the need by a woman to get permission from their husbands to go to health facility, lack of transport to get to health facilities and lack of basic staff or resources in health facilities. The proportion of women that use family planning is only 11% nationally (compared to 42% in Sub-Saharan Africa,) and around 5% in rural areas. Given the high level of early marriage[1] and low use of birth control, almost 20% of deaths from pregnancy are among adolescent girls 15-19 years old. Girls face many barriers in accessing birth control information and services, both from health providers and within their communities.
[1] Mozambique has the 10th highest rates of early marriage with 48% of girls marrying before they are 18 years of age (UNICEF 2015)

The health sector in Mozambique is underfunded with the country spending only $33 per person on health, when the internationally agreed cost of delivering basic health services is $86 per person[1]. More results could be delivered with existing resources, but it would still not close the gap. Meanwhile, the Ministry of Health (Ministry of Health) has limited oversight or control of future funds in the sector. Donor support is fragmented, and delivered largely through vertical, disease-based programmes. These take a medicalised approach to health while ignoring the social practices and behaviours influencing people’s decision to seek health care. The poor functioning of the health system also increases Mozambique’s risk to disease outbreaks.
[1] World Bank, Draft Public Expenditure Review, November (2015).

We can use our relationship with United Nations agencies to develop a more effective, coordinated and responsive approach to systems strengthening for reproductive and maternal health.

Helping Mozambique achieve its target of 34% contraceptive prevalence rate by 2020 will contribute to girls having more choice about when and how many children to have. This will in turn reduce the demand on social services caused by a large population.

What are the expected results?
Outcome: To strengthen the response and resilience of health systems in Mozambique

High level outputs will be refined during the first year of the programme. These are:

1: Equip health facilities to have sufficient inputs and infrastructure.
2: Respond appropriately to emergencies and disease outbreaks.
3: Enable an environment in communities and health facilities that supports reproductive and maternal health.
4. Deliver quality services in communities and health facilities.
5. Coordinate with other interventions in the sector, including those from the UK to maximise results

The main programme’s main risk is that reductions in the State budget as a result of the ongoing economic crisis, will constrain the Government’s ability to deliver basic health services. In addition, the lack of coordination between UN agencies may undermine programme performance. These risks are reduced by providing technical assistance which will help the Ministry of Health to take the necessary tough decisions to keep the system functioning in the midst of austerity cuts. The programme will also be flexible enough to enable different components of the programme to be scaled up or down according to need. The support for emergency preparedness should contribute to this by helping the Ministry of Health to prioritise areas that are essential to maintain health outcomes.

Strategic Case
Mozambique enjoyed high economic growth over the last 15 years (averaging 7% per year); but poverty rates changed little. According to latest available data (2009), over half of Mozambicans (55%) live below the national poverty line of 0.65 cents per day, while Mozambique ranks 180 of 188 countries on the Human Development Index [2]. Despite progress in improving child health, the maternal mortality ratio (MMR) remains high and stagnant, persisting at 408 deaths/100,000 live births since 2003[3]. There is serious risk that this situation could worsen further, as Mozambique faces climate-related natural disaster, low intensity conflict in the centre and north of the country and looming economic crisis, exacerbated by the recent revelation that government leaders contracted over $1.4 billion in secret, state-guaranteed debt.
[2] UNDP (2015) Human Development Index for Mozambique
[3] DHS 2011

Context for reproductive and maternal health
A good health system delivers quality services when and where people need them. Maternal mortality has traditionally been used as an indicator of the strength of the health system, given that all health system components (such as resources, the management and distribution of the resources and delivery of services) must function well to deliver quality maternal health services. Persistently high maternal mortality in Mozambique indicates wider health system challenges. Currently, 13 women die every day as a result of giving birth, the second highest rate in the region after Malawi[4]. Almost 20% of these deaths are among adolescent girls 15-19 years old[5].
[4] WHO et al 2015
[5] UNFPA Mocambique (2013),Suplemento Por escolha, nao por acaso- planeamento familiar, direitos e desenvolvimento. Maputo, Mocambique, 2013

High maternal mortality rates also reflect women and adolescent girls’ lack of choice about when and how many children to have. . Although the contraceptive prevalence rate (CPR) for modern methods of birth control increased from 5% in 2003 to 11.3% in 2011[6], this is well below the Sub-Saharan Africa average of 42%[7]. Meanwhile fertility rates are high and, exceptionally in the region, are actually rising (from 5.6 children per woman in 1997 to 5.9 in 2011). On average a Mozambican woman will have just under six children.
[6] DHS 2011
[7] UNFPA Mocambique, Suplemento Por escolha, nao por acaso- planeamento familiar, direitos e desenvolvimento. Maputo, Mocambique, 2013

Mozambique has some of the world’s highest rates of early marriage and childbearing in adolescence. Low age at marriage, a high number of young people having sex before reaching 14 years of age and low percentage of women using family planning, means that by age 18, almost half (48%) of girls are married and 40% have had a baby[8]. These issues can only be addressed by understanding and influencing the behaviours and, eventually, the social perceptions that influence health outcomes[9] .Improving reproductive and maternal health outcomes will therefore require improvements on the demand for services by looking at the social and cultural factors that influence the decision to seek health services, and the supply side which has to do with the actual provision of quality services in health facilities as figure 1 (below shows).
[8] (UNICEF, 2013).
[9] Paraphrased from the DFID handout on social norms

Fig. 1: Causes of maternal deaths in Mozambique

Health system context

Health Financing
The health sector is underfunded and relies heavily on funding from donors, over which the Government has little control. The essential health package costs US$86 per person,[10] yet Mozambique spends only US$33[11]. According to the World Bank, improved use of these existing health sector resources could provide an additional US$7 per person[12]. This would still leave a funding gap of U$56 per person. Total health expenditure in 2014 was £414million; of which 30% was covered by the state budget; 10% by a pooled fund where all donors joined their support to the sector, and the remaining 60% from vertical disease-focused programmes such as the Global Fund to combat AIDS, TB and Malaria and United States Government Presidential Malaria Initiative[13]. These vertical programmes set up separate reporting and financing structures to the Government’s. These additional structures demand time and management ability from the Ministry of Health.
[10] World Bank, Draft Public Expenditure Review, November (2015).
[11] World Bank Presentation on Public Expenditure Review in the Health Sector, 22 May 2015. Human Resources Observatory.
[12] World Bank, PER (2015)
[13] Ekman B, Pathmanathan I, Liljestrand J(2008): Alma ata rebirth and revision7: Integrated health interventions for women, newborn babies and children: a framework for action. Lancet 2008: 372:990-1000.

Governance arrangements
The Ministry of Health remains largely centralised, with a disconnect between the central level where policies are made and the subnational (provincial and district) levels where service delivery takes place. The Ministry of Health manages the National Health Service and is, responsible for the delivery of over 90% of health services. There is a growing private sector, but limited to serving the urban middle class. Decentralisation of decisions and management to the sub-national level has resulted in some patchy availability of funding in the provinces. However, 63% of the state budget is still retained at central level every year. Policies are made centrally and therefore not able to adjust to the context in each of the 11 provinces of the country. The result of this is that provinces and districts therefore have little actual funding for service delivery.

The distribution of resources across provinces tends to be inequitable while the potential for getting more results by using these funds better has not been realised. Allocation decisions at the Ministry of Health take an incremental approach instead of being based on evolving population size, population density or disease burden. This tends to make inequality and inefficiencies in the system worse. For example, one of the results is that more densely populated areas may be severely understaffed. Meanwhile, the health workforce chas a lot of administrative staff (42% of staff) leaving the technical staff over-stretched. Restructuring of the workforce could improve their performance. One of the ways to do this is to increase the emphasis on community health workers who are placed in rural communities to deliver treatment and information for the most common diseases. Ethiopia and Malawi for example, improved health indicators while spending less money on average, an indication that there is room to get more out of the current health investment in Mozambique[14].
[14] PER (2015)
Table 1: Key health system constraints in Mozambique
Health system component	Challenge
Leadership and Governance		Large number of actors providing uncoordinated support including emerging economies (e.g. China, Brazil). Poor collaboration with other sectors (Education, Finance, Water) that influence health. Weak enforcement of service delivery regulations and guidelines. Poor prioritisation of numerous strategies. The Ministry of Health has been very weak at answering for the performance of the sector to the Mozambican public
Health workforce		Qualified staff poorly distributed, provider knowledge is low, and absenteeism rates high, weak supervision, management and accountability of the performance of providers. The full potential of the community health workers has not been achieved. .
Medical products, vaccines and technologies		Overly centralised control of medicines and regular stock outs of essential medicines in health facilities. Pilot projects exploring alternative ways to distribute medicines (eg. through the private sector) haveyet to be scaled up. Health sector still need to make best the use of new technologies such as cell phones to improve monitoring of drugs.
Financing		Relies on unpredictable earmarked funding from vertical programmes. Interventions currently not sustainable as rely on donor support. No clear strategy to secure long term financing for the health sector. Lack of transparency and coordination of funds among different actors (NGOs, donors, private sector for example).
Information		Decisions not based on evidence and low quality of routine data. Weak and overly centralised planning. Fragmented collation of data.
Service delivery		Biased toward urban areas, 40% of population not reached, minimum standards not implemented in health facilities, continuous disruption of services due to shocks (climate change, conflict, disease outbreaks) and inadequate infrastructure. Community services fragmented. Informal fees charged by health providers at all levels.

Disparities in health outcomes

There is significant provincial variation in reproductive health indicators. The Central Provinces (Sofala, Zambezia), and Northern province of Cabo Delgado have the worst reproductive and maternal health indicators overall. Generally, the maternal health and health of babies within 28 days after being born, requires improvement in all provinces(see figure 2 below). The poorest women and girls are most disadvantaged. For example, the average Mozambican woman has 5 children, the poorest women have 7. Caseloads which assesses the clinical and non-clinical activities of health workers were highest in the centre of Mozambique (17.7 patients per provider per day) compared to the south (17.2) and north (17.1). They also varied according to facility types with the highest activities found in basic health centres at 17.6 patients per provider per day compared to 8.9 patients per day for hospitals in urban and peri-urban areas[15]. The Ministry of Health is exploring incentives to motivate health professionals to work where they are most needed.
[15] World Bank (2015) Africa Region:Health service delivery in Mozambique: Results of the 2014 service delivery indicator survey (draft report).

Source: Yogesh et al (2016) Accelerating REPRODUCTIVE AND MATERNAL HEALTH Outcomes: Rapid Assessment and Investment Options for DFID, Thinkwell draft report.
Figure 2: A map of the country showing disparities across provinces for different repreoductive and maternal health indicators.

Disease outbreaks and disaster preparedness
Despite experiencing frequent outbreaks of, the country is ill prepared to deal with them. Cholera has been regular in Mozambique since 1973 with outbreaks reported every year between December and June in flood affected areas. In 2009 for example, there were 19,700 cholera cases and 155 deaths as a result of cholera. In 2015, there was an outbreak of dengue[2] in the Northern province of Nampula, affecting 110 people[16].These frequent outbreaks disrupt the normal delivery of health services and divert scarce resources to the outbreak response. Another problem is that disease surveillance is weak so that the size of an outbreak remains largely unknown until there is an investigation. There are concerns in the donor community that Mozambique will not be able to respond to health outbreaks such as the Zika virus caused by mosquitoes, which although not causing a lot of harm to most people, may result in in birth defects if contracted by a pregnant women.
[2] A tropical disease caused by the bite of a mosquito.
[16] Mozambique,- outbreak of dengue fever in Nampula province (2015) http://allafrica.com/stories/201503250321.html
Solutions
In order to reduce maternal and neonatal deaths, the proposed programme will:
(i)Reduce delays in the decision women make to seek care, by involving communities. Interventions to change practices and beliefs around family planning and giving births in health facilities can create an environment women and girls to easily access maternal and reproductive health services in their communities or in health facilities. 28% of women in Mozambique want to stop or delay childbearing but are not using any contraceptive. This is an indication that there is demand to prevent unwanted pregnancies among women and girls. Greater access to family planning would enable 40% of young women who drop out of secondary schools as a result of pregnancies, an opportunity to complete their schooling. Communities can also provide local transport networks to enable women to reach health facilities including bicycle and motorcycle ambulances.
(ii)Strengthen the partnerships between the community and health facility. The provision of services to rural communities including the Community Health Worker programme, have the potential to reach underserved communities in a relatively cheap way. The expansion of community services to address bleeding after a woman gives birth, late referral to emergency services in cases of birth complications and low family planning uptake, may contribute to the reduction in maternal deaths. The health programme can also liaise with DFID Mozambique’s Citizen Engagement Programme which aims to strengthen the communication between health providers and the communities they service.
(iii) Increasing access to quality care for pregnant women and during childbirth. Enable women to access trained staff, medicines and transportation where referral to specialist care is needed. Health facilities should have small up front investments to address gaps in quality including infrastructure (water, electricity and equipment) and equipment. The management of human resources also needs to improve so that provider knowledge increases and absenteeism reduces.
(iv)Strengthen the response to disease outbreaks at all levels of the system. These efforts can also support the Ministry of Health to ensure that reductions in expenditures maintain a minimum standard of acceptable care and reduce weaknesses in the system making it prone to future outbreaks.
DFID Experience to date
This programme will use a different approach to strengthening the health system, taking into account the fragmentation in the sector and the medicalised approach which influences the decision to seek care. We will draw on lessons from almost a decade in the health sector, to have a coordinated response to the UK investments in order to improve the results they achieve. We will also focus on the demand side to address the socio-cultural factors leading to the delay in seeking health care. And lastly, the programme will have a flexibile approach allowing for the use of different interventions simultaneously to tackle each of the constraints in the target provinces. This should make the results more sustainable as the Ministry of Health can learn from how different health system challenges will be addressed. We can also be responsive to the context which is constantly changing as a result of the macroeconomic situation, the low level conflict and the humanitarian crisis.

Our experience in the heath sector has seen some successes which we want to build on. The use of the Health Common Fund as the main funding mechanism through which our funding was channelled to the sector from 2007-2015, constrained our approach. The Common Fund facilitated donor harmonisation in support of implementing the Ministry of Health strategic plan for health, in an otherwise highly fragmented sector. In practice, however, Ministry of Health used the Common Fund to fill gaps in other resources due to inefficiencies or unpredictable funding. There was also inadequate accountability and dialogue between Ministry of Health and Common Fund partners was dominated by fiduciary rather than health care delivery concerns. Furthermore, the funding which reached $100m in 2010 was not complimented by technical support.

We were able to complement the Common Fund through a set of pilot programmes using alternative delivery methods.[17]. Key lessons include:
[17] Intelica (2014) Estudo sobre fontes de financiamento no sector de saude.

- UNFPA Community based delivery of family planning- demonstrated that family planning uptake can be increased through a focus on community mobilisation and communication. However, a multi-layered approach to supervision and monitoring made the UNFPA methodology too costly for wider scale-up. A more cost-effective (potentially market-led) approach will be required.
- Clinton Health Access Initiative (CHAI) medical supply distribution with the private sector (Coca Cola)- Outsourcing to the private sector has reduced the cost of supply distribution by 40% on average. Building government capacity and systems to manage out-sourced distribution is a long-term process, however, and still needs to be consolidated.
- Population Services International (PSI) Social marketing – Demonstrated that social marketing approaches can increase the uptake of family planning. Use of mobile technology can help with real time monitoring and payment of service providers.
- Options Consultancy -demand creation for institutional deliveries – a planned pilot project to promote demand for institutional births did not move beyond design stage due to a combination of resistance from the health authorities and weak capacity of the service provider to negotiate this. The process revealed potential risks around government buy-in to unsolicited support.
- The Reproductive Maternal and Newborn Health Trust Fund with three UN agencies (UNFPA, UNICEF and WHO). The Trust Fund was funded by Norway since 2013, and joined by DFID with £75 million since 2014. Mozambique was one of 19 countries that benefitted from the Trust Fund support. Support to Mozambique was £8 million which will be ending in August 2016. DFID-M wants to build on the synergies from this programme.

At a macro-level, DFID’s contribution to General Budget Support and un-earmarked financial aid, supported increased allocations from the state budget to the health sector and enabled discussions with Ministries of Finance and Planning on areas needing reform such as public financial management.
Why DFID should get involved?
There is a risk that the gains in health outcomes over the last two decades will be lost. High maternal mortality rates have persisted over the last decade, an indication that the national health system still has weaknesses and is, under-resourced. A squeeze on state funding, linked to the economic crisis, means that further stress on resources is likely in the short term. This could undermine the gains in the health sector and lead to a reduction in health outcomes. DFID can offer support to the Ministry of Health to bring about the changes needed to improve the use of scarce resources and prioritise interventions which are proven to be low cost and deliver results. This could include improving the use of resources through partnerships between the state and the private sector. DFID is well placed to support this process because of our experience from the pilot programmes, the respect that DFID has in policy dialogue, our inclusion of the demand side going beyond the current medicalised approach and the flexible nature of our support allowing the programme to respond to changes in the context. This programme can also be catalytic in helping to realise some of the institutional reforms set out in the Government’s Health Sector Strategic Plan (2014-19) while contributing to the UK Government’s manifesto commitment on family planning.

Coordination support can improve the results from the large UK investments in Mozambique. The range of programmes varies from large investments such as the Global Fund to Combat AIDS, TB and Malaria to small interventions targeting specific components of the health system. The Global Funds has contributed$578 million to Mozambique since 2004. However, there is a risk that these investments are not having maximum impact given the existing fragmentation in the sector and weaknesses in health systems. DFID Mozambique’s support to strengthen the health system and coordination will help to increase coherence across UK investments. DFID Mozambique is committed to owning the UK Government footprint in Mozambique.

Mozambique qualifies for the Global Financing Facility a mechanism to increase the coverage of reproductive and maternal health care in Mozambique. DFID is one of the investors in the Global Financing Facility while the World Bank is the Secretariat. Our support through this programme will help Mozambique to meet the pre-conditions the Global Financing Facility support. The Facility process is to create a platform where different stakeholders including civil society and the private sector can align their support to reproductive and maternal health. The Facility may offer an exit strategy for DFID in 2019. However, our current assessment is that Mozambique is unlikely to meet the conditions to access funding from the Facility by June 2017, when the country qualifies for this support. The reason for this is because the Ministry of Health currently lacks the technical capacity to meet the conditions for funding. Furthermore, there is lack of coordination of the various stakeholders. DFID support over the next four years can provide technical support and demonstrate what reproductive and maternal health results could be achieved with this funding.

Gender, Adolescents and Disability
The proposed DFID health programme will target women and adolescent girls as key beneficiaries. Childbirth exposes women and girls to death (13 women die every day) or living with disability due to birth related complications. The situation for adolescents is even worse, due to social and cultural practices and behaviours that block their access to reproductive health information and services. For example, parents and relatives of adolescents do not want them to access family planning because they are believed to be too young to be having sex.

Reproductive and maternal health services have a disproportionate effect on the health and wellbeing of women and girls. Women and girls will be the main beneficiaries of this programme. as it will help them to decide when and how many children to have. This will enable girls to stay longer in school and improve their opportunities of getting a better job and providing for their families. Delaying the time between births can improve the health of women. There is evidence that children without mothers are ten times more likely to die within two years of their mother’s death[18]. Our proposed support to health system strengthening will be complemented by additional support to promote knowledge and behaviours that generate demand for family planning in communities and create a supportive environment for women and girls to access family planning and get to health facilities on time.
[18] UNICEF (2004) Millenium development goal 5: Improve maternal health. http://www.unicef.org/mdg/maternal.html

We will be monitoring to what extent the proposed programme will be addressing gender inequality in accessing and in delivering health services. For example, the eligibility criteria for community health workers has resulted in two thirds of them being male, by excluding women who cannot read or write as well as men. These factors will be tracked through the programme and discussed with the various stakeholders. This business case is therefore compliant with the Gender Equality Act.
Outcome/Results

Outcome: To strengthen the response and resilience of health systems in Mozambique

High level outputs will be refined during the first year of the programme. These are:

1: Equip health facilities to have sufficient inputs and infrastructure.
2: Respond appropriately to emergencies and disease outbreaks.
3: Enable an environment in communities and health facilities that supports reproductive and maternal health.
4. Deliver quality services in communities and health facilities.
5. Coordinate with other interventions in the sector, including those from the UK to maximise results
Appraisal Case

Based on the needs set out in the Strategic Case, the main components of the proposed health programme are as follows:

Supply side support consisting of:

Technical and financial support to strengthen management of resources at the central and provincial level. This support should make sure that resources are distributed according to need on time. It will aim to improve the distribution of different components of the health system such as resources such as human resources, medicines and commodities to ensure that they are of optimal quality and are available where they are most needed. The support will help the Ministry of Health to make tough and decisions to keep the health systems functioning well in the midst of a squeeze on expenditures due to the macroeconomic situation in the country. It will include adopting new initiatives to improve how resources are used, for example the outsourcing of non-essential services to the private sector. This support will also strengthen the Ministry of Health’s ability to respond to emergencies and disease outbreaks. It will use UK technical expertise where appropriate to share knowledge with health professionals in Mozambique.

Funding and technical support for service delivery at sub-national level. This will involve channelling funds for delivery of Reproductive and Health services in line with the Government’s provincial plans. Given current DFID policy in Mozambique not to channel funds through Government systems, suppliers would be paid directly for the timely delivery of equipment, infrastructure (water, electricity and sanitation) and medicines/commodities to health facilities. The technical support will strengthen service delivery by helping to establish a minimum standard of care in different kinds of health facilities. It will also support discussions between health providers and service users by collaborating with DFID’s Citizen Engagement Programme. Up to four provinces will be selected, each with different health system constraints, allowing for different areas of the system to be strengthened. The selection of provinces will be decided in agreement with the Ministry of Health during the programme inception phase. The flexible nature of this support should ensure that provinces are able to minimise the disruption to service delivery as a result of reductions in expenditure due to the economic situation.

Demand side support to generate demand for family planning through interventions to involve and inform communities. Funding and technical assistance to try innovative interventions which will influence behaviours and creating an environment that supports adolescents girls and women to access family planning

Monitoring, coordination and lesson learning: This component would ensure greater cohesion of all UK Aid investments, those managed from the UK and those managed from the DFID country office. It would also support the coordination among the plethora of donors to the sector. Routine monitoring will use Government information systems to enable lessons from the approach to be gathered. The DFID Health Advisor will lead on discussions with senior Ministry of Health staff, helping to prioritise interventions that address health system constraints and set targets for the programme. Other partners or line ministries will be included when relevant through existing coordination mechanisms in the sector. An example of this are the various working groups consisting of donors, civil society and Ministry of Health staff focused on a thematic area such as human resources or service delivery. .

Table 2: Evidence ratings for the approach
Objectives	Evidence
Health policy at central and provincial level
Investing in health policy translates to improved quality, equity and coverage of services	Strong: A systematic review found that interventions focused on decision making in the health sector resulted in more consistent improvement on quality of care, equity, coverage and access than those using technical guidance alone[19]. This is supported by a systematic review which indicates that leadership reforms lead to improved health results, and a focus on basic health care increases access to services for the poor reducing inequalities according to wealth[20].
Service delivery at subnational level
Delivery of integrated services at facility and community level / Combined interventions for family planning	Strong at improving integrated reproductive and maternal services: Large and high quality evidence from many countries that the delivery of integrated reproductive and maternal health services at basic care. The evidence suggests that in contexts like Mozambique where there are partly functioning health systems an approach of combining both facility and community delivery of services is most effective[21]. / Medium evidence that suggest that various interventions combining education and contraceptives lowered the rate of unintended pregnancies among adolescents[22].
Demand generation for family planning
Social norms/ behaviour change	Medium evidence that interventions to reduce access to reproductive health underlying reasons for women and adolescents access little information and services on reproductive health in in Sub-Saharan Africa had components which looked at the social behaviours and cultural practices.[23]. / Limited evidence from Malawi that influencing males can increase contraceptive use; communication messages should target everyone involved in family planning decisions; and public awareness activities can change social attitudes that cause violence against women and girls[24]. / Limited: The suggestion that regular funding at household level through cash transfers, delayed early marriage and pregnancy among adolescents[25].
[19] Willey B, Smith Paintain L, Mangham-Jefferies L, Car J, Armstrong Schellenberg J (2013) Effectiveness of interventions to strengthen national health service delivery on coverage, access, quality and equity in the use of health services in low and lower middle income countries. London: EPPI-Centre, Social Science Research Unit, Institute of Education, University of London.
[20] Kruk, M. E., Porignon, D., Rockers, P. C., and Van Lerberghe, W. (2010) The contribution of primary care to health and health systems in low- and middle-income countries: A critical review of major primary care initiatives. Social Science & Medicine, 70(6), pp. 904–911.
[21] Zulfiquar, AB, Sumana A, Simon C, Talaha A et al (2008), Alma-Ata: Rebirth and Revision 6- Interventions to address maternal, newborn and child survival; what difference can integrated primary care strategies make? The Lancet. 372:972-89.
[22] Oringanje C, Meremikwu MM, Eko H, Esu E, Meremikwu A, Ehiri JE (2010) Cochrane review- interventions for preventing unintended pregnancy among adolescents.
[23] Wamoy J, Mshana G, Mongi A,Neke N, Kapiga S and Changalucha J( 2014) A review of interventions addressing structural drivers of adolescents’ sexual and reproductive health vulnerability in sub-Saharan Africa: implications for sexual health programming.
[24] Oringanje C, Meremikwu MM, Eko H, Esu E, Meremikwu A, Ehiri JE (2010) Cochrane review- interventions for preventing unintended pregnancy among adolescents.
[25] Baird S, McIntosh C, Ozler (2011) Cash or condition? Evidence from a cash transfer experiment. The Quarterly Journal of Economics.126, 1709-1753.

Based on the needs set out in the Strategic Case the findings from a series of scoping studies[3], and our experience in the health sector over the last decade, three options for DFID’s support to health systems strengthening were considered. These are assessed against a set of key success criteria (see table 2 below).
[3] Health stocktake (October 2014), Political and institutional analysis of the sector (January 2015), Situational Analysis of barriers to accessing reproductive health for adolescents (January 2016), Health system assessment for reproductive and maternal health (March 2016).

Table 3: Key success criteria:
1. Reaching the poor and vulnerable particularly adolescents: Poor communities in general and adolescent girls in particular are excluded from accessing to quality reproductive and maternal health services.
2. Value for money: The programme should demonstrate efficiency and effectiveness by improving coordination and synergy with other interventions, thus reducing managerial burden to DFID and the Government. This should also enhance our impact.
3. Risk: The approach should provide adequate reassurance that funds: (i) are not used for the intended purposes; (ii) are not properly recorded and accounted for by putting; adequate measures in place.
4. Ownership and Sustainability: Government support forthe programme approach both at central and sub-national level will be critical for the approach to strengthen health systems to achieve results.
5. Wider policy influencing: Beyond direct delivery of inputs, the programme should contribute to wider coherence and increased coherence of UK Aid to the health sector in Mozambique.

An assessment of each of the options against the success criteria is shown on (page 19 below)
Discarded options
Counterfactual (Do Nothing)
This option would mean no DFID bilateral support to the health sector in Mozambique. It was discarded because of the need outlined in the strategic case. We could rely on programmes managed from the UK including the global programmes in health to deliver health results. However, without focused support to health systems these will have limited impact, as they need a functional system and better alignment to fully deliver. DFID support through other sectors that determine the social and economic conditions responsible for good health such as water and sanitation and social protection can also influence health outcomes. However, these will take several years before they can have a significant impact on health outcomes.
Support through Government systems
Support through Government systems is not currently a funding option. In response to a serious breach in of trust in the aid relationship between the UK Government and the Government of Mozambique, Ministers decided in May 2016, that no direct funding can go through Government systems. However, they did agree that alternative non-Government payment mechanisms can be used to support Government priorities towards poverty reductions. Other donors have also stopped direct funding and the IMF has suspended their loans to the country. UKMinisters also agreed the continued provision of Technical Assistance, procured by DFID, can be provided to the Government. DFID Mozambique will periodically test the Government of Mozambique’s commitment to the Partnership Principles and revert with recommendations to Ministers as to whether we should re-start financial aid. If financial aid is re-started in future, that option will be considered for this programme.
Feasible options
After discarding the options above, three feasible options were considered in more detail. These are described and assessed below.
Option 1: Focus on Health Systems Strengthening, using our relationship with the UN
In this option, DFID would work with a consortium of three UN agencies, WHO, UNICEF and UNFPA, to support the delivery of quality services. Each agency has a specific comparative advantage which DFID would draw on, as follows:
- UNICEF: across a range of key areas that influence Reprodutictive and maternal health including community health, nutrition, malaria, neonatal and child health.
- WHO: in establishing policies and standards for service delivery; and supporting the Ministry of Health to improve management of the health workforce; and in building Ministry of Health capacity to prepare for health emergencies and disease outbreaks;
- UNFPA: in family planning, including procurement of commodities (funded by DFID centrally) and in promoting a policy and programme focus on adolescents.
Working through this UN Agency Consortium would build on an existing framework for collaboration between DFID and the UN through a recently ended programme well as a body of work on Reproductive and maternal health. This would not be the same programme but build on the synergies from the CMP in Mozambique. The UNA would deliver all three components set out above with one difference.

Demand generation activities for Reproductive and maternal health will be undertaken through health system outreach to local communities. This component will therefore strengthen demand side interventions being undertaken through the health system, through community health workers for example.

Advantages: This approach offers value for money and impact through improved coordination and coherence between different DFID interventions including through centrally managed programmes and multilaterals. For example, both UNICEF and WHO work closely with the global programmes: the Global Vaccine Alliance and the Global Fund to Combat AIDS, TB and malaria, thus a coordinated approach to working with the UN would leverage wider relationships DFID is able to draw on the comparative advantage of the different agencies such as UNFPA’s experience on sexual and reproductive health, WHO on human resources and emergency preparedness, UNICEF on malaria and nutrition whilst driving value for money through coordination. The UN agencies also have Government buy-in, based on three decades of providing policy and technical support to the sector.

Disadvantages: Relying on UN for fund management and programme implementation runs the risk of setting up or entrenching parallel systems and, or perpetuating dependency. Experience from Uganda and South Sudan has demonstrated that coordination among the agencies can be highly challenging.

To minimise this risk DFID would appoint an Reproductive and Maternal Health Programme Coordinator to work with the UN agencies Consortium. S/he would lead on coordination and lesson-learning within the Consortium. They could also support component four on improving the effectiveness of the UK interventions in the sector, by supporting the collaboration with other CMPs, such as the Global Fund to Combat AIDS, TB and Malaria).

Experience also suggests that the UN agencies demand side approaches can be either too expensive or not sufficiently flexible to be delivered at scale. For example, a DFID supported community based family pilot through UNFPA cost $54 per new user, inhibiting scale up while PSI’ a social marketing company’s - family planning interventions cost $7 per new user on average. There is also a potential conflict of interest between the UN’s supply side work and undertaking demand side work and, or engaging with the private sector.

Conclusion: The UN is well placed to support health systems strengthening. There are risks of dependency and that the approach will not be sustainable; however, this can be mitigated by including specific performance indicators on health systems in an Agreement with the UNA and the GoM. Placing a Programme Coordinator at the Ministry of Health to work with the UN agencies would mitigate the risk of weak coordination in practice. However, demand side work through this modality would encounter several constraints including high cost of delivery and a conflict of interest with their supply side work.
Option 2: Focus on increasing demand and supply of reproductive and maternal health services and family planning through an independent service provider
In this option, DFID would contract a service provider to deliver:

Technical assistance and financial support for Reproductive and Maternal health delivery: This component would provide the same support as in option one, at national and sub-national level; but delivered by a service provider. The only difference would be the approach to demand generation for reproductive and maternal health, which is set out below:

Technical assistance and financial support to pilot innovative reproductive and maternal health interventions involving communities. These are based on communication approaches to generate demand and change social perceptions and practices. Through this option DFID would promote market led models to scale up the delivery of family planning services and information to youth. It would directly involve adolescents to deliver communications and services where appropriate. Social communication pilots would be implemented to promote family planning as an aspirational lifestyle for the youth in urban and rural areas, and target influential members of the communities, to help create an enabling environment for youth access to and uptake of family planning.

Advantages: This option allows for flexibility and innovation, enabling an adaptive programming approach where different implementation models can be piloted. It can include the use of cell phones and new technologies for gathering real time data to monitor the programme and interact directly with beneficiaries. The situational analysis on barriers to reproductive health among youth in Mozambique, commissioned by DFIDM to inform our new programme, recommended that both the economic as well as health-related dimensions of access to and uptake of contraception[26]. This option responds to that through a lesson-learning approach to communications and marketing.
[26] Palladium (2016),Situation analysis and recommendations for addressing social and behavioural barriers to reproductive health

Disadvantages: It would be difficult for a private sector service provider to secure a similar level of ownership/ buy in from the Government compared to the close working relationship already enjoyed by the UN agencies; or to get a seat at the policy dialogue table in such a fragmented sector. The service provider would not be well placed to play a role in local coordination of UK Aid interventions in health, managed from the UK. Implementation would be delayed by the EU tendering process which can take between six and nine months, but this can be minimised by having intermediate interventions which can be implemented while the tendering process is taking place. Furthermore, DFID can start implementation through one of the UN agencies while waiting for the EU tender process to conclude. .

Option 3: Combination of support to supply and demand for Reproductive and maternal health services
In this option, DFID would support a complementary package of support to Reproductive and maternal combining the speciality of each UN agency with the advantages of the private sector for a flexible and innovative approach to demand generation.

Figure 3: How the programme approach addresses the three delays mentioned in the strategic case

It would consist of the following components:
Technical assistance and funding through UN for service delivery. This component would link national policy support with subnational service delivery in up to four provinces. This approach would reap the benefits of coordination between UNAs and other UK aid interventions in the health sector. It would provide central level policy support to ensure that the Ministry of Health are able to prioritise their scarce resources to ensure quality delivery basic services to the most needy in selected provinces. It would enable DFID to assess the impact of policy support for improvements in service delivery.

Technical assistance and funding through a service provider for family planning out-reach, demand generation and independent verification. This component would draw on the comparative advantage of a service provider to deliver an adaptive programming approach, piloting market led, social marketing and communication interventions to increase family planning uptake among adolescents In addition, the service provider would be responsible for the independent mid-term assessment (after two years) and an endline review to assess the performance of the overall programme. This would ensure that there is a link between the demand and supply sides of the programme. The mid-term assessment will be linked to a break clause in the agreement with the UNA Consortium (please see break clause below) and inform decisions on the way forward.

Lesson learning, coordination and policy advice. DFID Mozambique would retain management of this component, by placing a programme coordinator to be based within the Ministry of Health . They would be responsible for oversight of the UK managed investments to the health sector and coordinating with the UNA. It would include advisory time from the DFID Mozambique Health Advisor.

DFIDM will take an adaptive approach to the programme whereby successful components will be scaled up while those that are underperforming will either be changed or scaled down.

Break Clause
The rationale for supporting health systems strengthening through a third party has been selected largely due to a breach in the trust by the Government of Mozambique. Where there is compliance with the underlying conditions for direct aid, a more direct approach to working through national systems in order to strengthen them would be appropriate. DFID Mozambique has committed to update Ministers on an annual basis with regard to GoM compliance with these direct aid conditions, in the same vein, we will continue to assess the context for health sector support.

A programme review after two years will give DFID Mozambique the opportunity to respond to programme performance issues and to any changes in the external environment. This could be in relation to the Partnership Principles and, or other changes to the aid environment. For example, the GFF platform may be set up with an effective funding mechanism through which donors can support Reproductive and maternal health, implying that the programme can be integrated with the Global Financing Facility. We therefore recommend that our Agreements include a break clause in the third year to review the approach in order to decide whether we integrate with the Global Financing Facility or continue separately until the end of the programme. This will be included in the mid-term evaluation of the programme.

Unpacking the Theory of Change
The Theory of Change provides a flexible approach for health system strengthening to enable the programme to respond to different constraints in each province as well as a rapidly changing external context. The outputs have therefore been designed so that a different set of interventions can be delivered in each province or across time depending on the needs.

Output 1: EQUIP health facilities to have adequate inputs and infrastructure. This output aims to ensure that health facilities are prepared to deliver services by achieving the minimum standard of inputs they need. It will therefore ensure that health facilities of different types from health posts to district hospitals have all the priority drugs, sufficient human resources and infrastructure (water, sanitation and electricity) that they need. It acknowledges that this will require improvements over time. To support this, an initial health facility assessment will be undertaken to identify gaps and prioritise needs jointly with the health authorities. There may also be some light construction to upgrade health facilities or for example make running water available.

Output 2: RESPOND appropriately to emergencies and disease outbreaks. To strengthen the Ministry of Health ’s ability to prepare for emergencies and respond to them when they arise. This will include strengthening the surveillance system; improve the ability of primary or community level health workers to act as public health surveillance point and establishing guidelines for how to deal with different outbreaks. Responding to emergencies will therefore strengthen routine systems so that routine surveillance and reporting systems are able to respond to emergencies.

Output 3 ENABLING a supportive environment for reproductive and maternal health services to be delivered in communities and health facilities. The aim of this output is to create an enabling environment that addresses the barriers women and adolescents face in their communities when they try to access health services or information These range from long distances to health facilities which communities can reduce by making local transportation available (with support from the programme if necessary) to strongly held beliefs by influential community members. Different approaches will be used to bring about social change. Research will be needed to ensure that these approaches are the most appropriate for the different barriers and contexts in Mozambique.

Output 4: COORDINATE with other interventions including those from the UK to maximise results
This output takes into account the fragmentation in the sector by trying to link this programme with relevant interventions supported by other donors or those the UK supports through programmes managed from the UK. In order to achieve this DFID will engage in policy dialogue with other partners and the Ministry of Health. There will also be engagement with the Centre on the various programmes managed from the UK to support them to be more effective.

Output 5: DELIVER quality services in communities and health facilities. This output relies on outputs 1-4 to be effective. At the same time service delivery also requires technical support so that a minimum standard of care is provided. Many health providers lack the competencies to talk to their clients. There also needs to be dialogue with service users to ensure that services are acceptable. This output therefore includes social accountability. For example, if women are on farms from sunrise until 2pm, they will not be able to go to health facilities if these are open between 7:30am -3:30pm.

All these outputs will be informed by evidence base on what works both from studies in Mozambique and internationally, and from experience

Figure 4: The Theory of Change for the Programme

The Theory of Change from a provincial perspective

Province: Nampula
Health System Constraints: Long Distance to health facilities, early marriage and pregnancies among girls. High population density
Solution: Focus on improving the interaction between communities and health facilities by making more community health workers available in remote communities. Ensure that health facilities are ready when needed and can respond to emergencies because a large number of pregnant women will be girls who are likely to have complications.

Fig. 5 How the theory of change will be applied in Nampula province

Table 4: Theory of Change
Assumption	Evidence base
Inputs to processes
The Ministry of Health is committed to improving health outcomes	Strong. The Ministry of Health has numerous studies they have undertaken to analyse why indicators are not improving. However, there is little technical capacity to prioritise interventions[27]. Furthermore, recommendations are often not disseminated to policy makers in a way they can understand so as to translate the findings of these studies to practice.
Salaries for health workers will continue to be paid	Limited: The Ministry of Finance has stated that social sectors such as health and education will continue to be prioritised. However, salaries do not include contracted health workers not on the payroll who are essential for the delivery of services. / This will be monitored as one of the risks (table 9 below on page 34)
Processes to outputs
Health system issues will vary from one province to another	Strong. The underlying reasons for equity are context specific including geographical location, acceptability of the health service and affordability[28].In Mozambique this has translated into different Reproductive and maternal health outcomes in each province[29].
Minimum standards will translate into improved quality services	Strong: Minimum standards are one of the factors contributing to quality of care. Others are patient satisfaction and acceptability of services by families and health providers, referrals when needed and sound financial performance[30].
The right social change interventions can be found for each context	Limited: There are various approaches used to address social norms. However, there is limited analysis of which interventions are more effective in different contexts and why[31].
Outputs to Outcomes
There is political will to base practice on evidence of what works	Limited. There have been changes to implementation because of evidence at the Ministry of Health . Evidence suggests translating evidence into policy and practice requires stakeholder engagement and collaboration, community participation and local research[32]. .
Improving service delivery (through outputs 1-5) will result in stronger health systems	Strong: Equipping health facilities with adequate health workers, infrastructure, commodities and medical equipment contributes to quality service delivery. Interventions also need to empower communities to demand and access quality and improve linkages between communities and health facilities[33]. There also needs to be coordination to ensure an integrated approach to implementation and financing of Reproductive and Maternal Health interventions[34].
Outcome
A strong[4] health system is able to respond to arising needs	Strong. Health systems which can adapt to different challenges and needs within the population are considered to be strong[35].
Emergency preparadness translates into resilient[5] health services	Medium: Health systems are resilient when they are able to minimise the loss of life and still deliver health outcomes during and after a crisis[36]. Preparedness is a large part of this but the response of the system can usually only be revealed by a crisis event. .
[27] World Bank (2015) Public Expenditure Review.
[28] DFID (2010) Framework for results for improving reproductive, maternal and newborn health(pillar 3). https://www.gov.uk/government/uploads/system/uploads/attachment_data/file/67640/RMNH-framwork-for -results.pdf.
[29] Thinkwell (2016)
[30] Pittrof R, Campbell O (2000), Quality of maternal care: Silver bullet or red herring? London School of Hygiene and Tropical Medicine. http://r4d.dfid.gov.uk/PDF/Outputs/HpregQoMCSilverBulletorRedHerring.pdf
[31] Herbert S (2015) Social norms, contraceptives and family planning . GSDRC Helpdesk Research Report. http://www.gsdrc.org/wp-content/uploads/2015/09/HDQ1249.pdf
[32] Clar C, Campbell S, Davidson L, Graham W (2011)What are the effects of interventions to improve the uptake of evidence from health research into policy in low and middle-income countries? University of Aberdeen. http://r4d.dfid.gov.uk/PDF/Outputs/SystematicReviews/SR_EvidenceIntoPolicy_Graham_May2011_MinorEditsJuly2011.pdf
[33] International Federation of Red Cross and Red Crescent Societies (2013) Maternal, newborn and child heath framework. (based on lessons from 75 countries)
[34] WHO (2009) Investing in maternal, newborn and child health (based on Asia).
[4] A health system is considered to be strong when it it improves the health status of the populatin, defends people against diseases, allows people to participate in decisions that affect them and delivers equitable access to care. http://www.who.int/healthsystems/EN_HSSkeycomponents.pdf
[35] WHO (2010) Key components of a well functioning health.system http://www.who.int/healthsystems/EN_HSSkeycomponents.pdf
[5] Health system resilience can be defined as the capacity of health actors, institutions, and populations to prepare for and effectively respond to crises; maintain core functions when a crisis hits; and, informed by lessons learned during the crisis, reorganise if conditions require it.(the Lancet 2015- http://www.thelancet.com/pdfs/journals/lancet/PIIS0140-6736(15)60755-3.pdf)
[36] Kruk ME, Myers M, Varpilah ST, Dahn B(2015) What is a resilient heatlh system? Lessons from ebola.The Lancet http://www.thelancet.com/pdfs/journals/lancet/PIIS0140-6736(15)60755-3.pdf

50. All areas where evidence is weak will be monitored as part of the programme. For example, we will monitor how quickly the Government will translate lessons and evidence from the programmes into policies and interventions.51. The service provider will also monitor which interventions are more effective in different contexts throughout the country and the reason for this.
Table 5: An Assessment of potential programme options (individual scores out of 5)

Criteria /Options	Delivery through a joint UN programme		Support to the Ministry of Health through a service provider		A combination of the first two options + independent verification
	Description	Score	Description	Score	Description	Score
Reaching the poor and vulnerable particularly adolescents	Fully able to meet this objective on the supply side.	5	Full fit with objective and aims on both the demand and supply side. .	3	Fully able to meet this objective on the supply side	5
Value for money	UN has efficient procurement mechanisms. Paying service providers directly instead of the Ministry of Health is likely to be inefficient as this arrangement has not been used at scale in the sector. It may still be faster than Government systems at the sub-national level.	3	Difficult to separate administration costs of service provider from delivery costs. Need to ensure a separation between them to get true cost of approach.	2	Explore with UN how to reduce inefficiencies of not channelling funds through Government system	3
Management of risk including financial risk	Has good monitoring framework for financial risk although more transparency to donor is needed. Programmatic risk will need to be strengthened given constant changes in the context.	3	Strong on financial risk as paying suppliers directly. Programmatic risk may require political economy analysis which can be achieved by working with local partners.	3	Assessment at beginning of programme needed to map out all risks and review every three months	4
Sustainability and ownership of the approach	Government systems used for planning, and monitoring. Not channelling funds through Government systems will make system strengthening less effective.	3	Ministry of Health may refuse to work with the service provider. May also have to learn about Government systems such as the planning cycle.	2	Explore how to minimise the risks during programme inception. Service provider only involved in demand side so interaction with Government reduced. Will review if context changes so that Government systems can be used after two years and a half years.	3
Ensure DFID is meaningfully engaged in national policy dialogue	UN at policy table already. Will require some coordination to ensure DFID and UN messaging consistent, and that DFID retains a space in policy dialogue.	2	Government resistance to the service provider may undermine DFID influence with Government.	3	Include programme coordinator to represent DFID interests at the technical level and create space for DFID in policy dialogue.	4
Oversight of centrally managed programmes	UN has good partnerships with larger centrally managed programmes. They are not very good at sharing this knowledge.	3	Need to establish relationships with programmes. May struggle to get information from these programmes.	2	To be largely done through UN for larger programmes .Programme Coordinator can support through work at the Ministry of Health .	4
Total		19		15		23

Social and Gender Appraisal
Improving sexual, reproductive and maternal health in Mozambique will require a multi-pronged approach, with a particular emphasis on reaching adolescents. This calls for a concerted, innovative and iterative approach to addressing social and economic barriers to reproductive and maternal health, alongside strengthening the health system to provide the quality information, supplies, services and care that is needed.

Option 1- will strengthen the supply side of service delivery. Perceptions of low quality services and long distances prevent 54% of women from delivering in health facilities. This in turn increases the risk of illness or deaths from complications associated with childbirth. Support to system strengthening should address the systemic constraints to quality services. Community involvement interventions should also improve women’s decision to seek care while minimising post-partum bleeding, the main cause of maternal deaths in communities. The intervention will explore ways to reduce the effect of transportation delays in the decision to seek care.

Some two thirds (66%) of community health workers are men. The eligibility criteria excludes a large proportion of women by requiring them to have basic literacy. Although not reported, anecdotal evidence suggests that this gender disparity affects the delivery of outreach services for women and girls. Meanwhile only 11% of health facilities have youth friendly services, most of which cater to pregnant adolescents, excluding young men and young women who are not pregnant. Access to family planning will reduce the number of unwanted pregnancies. This in turn will reduce high risk pregnancies and unsafe abortions particularly among adolescents who make up 20% of maternal deaths. Family planning may also offer dual protection against pregnancies and HIV which have a disproportionate effect on young women.

Option 2- focused on generating demand for improved Reproductive and Maternal Health and family planning, will aim to address negative attitudes and beliefs around family planning methods, particularly around fear of sterility, based on myths about certain methods and misunderstanding of some of the physical side effects of methods. By using market led approaches to ensure access to contraception and promote contraceptive use as an aspiration, instead of through negative health messages, the programme will seek to promote voice, choice and control for women and girls over their fertility. It will also target influential people in local communities (including parents) to influence attitudes around women and girls’ control over their own fertility. An adaptive approach to programming will help to build in lessons on how to address to a shift in attitudes and behaviours.

Decisions and behaviours around reproductive and maternal health take place in the context of deep-rooted inequalities in gender relations. Gender norms mean that girls and their sexuality are often treated as a commodity. This translates into high rates of child marriage. Lobolo, or bride price, (where practised) is a vital source of income for families implying that daughters are married away when families are struggling[37]. Unmarried girls are under pressure to have transactional sex, and often also to get pregnant, with an older man who will provide some sort of economic security for herself or her family. These factors contribute to the high rate of early pregnancy[38].
[37] World Bank Gender paper (2011)
[38] UNICEF (2013)

The combination of option 1 and 2 should therefore imply a well-rounded approach to social factors affecting Reproductive and Maternal health.

What are the costs and benefits of each feasible option?
All the health conditions along the Reproductive and maternal health continuum (family planning, maternal, newborn and child health) contribute to a significant proportion of illness and premature deaths in Mozambique. The earlier section in the appraisal has already outlined a strong justification for option3. This section will therefore focus on assessing the balance of costs and benefits for the proposed intervention. The analysis includes a quantitative assessment of the costs and benefits of the service delivery and family planning components which make up the largest portion of programme costs. The expected benefits from health systems strengthening are more qualitative in nature and are discussed as part of the narrative, but are expected to help drive value for money of the programme through their impact on efficiency of overall spend.
Costs and benefits of the programme compared to the counterfactual
The total cost over the four years will be £34.3 million. These costs are expected to be highest in the third year of the programme when they will reach £11.5million annually. Table 6 (below) outlines the profile of expected programme costs. The costs for the service delivery component in year 1 are lower as the programme will finalise its design during this period. Spending will also be low in the first year for the family planning component reflecting the need to complete the European Union tendering process.

Table 6: Breakdown of the programme costs
Description	%	2016/17	2017/18	2018/19	2019/2020	Total
	100
Health Policy	4	100,000	500,000	500,000	425,000	1,525,000
Service Delivery through UN	69	1,500,000	7,000,000	7,500,000	7,500,000	23,500,000
Demand generation and M&E	22	100,000	1,500,000	3,000,000	2,925,000	7,525,000
Coordination (including Programme Manager and follow up of CMPs)	5	250,000	500,000	500,000	500,000	1,750,000
Total (£)		1,950,000	9,500,000	11,500,000	11,350,000	34,300,000

In addition to programme costs, it is also assumed that beneficiaries will bear some costs whilst accessing services. These are likely to include some foregone income, travel and medicine costs. The costs are estimated on the basis that approximately 60% of the population in the country currently access services of which a proportion will actually use services in a given year. An average of two half day visits a year per user is assumed. It is hoped that coverage of health services will in fact increase over the lifetime of the programme although the impacts of the economic crisis may limit this trend.
Calculating the benefits of the programme
To calculate the expected benefit of the service delivery and demand for family planning components, we estimate the impact of the programme on the number of Disability Adjusted Life Years averted, a measure of the burden of disease and number of years lost due to ill health in a country. We use existing WHO projections of Disability Adjusted Life Years averted for the Africa region for the years 2015 and 2030 together with trends in mortality in the Mozambique Demographic Health Survey to estimate the likely reduction in disease burden in the absence of DFID support.

In this particular case, we assume that in the absence of DFID support, Disability Adjusted Life Years averted will actually fall below the baseline projections due to pressures on the government’s budget. We therefore model DFID support as contributing to the original projection by an amount relative to the share of the population that DFID will support – effectively mitigating some of the shortfall in Disability Adjusted Life Years averted. This is considered a realistic approach given that it would be difficult to project an overall expansion in coverage at a time when resources for health service delivery are under pressure. A lag of a year is also introduced to reflect the fact that not all health benefits will impact immediately following access to a health service.

The counterfactual, or ‘do nothing’ scenario, reflects the effect of interventions in other sectors that will have an indirect effect on health outcomes (such as water or education), investments in health by the Government and support from other partners and centrally managed programmes supporting health including the Global Fund. Thus, the counterfactual would be a scenario of reduced resources available for discretionary spending by the health sector, assuming spending decisions by the Government and by other donors would not be affected by DFID’s decision not to intervene in health. These reduced resources would lead to reduced results overall and would not be enough to address the need set out in the strategic case.

Although an expansion in coverage is not modelled, increasing access still remains an overall aim of the programme. For instance, there is evidence that maternal and neonatal health suffers from systemic issues such as poor governance in terms of organisational weakness and fragmentation, inadequate information and accountability systems, institutional turf, poor management capacity within decentralised institutions and poor human resource management[39].If improved quality and expanded coverage is achieved, evidence suggests that this could lead to a reduction in mortality of over 30% with similar impacts on Disability Adjusted Life Years averted averted[6]. T Bhutta et al (2008) show that maternal and child health programs in primary health care at pragmatic coverage in Pakistan and Uganda could prevent 20–30% of all maternal deaths.[40] A study of a package of Maternal, Neonatal and Child Health interventions in Nepal that increased coverage by 15% led to a reduction in mortality of over 40%[7].
[39] Hulton et al, (2010), The Evidence Twoards MDG 5: A Working paper.
[6] Whilst closely correlated, the relationship between reduction in deaths and reduction in Disability Adjusted Life Years avert may not be linear as they also reflect reductions in healthy years of life due to morbidity.
[40] Bhutta et al (2008) Lancet 2008; 372: 972–89).
[7] The costs, benefits and cost effectiveness of interventions to reduce maternal morbidity and mortality in Mexico; 2007; Hu et al.

The estimate of Disability Adjusted Life Years averted for the family planning component is based on evidence that increased use of family planning leads to reduced maternal mortality and reduced maternal morbidity, due to both fewer pregnancies and fewer unsafe abortions. The cost per Disability Adjusted Life Year averted is based on analysis of a previous programme in Mozambique that sought to raise demand through social marketing of family planning products. Costs included a share of overheads and are expected to fall within a similar range for this programme.

We assume all benefits under the family planning component are additional. This seems reasonable given that the programme will be targeting adolescents in areas where demand is largely unmet. Other types of benefits that are less easily quantified, including direct benefits to families and wider impacts on social norms and increased women’s empowerment, are not included in the calculations. Table 7 sets out the anticipated change in Disability Adjusted Life Years averted.
Table 7: Estimates of reduction in Disability Adjusted Life Years averted lost

DFID best practice as described in DFID’s guidance note[8] on the use of Disability Adjusted Life Years averted in economic appraisals is to multiply the Disability Adjusted Life Years averted by the GDP per capita of the country. This provides an estimate of how much the reduction in the health gap is worth to the economy by looking at the income gained from one additional year of healthy life. The programme will avert an estimated 284,000 Disability Adjusted Life Years averted with the highest benefits expected to be achieved in 2018.
[8] A DALY can be thought of as representing one lost year of a healthy life due to death, disease or injury. GDP per capita can be taken as a lower-bound estimate of the value of a DALY averted in a given country in terms of income lost.

The family planning component averts significantly more Disability Adjusted Life Years averted than the service delivery component. Whilst well-designed family planning interventions are known to be cost effective, this difference is at least part due to the conservative approach used to estimate the impact of the service delivery intervention. The main argument for providing support via the Government is that it enables many, often interrelated issues to be tackled at once. Moreover, support provided through the system is more likely to produce equitable outcomes, and enables health system strengthening, which is a crucial outcome because health systems provide “the context within which strategies to improve health outcomes are designed, delivered and accessed”[41].[9]
[41] Hulton L et al, (2010), The Evidence Towards MDG5: AWorking Paper, p69

Through a functioning national health system the causes and consequences of poor health can be addressed efficiently as they are treated holistically and, sustainably, as opposed to interventions that address single diseases (draws from DFID note. The effects of system strengthening at the central, and subnational level should translate into improvements in service delivery over time but are not captured within the model. Option 1 includes the entire reproductive and maternal health continuum of care including longer acting contraceptive methods such as implants for older women who want to space their births (compared to Option 2 where adolescents want short term contraceptives which avert significantly lower Disability Adjusted Life Years averted). However, these Disability Adjusted Life Years averted are not included in the service delivery component. Option 2 also relies heavily on Option 1 as without a functional health system to ensure that commodities and qualified staff are available on the supply side, the demand generation component will be less effective and unsustainable

Additional indirect benefits to individuals and extended families from access to maternal and child health services are also not captured. System strengthening should result in improved management of the sector allowing for greater efficiencies in programming, allocation of resources and monitoring of results. These less easily quantifiable benefits are likely to be large in the long run, and crucial to ensure the sustainability of the results. It is likely that they would both increase the benefits relative to costs, and would be more significant under Option 1 and Option 3.

Cost Benefit Analysis
By discounting future benefits and costs at a rate of 10% per year we are able to calculate the overall net present value of the two largest programme components. Based on the assumptions outlined above, the analysis suggests a net present value of £84 million and a benefit cost ratio of 3.0, meaning that for every £1 spent, the programme is expected to generate benefits worth at least £3. Dividing the undiscounted total Disability Adjusted Life Years averted saved by the full economic costs associated with the two components provides a cost per Disability Adjusted Life Years estimate of £152. The WHO considers strategies and interventions to be highly cost-effective if the cost per Disability Adjusted Live years averted is less than the GDP per capita of the country. At an estimated GDP per capita of £529 in Mozambique in 2016, this indicates that the programme offers good value for money.

Sensitivity Analysis
There are a number of assumptions in the analysis that are likely to impact on the outcome of the cost benefit analysis. Sensitivity analysis tests the impact of changes to key assumptions on the overall balance of costs and benefits in the programme. These are summarised in the benefit-cost ratios in Table 8. A ratio value less than one indicates the programme at this point might cease to offer value for money.

Gross Domestic Product per capita is typically used to value a Disability Adjusted Life years averted. Where the very poor are targeted, this may be an over-estimate of the income gained. Halving the amount at which Disability Adjusted Life Years averted are valued at generates a benefit cost ratio of 1.5. Applying the minimum wage in the agricultural sector however, which is likely to represent much of the labour in rural areas, leads to an overall increase in the benefit cost ratio above the baseline.

The model is also sensitive to changes to the assumptions underpinning the impact of DFID support on Disability Adjusted Life Years averted. An increase in coverage in areas targeted with DFID support should improve the number of Disability Adjusted Life Years averted. Taking a different approach to estimating Disability Adjusted Life Years averted generates a lower but positive benefit cost ratio. Under this alternative approach, it is assumed that the programme supports an additional reduction in Disability Adjusted Life Years averted above the WHO projections equivalent only to the estimated uplift in maternal and child health resources contributed by the programme. This approach is considered to give an underestimate however as it does not take account of targeting funds or changing marginal effects of additional support.

Finally, the cost at which the family planning component is able to avert Disability Adjusted Life Years averted is based on previous programme experience in Mozambique and other countries. It is possible that targeting a new group of beneficiaries could lead to an increase in the average cost. This is tested by doubling the cost per Disability Adjusted Life Years to deliver family planning through demand side interventions.
Table 8 Sensitivity analysis
Scenario	Benefit-cost ratio
Baseline	3.0
Disability Adjusted Life Years averted valued at half GDP per capita	1.5
Disability Adjusted Life Years averted valued a minimum wage for agricultural sector	3.1
Disability Adjusted Life Years averted for service delivery component modelled on basis of percentage uplift to MNCH resources available	2.3
Cost per Disability Adjusted Life Years averted under family component doubled	1.9

The alternative outcomes modelled above demonstrate the importance of assumptions in the model, in assumptions on how Disability Adjusted Life Years averted are valued and the effectiveness of the programme in averting Disability Adjusted Life Years averted. The baseline analysis has sought to use conservative estimates to ensure robustness to changes in performance. None of the alternative scenarios lead to costs outweighing benefits suggesting the programme has high chances of delivering value for money. Nevertheless, the programme will aim to monitor and test assumptions with real evidence over the course of the programme to contribute to ongoing assessment of whether the programme represents good value for money.
Breakeven analysis of TA support for systems strengthening
77. Since most of the technical assistance support will be focussed on improving the quality and efficiency of the health system, we can estimate the percentage gain in efficiency of government expenditure on health necessary for the investment in technical support to effectively ‘break even’. Assuming a more gradual increase in total health expenditure over the next four years, and approximately £2 million in technical assistance, it is estimated that the technical assistance will need to generate less than 1% of efficiency savings in health spend over the four years of the programme to justify the investment. The value for money section below sets out some potential areas for monitoring efficiency improvements depending on the exact nature of the final support.
What measures can be used to asses value for money for the intervention?
78. The programme will develop value for money indicators for the different components during the inception phase. The adaptive nature of the programme means that although some value for money indicators will be constant over the life of the programme, others will be developed as the programme evolves. These indicators will be reviewed at least twice a year to inform programme implementation.
Economy
79. Value for money will be considered when awarding contracts to the service providers and when signing agreements with the UN. Various unit costs will be monitored throughout the life of the programme. These will include: unit costs of distributing medical supplies, procuring equipment and medical supplies and commodities. The programme will also work with partners to estimate the unit costs of training facilities and community health workers.
Efficiency
80. As mentioned in the strategic case, it is estimated that an additional $7 per person can be gained in health expenditure through allocative and operational efficiencies[42]. Opportunities exist through the proposed programme to improve value for money by helping the Government make their resource allocations based on evidence including disease burden and population size. The proposed programme will include the following tools to inform planning and prioritisation to bring about more efficiency:
[42] World Bank (2015) Public expenditure review of the Health Sector in Mozambique.
- Dissemination and discussion with the Government of the World Bank’s Public Expenditure Review of the Health Sector
- Analysis and research as recommended by the Public Expenditure review including a public Expenditure Tracking Survey to monitor whether funds are reaching their intended beneficiaries and are used for the intended purposes.
- This will be complemented on the demand side by beneficiary feedback through various methods implemented by DFID’s Citizen Engagement Programme

81. The focus on health financing and human resources as part of the systems strengthening support is likely to result in improved performance of health workers, reduced absenteeism and better use of existing resources. Depending on the focus of technical assistance and availability of data, some or all of the following indicators could be selected to monitor the contributions of technical assistance to efficiency gains:
- Time savings by streamlining procurement processes and economy savings through stronger procurement negotiations
- Reduced wastage from more transparent procurement
- Better targeting and allocation of resources in line with need, enabled through strengthened monitoring and budgeting systems
- Better flow of funds at all levels and timely budget execution through improvements to public financial management processes
- More detailed information through the programme’s budget will allow us to develop a large range of efficiency metrics for the programme in terms of costs per specific intervention. This will be prioritised during the inception phase and programme mid-term review.

82. We will also work to ensure that proposed budgets from service providers, the UN and other suppliers will represent value for money from an efficiency perspective. Indicators to measure efficiency will be included in a value for money matrix that will be monitored throughout the implementation of the programme.

Effectiveness
83. The effectiveness of the programme will be measured through:
- Programme outcomes to monitor cost per Disability Adjusted Life Years averted on a periodic basis.
- Changes to health outcomes, particularly those outlined in the business case (child, newborn, maternal mortality rates, contraceptive prevalence rates) against implementation costs and expected results in the focus provinces and overall in the country.
- Government commitment to institutionalising elements of the programme as noted in minutes of meetings with the Ministry of Health and policy documents.
- Coverage of maternal and child services across the country, in particular in rural areas.
84. We can also measure the effectiveness of the overall programme by assessing the extent to which it helps other UK programmes to deliver their targets. This can include the delivery of integrated programmes in health facilities. For example, the delivery of HIV & AIDS testing for pregnant women and adolescents as part of a comprehensive package for sexual reproductive health.

85. As with efficiency measures, we will use contracts and agreements to develop effectiveness indicators and set baselines and processes for monitoring these with service providers and implementing partners

Commercial Case
86. The preferred option will use a combination of direct and indirect procurement. This will allow the UK Government to take advantage of the UN’s policy influencing and technical support for system strengthening. A service provider will be contracted to explore innovative ways to generate demand for family planning.

Table 9: A summary of the procurement arrangements in the programme
Components	Delivery Channel	Procurement type	Procurement method
Health policy	UNFPA	Indirect	Standard agreement between DFID and UNFPA
Service Delivery	UNICEF, UNFPA and WHO	Indirect	Standard agreement between DFID and UNFPA[10]
Demand generation and M&E	Service Provider	Direct	Contract
Coordination and oversight	Programme Coordinator	Direct (local if < 106k)	Contract
[10] UNFPA will then have an agreement with the other two agencies so that it can disburse funds to them once these are received from DFID.

Indirect procurement
87. Indirect procurement through the UN agencies will account for £23.5 million (69%) of the total budget. The agencies will be contracted using a Standard Administration Arrangement whereby UNFPA will be the coordinator responsible for reporting on behalf of all three agencies. An 8% overhead recovery cost would be applied by each agency on their allocation portion of the funds.

88. UNFPA will be the fund manager responsible for managing all the funds. Funds will be allocated to all the agencies as agreed in the annual plan, but the accountability will rest with UNFPA who will charge an additional 1% managing fee as part of the Standard Administrative Agreement (SAA) which exists to enable the lead agency to play a coordination role which then incurs an additional 1% charge on the ‘total funds’ as a coordination fee rather than an extra 8%. UNICEF would take lead accountability but DFID will retain dialogue with the other implementing agencies via the programme steering committee.

89. As DFID funds will not be channelled directly to Government, there will be an added layer of administration in spending the funds. The UN agencies will need to act as Fund Managers in paying the Ministry of Health ’s suppliers directly.

90. We would anticipate an indirect management cost in the region of 4-5% from each UN agency in addition to the standard 8% central overhead recovery cost i.e. approximately 12-13% of costs being central and indirect costs, plus an additional 1% for UNFPA as Fund Manager. This is competitive with the potential indirect management costs from the private sector in Mozambique. However, we will need to ensure that the base costs upon which the overheads are applied are also competitive prior to any commitments being made.

91. We will also ensure that a detailed Due Diligence is undertaken on each UN partner to fully assess their capacity and capability to deliver prior to any commitments being made. Disbursements to the UN partners will only be made upon receipt of an agreed activity and workplan to fully justify the disbursement value. We will work with the UN partners for each of them to deliver specific value for money indicators in line with those outlined in the appraisal case.

The role of each agency in the programme:

UNICEF
The strongest of the UN agencies, UNICEF has a strong presence at both policy dialogue and implementation at the sub-national level. Their technical expertise is across several interventions that affect children under five years of age including nutrition, malaria and community health. The agency also supports the Ministry of Health in health financing and the centrally funded GAVI Alliance on vaccines. DFIDM has successfully worked with UNICEF over the years on a number of programmes across the office.

WHO
This agency specialises in health allowing it to support the Ministry of Health to set up policies and actions to improve the effective delivery of public health. Their work includes supporting surveillance of the main diseases, supporting the management of human resources for health and helping the Ministry of Health to prepare for disease outbreaks. WHO is able to draw on their international expertise when necessary.

UNFPA
UNFPA specialise in sexual and reproductive health and rights, working closely with the Ministry of Health and the private sector to increase the uptake of family planning throughout the country. DFID centrally is supporting the UNFPA Supplies programme with £340m over seven years (from 2013-2019) to procure contraceptives and essential medicines for maternal health in 46 countries including Mozambique. This programme counts on UNFPA’s comparative advantage in procuring family planning commodities at competitive prices. UNFPA currently procures 60% of all the family planning commodities in Mozambique. UNFPA will act as the Fund Manager of this programme.

92. The programme approach has secured buy-in from the Ministry of Health and the three UN agencies. There is also interest from other health partners who are looking for alternative delivery mechanisms given that the Common Fund is currently on hold. The UN collaborates with a range of stakeholders including a few centrally managed programmes. These include the Global Funds who are getting complimentary support from WHO on tuberculosis and the Clinton Health Access Initiative who are contracted by UNICEF to distribute commodities from provincial levels to high volume health facilities. DFID will be able to take advantage of the UN’s collective expertise and experience, to enhance the long-term impact of this project.

Direct Procurement
93. Demand generation of family planning and independent verification: DFID will undertake competitive tender process advertising via the Official Journal of the European Union (OJEU) for a non-state company or civil society organisation/consortium with relevant local and international experience to undertake the management and implementation of this component.

94. We will again ensure that the appointed service provider is held fully accountable for the contract management as well as their programme management via an agreed suite of contract management key performance indicators. We will ensure that the appointed service provider commits to an agreed list of Value for money indicators to ensure they and DFID Mozambique maintain a clear oversight of the on-going value for money of this component.

95. Independent verification: Procurement of services for third party validation of results. This will include the development of an monitoring and evaluation framework for the programme and periodic field visits to monitor results which will feed into the annual reviews. There will be a baseline study and a more in depth mid-term and end of programme evaluation. .A competitive tender via the OJEU will be launched to seek a combination of local and international expertise. This can also provide an opportunity to strengthen the local monitoring capacity. The independent verification will be undertaken by the service provider that will be responsible for the demand generation to ensure a stronger link between the supply and demand sides of the programme.

96. Coordination and oversight: The DFID-M office will retain these funds to undertake audits and annual reviews which will enable greater oversight of the programme. These funds will also cover the costs of the Programme Coordinator placed at the Ministry of Health for technical support.

97. All procurement will be contracted through a competitive bidding process in line with DFID procurement guidelines. For procurements below the European Union threshold (<£106k) the programme team will work with the DFID Mozambique Delegated Procurement Officer to secure services.

98. For those services above the European Union threshold (>£106k), the team will work with the Procurement and Commercial Department (PCD) to manage tenders as per the European Union guidelines. All bids will be assessed on the basis of cost, deliverables, quality and value for money. The programme team will work with the Regional Commercial Adviser, and commercial experts from PCD to have a competitive procurement process, which should deliver costs at market rates and maximise value for money to the programme.

99. Transparency, competitive process and value for money will be maximized in all contracts through early market engagement, setting effective evaluation criteria and contract management processes.

100. All suppliers in the programme will have up to 8 months for inception where they can finalise their design, followed by an implementation phase.

Break Clause
111. For the service provider, there will be a break clause whereby DFID-Mozambique will decide if they will transition from the inception to the implementation phase. If the design is assessed as not being feasible then the team may decide not to go on with the supplier. An alternative supplier will be sought although this will delay the programme approach. During implementation, all suppliers and implementers will be required to present quarterly progress reports.

102. All agreements will be up to the end of the third year and include the possibility of renewal to take into consideration the break clause in the programme.
Financial Case
What are the costs, how are they profiled and how will you ensure accurate forecasting?
103. The total programme budget will be £34.3 million over four years (2016-2019). The initial allocation for each component is outlined below. This would be reviewed at least once a year in line with the performance of each component and any emerging evidence in line with the adaptive programme approach. For this reason, the budget in Table 10 is only indicative. £23.5 million (69%) of funds will be channelled to the UN agencies, £7.5 million (22)% will be to a contracted service provider for demand generation of family planning and monitoring and evaluation mid- way and then at the end of the programme. £1.75 million (5%) will be for the DFID office to be able to coordinate UK support to the sector, collaborate with other partners and have oversight of the programme (eg through field visits). The latter will include a programme coordinator who will be placed at the Ministry of Health to support coordination between the agencies and have oversight of the selected centrally managed agencies in the sector. Table10 below shows the budget breakdown.

Table 10 Annual budget breakdown of the programme

Description	%	2016/17	2017/18	2018/19	2019/2020	Total
	100
Health Policy	4	100,000	500,000	500,000	425,000	1,525,000
Service Delivery through UN	69	1,500,000	7,000,000	7,500,000	7,500,000	23,500,000
Demand generation and M&E	22	100,000	1,500,000	3,000,000	2,925,000	7,525,000
Coordination (including Programme Manager and follow up of CMPs)	5	250,000	500,000	500,000	500,000	1,750,000
Total (£)		1,950,000	9,500,000	11,500,000	11,350,000	34,300,000

What are the costs to be incurred directly by DFID?
104. All costs described on Table 10 will be directly funded by DFID from programme resources. The cost estimates are based on implementation of similar programmes. The main cost drivers are technical and management support which will be provided in both the health policy and service delivery components. The second largest cost is expected to be medicines and commodities which are necessary for service delivery. The annual programme plan to be agreed at the end of the inception phase will identify and quantify the cost drivers

How will it be funded: capital/programme/admin?
105. The programme will be funded from resources which have been budgeted for DFID Mozambique’s business plan (2016/17-19/20). Most of the funding will be from DFID’s programmatic budget. However, up to £5 million will be from the capital budget for upgrading health facilities, providing water, sanitation and electricity in health facilities, and buying incinerators for the disposal of medical waste.

How will funds be paid out?
106. The programme will have the following funding mechanisms:
UN agencies
A Standard Agreement will be signed between DFID and with UNFPA as the Fund Manager. It will clearly set out the roles and responsibilities of each of the member of the consortium, including UNICEF as the convening agency. UNFPA will then sign an agreement with UNICEF and WHO respectively. This second agreement will be shared with DFID. Payments to UNFPA will be made in arrears where possible. We will however approach UNFPA to decide if payments should be in arrears or if they provide justification, supported by a project budget, we will consider the case for payments quarterly in advance. Any requests in excess of quarterly advance payments will be need to be cleared with the Fund Manager. Figure 6 (below) explains the flow of funds for delivery through the UN.
Figure 6 indicates that support to the subnational level will be made directly to contractors or service providers (for water and electricity for example). There will be a few instances where goods or services will first go through the central level at the Ministry of Health to reach provinces. For example, commodities from the central warehouse.

 Figure 6: Programme flow of funds (UN Agencies model)

Service Provider
Disbursements will be made in arrears and subject to satisfactory performance and delivery of outputs. The service provider will be able to pay non-state actors directly. Any support to the Government will follow a similar approach to Figure 6 above where the service provider will be paid directly.

What is the assessment of financial risk and fraud?
107. DFID support to the sector will be mainly through the UNA and a service provider. No funds will be channelled directly to Government. A due diligence assessment of all UNA will be carried out before any funds are channelled through them. This will include a new due diligence assessment for UNICEF as their existing assessment will be coming to the end of its three year validity in March 2017. The main suppliers the UN will work with will also have to demonstrate that their PFM systems are robust as demonstrated by similar risk assessments or due diligence assessments that the UNA will be required to undertake with their suppliers. The agreement with the UN will state that any incidents of suspected fraud or corruption will need to be reported to DFID immediately. UNICEF will also have to undertake periodic spot checks of suppliers and in health facilities to ensure that all goods and services that were paid, are being used for their intended purpose. DFID- Mozambique will ask for evidence of these spot checks as in the quarterly reports.

108. PFM in the health sector remains an overall concern. The DFID fiduciary risk assessment of the Ministry of Health carried out in 2012, assessed risk as being “substantial”. Nonetheless, the Ministry of Health continues to demonstrate commitment and accelerated actions to improve public financial management performance through on-going reform of the Finance Department with a recent (2016) Health adjusted Public Expenditure and Framework Assessment noting a positive trajectory in most areas. However, these improvements come from a very low base.

109. In terms of the Service Providers, bidders will be asked to prove their financial credibility including through a due diligence questionnaire to ascertain the capacity of their systems (financial, human resources and procurement). This requirement will be made a key selection criterion during evaluation of bids to ensure that the risk is minimal. For any downstream recipients, a clause will be embedded in the contract making it mandatory for the Service Provider to carry out due diligence checks on all sub recipients before any agreements can be entered into and funds released.

110. DFID-M recently (April 2016) formulated an Anti-Corruption Strategy which will provide a comprehensive and coordinated approach to anti-corruption in the provinces, assessing where gaps are or there is a lack of necessary safeguards and defining interventions to address such gaps, maximising synergies between different interventions and teams. This strategy will bring together DFID Mozambique’s interventions to manage the fiduciary risk to UK tax-payer’s funds as well as actions being taken to ensure corruption is addressed.

111. A significant portion of technical assistance for this programme will also focus on strengthening government capacity to address fiduciary risk, strengthen procurement mechanisms and monitoring and evaluation.
How will expenditure be monitored, reported and accounted for?
112. The Senior Responsible Owner is ultimately accountable for the expenditure of funds against this BC. The Programme Coordinator will set up an ARIES project with separate components for each programme or contract managed and with accurate funding types and sector input codes. In the implementation phase, the PM will be responsible for producing reports on actual and forecast spend against each component on a monthly basis, which will be used to monitor partner performance.

113. The Senior Responsible Owner will authorise disbursements of funds based on the agreed funding profile set out in the funding agreements and contracts and upon the assessment of partner performance and reporting. All the service providers will be expected to provide proper documentation of expenses and provide evidence of satisfactory delivery of milestones and project progress reports. Expenditure will be monitored through quarterly financial and narrative reports which will be reviewed by the DFID team to ensure value for money principles are being met and ask for further information in the case of any discrepancies; or where information is unclear or incomplete. Overall project expenditure will be managed through ARIES, in line with DFID smart rules.

114. Management arrangements for all assets bought by private service providers will be stated in the formal agreement to remain as the property of DFID until the end of the project when DFID will take a decision on the disposal options. DFID will ensure that implementers maintain an asset inventory and monitor assets on a bi-annual basis. Assets bought by a UN organisation are transferred to the UN at the point of funding. The relevant UN agency will therefore decide how to dispose of assets in line with their internal procedures.  UN agencies should maintain an asset register and share this with DFID

Management Case

This section explains the governance and management arrangements for the implementation of the programme. It outlines the expected roles and responsibilities of the stakeholders involved including DFID’s resourcing (Senior Responsible Owner, Programme Coordinator, and project team). It is important to note that no funds will be channelled directly to the government.

Delivery
The programme will be set up based on proven flexible and responsive approaches being used in DFID Mozambique. It will entail the following:

Inception phase
6-8 months, led by DFID and focused on setting up the programme management arrangements with the UNA and the Ministry of Health. The following activities will be undertaken during this period:
- Deciding on the focus provinces where different health system constraints will be addressed. A clear set of criteria will be set out for identifying the provinces. Areas to be assessed will include: disease profile, health system constraints, population density and socio-cultural barriers affecting health outcomes.
- Health system assessments in each of the provinces to get a baseline for Reproductive and Maternal Health indicators. This will include health facility assessments to prioritise which interventions and equipment will need to be purchased in each of the target areas.
- UNICEF as the convening agency will be the lead reporting agency. However, they will not be responsible for the performance of the other two agencies Each agency will agree with DFID how they will manage and report performance. This will include mechanisms for DFID to review and challenge the UNA on performance.
- Quick wins activities for the demand generation component while the procurement process for a service provider is ongoing. These are likely to include research to identify the most appropriate social change messages and interventions. This research will ensure that the DFID team are prepared for the designs that will be proposed by bidders during the procurement process.
- Outline of a workplan and budget for the first two years of the programme based on the proposal that DFID received. This workplan will be more detailed than the proposal and involve the Ministry of Health at the central, provincial and district level in the focus provinces. It will also outline any research that the UNA and Ministry of Health think needs to happen during the implementation period.
- Recruitment of the Programme Coordinator and their induction into the Ministry of Health.

Implementation phase 9-24 months
During this period the four components (health policy, service delivery, demand generation and monitoring and evaluation and coordination) will be implemented simultaneously. There will be an annual planning process in September of each year where the different stakeholders will meet to learn and change approach. There will be clarification of the role of the different stakeholders including the service providers and UN Agencies.

It is not expected that the Programme will continue after the four years as the Global Financing Facility should take over each of the components that this programme will be implementing. However, during implementation of the programme, the possibility of continuing the programme even with the Global Financing Facility process in place, will be assessed.

Management and governance arrangements
A flexible approach to spending decisions and results setting will be built into the programme to enable it to respond quickly to changing circumstances and arising needs. These will enable funding to be scaled up or down across the four outputs when needed. Output 1 on equipping health facilities is likely to absorb most of the funding as resources are channelled to health facilities to deliver services. However, it is expected that the other three components will also require different resources over time depending on the province and its specific health system constraint.

In addition to the annual planning meeting in September and a review meeting in March, the programme will have regular planning and strategy meetings with all the stakeholders to revise activities, spending decisions and timeframes. Having an Monitoring and evaluation framework embedded into the programme should enable this flexibility to be accompanied by accountability.

Governance Structure
The governance structures to manage the programme will build on lessons learned from other similar projects. The diagram below illustrates the overall governance structure, including the following members:

STEERING COMMITTEE
Key stakeholders including beneficiaries

With refere

Administration Committee
DFID, MoH representatives

Ministry of Health (Provinces and Central Directorates)
Service Provider

UN Agencies

DFID team
The core programme team will include the Mozambique Health Adviser as the senior responsible officer (Senior Responsible Owner), the Programme Coordinator placed at the Ministry of Health , the human development and resilience team leader and a programme manager. The Senior Responsible Owner will represent DFID at the Implementation Group meetings. Technical inputs will be sought from the DFID Social Development, Water and Sanitation, Governance and Results advisors for the different components of the programme as needed. This will ensure that work is across the team and the health portfolio can achieve its potential. Overall oversight will be provided by the Head of Office.
UN Agencies team
A Standard Administrative Arrangement will be signed between DFID and UNFPA as the Fund Manager for the UN. This agreement will outline the roles and responsibilities of each of the agencies.
A break clause in Agreement will allow DFID-M to review the agreement to assess value for money of the approach including whether not channelling UK Government funds through Government systems is still the best approach given the context in the country. If no changes are needed then the agreement will be renewed for the remainder of the programme.
Contract with the Service Provider
The break clause at the end of the inception phase will provide DFID with the opportunity to decide if it doesn’t continue with either the UN Agencies or the family planning service provider. This decision will be based on the feasibility of the approach and whether it represents good value for money.

The Senior Responsible Owner will also continue to participate in strategic sector meetings including the monthly health donor group meetings and relevant technical working groups to further our influencing agenda.

The Ministry of Health at central level chaired the Reproductive, Maternal, Neonatal and Child Health Trust Fund in Mozambique. Since 2013 the £201m programme supported catalytic Reproductive and Maternal Health interventions in 29 countries in Africa and Asia. DFID centrally contributed £79m until June 2016. In Mozambique the Programme was implemented by the UN Agencies. Drawing upon lessons globally through the Trust Fund , the key features in the management of the programme are:
- Government ownership/leadership: ensuring the priorities are those of the government and that actions fully align within the defined strategic aims
- Adaptive/ flexible programming ensuring that any defined activities that are not performing or no longer relevant can be changed. Components that succeed can be scaled up while those that fail or face challenges can be scaled down.
- Coordination: ensuring that actions complement, rather than compete with other channels of support (including domestic revenue), giving space to ear-marked funding where appropriate to to maximize the total resource envelope for Reproductive and Maternal Health and health system strengthening.

The Steering Committee: Provides strategic direction, oversight and decision making on priority actions. These will be based on an annual plan of action aligned to the sector’s national annual plan prepared by the Implementation Group with support of the Convening Agent. The Steering Committee will be chaired by the Ministry of Health (proposed candidate Permanent Secretary) would include participation of the Head of Cooperation for DFID, Representative of each Participating UN Agencies, and if agreed, representative of civil society organizations. Where sub-national results (e.g. a geographical focus) are central to the discussion, the Provincial Health Directors would be invited. The Convening Agent would coordinate the organization of meetings with the chair and minute the discussion and decisions. The steering committee would meet twice yearly, synchronized to the wider health donor group and annual planning processes.

Administrative committee: Provides technical and operational direction to agreed priority actions, making minor corrections during the year with quarterly meetings or more frequently if needed. As a subset and complement, but not replacing existing health donor and technical working groups, the Administration Group, chaired by the Director of Public Health would meet with the UN agencies and DFID Senior Responsible Owner and other staff as needed. The scope of discussion would be upon the DFID supported activities but would include related parallel support given for the same actions for better clarity and transparency. The convening agent would coordinate the organization of meetings with the Chair and minute the discussion and decisions.

Fund Manager- (FM) Accountable for effective and impartial fiduciary management. This role will be UNFPA’s responsibility. DFID will ensure that UNFPA have adequate capacity to perform this role through the due diligence assessment and in discussions with the UNA.

Convening Agent (CA). Accountable for coordination among participating organizations and for consolidating narrative reporting; responsible for coordinating all the Joint Programme partners, and reporting back to the Steering Committee. UNICEF will play this role.

Service Provider- Will have a representative in the steering committee and the administrative to inform how demand is meeting supply and to report on the performance of the programme based on their assessments. A representative will also participate in the quarterly administration group meetings providing updates on the demand side programme. This will aid the coordination of the different components of the programme.

Other Stakeholders including beneficiaries- Donor representatives that support the target provinces or communities directly benefitting from the programme will be invited to the Steering Committee. They will be able to provide additional accountability and insights to the programme.
GROSS RISK / Table 11: Summary of Programme Risks					NET RISK
Risk Area	Triggers	Proba-bility	Impa-ct		Mitigation Measures		Probabi-lity		Impa-ct		Risk Owner
	Political/Economic
1. Conflict and debt crisis continue, affecting DFID’s ability to deliver its programmes.	a. Sustained fighting in parts of central/north Mozambique, with military and civilian casualties; / b. Increased reporting from credible sources of internally displaced persons and health workers abandoning their posts;	H		Ma		i. Liaise with the Governance Team and the High Commission to monitor developments closely. / ii. Ensure that the Health programme is “conflict sensitive” through a process, with up-to-date risk matrices and regular conversation with partners on their approach to risks. / iii.Ensure that the programme adapts to changes in the context while maintaining focus on the poorest and most vulnerable;		Med-H		Mo	Team Leader
2. A reduction in State expenditure in Health undermines the ability to deliver the programme	a.Increased prices of medicines and commodities as a result of currency depreciation/shortage of foreign currency leading to stock outs in health facilities; / b.GoM budget cuts affect allocations for service delivery including salaries	H		S		i.Strategic technical support through this programme can engage with Government of Mozambique to ensure that cuts are planned and minimise their effect on the poorest and most vulnerable; / ii.Adaptive approach of the programme should ensure that the programme can help the Ministry of Health to minimise the effect of the cuts (except for salaries). / iii. Escalate dialogue between partners and Government to discuss ways to minimise disruption to service delivery through cuts.		Med-H		Ma	Senior Responsible owner
	Programmatic risk
3. UN agencies fail to coordinate undermining programme performance	a. UN agencies don’t have clear roles and responsibilities / b.Agencies do not speak to Government of Mozambique or other partners with once voice / c. UNFPA as fund manager doesn’t allocate on time or forecast accurately affecting overall programme performance / d.UN do not coordinate with each other or with the service provider	H		Ma		i. Ensure first 6 months of programme are to agree roles and ways of working / ii. Agree on mechanisms to communicate with Government and partners / iii. Ensure that due diligence is carried out and gaps addressed quickly. d. Include indicators for coordination among UN and with service provider in performance based tranche		Med-H	Mo				Senior Responsible Owner
	Partner/Results and VfM
4. Weak Ministry of Health capacity impacts negatively on results,	a. Annual reviews reveal that programme implementation is unsatisfactory; / b. Delivery plans in place to address slippages not fulfilled; / c. Lack of Government counterpart at the different levels;	Med-H		Ma		i. Include strategic decision makers in the Steering Committee / ii. Monitor implementation of delivery plans through quarterly meetings / iii.Agree with the Ministry of Health that their responsibility includes providing a counterpart at the different levels ;		Med-H	Mi				Senior Responsible owner
5.High costs of the programme as funding not be channelled directly through Government	a. UN/Service provider charge DFID high costs as paying suppliers directly / bc. Delays in implementation because funding not going through Government	Med-H		Ma		i.Kick-off meetings with UN/Service providers to understand funding flows / ii.Set and monitor value for money indicators jointly with UN and Service provider / iii.Ensure UN have sufficient capacity to manage added layers to prevent delays / iv.Consider changing partners during programme break clause		Med-L	Mo				Senior Responsible Owenr
6. Little beneficiary feedback in reports	a.Little beneficiary feedback in annual reviews or other reports / b. Low uptake of services including family planning	Med-H		Mo		i.Strengthen existing mechanisms in health centres to get beneficiary feedback / ii. Include qualitative research in annual reviews / iii. Have regular field visits where views of beneficiaries are heard.		L	Mi				Senior Responsible Owenr
	Fraud and Corruption
7. Fraud and corruption in the programme adversely impact on achievement of objectives and DFID’s reputation.	a.Health reforms slow down; / b. Surveys indicate misuse of funds and commodities; / c. Beneficiaries report increased informal fees.	Med-H		Mo		i.Liaise with the World Bank financial management support to Ministry of Health (especially audit and procurement); / ii. Agree anti-corruption and Counter-Fraud measures in the programme including: / More systematic use of Beneficiary feedback in programmes, including to ensure corruption cases are captured. / Systemic reporting and escalation of fraud concerns	Med-L		Mi				Senior Responsible Owner
	Shocks
8. Major humanitarian emergency due to climatic shocks and or disease outbreak	a. Outbreak of disease disrupts services / b. Some kind of climatic shock undermine delivery of routine services	Med-H		Ma		a). Ensure that support for disease preparedness is robust and systemic minimising disruptions to service delivery and making systems more robust. / b) Support institutional capacity building for disease outbreaks.	Med-L		Mo			Senior Responsible Owner
9. There are multiple partners in the health sector and the programme struggles to bring coherence	a)The programme is not discussed as part of the sector dialogue / b)Ministry of Health staff are not available to make strategic decisions / c)The GFF is discussed separately from the programme	M		Ma		a)Ensure that the programme is embedded into existing dialogue mechanisms / b) Discuss the programme with relevant stakeholders during the inception phase eg. World Bank	Med-L		Mo			Senior Responsible Owner

Probability: Med-L= Medium Low, Med-H= Medium High, H= High
Individual issue/risk: Mi= Minor, Mo= Moderate, Ma= Major, S= Severe

Smart Guide
The Business Case

- Sets out the case for a programme, adapted to suit the context
- Explains very clearly what the programme will do within what timeframe and is explicit about the risks and uncertainties and how they will be managed
- Records an understanding for DFID, our partners and intended beneficiaries about what we are planning to do and the results we expect to achieve
- Allows DFID to report to the UK public on what we are doing with taxpayers’ funds

The Business Case is structured around the Treasury 5-case model. Within this broad framework the design should be adapted to suit different contexts and investment types. The content is indicative, not prescriptive and teams are encouraged to use judgement in making a logical argument to make the case in a way that suits the individual investment. There is also a set of questions in the Smart Rules that design teams should consider during the process. This is not a checklist and only the questions relevant to the context should be answered.

Teams should refer to the considerations below as a guide to writing the business case

Intervention Summary (2 Pages)
A succinct and unambiguous description of what the project will do. The summary sets out the problem the programme will address, what it will do and what the money will be spent on. It sets out the expected results in the context of the Operational Plan and DFID’s wider priorities and a summary of risks. The accompanying submission should set out any sensitive information that supports the case (e.g. risk tolerances and escalation measures)
Strategic Case
This section makes the case for DFID intervention by setting out the overarching context and the problem to be addressed. It should be clear what the programme will do and how with evidence. It should link to – but not repeat – the Operational Plan with a clear illustration of how the programme contributes to DFID global and portfolio priorities of poverty reduction.
Appraisal Case
The Appraisal Case explores how we will address the need in the Strategic Case in a way that optimises value for money. It appraises genuinely feasible options for achieving the objectives, including high level commercial choices , with a summary of the quality of evidence. The appraisal considers delivery mechanisms including capability and capacity, costs and benefits, risks and likelihood of success. It concludes with a preferred option.
Commercial Case
This section provides more detail on implementation and how value for money will be achieved. It sets out the procurement approach and requirements, proposed funding instrument and how the choice of instrument will be used to ensure vfm. It considers the market place response to this intervention with an explanation of how supplier performance would be managed. It sets out the procurement policies, capabilities and systems of the third party entity to ensure we get vfm.
Financial Case
This section sets out issues of affordability and the sources of funding. It includes a high level budget which does not impair VfM in procurement exercises for individual contracts. It sets out how funds will be disbursed and how expenditure will be monitored, reported and accounted. It highlights the evidence underpinning a judgement that funds will be used for the intended purposes.
Management Case
This section focuses on governance and management arrangements and the ability to deliver. It sets out the management implications for the business unit/ level of effort with realistic timings for mobilisation and start up. It outlines out the expected roles and responsibilities, including DFID’s own resourcing strategies (SENIOR RESPONSIBLE OWNER, project team etc). / It sets out how it will respond to changes in context and the key elements of the Delivery Plan, key milestones and decision points where we can course correct. It includes a clear illustration of the risks, tolerances and approach to escalating problems and issues as well as exit and possible closure scenarios.