Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Global Mine Action Programme (GMAP) – First Annual Review
Programme Value: £30,000,000		Review Date: 15/01/2015
Programme Code:	Start Date: 28/01/2014	End Date: 31/07/2017

Summary of Programme Performance
Year	1
Programme Score
Risk Rating	Med

Summary of progress and lessons learnt since last review

The purpose of the Global Mine Action Programme (GMAP) is to reduce the humanitarian and development impact of landmines and Explosive Remnants of War (ERW).

Approved in January 2014, operations in five countries (Mozambique, Sri Lanka, Vietnam, Cambodia and Laos) began in July 2014. This included six contracts to conduct demining activities, alongside some Mine Risk Education (MRE) work; and a single contract to conduct capacity building activities with national and regional demining authorities. Activities have begun in all countries resulting in 229 ha of land being released.

Delays to procurement has meant that implementation in Cambodia and Laos has been slower to start. Greater realism about procurement timescales and set-up phases is needed as further contracts are awarded in new countries under Phase Two.

The first major six-monthly reports for each of these contracts are due early in 2015. This annual review is therefore reporting on the first quarter of contract operations for which reporting is available.

Baseline community surveys have been completed (with the exception of Laos) for the outcome indicators.

Summary of recommendations for the next year:

- To avoid similar programme extensions being required at the end of GMAP, consideration of the design of the next programme should begin later in 2015.
- Logframe to be finalised before programme reports are due in July 2015, with agreement on key milestones for output 4.
- Partner reporting to be brought
- Phase Two contracting should be initiated by end March 2015.
- Continue to update asset register and ensure asset monitoring is included on visits.
- DFID to review programme risks with partners as implementation continues.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-203243/documents/
DevTracker Link to Log frame:	N/A

Outline of the programme

The purpose of the Global Mine Action Programme (GMAP) is to reduce the humanitarian and development impact of landmines and Explosive Remnants of War (ERW). It aims to achieve this through i) clearance and direct release of contaminated or suspected contaminated land (demining), ii) Mine Risk Education (MRE) and iii) building the capacity of partner countries to manage their national Mine Action programmes.[1]
[1] Further information and background can be found in the GMAP business case

GMAP has initially funded work in five countries where a predecessor programme (the Global De-mining Programme, or GDP) had been undertaking operations, building on the GDPs results in Mozambique, Sri Lanka, Vietnam, Cambodia and Laos (Phase One). Work in a further six countries (Burma, Somalia, South Sudan, Sudan, Yemen and Zimbabwe) is being scoped and considered for operations under Phase Two).

Expected results

Based on Phase One country contracts let to date, GMAP is expected to clear over 25,000,000m2 of contaminated or suspected contaminated land, and release[2] significantly more. This activity should save lives, reduce fear and can provide a spur to development, increasing livelihood opportunities as land is put to productive use, and increasing access to basic services.
[2] Land release definitions in national standards are not uniform across the countries in which GMAP operates. With this understood, operators are cumulatively targeting land release of 95,000,000m2 for GMAP phase one countries.

GMAP will also build the capacity of regional and national demining authorities based on their priorities, including improving information and risk management systems, increasing the effectiveness of local management of contamination.

To ensure that UK-funded demining work continued without a gap in operations, GMAP also funded extensions to the GDP programmes, while GMAP operators were setting up. The results from these extensions were included in the GDP Project Completion Report.

Progress to date

GMAP was approved in January 2014, initiating procurement for Phase One countries. Contracts for demining and MRE were awarded through open competitive processes for each country, resulting in a contract for each of the five countries being awarded with a start date of July 2014. Due to bids offering higher than expected value for money, DFID were able to award a further contract (through an accelerated competitive process) for work in Laos (start date October 2014).

The contract for capacity development was awarded through an open competitive process to cover all Phase One countries (start date August 2014), with scope to extend the contract to Phase Two countries if appropriate. A summary of these contracts is below.

GMAP Contracts:
Supplier[3]	Scope	Country	Start	End
HALO	Demining/MRE	Mozambique	01/07/14	31/03/15
HALO	Demining/MRE	Sri Lanka	01/07/14	31/12/15
MAG	Demining/MRE	Vietnam	01/07/14	31/03/16
HALO	Demining/MRE	Laos (1)	01/07/14	30/06/16
MAG	Demining/MRE	Laos (2)	17/10/14	30/06/16
HALO	Demining/MRE	Cambodia	01/07/14	30/06/17
NPA/GICHD	Capacity Development	All	01/08/14	31/07/17
[3] Supplier names in full: The HALO Trust; Mines Advisory Group; Norwegian People’s Aid; the Geneva International Centre for Humanitarian Demining

GDP Contract Extensions
MAG	Demining/MRE	Vietnam	01/04/14	30/06/14
MAG	Demining/MRE	Cambodia	01/04/14	30/06/14
MAG	Demining/MRE	Laos	01/04/14	30/06/14
HALO	Demining/MRE	Mozambique	01/04/14	30/06/14
HALO	Demining/MRE	Sri Lanka	01/04/14	30/06/14

Delivery milestones against programme objectives have been set for December 2015. This was in recognition of the substantial timeframe needed to agree with national demining authorities before most mine action activities could begin, and subsequent agreement with DFID over specific targets. Currently reporting from partners arrives in the month following the quarterly cycle from the contract award (ie. Oct, Jan, April, Aug. This Annual Review is therefore reporting against the implementation of contract delivery plans to end September 2014. Reporting cycles will be changed in 2015 to align with annual review dates.

Scoping work on Phase Two countries continues, and has included scoping missions to Burma and Zimbabwe. Draft reports are prepared on each Phase Two country. Final decision and implementation are expected early in 2015.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment
Based on only three months of operations, it is too early to draw substantive conclusions on project outcomes. Baseline community surveys have already been completed (with the exception of Laos) which will allow early comment on community perception-linked outcome indicators in future reviews.

Overall output score and description
Based on the operations of Phase One contracts, outputs are broadly in line with expectations set out in project plans and are therefore scored ‘A’. It is important to note that for all outputs, logframe milestones were not available for this annual review because projects had only been operational for three months. The first nested logframe milestones will be available at the six-month point. Progress has therefore been judged against project plans. In the next annual review the logframe will have been reviewed and the milestones will be reflected in it.

Output 1 (Land Release) met overall expectations but saw some underperformance in two countries due to procurement delays (made up for by outperformance elsewhere). Output 2 appears to have met expectations. There is limited evidence for reviewing Output 3 at this early stage, and it is therefore scored a B, with the expectation that it will be scored an A once results are available. Output 4 moderately underperformed the original plan, with most activities expected to start in 2015. Given this is due to agreement of timelines with the national and regional authorities that GMAP is hoping to help build capacity, no action is recommended, except for continued monitoring.

Key lessons
Consideration of follow-on programme design should begin during the next year. GMAP was designed and implemented over two years. The previous demining programme was extended to allow the completion of this design phase. Given GMAPs three-year term, a follow-on programme should begin to be considered during the next year. It may wish to consider a longer project term and should weigh up the management burden of procuring individual contracts in each country of operation, phasing the procurement over the project term, against the flexibility this entails. This current project set-up has set a high administrative burden for both DFID and operators. Operator feedback has suggested it appears fragmented and detracts from a clear project narrative.

Ensure continuing line of dialogue with key national stakeholders. Feedback from DFID Mozambique suggested the scoping work had not reflected all national views and the capacity development solution proposed felt somewhat ‘imposed’. Clearer communication from DFID and their consultants to the national authority on intentions would have avoided this – the scoping was meant as a starting point for a conversation between the capacity development suppliers and national authorities. This conversation between Norwegian People’s Aid (NPA), the Geneva International Centre for Humanitarian Demining (GICHD) and national authorities appears to have worked well and closely linked work-plans to national priorities.

Key actions
- Given the delay to launching Phase Two (see section F), linked decisions and implementation will be prioritised early in 2015.
- Begin to consider design of follow-on programme.
- Establish line of communication with key national stakeholders.

Has the logframe been updated since the last review?
N/A – The majority of operator logframes for individual countries have been received[4] alongside Q1 reporting. These are ‘nested’ logframes, all contributing to a single over-arching ‘project’ logframe which will be reported against in six-monthly operator reports, and in future DFID reviews. Outputs for Q1 are below and are judged against project plans submitted during the procurement process. The next annual review will indicate how close we are to achieving the milestones set out in the logframe in terms of percentage. It is currently too early in the programme to do so and would not provide a meaningful indication of progress.
[4] The HALO Laos logframe had been delayed pending the completion of the baseline assessment

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Land released for productive use following effective tasking and prioritisation
Output number per LF		1	Output Score	A
Risk:		Med	Impact weighting (%):	55%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Progress[5]	Milestone (Dec 2015)
Land Released (Square Metres)	2,294,129	3,609,229
Mines / Unexploded Ordnance (UXO) removed	6,378
[5] For all outputs, logframe milestones were not available for the first three months of operation, with the first nested logframe milestones at the six-month point. Progress has therefore been judged against project plans.

Key Points

Output results are broadly in line with expectations. We expect results to be on track despite contracting delays prompting underperformance in two countries.

Summary of performance

In Cambodia and Laos, a delay in the confirmation of the winning bid meant the start of activities was delayed. HALO began operations in these countries in August rather than July. This one-month delay has had an outsized impact on reporting against a three-month plan target, and in each case operators are confident of returning to plan.

As a result of the late start, area cleared by HALO in Laos is in line with plan but land release is below that expected. Unaffected by a later start, MAG land release exceeded expectations (by 35% of target), in part due to land being cleared of vegetation ahead of MAG arrival, and clearance at some sites increasing efficiency.

Despite the delay, in Cambodia, HALO exceeded planned clearance area by 10% of target. Targets for reduction and cancellation were not met, with the relevant teams focused on the baseline survey. HALO expects to make up this shortfall over the term of the project.

In Vietnam, Q1 operations exceeded planned land release targets by 5%. This included clearance of 31 sites for development projects conducted by Roots for Peace, an NGO working with small subsistence farmers in Quang Tri Province to provide them with the tools and equipment to establish small-scale pepper plantations. MAG undertakes clearance of these sites before planting begins. In Sri Lanka, GMAP operations are ahead of plan, clearing over 350,000m2 of land in the quarter.

In Mozambique, GMAP operations were only able to clear 60% of the planned area, in part due to an unexpected anti-tank mine threat on a vital access road; but exceeded expectations in releasing land through cancellation[6] (164%). It is likely that HALO will underperform on land reduction in Mozambique across the programme, as the area requiring full clearance is larger than anticipated.
[6] Cancelled land is land that has been surveyed and then found not to contain evidence of mine/ERW contamination.

Recommendations
Consider allowing additional time between expected procurement end date and start of contract in future processes. This would ensure delays don’t impact on plan activities, but would increase the time between procurement initiation and the start of operations. Build lessons learned on procurement into the action plan for Phase 2 contracts.

Output Title	Affected communities aware of the risks of landmines and ERW and able to manage these risks effectively.
Output number per LF		2	Output Score	A
Risk:		Low	Impact weighting (%):	8%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Progress	Milestone (Dec 2015)
Beneficiaries reached through MRE activities	13,321	215,189
Beneficiaries demonstrating increased knowledge and retention of key RE messages	N/A[7]
[7] Not yet measured/reported in Q1

Key Points

Progress on reaching people through MRE activities has met expectations.

Summary of performance

Activities in Cambodia began only in September, following the procurement delay and time taken to develop materials and conduct training. HALO expects to return to plan over the course of operations.

In Laos, between July and September, MAG supported the National Regulatory Authority’s (NRA) MRE unit in producing 3,000 copies of Unexploded Ordnance (UXO) curriculum books, 2,500 copies of UXO story books (both targeted at primary school students) as well as 500 copies of UXO song books. The materials have been developed to support the MRE activities that are part of the national curriculum for primary schools. With schools in recess in September, HALO concentrated efforts on educating project staff of development partners about the risks and implications of UXO contaminations for the implementation of development projects; and on running a number of training sessions for teachers in Sepon and Vilabouly districts.

In Vietnam, MAG have conducted Safety Briefings during village meetings, but found that few children (one of the key risk groups) are able to attend due to their timing. Activities will be expanded to directly target children, including working with the UXO visitors centre in Dong Ha to improve their Risk Education syllabus (and materials) which are delivered to school children from throughout the province.

In Sri Lanka, the government requires that MRE activities are undertaken by a local agency. As in previous programmes, HALO has subcontracted Sarvodaya to conduct MRE, whose activities have reached over 4000 people.

In Mozambique, GMAP MRE activities are ahead of target, having reached 1300 people in Q1.

Output Title	Integration of mine action with wider development planning and implementation
Output number per LF		3	Output Score	B
Risk:		Med	Impact weighting (%):	12%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Progress	Milestone (Dec 2015)
% of target Confirmed Hazardous Areas (CHAs) that have existing NGO or authority led plans for development activities in place prior to clearance	N/A[8]	58%
% of target Confirmed Hazardous Areas (CHAs) that have existing community-led plans for development activities in place prior to clearance	N/A[9]	60%
[8] Not yet measured/reported in Q1
[9] Not yet measured/reported in Q1

Key Points
No evidence yet provided for the indicators, however some evidence is given below of how the organisations are collaborating with national and community based organisations.

Summary of performance

GMAP operators are working closely with national and regional authorities to support wider development plans. For example, in Mozambique, faced with a delay in deploying teams to the border minefield at M’solowamunthu, HALO coordinated with National Demining Institute (IND) to redirect affected teams to the Beira power line clearance, which is a priority of the National Authority. In Vietnam, MAG cleared 31 sites for development projects, but were not assigned further sites by the provincial authority in September. They are working with the authority to ensure new sites are assigned early in the next quarter.

GMAP operations have supported NGOs in each country in their development programmes. In the quarter, the 31 sites cleared by MAG mentioned above supported the work of Roots for Peace in Vietnam, an NGO working with small subsistence farmers in Quang Tri Province to provide them with the tools and equipment to establish small-scale pepper plantations. MAG undertakes clearance of these sites before planting begins. HALO conducted MRE training for employees of several local development partners in Laos, including Catholic Relief Services and World Vision.

No reporting was provided for Cambodia and Sri Lanka. This will be rectified in the next quarter.

Output Title	Strengthened capacity in national mine action authorities
Output number per LF		4	Output Score	B
Risk:		Med	Impact weighting (%):	25%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone
Total number of capacity development workshops/trainings undertaken	TBD
Total number of policies, standards, strategies and plans produced with significant input from GMAP technical assistance	TBD

Key Points

There has been a lower level of GMAP activity then initially expected in 2014, with most activities planned for 2015. .This is in line with timelines negotiated between national/regional authorities and NPA/GICHD during the exercise to refine workplans and logframes, which may lead to a request for no-cost extensions in some countries. Although this output is scored a B in relation to original expectations, no corrective action is proposed, given the increased national buy-in to the altered timelines. Activity will continue to be monitored closely.

Summary of performance

Two workshops were held and one transition plan developed. The major activity undertaken under the capacity development contract in 2014 was the ‘outcome-mapping workshop’. This gathered senior representatives from national and regional authorities from Vietnam, Cambodia, Laos and Mozambique[10] together in Hanoi to discuss and refine planned activities and outcomes under GMAP support. Led by NPA and the GICHD, this participatory process enabled national and regional authority buy-in to plans, and ensured plans reflected current needs (important as the original DFID design process included data from almost a year ago). It resulted in more detailed and relevant plans being produced. At the request of national authorities, many of these plans do not begin operations until 2015. GMAP-funded operations in 2014 were undertaken in Mozambique and Sri Lanka (see below).
[10] Representatives from Sri Lanka were unable to attend, and instead were visited by the GICHD/NPA project team to ensure plans reflected their priorities.

Feedback from the event was positive. One piece of feedback suggested DFID’s detailed original terms of reference (ToR) were viewed as inflexible and not reflecting national priorities. DFID have clarified with NPA/GICHD and national authorities that the ToRs were designed to be a starting point for discussion only.

For Vietnam, the Quang Tri provincial level plan of support is well-developed and ready to begin implementation. Planning for national-level support to Vietnam’s National Mine Action Program (also known as Programme 504) has been delayed by a lower-level of buy-in and the absence of some key personnel from planning meetings. Following work by NPA/GICHD, this is changing, and a programme is in development for 2015.

In Mozambique, GMAP has supported the drafting of a ‘transition plan’ following workshops and meetings with the national authority and other stakeholders. Mozambique is close to being declared mine-free, a major achievement. The national authority is therefore considering how best to transition to respond effectively to residual mine and ERW contamination, ensuring a residual capacity to deal with this issue long into the future, albeit reactively as opposed to proactively. The draft plan has been submitted, and a final version is expected in early 2015.

In both Mozambique and Sri Lanka, GMAP has updated the Information Management System (IMSMA) and optimised and demonstrated a new information management tool (MINT) designed in part to clearly present real-time data in dashboards for effective management decisions. This included trainings in both countries. In Sri Lanka, the training on information management was also attended by 10 representatives of MRE and Victim Assistance organisations. It is hoped that, with a better understanding of IMSMA reporting, they will provide valuable data to the national authority in future.

Recommendations

The participatory process involving a workshop with multiple national and regional authorities worked well. GMAP undertook in-depth design work for the ToRs ahead of project procurement. Adopting a participatory process during the inception phase in future programmes could reduce the amount of design work initially needed, yet be more current and relevant to national authorities.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
VfM performance compared to the original VfM proposition in the business case
Assessment of whether the programme continues to represent value for money

Staff are the main cost driver of the programme. Supplier teams include a high proportion of national staff, particularly for operational and support roles. This represents a lower cost than international staff, and makes some contribution to the development of national capacity through the provision of training. International staff are used to provide additional experience or technical expertise, to contribute to quality assurance of operations and to support and mentor local staff. Demining assets will also be procured and maintained under the programme. Demining assets procured under previous DFID programmes have been transferred to new GMAP contract work where useful and possible.

Judged on the 3 E’s framework for Value for Money, GMAP appears to be performing moderately ahead of expectation in both Economy and Efficiency, while it is too early to judge Effectiveness.

On Economy, the five initial Phase One demining contracts were procured well within planned budget, allowing the letting of a further contract in Laos which will release an additional 3.5million m2 of land contaminated by cluster munitions and UXO. The capacity development contract was also procured within budget.

With regards Efficiency, bid plans were at least in line with business case assumptions on outputs and in some cases exceeded them (e.g. Cambodia demining, where bid cost was 25% above budget but outputs almost 300% above business case assumptions). Suppliers were asked to demonstrate in their bids how they would achieve significant increases in both efficiency and effectiveness over the course of contracts – these improvements should be seen over the course of the programme.

It is too early to judge GMAP Effectiveness as baselines for Phase One have only recently been completed and operations begun only in July 2014. All demining suppliers will undertake impact assessments over the course of their contracts.

GMAP is judged to continue to represent value for money - the value for money case outlined in the business case has not changed and as noted above there has been strong performance in both Economy and Efficiency of the programme.

Quality of financial management
Due to the additional time taken in scoping operations under Phase Two, GMAP expenditure has been at a slower rate than originally forecast. Narrative and financial reporting requirements from suppliers have been adhered to – this annual review is being undertaken on the basis of Q1 reporting from GMAP contracts which began in July - August 2014.

Date of last narrative financial report	MAG contracts for Vietnam and Northern Laos on 5 January 2015
Date of last audited annual statement	No Annual Audited Statements received so far as project only began in July 2014.

E: RISK (½ page)

Overall risk rating: Medium

In line with the business case, this programme is considered Medium risk.

Overview of programme risk

Risk registers for each country contract are kept by operators, and updated and discussed with DFID once every six months. The first update is due in the first reporting of 2015. On the basis of risk registers submitted via the procurement process, all country programmes are judged to face a ‘medium’ level of (external) risk, with the exception of Cambodia, which is judged to face ‘low’ level of risk.

A programme risk register is kept to monitor risk at a programme level. At this programme level, Fraud, Fiduciary and Financial risks are considered low level. Phase One contracts have been awarded to established and financially secure operators with long track records of working in the sector. Indeed, MAG and HALO have a long history of partnership with DFID, including working on the previous Mine Action Programme (2011-2014).

Risks surrounding Delivery, Political and Economic Return are judged to be medium. On Delivery, the programme is running behind its original schedule for Phase Two and the political risk in some of the countries considered will complicate Phase Two initiation. The reasons for this are explored in Section F. On Economic Return, the cost-benefit analysis was conducted on a sample of countries and the conclusions applied across the programme as a whole. While this means returns on investment (RoI) may be lower than anticipated in the business case, the procurement process is designed to ensure the best value for money bid is chosen in each instance, part of which will be to maximise returns on the contract value.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

- Phase One contracts were let to expected procurement timelines. An extension to the standstill period for the decisions on the Cambodian and Laos demining contracts, to allow further discussion of decisions with bidders, meant that there was a delayed start to some operations in Cambodia and Laos of around one month.
- The adjustment to unexpected remaining budget by letting an additional contract in Laos was undertaken swiftly via an accelerated procurement process. This second Laos contract began in October 2014.
- Delayed scoping and decision-making on Phase Two means procurement is yet to be launched, and is therefore behind the planned 2014 schedule. This will be the focus of the programme team in 2015.

Performance of partnership (s)

GMAP has contracted with experienced partners, who continue to perform at a high level. Future reviews will be able to judge lesson-learning more effectively as it is a feature of contractor bids and reporting. Feedback from partners will be fed into the consideration of future programmes.

Asset monitoring and control

Asset registers were supplied as part of bid pack released by DFID during the procurement process, and these will be updated by operators on at least a six-monthly basis. Spot checks will be undertaken during monitoring visits. A decision concerning the transfer of demining assets from the previous programme is in process for DRC.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
N/A

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

An evaluation or independent review is planned for the final year of the programme. The monitoring regime has been set up to collect relevant information, and each demining and MRE contract will undertake an impact assessment of their work as a further input.

Monitoring progress throughout the review period

Programme monitoring has been undertaken through scrutiny of operator reporting and regular meetings with suppliers throughout the period of operation. Quarterly reporting templates have been agreed with suppliers (including more in-depth 6-monthly reports) to ensure risks are monitored, lessons are documented and can be fed back into the programme, and progress towards results is tracked. Only the first quarterly reports for GMAP contracts (Jul-Sep 2014) is available at the time of the annual review.

In future, reporting will be complemented by the procurement of specialist mine action expertise to aid the interpretation of operator data and information; and monitoring missions conducted by either HMG staff or the contractor. A monitoring mission to Mozambique in November 2014 was cancelled at short notice due to staff illness – alternative options are being assessed.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process