Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Facility for Oil Sector Transparency (FOSTER)
Programme Value: £14m		Review Date: 1-5 December, 2014
Programme Code: 200341	Start Date: January 2011	End Date: March 2016

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	A+	A	A+	A
Risk Rating	Medium	Medium	Medium	Medium

Summary of progress and lessons learnt since last review:
FOSTER has progressed well since its last annual review and remains an impressive and well performing programme, particularly once the very difficult terrain it is working in is taken into account. Headline achievements this year include FOSTER’s contribution to the innovative Gas Flare Tracker (http://gasflaretracker.ng/) which uses satellite data to create a visual map and database holding details of how much gas is burned and where, its carbon dioxide content, its potential value in terms of fines that the Nigerian Government should be levying. In addition to identifying up to £690m in unpaid fines, the system provides an evidence base for policymaking and advocacy on gas flaring. Elsewhere, FOSTER’s support to initiatives to recover funds identified in an audit by the Nigerian Extractive Industries Transparency Initiative (NEITI) resulted in £344 million being identified and recouped by the Federal Government. The programme has also played an instrumental role in the development of oil and gas sector legislation – notably parts of the Petroleum Industry Bill and legal amendments to strengthen the role and powers of the National Oil Spill Detection and Response Agency, including to make the agency more effective at curbing oil spills and gas flaring. This work took place alongside a series of initiatives with civil society actors, the media and other non-governmental FOSTER partners.

FOSTER continued to reap benefits from its flexible and politically astute way of working; the high technical quality of its direct and indirect contributions; the strong relationships and reputation it has built up across a range of stakeholders; and its emphasis on supporting and promoting local actors rather than pushing solutions. As the programme goes into its final full year of implementation, it is broadly on track to achieve its outcome of ‘enhanced management of Nigeria’s natural resources’. But it will need to review outcome-level indicators and targets and may well find it even more difficult to engage with the Nigerian Government on reform given that elections and their fall-out may occupy much of the political ‘band-width’ of 2015. The programme should also consider closely the recommendations contained in this review to put it in a stronger position for 2015 and any successor programming.

Summary of recommendations for the next year
Key recommendations contained in more detail below centre on:
- Reinforcing the logframe;
- Ensuring strong programme leadership and management following recent FOSTER staffing changes;
- Seizing opportunities and mitigating risks around the recent oil price shocks and the 2015 Nigerian elections;
- Improving the theory of change and investment in, and use of, evidence;
- Ensuring continued and strengthened collaboration with the Natural Resource Governance Initiative;
- Strengthening FOSTER’s engagement with the private sector;
- Strengthening learning within the FOSTER programme and for broader consumption.

It is the strong recommendation of this annual review that a ‘FOSTER II’ programme should be developed. DFID Nigeria should give early and careful thought to the process for transitioning to such a programme as well as to how it would build on the progress achieved under FOSTER I.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	4570094
DevTracker Link to Log frame:	4569728

Programme and context: Oil is the backbone of the Nigerian economy with oil revenues providing over 90% of foreign exchange earnings and at least 70% of government revenues. FOSTER is a DFID funded programme designed to promote greater transparency and accountability in Nigeria’s oil and gas sector. By strengthening the governance of the sector at different stages of the value chain, and by working with Government and with civil society, FOSTER seeks to reduce opportunities for corruption or revenue mismanagement. The ultimate aim is to make more effective use of Nigeria’s natural resources. Given the magnitude of oil and gas revenues and their importance to the Nigerian economy even small improvements in the sector can produce substantial benefits. The programme has three output areas:
1. Increase in extractive industries revenues identified (40%)
2. Improved management and accountability of extractive industry resources (40%)
3. Improved policy outcome for local communities affected by natural resource extraction (20%)

FOSTER seeks to build on and build up appetite for reform within the Government of Nigeria and more broadly. The programme works opportunistically and strategically with government (supply side) and civil society (demand side) institutions and actors – often simultaneously and on specific issues – to improve oil-related laws, policies, institutions and oversight bodies. Oil revenues are intimately bound up with Nigeria’s political system and with corruption in Nigeria. FOSTER’s approach is informed by recognition of this dynamic and by the challenges it presents:

[FOSTER] aims to reduce the many incentives for misuse of power and capture of oil revenues in Nigeria. Abuse and malpractice in the oil and gas sector in Nigeria is well documented and deeply entrenched. Corruption distorts policy and politics and undermines the potential for revenues to be used to accelerate economic and social development. By seeking out different strands of commitment for reform, within government and outside, FOSTER provides organisations with an interest in improving governance with a mixture of direct technical assistance and arms-length support. By constantly scanning and analysing the political economy of oil in Nigeria, the FOSTER team seeks out and supports ‘pockets of effectiveness’ - identifying the key players and institutions that have the potential to catalyse change, and then supporting them in their pro-reform efforts.[1]
[1] FOSTER overview, Oxford Policy Management (programme contractor): http://www.opml.co.uk/projects/facility-oil-sector-transparency-and-reform-nigeria-foster

Context for the 2014 Annual Review: While the overall context for this review remains unchanged, important developments have occurred in 2014 that have direct implications for the FOSTER programme. The first is impact of the sharp fall in oil prices, for an oil-dependent economy. The December 2014 fall in world prices of Brent Crude to around US$63 per barrel, and the decision by OPEC not to reduce production to drive up prices, is already impacting heavily on Nigeria’s economy. Unofficial calculations suggest that at Nigeria’s current rate of production (c.1.8m barrels per day (bpd)), per barrel prices need to exceed US$100 for the government to meet its spending plans. The second is Nigeria’s elections. Manoeuvring for the 2015 presidential, legislative and gubernatorial elections has dominated the political landscape in the past year, consuming political energies and shortening politicians’ time horizons, thereby reducing policy space for oil-related reform (and therefore space for FOSTER to make headway with the Government on this agenda). Partly in view of 2014 being a pre-election year, FOSTER re-balanced its emphasis in favour of activities and partnerships with non-governmental ‘demand-side’ actors and institutions. FOSTER has therefore supported local NGOs, the media, think tanks, parts of the private sector and others to increase understanding of the issues, to get easily-understood information into the public domain and to press for transparency and accountability.

Whilst the oil price shock may well have negative repercussions, it also represents an opportunity for FOSTER in terms of strengthening incentives for Nigeria’s (diminished) oil revenues to be used more effectively and for reducing oil dependence/seeking diversification of Nigeria’s economy into new activities and exports with better productivity and employment prospects over the medium-term. FOSTER is particularly well placed to stimulate and shape the terms of such debates during the final year of its implementation. In the immediate term, however, the new post-elections Nigerian administration will inherit a particularly troubled economy with diminishing state revenues to settle debts and honour political deals at the same time as delivering services and maintaining macroeconomic stability.
## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment: As the FOSTER programme is going into its final full year of implementation a close look at its progress towards its expected outcome in just over a year’s time is particularly necessary.

Outcome: ‘Enhanced management of Nigeria’s natural resources’
Based on the progress achieved to date – both in terms of outputs and as against outcome indicators and milestones – it is reasonable to expect that the programme will achieve its overall outcome. However, there are several qualifiers to this, as discussed below. Notably, whilst the programme is on track to achieve its target in one of the outcome indicators, it is off track in terms of the other outcome indicator.

Outcome Indicator 1: ‘Value of additional revenue realised’ (as result of the FOSTER programme)
- Target by end 2015: £300m.
- Expected achievement by end 2014: £300m
- Achievement: £346m
- Assessment: Over achieving
In 2014, FOSTER, together with several other actors, contributed to £344m of additional Government revenues through its engagement with Nigerian Extractive Industries Transparency Initiative (NEITI), of which 33% (£115m) can be attributed to FOSTER.[2] This is below the £150m milestone for 2014. But the 2013 annual review identified a total of £231m of additional revenues realised - £81m in excess of the £150 million milestone for that year. So once the overachievement from 2013 is factored in, the cumulative total (£346m) is above the £300m that the programme expected to achieve by the end of 2015. Although this logframe outcome level end of project target has already been surpassed, the programme should agree with DFID a new target for 2015.
[2] Disaggregating FOSTER’s specific contribution and attributing a specific financial sum is difficult, particularly given that numerous local and international actors contributed directly and indirectly to achieving this result. Nonetheless, the £33% figure was reached following discussions with interviewees for the annual review underlined that FOSTER was a central player in the remediation effort, notably in terms of working with civil society to build demand for follow up.

Outcome indicator 2: ‘Proportion of natural resource revenues regularly accounted for’
- Target by end 2015: ‘Improved price and volume information for oil, gas and mining revenues made public by the Federal Accounts Allocation Committee’.
- Expected achievement by end 2014: ‘Improved price and volume information for oil, gas and mining revenues provided by revenue collection agencies to the Federal Accounts Allocation Committee’
- Achievement: Off-track and the suitability of this indicator should be reviewed.

The 2013 annual review noted that the programme had made some progress towards its 2013 milestone but that much would depend on greater progress during 2014. During this year’s annual review it was difficult to discern progress in this area. The FOSTER programme supported NEITI’s 2014 Fiscal Allocations and Statutory Disbursements Audit which shed important light on how collected revenues have been allocated and spent, raising a number of significant concerns.[3] But the emphasis of this NEITI audit is somewhat different to the emphasis in the logframe on Government of Nigeria revenue collection agencies providing improved price and volume information for oil, gas and mining revenues. FOSTER has also linked with newspapers in relation to the publication of data (in simplified formats) from the Central Bank of Nigeria’s monthly economic reports on federally collected oil revenues. But again, whilst important, this work lies somewhat outside the focus of the indicator and milestone.
[3] https://eiti.org/blog/deepening-knowledge-about-how-oil-money-spent

Observations on impact-level developments: Whist this annual review is not required to assess progress at impact level, new data became available on such progress during the annual review mission. The impact is ‘more effective use of Nigeria’s natural resources’. The end 2015 target for Impact Indicator 1 is positive change in four of the 12 precepts assessed against the benchmarks in the Natural Resource Charter. The 2014 milestone is a cumulative total of positive change in 3 precepts. However, by the end of 2014 Nigeria’s score had not recorded any precept improvements against the 2012 baseline. Data to assess progress against the other impact-level indicator, Nigeria’s progress against the revenue watch index, will be available later in 2015.

Overall output score and description: A – Outputs met expectations.

The programme has scored an A overall based on the individual output scores and their respective impact weightings. The outputs scored an A+ on the increase in revenues identified (weighted 40%); a B for improved management and accountability of extractive industry resources (weighted 40%), and an A grade on improved policy outcomes for local communities (weighted 20%).

Key lessons and actions: The FOSTER programme deserves to be recognised as epitomising many of the strengths of flexible programming that is at once politically-smart and technically robust. FOSTER also showcases the benefits of approaches which avoid taking a directive approach and instead focuses on bringing local actors together around specific problems and supporting them to take the lead in how to address them. Rather than pushing solutions first-hand, FOSTER seeks to convene various stakeholders, ensure the right material is made available for informed debate, and build coalitions from across constituencies that are often mutually suspicious of one another (see also quotes from stakeholder feedback, below).[4] FOSTER is also particularly strong in terms of:
[4] See, for example case studies in ODI’s ‘Politically smart, locally led development’ discussion paper (September 2014) as well as discussions/manifesto on ‘Doing Development Differently’, flexible and problem-driven programming approaches etc.
- Continuously scanning the policy/political environment to identify reformers and pockets of opportunity to advance reform and consistently positioning itself in and around these spaces.
- Not just working on both the supply-side and demand-side but doing so in ways that tackle specific issues from both angles simultaneously.
Experimenting and adapting to changing circumstances – including trying, failing and adjusting activities and partnerships.
Full exploration and illustration of these qualities is outside the focus of this annual review but should be considered as a separate exercise (see recommendation #10 below).

Reinforce the logframe: The programme logframe should be strengthened to make it clearer and easier to assess progress and to better reflect important areas of FOSTER’s work.[5] Specific areas for improvement have been suggested to FOSTER and DFID Nigeria. Action: Rather than attempting fundamental changes, the focus should be on clarifying terms and meanings in the logframe to better guide shared understanding and implementation over the next year as well as to enable a rigorous and efficient Project Completion Review in early 2016.
[5] It was suggested that some aspects of the FOSTER programme (e.g. its flexible and adaptive nature) are not conducive to standard approaches to logframes. However, within the constraints of a logframe, there are nonetheless various improvements that could be made.

Ensuring strong programme leadership and management: As of December 2014, the absence of a FOSTER Programme Manager poses challenges for sustaining and increasing momentum in the programme’s final year of implementation. Action: Oxford Policy Management (the contractor), in close liaison with DFID Nigeria, should ensure a swift and effective arrangement is found following recent staffing changes.

Seize opportunities from the oil price drop: The November 2014 dive in global oil prices has exposed major structural vulnerabilities in Nigeria’s economy and in the political economy surrounding oil in Nigeria. FOSTER is uniquely positioned to identify and seize opportunities presented by the oil price shock and to shape the terms of the debate in Nigeria about reform. Action: Move quickly to seize new opportunities to steer the terms of the debate.

Seize opportunities around the 2015 elections: This will be particularly important in relation to generating early buy-in and momentum around important areas of legislation such as the Petroleum Industries Bill (PIB) and the National Oil Spill Detection and Response Agency (NOSDRA) Amendment Bill which may not be passed prior to the elections. Action: Working with its partners, the FOSTER team should ensure it is well positioned to take advantage of opportunities and to build relationships in the immediate aftermath of the 2015 elections, scheduled for February.

Strengthening FOSTER’s emphasis on economic development: The prevailing narrative of the FOSTER programme is one of transparency and accountability for the use of Nigeria’s oil revenues. This ‘governance’ emphasis is important and necessary. However, the programme is also well positioned to emphasise the economic development opportunities surrounding the oil sector as well as issues of economic diversification/reducing Nigeria’s oil dependence. Giving increased emphasis to this latter agenda may also help to achieve greater traction in some areas with the Government of Nigeria. Action: Adapt the FOSTER narrative to better reflect how the programme is also about opportunities for economic development and take stock on whether the substance of FOSTER’s work could also speak better to this narrative (this recommendation could be pursued further under a potential FOSTER II - see also point 11 below).

Improving investment in, and use of, evidence: The programme’s theory of change relies on increased transparency leading to increased accountability for the management of Nigeria’s oil revenues. As one FOSTER partner put it during the review, ‘we believe that if citizens are aware then Government will be forced to act’. The FOSTER programme is alive to the challenges of achieving such a progression in the Nigerian context but could do more in terms of its use of evidence to measure progress and support its theory of change in this crucial area. Action: Review Nigeria (and wider as appropriate) evidence underpinning the transparency → accountability assumptions in the FOSTER programme; consider opportunities for strengthening this area of the programme and for commissioning and/or drawing on public opinion survey data as part of a renewed evidence focus. Under FOSTER II (see recommendation #11 below), there should be greater attention to using disaggregated data, particularly in terms of sex and age.

Collaboration with the Natural Resource Governance Initiative (NRGI): The Natural Resource Governance Initiative (NRGI), a DFID centrally funded extractives initiative covering a number of countries including Nigeria, will increase its Nigeria work and Nigeria country presence from early 2015. Further coordination and collaboration between FOSTER and NGRI will become all the more important given the latter’s scale up in Nigeria and the complementarity between the work of FOSTER and NRGI. Action: Establish and clearly set out in a joint document the nature and extent of FOSTER - NRGI collaboration and coordination in Nigeria, building on the positive collaboration to date and including potential for FOSTER and NRGI staff to be co-located.

Strengthening FOSTER engagement with the private sector: FOSTER already engages private sector actors in the oil and gas industry but should expand its work in this area. Action: Review the balance of FOSTER’s investment of effort with civil society and the Nigerian Government relative to that with the private sector. Consider increasing engagement both with international oil majors but also with Nigerian companies.

Focusing on areas which can generate overlapping national and international reform pressure: Some of FOSTER’s most effective work has been targeted at issues that can attract both national and international attention simultaneously such that pressure for reform is amplified. Action: FOSTER should consider prioritising issues where the potential for achieving such synergies is greatest.

Strengthen learning within the FOSTER programme: FOSTER is innovative both in terms of its programme content but also its ways of working. The programme should do more to ensure it creates time and space internally to capture and reflect on lessons from its work – both in terms of improving practice within the programme but also in terms of being able to preserve institutional memory and be in a better position to draw out broader lessons of relevance to extractive programmes in other countries. Action: Address FOSTER’s ability to generate and capture learning within the programme and amongst the team (e.g. beginning with discussions on this as part of the next FOSTER away-day).

Managing transition to FOSTER II? DFID Nigeria will need to take a decision on whether to design a ‘FOSTER II’ successor programme for which there appears to be a strong justification. Action: Tee-up FOSTER II early. If there is to be a FOSTER II, and given the lead-time for developing new programmes, DFID Nigeria should invest time in the first half of 2015 to ensure the timing and process for design, procurement etc. don’t compromise programme momentum.

Has the logframe been updated since the last review? No

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Increase in extractive industries revenues identified
Output number per LF		1	Output Score	A + (output moderately exceeded expectation)
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	2014 Milestones	Progress
1.1: Policy recommendations, analysis, reports, transparency and advocacy initiatives that lead to new policies, roles and laws	2 policy recommendations targeted at increased revenues [of which] / 1 policy recommendation adopted and supported that increases revenues captured by the Federal Government of Nigeria.	Achieved: / 1 X advocacy and recommendations directed at the Nigerian Economic and Financial Crimes Commission (EFCC) for follow up on allegations of corruption in the sector.[6] This eventually prompted a public response from the EFCC.[7] / 1 X advocacy and recommendations on curbing crude oil theft. This prompted responses by heads of various Government agencies who committed to play an enhanced role in addressing crude oil theft (i.e. also 1 X advocacy initiative leading to a new role).
1.2: Capacity building interventions in revenue generating and oversight agencies (including Min. Finance, Revenue Mobilisation Allocation and Fiscal Commission and other demand and supply actors)	2 capacity building initiatives in revenue management agencies targeted at increasing natural resource revenue capture	Achieved: / 1 X training of 24 staff at the Revenue Mobilisation Allocation and Fiscal Commission (RMAFC). / 1 X training on oil and gas revenue flow for 27 officers across the EFCC and other departments and agencies.
1.3: Systems and processes improved in revenue generating and oversight institutions and agencies (including Min. Finance, Revenue Mobilisation Allocation and Fiscal Commission and other demand and supply actors)	1 system in revenue generating and oversight institutions strengthened and; / 1 supporting transparency	Achieved: / 1 X strengthening of templates used by NEITI in order to apply new global EITI standards introduced in 2013. / 1 X supporting transparency via work with NOSDRA to generate and make publicly available data on illegal gas flaring.
[6] E.g. c.f. http://www.punchng.com/news/probe-n785bn-subsidy-fraud-falana-others-tell-efcc/
[7] E.g. c.f. http://efccnigeria.org/efcc/index.php/news/976-oil-subsidy-efcc-recovers-n5bn

Key points and highlights:
During the year, and on the basis of political economy analysis of where the programme could achieve greatest traction given unfolding developments, the FOSTER team opted to increase its demand-side work – notably with civil society and the media. In this context, and in addition to what is included in the table above, several further areas of FOSTER activity should also be acknowledged under this output. The following activities relate directly to generating demand-side momentum for increasing extractive industries revenues but don’t neatly conform to some of the terminology used in the indicators and milestones:
- FOSTER’s provision of small grants to five civil society organisations (CSO) to pursue focused advocacy strategies around crude oil theft (under the ‘Naija is Bleeding’ banner) and the legal, policy, environmental and institutional weaknesses exposed by the theft.
- FOSTER’s provision of training and small grants to journalists to pursue informed and in-depth stories on alleged oil sector-related corruption (www.probing.org)

Factoring in these further initiatives and others which are not covered here for reasons of space, this output is assessed as having moderately exceeded expectations.

Summary of responses to issues raised in previous annual reviews (where relevant): The previous annual review identified a need to increase joined-up working with NEITI and provide more coherent support, particularly in terms of giving greater attention to improving transparency and in the context of the introduction of the new EITI standards. Overall, the FOSTER programme responded well to this finding, including by deepening its engagement with NEITI and giving extra emphasis to transparency-related issues (shifts which were positively acknowledged by NEITI staff during this review). The FOSTER programme also gave particular attention to partnering with NEITI to adapt existing templates and approaches and align them with new EITI global standards as well as to summarising, popularising and amplifying the findings of long and technical NEITI audits.

Recommendations
- FOSTER should maintain its flexible and responsive approach which allows it to seize emerging opportunities and to back ideas and activities which may not have been foreseen in the annual workplans of more linear kinds of programme. At the same time, FOSTER should recognise that this approach can create uncertainties for the planning and budgeting processes of FOSTER partners such as NEITI and that NEITI is keen to have up-to-date information on FOSTER-backed initiatives which correspond with NEITI’s priorities and workstreams. FOSTER should invest more time in managing relations with NEITI in the context of these different ways of working.
- FOSTER’s coordination with NRGI in relation to NEITI will be particularly important as NRGI ramps up its Nigeria work and country present. On this, c.f. lesson/action #7 under ‘key lessons and actions’ above.
- In terms of FOSTER’s demand-side work and its evidence base and theory of change in this area, c.f. lesson/action #6 under ‘key lessons and actions’ above.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved management and accountability of extractive industry resources
Output number per LF		2	Output Score	B (output moderately did not meet expectations)
Risk:		Medium	Impact weighting (%):	40%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
2.1: Policy recommendations, analysis, reports, transparency and advocacy initiatives that contribute to new policies, roles and laws in resource management and accountability	2 policy recommendations targeted at improved management and accountability of the NR sector / 1 policy recommendation adopted by the NR sector and supporting accountability	Partially achieved / 1 X policy recommendation aimed at improving the performance of marginal oil fields proposed. / 1 X policy recommendation adopted in current version of PIB.
2.2: Capacity building interventions in resource management and accountability institutions and agencies (including DPR, PPPRA, NAPIMS and other demand and supply side actors)	2 capacity building interventions targeted at improving management and accountability of the NR sector	Achieved / 1 X support to Senate Committee on Environment regarding the NOSDRA Amendment Bill. / 1 X training: 10 bloggers, 3 journalists, 2 CSO representatives on oil sector governance issues. / 1 X convening multi-stakeholder conferences on better regulation in relation to development of gas and downstream petroleum.
2.3: Systems and processes improved in resource management and accountability institutions and agencies (including DPR, PPPRA, NAPIMS and other demand and supply side actors)	2 systems supporting improved accountability of oil and gas resources strengthened in resource management and accountability institutions	Not achieved

Key points and highlights: Despite a difficult political environment, important progress was achieved in working with the legislature. FOSTER built genuine consensus around two pertinent pieces of legislation – NOSDRA Amendment Bill and the PIB – both of which could conceivably pass before the end of this legislative session. It should also be noted that support to the Senate Committee on the Environment entailed engaging relevant and informed demand side actors in this process – Stakeholders’ Democracy Network (SDN), Yar Adua Centre and a DFID-funded infrastructure programme.[8] Additional activities were also pursued that do not neatly conform to some of the terminology used in indicators and millstones:
[8] Nigeria Infrastructure Advisory Facility (NIAF).
- Consistent and sustained support for journalists and CSOs to increase debate on key oil and gas issues, including on the ‘fuel subsidy scam’, crude oil theft, industry restructuring and the PIB. Increased discussion of these issues in print and social media has resulted.
- Important work linked to the Nigerian Natural Resource Charter (NNRC) to complete an updated assessment of Nigeria against globally-agreed extractives industries standards.
- High quality work pursued to simplify complex and detailed reports (including NEITI audit reports) into digestible products – including infographics – for lay readers.
- An online mechanism for identifying beneficial owners of companies servicing the oil and gas sector in Nigeria has been designed, but only exists in beta format and does not load on most web browsers. If the accessibility of this platform is improved in 2015, it should be considered a “system improved” for the next annual review.

Factoring in the totality of these initiatives, this output is assessed as having moderately not met expectations.

Summary of responses to issues raised in previous annual reviews (where relevant): The 2013 review recommended that efforts to support the PIB should not be scaled back. Response: FOSTER has maintained and stepped up its engagement on the PIB. The PIB has not been enacted but is at an advanced stage in the legislative process and seven recommendations emerging directly from FOSTER-related engagement have been adopted into the current version. The review also noted there was scope for the NNRC to offer an overarching framework for the multiple FOSTER interventions and add coherence to the programme. This suggestion has not been fully adopted (see directly below).

Recommendations
- More could be done to capitalise on the standing, experience and expertise of the NNRC Expert Panel members, particularly as a possible entry point for working more with the private sector to improve management and accountability of extractive industry resources. (c.f lesson/action #8 under ‘key lessons and actions’ above)
- FOSTER should plan for the possibility that neither the PIB nor the NOSDRA Amendment Bill will pass before the end of the current parliamentary term. While this scenario would not necessarily derail these agendas, FOSTER should move quickly with the new post-elections administration to ensure the draft legislation gets traction and buy-in with new MPs so as to keep up momentum and maximise prospect of the legislation being passed.
- FOSTER relies heavily on the use of social media and on simplifying reports into infographics in order to promote awareness and accountability. FOSTER’s Theory of Change (ToC) around this work could be stronger, particularly with respect to articulating which audiences are most effective at pushing for accountability in particular contexts and the evidence for this. Could FOSTER, for example use more SMS technology and local vernacular radio (e.g. Wazobia) in their demand side activities so as to reach broader sections of the population. Useful lessons could potentially be gleaned from the Twaweza programme in East Africa.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved policy outcomes for local communities affected by natural resource extraction
Output number per LF		3	Output Score	A (Output met expectations)
Risk:		Medium	Impact weighting (%):	20%
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress
3.1: Policy recommendations, analysis, reports, transparency and advocacy initiatives that contribute to new policies, roles and laws	2 policy recommendations targeted at improved outcomes for communities affected by NR extraction / 1 policy recommendation targeted at improved outcomes for communities affected by NR extraction adopted by relevant agencies	Partially achieved / 1 X support to National Coalition on Gas Flaring and Oil Spill in Niger Delta (NACGOND) to implement recommendations of the ‘Communities not Criminals’ report. / 1X recommendations towards improvement of the Oil Spill Joint Investigation regime. / 0 X policy recommendations adopted.
3.2: Capacity building interventions for supply and demand side actors that have a role in improving outcomes for local communities (including DPR, NOSDRA)	1 capacity building initiative in institutions and agencies charged with improving outcomes for local communities	Achieved / 1 X training of 18 staff from NOSDRA to use data from the online oil spills mapping and tracking platform.
3.3: Systems and processes improved in institutions and agencies that have a role in improving outcomes for local communities	1 system and process strengthened in institutions and agencies charged with improved policy outcomes for local communities	Achieved / 1 X institutional system strengthened through the development and roll out of an online Gas Flare Tracker, housed in Ministry of Environment but whose data is publically available in user-friendly format.

Key points and highlights: The standout activity in Output 3 was the Gas Flare Tracker (http://gasflaretracker.ng/) which uses satellite data to create a visual map and database holding details of how much gas is burned and where, its carbon dioxide content, its potential value in terms of fines that the Nigerian Government should be levying and what the gas could be contributing to Nigeria’s unmet energy needs. In addition to identifying up to £690m in unpaid fines, the system provides an evidence base for policymaking and advocacy on gas flaring. Separately, new training was provided to NOSDRA staff on how to use the Oil Spills Platform, specifically in relation to clarify the roles between zonal offices and the head office. In addition, and not neatly captured under the logframe, representatives from 7 CSOs were trained in use of the Gas Flare Tracker for advocacy purposes. Factoring in the totality of these initiatives, this output is assessed as having met expectations.

Summary of responses to issues raised in previous annual reviews: Last year’s review noted that FOSTER could focus more on environmental awareness and oil and gas-related health issues, particularly around oil spills. The development and roll out of the Gas Flare Tracker and the work to support the Senate Committee on the Environment on NOSDRA Amendment Bill have contributed significantly to this work as has the ongoing use of the oil spills platform. The weighting for output 3 has been maintained at 20%, as per the recommendation from the 2013 annual review.

Recommendations
- The development of the Gas Flare Tracker should be regarded as contributing towards a wider objective of improving outcomes for local communities affected by NR extraction. There is also a link with domestic gas pricing reforms in Nigeria as part of the power market development. This led to a substantial increase in domestic gas prices in January 2015 that may increase the market incentive to use gas productively rather than flare it. In 2015, FOSTER should develop strategies to ensure that revenues identified from unpaid flaring fines are realised, and that those revenues are invested in initiatives that build resilience amongst communities affected by gas flaring. There may be increased appetite for the former in light of the drop in oil prices.
- FOSTER could do more to reflect DFID’s overarching objective of eradicating poverty, not least in terms of being able to draw out the links in case studies between the programme’s activities and tangible improvements to the lives of poor communities affected by natural resource extraction in Nigeria.
## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance: The underlying cost drivers of FOSTER are the contractor’s management services (Oxford Policy Management). The main input in terms of programme delivery is technical assistance, specifically in the form of consultancy fees for international and local specialist skills in the oil and gas sector. This technical assistance has been greatly valued by recipient partners in the sector, and has delivered tangible results.

VfM performance compared to the original VfM proposition in the business case: The VfM proposition of the FOSTER programme is to increase extractive industry revenues, improve management and accountability within the oil and gas sector and improve policy outcomes for local communities affected by natural resource extraction. An underlying assumption of FOSTER is that small improvements in the governance of the oil and gas sector have the potential to deliver significant returns for the government of Nigeria and Nigerian citizens. This logic remains valid, despite experiencing additional challenges in working with the government over the past year.

Assessment of whether the programme continues to represent value for money: In terms of overall effectiveness, FOSTER continues to represent good value for money. In 2014, FOSTER played a significant role in the government’s realisation of £115m (33% of £344m) in additional revenues via remediation initiatives spearheaded by NEITI (see section on Outcome-level progress, above). This comes on the back of £231m realised in 2013, some £81m above target for that year. This means that FOSTER has already gone beyond its £300 million target in additional revenues, from an investment of £14m[9]. In addition to revenues realised, FOSTER has assisted the government of Nigeria in identifying £690m in unpaid fines from largely illegal gas flaring in 2014. Even if a modest proportion of this sum is eventually realised, it would represent a significant financial accountability achievement and the absolute amount recouped would be likely to further reinforce the value for money of the programme.
[9] Already representing a Net Present Value (NPV) of more than £260 million for DFID’s initial investment a year before project completion

The 2014 report on ‘Monitoring value for money in DFID Nigeria’s Economic Growth Portfolio’[10] contains a number of relevant recommendations for the FOSTER programme to consider. With flexible, adaptive programmes a key driver of the overall value for money of the programme is the quality of the portfolio of interventions and how this is managed over time. Political economy analysis with reliable local knowledge can help improve the chances of a given intervention leading to successful results, but there is still need to actively expand and contract interventions based on the extent of traction they are able to achieve once implementation takes place. The nature of some of FOSTER’s interventions makes it difficult to assess how well this is being done. It is clear that FOSTER providing £20,000 worth of technical assistance to help NEITI realise additional revenues of £344m for Government is excellent value for money, but this is a small proportion of the type of interventions FOSTER uses its resources on. Many of the results are less quantifiable and the programme needs to be clearer about when these are succeeding, what the benefit of the success is, and clearly flagging when interventions are not delivering to expectations.
[10] ITAD 2014, ‘Monitoring Value for Money in DFID Nigeria’s Economic Growth Portfolio’: QUEST # 4543975

In terms of the ‘economy’ of the programme, FOSTER has continued to reduce its reliance on high and medium fee consultants. The programme spends 3% of its budget on high fee consultants, compared with 11% in 2013; and 45% on medium fee consultants, compared with 47% in 2013. The average cost of international consultants is £592 and £262, within the range of other similar DFID Nigeria programmes. The limitations of this type of analysis, is that it does not demonstrate the relative ‘value’ that different consultants may add to the work and is therefore an incomplete value for money measure. FOSTER should specifically consider some of the recommendations on economy measures from the 2014 ITAD report to strengthen its reporting in this area.

More broadly, FOSTER’s use of regularly updated political economy analysis and ongoing politically-informed ways of working enables its activities to be grounded in a strong understanding of the incentives and interests which determine space for reform and, by extension, to focus its efforts on areas of greatest strategic opportunity. This quality, combined with FOSTER’s attention to building and maintaining strong networks and relationships, enhances the ‘effectiveness’ dimension of the programme’s VfM.

The following areas should be considered ahead of the next annual review:
Implement the relevant recommendations of the DFID Nigeria 2014 report on ‘monitoring value for money in DFID Nigeria’s Economic Growth Portfolio’.
- It can be difficult to quantify the value to all of FOSTER’s activities, not least FOSTER’s more arm’s-length influencing work (e.g. convening different actors and brokering discussions etc.). Where this is the case, FOSTER should place extra emphasis on compiling compelling and well-evidenced qualitative information (including drawing on independent sources as far as possible) to enable robust assessment of its achievements.
- FOSTER has shown a willingness to ‘test the water’ and, where necessary, end activities that are not delivering the expected results or where they are failing to get the desired traction. This approach is a significant strength but more could be done in this area to demonstrate to DFID the criteria they use in coming to these decisions.
- FOSTER could provide more information on how VFM considerations are used when deciding which activities to support, and the metrics that are used to make these portfolio choices.

Quality of financial management: The programme is on track to attain results within the approved budget of £14m. However, in May 2014, FOSTER was notified that its spend for 2014 would be reduced from £2.5m to £2m due to a DFID Nigeria budget reduction that impacted on all programmes. FOSTER has dealt with this shortfall in funding well, and it does not appear to have impacted on results for 2014. FOSTER will be extended by an additional three months, running to the end of March 2016, to enable the programme to reach the results in its logframe. FOSTER has developed a programme dashboard which maps all activities to the logframe, provides information on the status of activities, and indicates the responsible consultant. In addition, the submission of invoices has been regular and accurate. Reports on programme expenses and the management of sub-grantees have shown good financial management. However the programme should improve its financial forecasting by providing reliable figures that are accurate in the short term, within a region of 5 - 10% variance from the expenditure on a monthly basis. In the long term, FOSTER should be able to programme activities on a rolling basis, to ensure that they deliver on budget allocations. Where this is not the case an early warning to DFID should be made.

Date of last narrative financial report	12 November 2014
Date of last audited annual statement	30 Sept 2013

E: RISK (½ page)

Overall risk rating: Medium

Overview of programme risk: The service provider’s accounting and management systems to minimise the risk of fraud are good, and were strengthened after the 2013 independent audit. Another independent audit is proposed for late 2015. The risk environment underpinning the FOSTER programme has changed in the following ways, which could impact on successful delivery of the programme:

- The FOSTER programme manager position became vacant in December 2014. It is important OPM, ensures that the FOSTER team is equipped with the necessary management and leadership skills as the programme enters its final year (c.f lesson/action #6 under ‘key lessons and actions’ above).
- The 2015 presidential, legislative and gubernatorial elections are scheduled for 14 February 2015.
Whether the incumbent remains in office, or a new APC government is formed, it may take time for the new government to find its feet, not least if the immediate post-election period is turbulent. This could once again limit opportunities for working with government and other supply-side actors. In addition, if the PIB or the NOSDRA Amendment Bill are carried over into the next Parliament and there is high turnover of MPs who have backed the legislation, there is a possibility that much of the progress around sensitising MPs and building coalitions of support and momentum around these agendas will be significantly set back.
Although the fall in oil revenues represents an opportunity for reform in the sector, there are also associated risks. The fall in prices could result in the scramble for resource revenues intensifying and increased opacity in the management of the oil and gas sector. In turn, this could negatively affect FOSTER’s overall impact.

Outstanding actions from risk assessment
- The risk matrix in the 2013 Business Case notes that FOSTER should ‘articulate concise, concrete theories of change and expected results for each project’. FOSTER could do more on this, particularly in relation to the link between transparency and accountability and how the programme contributes to furthering poverty reduction in Nigeria.
- In terms of the risk associated with enforcement and collection agencies not receiving necessary political support, last year’s annual review noted that FOSTER had less engagement with the Petroleum Unit (PU) in the Ministry of Finance, following funding for TA within the unit being transferred to another DFID-funded programme (the Federal Public Administration Reform Programme). This arrangement has continued in 2014. FOSTER should consider the extent to which this arrangement has diluted engagement with the Unit and how to strengthen FOSTER-related collaboration.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is broadly on track to achieve its logframe results on time. DFID Nigeria’s budget reductions in 2014 necessitated an extension of the programme timeframe for an additional 3 months.

Performance of partnership(s) The service provider has managed the programme well and responded adequately to periodic requests from DFID. DFID engages with OPM regularly to monitor progress and assess risk. FOSTER has worked collaboratively with other DFID programmes such as FEPAR and Justice for All. It will be important for OPM to capably handle the fallout from losing its Programme Manager in December and quickly find a suitable replacement to ensure that the programme can deliver against its ambitious 2015 targets.

Asset monitoring and control The programme’s assets are managed properly and when new items are purchased, the asset register is updated accordingly. A copy of the updated register is shared with DFID and saved in DFID’s electronic filing system - QUEST. Programme assets, including vehicles have been used for their intended purposes and the programme has followed correct procedure for the disposal of any assets. A spot check was also done in September 2014 to confirm that assets are in good condition. An audit was conducted in 2013 which validated the status of FOSTER assets and another independent audit is proposed in late 2015 prior to closure of the programme.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)
Partnership Principles were not assessed during business case design.  The principles are however considered valid in reviewing FOSTER’s approach and objectives. This project aims to support Nigeria government make more effective use of its natural resources by strengthening the governance of the oil and gas sector, at different stages of the value chain, and working with accountability actors for reforms.  The programme is implemented through a commercially contracted service provider and no funds are passed through government systems. This is in direct response to the high fiduciary risks associated with funding through Nigerian government. Partnerships are substantially with the private sector. The programme will enhance domestic accountability through strengthening of accountability actors such as civil society organisations and media organisations.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation: The assumptions column of the logframe should be reviewed and expanded to capture more fully the assumptions made in the programme and changes in the operating context. In addition, there is scope for FOSTER to better articulate in its ToC how it approaches the challenges (including in terms of evidence and measurement) associated with bridging the gap between securing transparency and this translating to accountability (see recommendation #6 at the front of this review).

The wording in the logframe indicators and milestones speaks more directly to the supply-side aspect of the programme (for example, the emphasis on FOSTER influencing policy recommendations, strengthening systems and laws as well as reference to particular government agencies). The demand-side aspect of FOSTER’s work is not as well represented in the logframe which therefore underplays the significance of FOSTER’s work in this area and makes it more difficult to review and reflect results. This limitation is amplified by the fact that – on the basis of FOSTER’s continuous political economy analysis of areas of opportunity – the programme has increased its focus on working with demand side actors relative to its Governmental focus. It is a significant strength that FOSTER’s approach allows it to be flexible in this way but the logframe needs to be reviewed and updated in light of such shifts.

See recommendation #10 above in terms of the need to do more to ensure that the evidence from the implementation of FOSTER contributes to the wider evidence base. In addition, the logframe does not include any evidence disaggregated by sex and age, or any other variables. This issue should be addressed under a FOSTER II programme should it go ahead. However the FOSTER programme has made effort to monitor the gender of individuals trained across its outputs. Out of 22 journalists trained by FOSTER in 2014, 19 were women. Of the civil servants trained at two agencies, 10 out of 24 participants were women (RMAFC) and there were 6 women out of 25 participants at the environmental agency (NOSDRA).

The review process and stakeholder feedback: The one-week annual review mission was spent within Abuja. The review team, comprised of two UK-based DFID Governance Advisers and DFID Nigeria’s lead programme officer for FOSTER, liaised closely with UK-based Extractives Advisers who reviewed the programme in previous years. The review mission was spent almost entirely with external stakeholders and partners, including CSOs, academics, media organisations, government bodies, providers of technical assistance and MPs. The FOSTER team set up the meetings but did not attend them, thus allowing for a candid exchange of views and opinions. These partners were extremely consistent in their praise of, and appreciation for, the support and guidance received from FOSTER, particularly with respect to FOSTER’s “back seat” approach (see below). Crucially, beneficiaries underlined that FOSTER’s input was always practically and concretely helpful in enabling them to address specific priority challenges that they were grappling with and/or to think differently about their approach. Notwithstanding the potential for some selection bias, the consistency of positive feedback – as well as elements of constructive criticism – from such a large number and wide range of stakeholders meant that the annual review team could be confident that it heard a reasonably true and fair representation of FOSTER’s work. Below are some examples of testimonies heard during the annual review:

- FOSTER worked in the background. They played a linking role, brought in evidence and created space for discussion. FOSTER didn’t make itself the engine of the change. Otherwise people can say ‘who are you anyway?’ and that is not good. We must be seen to be the ones pushing for it, not FOSTER.
- A whole lot was achieved not only because of the content but also how we positioned the agenda and the messaging we used
- They have expertise at their fingertips, either in-house or through bringing in others and they can mobilise this quickly
- FOSTER’s contribution helped fire up people’s awareness and demystify complex issues but also crucially sparked their passion and commitment
- The focus on win-wins helped soften the position of potential spoilers on areas they were more sceptical about

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process