Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: South Sudan - Humanitarian Crisis Response
Programme Value: / £195.9 million. (£132.5m South Sudan, £63.4m regional)		Review Date: 14 December 2014
Programme Code: 204400	Start Date: January 2014	End Date: 31 December 2015

Summary of Programme Performance
Year	2014
Programme Score	A
Risk Rating	High

Summary of progress and lessons learnt since last review
This is the first annual review for the South Sudan – Humanitarian Crisis Response programme. Good progress has been made in 2014 despite all the challenges faced, including the DFID South Sudan staff evacuation and recent (December 2014) return of a full team in country. The programme is on track and outputs are meeting expectations. United Nations (UN) partners and International Organisations receiving DFID support have the right systems and processes in place to manage risks in challenging operating environments. However, staff turnover in many humanitarian agencies (and within the DFID Humanitarian Team) remains high, making delivery and monitoring a challenge.

DFID’s emergency humanitarian response to the South Sudan crisis is achieving its overall purpose which is to save lives, reduce suffering, maintain the dignity of affected people and strengthen resilience in South Sudan, Ethiopia, Kenya, Uganda and Sudan. To date DFID has supported water, sanitation and hygiene (WASH), food, non-food, nutrition, shelter, health, protection and livelihoods interventions. While interventions have varying start dates and durations, the overall programme will end on 31 December 2015. Given the staggered intervention dates, many agencies have not yet submitted interim or final results.

DFID’s Rapid Response Facility (RRF), activated in January 2014, enabled pre-qualified partners to mount an immediate response at scale to alleviate critical humanitarian needs. DFID also provided technical expertise seconded into responsible UN agencies to address key capacity gaps in emergency response. DFID also funded the World Food Programme (WFP), and the International Committee of the Red Cross (ICRC) to strengthen logistical capacity and maintain pipelines for food and non-food assistance throughout the overall response. The multi-sectoral approach of support enabled urgent needs to be met across all priority sectors (i.e. health, food, nutrition, shelter, nutrition, protection, livelihoods and non-food assistance).

Progress made and lessons from previous reviews

The Project Completion Report (PCR) for the ‘Supporting The International Humanitarian Response in South Sudan (September 2013 – June 2014) project (providing £24m total funding for the Common Humanitarian Fund (CHF) and WFP) conducted in June 2014 found the overall impact for DFID’s contribution to both agencies had been achieved, scoring a B for overall output (mainly because the outbreak of conflict meant some planned outputs could not be delivered) and A for overall outcome.

It highlighted the following points on progress at that time and areas to improve:
- It found the overall impact for DFID’s contribution against both agencies had been achieved
- The logical framework at that time needed improvement (outcome indicators were for example not linked directly to outputs). This has been addressed in the logframe for the current response.
- Programmes overall had been delayed in both implementation and reporting due to insecurity, and the reporting capacity of agencies (in this case WFP and the CHF) remained weak. A high number of no cost extensions had been requested through the CHF.
- The lack of reliable data, including on nutritional status or mortality, in addition to the absence of baseline data made it hard to attribute improvements directly to DFID funding. Nonetheless on the whole, indicative results across both agencies were on track.

The PCR for the £39.5m ‘Supporting the International Response in South Sudan’ programme for UN High Commissioner for Refugees (UNHCR), CHF, UN Office for the Coordination of Humanitarian Affairs (OCHA) and ICRC[1] of February 2013- December 2013, was conducted in June 2014. It found that outputs met expectations and the programme scored an A in overall output and A in overall outcome. Relevant findings and recommendations include:
[1] United Nations (UNHCR), Common Humanitarian Fund (CHF), Office for the Coordination of Humanitarian Affairs (OCHA), International Committee of the Red Cross (ICRC)
- Though outputs met expectations and the programme scored an A - results were in part measured using qualitative information, which, given the context and inability to visit field locations, was deemed acceptable as reporting from agencies was not due at the time of the review.
- The CHF developed a partner performance index – drawn from monitoring activities, financial, narrative and audit reports. This performance index was used in 2013 to inform the selection of projects to be funded. It has been incorporated into the overall risk management framework for the CHF (due to be implemented by in February 2015) allowing CHF stakeholders to monitor changes in performance over time.
- The effectiveness of the CHF in the past has been directly impacted by levels of donor funding. It was recommended that DFID assess whether UNDP could release payments according to urgent need, rather than waiting for the total expected funds to be received.
- That any forward looking DFID logframe needs to have relevant and measurable indicators and targets, as well as space to measure/comment on the quality of services being offered (i.e. numbers of consultations seen in a health clinic exceeding a DFID target does not mean that the quality of that service is acceptable).

Outlook
The humanitarian outlook for 2015 is poor. Changing frontlines and fighting could bring fresh displacement and/or further secondary internal displacement and new refugees. Internally displaced people (IDPs) are likely to remain scattered among ad hoc shelters in peri-urban or remote rural areas – many seeking safety in or near to international actors (and their hubs).

New food security/nutritional data[2] supports the case that humanitarian assistance in 2014 contributed to reducing levels of vulnerability and better food security situation through 2014. Famine was averted. However, the situation is still worse than in a normal year, with significantly more people in crisis and emergency (using Integrated Food Security Phase Classification), and malnutrition levels well above emergency thresholds. Moreover, as displacement has affected planting in some areas, the 2015 lean season is expected to start earlier than normal, as families start to exhaust their own harvest stocks from January, rather than later in the year, and so become reliant on food from markets (or humanitarian supplies) earlier and for a longer period than normal.
[2] International Peace Commission (IPC) September 2014 reports

There is a consensus among stakeholders that the wellbeing of people affected by the conflict may deteriorate further in 2015 due to:
- Poor coping mechanisms following a succession of poor harvests and stretched capacity of host families.
- Continued lack of investment in infrastructure, including roads and basic services, given capacity constraints and the need to prioritise lifesaving assistance.
- The logistical burden and difficulty of reaching large numbers in “hard to reach areas” if the 2015 appeal requirements ($1.8bn[3]) are not met.
  [3] The 2015 Humanitarian Response Plan appeals for $1.8bn, the same amount as appealed for via the 2014 Crisis Response Plan.

Further, there is consensus that, given the current context, refugees in the region are not likely to seek any permanent return to South Sudan during 2015 and numbers are projected to rise significantly from 500,000 to 821,000 by the end of the year according to the UN. Such an increase will continue to challenge the capacity of host countries to accommodate such numbers. Therefore, refugees in the region will continue to require a full package of humanitarian assistance through 2015 while securing the required funding will be increasingly challenging in light of current global humanitarian needs.

Summary of recommendations:
In South Sudan
- Continue a programme of multi sectoral support but focus in 2015 on quality of the response and addressing needs for a protracted caseload (e.g. primary health, livelihoods, urban populations if IDPs return to cities if security improves, and possibly some form of education in line with DFID Regional refugee programme, if appropriate).
- Drive partners to continue to improve monitoring and reporting, including the CHF and FAO, and revise the logframe with figures from the CHF 2015 allocations.
- Multi-year funding would be efficient. Funding should be aligned with the seasonal calendar around rains, harvests and seasonal conflict patterns.
- Continue support to the CHF and OCHA in 2015, to ensure staffing gaps are filled (if necessary through DFID Surge and secondments).
- Continue to assess with UN Development Programme (UNDP) the possibility of releasing CHF payments according to urgent need rather than waiting for the total expected funds to be received.
- DFID should do an assessment of the effectiveness of the CHF Rapid Response model, and consider how the response can continue to reach those in need in inaccessible areas.
- Advocate as necessary for the official appointment of the Deputy Humanitarian Coordinator for South Sudan to provide leadership on the operationalization of the response.
- Contribute to the Protection of Civilian (PoC) Sites debate – following humanitarian principles but at the same time exploring the feasibility of voluntary return and DFID support for those who do. The timeframe for any safe return to occur in early 2015 is short, due to the seasonality of South Sudan. Planning will need to start January 2015.
- Bolster the DFID South Sudan programme team given the size of the programme and number of partners and reporting requirements.
- Provide further support to DFID funded partners to help improve their internal reporting on results. Continue with field visits to monitor progress on the ground in real time.
- Provide further support to surge staffing including more senior/transformative posts if needed. As of mid-December 2014 there are 3 cluster co-lead gaps that need filling.

In the Region
- Review these recommendations in a regional advisers’ meeting in Ethiopia in February 2015.
- Focus where possible on further support to lifesaving activities including food assistance, nutrition and ongoing protection needs, as well as livelihoods (including access to land), vocational training/education and support to host families and local integration, and more permanent shelter.
- Multi-year refugee programming providing longer term assistance aligned to the seasonal calendar should be developed in order to improve efficiency and sustainability. Pilot examples could be developed and then replicated where possible on a case by case basis. Such programming should, however, allow for addressing acute needs that are foreseeable for new arrivals.
- The Regional DFID Humanitarian Adviser will continue to support country offices in the region to ensure good coherence, coordination and communication while contributing to knowledge sharing.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/4401289.docx
DevTracker Link to Log frame:	http://iati.dfid.gov.uk/iati_documents/4700340.xlsx

Outline of the DFID programme
Nearly 2 million South Sudanese people have been displaced since the outbreak of conflict in December 2013. The majority (1.5 million) remain within South Sudan whilst nearly 500,000 seek refuge in the region (Ethiopia. Kenya, Sudan, Uganda). Since December 2013 the UK has provided £132.5 million to humanitarian support in South Sudan and a further £63.4 million for refugees in the region. The overall DFID package of funding for South Sudan is in line with the UN led Crisis Response plan and the response covered all sectors. Strong technical expertise surged into UN agencies has helped ensure strong functioning clusters and an adequate rapid response at field level. DFID’s response also supported the strengthening of logistics and included the provision of support to common air services and food/non-food pipelines (i.e. enabling assistance).

The composition of DFID’s field team changed in size and expertise over the duration of the response. At its largest, the humanitarian team in Juba totalled 4 humanitarian advisers and a share of 2 programme personnel as well as senior leadership (i.e. an additional humanitarian and livelihoods team leader) and a Regional Humanitarian adviser to help co-ordinate the refugee response. DFID Humanitarian Advisers attend cluster meetings and donor meetings to keep abreast of unfolding events and to help manage/steer the response both in Sudan and within the region. In addition, regular partner meetings take place to support and guide UN and NGOs receiving or being considered for DFID funding. Agencies receiving support already have a proven track record with DFID.

Humanitarian advisers based in DFID offices in the region continued to lead the programme during 2014, with coordination from the new DFID Regional Adviser post, based in the DFID Uganda office. UNHCR for the region led on the UN appeal process and coordination of the humanitarian response across all countries, with inputs from others.

Pages 9 – 16 provide interim results where they have been made available. Note: Most partners reporting were not due at the time of this annual review. It is therefore premature to undertake % of results achieved until interim reporting is submitted.

Overview of South Sudan and Regional tranches allocations
Organisation	Tranche 1 - £39.5m (approved Feb 2014)	Tranche 2 - £60m (approved May 2014)	Tranche 3 - £50m (approved Sep 2014)	Regional spend - £30m + £16.4m (approved May 2014 and Nov 2014)
RRF:
GOAL	400,000
Oxfam	1,347,578
Save the Children	305,362
International Medical Corps	840,431
Concern Worldwide	1,100,000
International Rescue Committee	917,206
World Vision	1,089,423
International NGOs:
Mercy Corps			3,500,000
International Rescue Committee			1,890,301
International Medical Corps			1,100,000
ICRC	3,000,000	5,000,000	6,000,000
Surge capacity support
UN Surge capacity	1,000,000	1,000,000
DFID internal surge capacity	652,183
UN Agencies:
WFP (UNHAS logistics)	2,500,00	2,500,000	1,000,000
WFP		16,000,000	10,000,000
UNDP – Common Humanitarian Fund		25,000,000	13,500,000
UNICEF[4]		4,000,000	7,000,000
UNHCR		2,500,000
Crown Agents (tents and logistics to IOM)	590,202
IOM (Malakal)		1,600,000
IOM		2,000,000
FAO	8,300,000		6,500,000
Regional:
Ethiopia	4,000,000			17,500,000
Kenya	2,500,000			6,600,000
Sudan	4,500,000			5,400,000
Uganda	6,000,000			15,900,000
Region wide surge support				1,000,000
Contingency	457,615	399,996	-490,301
Total	39,500,000	60,000,000	50,000,000	46,400,000
[4] United Nations Children’s Fund.

Allocations for the regional aspect of the programme at the country level are as follows;

Country	Tranche 1 (regional IRSs per agency)	Tranche 2	Tranche 3	Total
Ethiopia	WFP £2.2 m / UNHCR £ 1.8 m	UNICEF £4 m / WFP £2.6 m / IOM £1.6 / NRC £ 1.4 / GOAL £0.5	UNHCR £4.4 m / WFP 3.0 m	£21.5 m
Sudan	N/A	UNHCR £2.7 m (£1 million still being programmed) / UNICEF £2 m / WFP £700,000 (in progress).	N/A	£6.4m
Kenya	WFP £ 1.5 m / UNHCR £1 m	WFP £2 m / UNHCR £1.4	WFP £3.2 m	£9.1 m
Uganda	WFP 1.0 / UNHCR £4 m / UNICEF £1 m	UNICEF £3.8 m / WFP £4 m / UNHCR £2.3	WFP £ 5.8 m	£21.9 m

B: PERFORMANCE AND CONCLUSIONS: SOUTH SUDAN and REGION (1-2 pages)

Annual outcome assessment

The outcome for this programme in South Sudan is: “Humanitarian coordination and interventions reduce the vulnerability of people in need in South Sudan (measured by numbers of people reached across sectors)”.

Outcome indicator 1 (South Sudan):

Humanitarian coordination and interventions reduce vulnerability of people in need in South Sudan.

The milestone of 3.8 million people reached by the end of 2014 has been reached according to the UN reporting[5].
[5] http://reliefweb.int/sites/reliefweb.int/files/resources/South_Sudan_Situation_Report_68_as_of_1_January_2015.pdf

- The UK contribution to support humanitarian assistance within South Sudan is £132.5m (c. $216m)[6] against the UN appeal of $1.8bn for 2014, with gives an attribution of approximately 12 (i.e. above the 10% target).
  [6] Assuming an exchange rate of $1: £0.63
- This means that DFID funds have assisted approximately 444,600 people in 2014. The majority of DFID humanitarian assistance has been targeted in the three most conflict affected states of Jongeli, Upper Nile and Unity state where a total of 1.1 million internally displaced persons live.

High-level outcomes/impact of the programme include:
- Risk of famine for 2014 was averted thanks to humanitarian support[7]
  [7] IPC data confirms this
- Pipelines for food, WASH and nutrition have not ruptured in part due to timely DFID support
- New approaches to make sure aid can be delivered in hard-to-reach places adopted (the CHF Rapid Response model)
- Massive scale up of logistical capability of the response (e.g. through 2014 United Nations Humanitarian Air Service (UNHAS) scaling up size of fleet from 7 to 17 airframes and flying to 11 new destinations)

Outcome indicator 2 (Regional)

Final results for the outcome of “Humanitarian coordination and interventions reduce vulnerability of South Sudanese refugees in the region” will be available after the country programme completion reviews – formal reporting from some partners will be not be received until 2015.

- Ethiopia: Results for food assistance (WFP) have almost reached their target; education activity (UNICEF) is generally on track with some minor delays due to risks around flooding and in the construction of schools; and generally UNHCR preliminary results are also on track.
- Kenya: Anticipated results for UNHCR and WFP are on track. In some sectors, targets were exceeded.
- Sudan: A restrictive operating environment resulted in delays in finalising project design but some good results observed to date, with UNHCR on track in supporting 35,700 refugees. Targets are to be met by mid-March.
- Uganda: The milestone for July 2014 of 118,400 was met. The outcome indicator milestone for December 2014 was to reach 150,000, based on the expected number of new arrivals according to the 2014 emergency appeal. Although final reporting was not due from all partners until after the drafting of this report, field visits and interim reporting suggest that all new arrivals were reached with humanitarian assistance. At the time of reporting in December WFP, through General Food Distribution, had reached 119,560 refugees with DFID funding which although lower than projected figures constitutes 100% of the registered new arrivals. Further work had been done broadly in line with milestones across the sectors that DFID was funding: education activity is underway but activities have yet to reach targets; WASH is well on track; nutrition (UNICEF) targets have been surpassed for the South Sudan influx; and general food distribution targets (WFP) have been met. Qualitative monitoring (five field visits by DFID staff in 2014) indicates UNHCR programming is on track, but results reporting will not be submitted until 2015.

High-level outcome/impacts of the programme include:
- Food pipelines have not ruptured in the case of WFP due in part to timely DFID support.
- There has been a concerted focus on protection given some camps, for example in Uganda, have more than 80% of refugees are women and children, many of whom have been subject to Sexual Gender Based Violence (SGBV).
- Global and severe acute malnutrition rates (GAM and SAM rates) have stabilised and even decreased substantially at some refugee locations due in most part to the efforts partners have made to screen and treat malnutrition early and appropriately.

Overall output score and description

A – Programme is meeting expectations

The programme of support for South Sudan and the region is on track and expectations are being met. However, this is qualified by the fact that reporting from some partners is not yet due, and some of the quality and scope of the reporting from partners is not as strong as it could be. Qualitative analysis and preliminary results shared with the reviewer were used to build a picture of whether targets are set to be achieved (see pages 9 - 16 for data collected and that contribute to DFID milestones).

Although partners took some time to scale up their responses through 2014 (nutrition, for example was significantly under prioritised for the first part of the year), capacity and reach was increased throughout the year. Given the challenges of working in South Sudan, and the stretched capacity of nearly all partners, qualitative monitoring which assesses impact and outcome and not just outputs is critical. A large portion of the programme funds were channelled through the CHF, which has increased its monitoring and evaluation capacity throughout the year, however this process needs to continue through 2015, and DFID should explore ways of better reflecting the CHF contribution in a revised logframe.

The DFID allocations of funding address acute lifesaving needs. Support has clearly taken the multi-sectoral approach required to meet the range of needs the displaced population has and the majority of assistance has been focused on people residing in the three conflict affected states in South Sudan and addressing urgent refugee needs in the region. Gender sensitivity and protection activities have been mainstreamed throughout the programme (as well as specifically targeted through sexual or gender based violence (SGBV) interventions through International Rescue Committee (IRC) and International Medical Corps (IMC)) and nutrition has featured strongly in the response, particularly during the latter half of 2014.

There is clear evidence that as new urgent needs have been identified throughout the year, DFID has stepped up and provided new and different support (e.g. International Organisation for Migration (IOM) and the urgent relocation and expansion of the PoC camp in Malakal; addressing SGBV and integrated Nutrition with UNICEF and maintaining pipelines early on – to allow for agencies time to purchase and pre-position before the rains).

DFID phases of support across 2014 have been planned, and coincided, with increases in UN appeals (both the Crisis Response Plan (CRP) and the International Committee of the Red Cross (ICRC) appeal were revised mid-year) and the Regional Refugee Appeal. As vulnerability increased in conflict affected states and as better analysis was produced around gaps – DFID quickly responded working in partnership with OCHA to adapt part of the CHF to include a rapid response model. This model enabled agencies to receive rapid funding to meet urgent needs in hard to reach areas once security was stable enough to move. However, thousands of people have still not been reached in many areas around the country, due to access and security issues, and the response needs to continue to focus on these people and not just on the 7% (102,000) internally displaced people sheltering inside UN PoC sites.

The DFID programme has spread its risk – by providing funding through multiple channels including to the UN through the CRP and the Regional Refugee Appeal, to the CHF, to NGOs directly for SGBV work and to the ICRC who provide expertise across medical, livelihoods/some food assistance, protection and water sectors in particular.

DFID remains the second largest donor to South Sudan, with the USA first and ECHO third[8]. The coordination between the three main donors on the ground is excellent.
[8] Based on figures in UN OCHA Financial Tracking System (FTS)

The DFID regional part of the programme is on track and clear monitoring processes including regular field visits are in place to manage the programme. There are permanent humanitarian advisers based in the region at the country level, including in Uganda, where the regional Humanitarian Adviser has been deployed in response to this crisis. Though it is too early to comment on interim/final results in most cases – preliminary findings have been gathered and reflected.

There are some delays in projects caused by seasonal flooding and partner capacity. Delays have not been more than 2-3 months and the justification given by partners and/or DFID in the region has been reasonable.

The right agencies have been selected by DFID to address urgent refugee needs across the region. This includes in particular support to UNHCR, WFP and UNICEF. In the Ethiopian case, UN partners with their implementing partners – which DFID support - work together on joint targets. This is an example of excellent practice. It is efficient and helps to ensure consensus around gathering results and addressing constraints together.

Key lessons and key actions
- The multi sector approach covering all urgent humanitarian areas of need is appropriate in the South Sudan and regional contexts and should continue into 2015. Though the current DFID humanitarian focus is on the three conflict affected states in South Sudan it will be important to monitor for any deterioration across other states too (e.g. 80% of current cholera cases are in non-conflict areas this year).
- Multiple tranches of DFID funding have created a lot of work for all parties concerned (intervention review sheets, and keeping on top of reporting and results, MOUs in particular and reporting demands from partners). A multi-year business case, or at least planning for two tranches of funding in 2015, around the seasonal calendar (with a contingency reserve for unforeseen events) might be more efficient.
- If possible the revised DFID programme log frame could try to include qualitative information/data too. Numbers alone (i.e. results) do not provide the reader with adequate analysis on the quality of the responses entailed.
- Provide further support to DFID funded partners to help improve their internal reporting on results. Continue with field visits to monitor progress on the ground in real time.
- Coordination is key. Advocate as necessary for the official appointment of the Deputy Humanitarian Coordinator for South Sudan to provide leadership on the operationalization of the response, in hard to reach areas.
- The delivery of humanitarian assistance to IDPs and conflict affected persons in South Sudan and the region is not possible without continued significant inputs to “enabling activities” including common logistics and pipeline support (food, nutrition supplements, non-food assistance) and to surge staffing to fill urgent gaps.
- The situation is a protracted one. It may be more efficient in the long run to plan and address medium/long term needs (development) for refugees including support to livelihoods, education and access to land.

Has the log frame been updated since the last review?
n/a

## C: DETAILED OUTPUT SCORING South Sudan

Output Title	Frontline and pipeline humanitarian assistance to meet the needs of IDPs and conflicted affected in South Sudan.
Output number per LF		1	Output Score	A (programme is meeting expectations).
Risk:		High	Impact weighting	60%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by 31st December 2014)	Progress (i.e. meeting expectations so far)?	Score against indicator
Number of beneficiaries receiving health interventions	ICRC (not set milestone but DFID attribution is 16%) / CHF 250,494. / UNICEF (all pipeline). / A total of 138,000 vaccinated against measles, 144,760 vaccinated against polio and 33,000 households reached with cholera prevention measures	Overall ICRC results mid-year exceeded initial planning. Around 4,000 surgeries have taken place (ref: interview). Each week 500 children were admitted and cared for in the health centre in Kodok, 33 medical facilities received ICRC support (supplies, staff, infrastructural improvements). A new inpatient structure with 60 beds built in Waat. / There are no final results against the CHF yet. The following can be used to indicate programme on track. / The CHF prioritises well. To date, 67% of all projects are in the 3 most affected states where most needs are; / 90% of funds have been allocated to support high priority projects in the UN Crisis Response Plan 2014 / The health sector of the CHF has received 17% of total funds ($22.8m) / Policy paper guiding rapid response model in place and being followed. Parameters set for reserve allocations, with established advisory board in place. / Majority of funding is allocated to frontline projects including health. / The CHF is strategic and helps to coordinate through the clusters, appropriate health interventions in South Sudan. / Based on discussions, UNICEF has reached 40,000 children for vaccination against measles and polio with the DFID funds, against the original 50,000 target (tranche 1). The targets are expected to have been reached by end December 2014 / There have been delays in the target against cholera, but reports state that the target has been met (by recruiting trained social mobilisers through Ministry of Health).	A - outputs met expectation / A / A
Number of people reached with WASH interventions	ICRC 67,200, / RRF 71,983 / CHF 161,520 / UNICEF 80,000 reached with WASH (pipeline only).	ICRC reported in May that a total of 20,992 persons gained access to improved water, and targets for the year end would likely be met / RRF results indicate 84,540 were reached. / CHF / WASH has received the most funding across the CHF for 2014 (i.e. 22%). Again, needs have been addressed mostly in the three conflict affected states. Quality of the data and reporting post rapid deployments varies (and the DFID team are working with OCHA to improve this). / In preliminary results submitted during the review, UNICEF documented they had reached 70,000 of the 80,000 DFID target and would likely meet or exceed targets by end December 2014.	A / A+ outputs moderately exceeded expectation / A / A
Number of people reached with nutrition support	CHF 91,805 people / UNICEF (1st tranche) 10,000 children provided with therapeutic nutritional supplies. / UNICEF 2nd tranche is new but is part pipeline again of therapeutic food (for 35,000 children) and wider health for 48,000 children as well as 10 trainings and support to 65 nutritional surveys across 40 counties.	CHF / Nutrition receives 11% of CHF funding and is the 5th sector prioritised for allocations. Agencies have not stepped up fully across the nutrition sector and there is a lack of capacity (well recognised 5 months ago). Scale up is underway, and indications from interviews suggest the CHF will meet its targets. / UNICEF / Capacity is slowly increasing with presence across 10 states, but still lack of implementing partners for nutrition. DFID will support in tranche 3, training of INGOs for management of feeding and WFP/UNICEF are together rolling out joint methodologies and information systems. / Nutrition pipeline reportedly well stocked but no formal reporting due on DFID tranche 1. Preliminary results submitted by email state that 10,000 children have been reached and 4 out of 5 trainings conducted for management of SAM. / UNICEF state that currently of their 176,000 SAM target, 73,000 children have been reached and reports submitted back to Juba (i.e. 41% of their overall total 2014 target so far).	A / A
Protection	RRF 33,000 people / CHF 89,638. / UNHCR has agreed to increase advocacy and awareness efforts for refugees in the 6 camps in South Sudan.	RRF 39,260 people reached / CHF / Protection activities and projects receive around 10% of total funding from the CHF. No reports/results were available to provide preliminary analysis, but based on discussions with CHF understand target likely to be met / UNHCR / It is not clear whether targets are all being met – formal reporting is not yet due, but informal updates do not clarify the picture. UNHCR reported lack of capacity was undermining quality of the programme.	A+ - Outputs moderately exceeded expectation / A / B - Outputs moderately did not meet expectation
Number of people given household items	CHF 58,640 / RRF 33,000 / IOM first tranche 8,196 / IOM second tranche 84,000.	CHF– results have not yet been submitted across proposals; however indications are that targets will be met. / RRF – 86,542, people reached (though some project delays, may include double counting) Exceeded target in part because some funds initially intended for other activities were reallocated to household items. / IOM first tranche (based on interviews – targets are on track for Malakal non-food items (NFI) distribution and extension of the PoC base). Work will be completed on time in February. NFIs had been purchased already and the dry season provided good opportunity to improve the Malakal PoC as agreed. / Tents in kind distributed through DFID at the beginning of the year had been useful (though in future IOM recommended sending individual family tents (rather than for two families). Indications that second tranche will meet targets.	A / A++ - output significantly exceeded expectation / A
Number of people assisted with food and unconditional cash transfers	133,317 people	WFP with the £16 million grant have reached 107,280 beneficiaries of the agreed 133,317 target up until September 2014, and are likely to meet or exceed the year-end target. / Through key informant interviews, WFP relayed they had 26 dedicated teams (of which 10 were WFP teams) delivering urgent food assistance in all areas across the 3 conflict affected states. Food pipelines are stable for the next 3 months (until March 2015). In 2015, WFP will have 7 of their own teams covering opposition areas (when INGOs can deliver assistance). / The barges are now operating and 5 distribution sites will be covered. Extensive mapping is in place for preposition sites (including opposition areas); forward hubs for road corridor; airdrop and airlift locations for conflict affected states. / Cash/voucher programme re-initiated for Juba (noting WFP revisited their methodology and have started again).	A
Number of households supported with livelihoods support	FAO – 390,000 people	FAO's September 2014 report states that during the first phase 224,664 people had been reached. However this is calculated based only on the amount of seeds and tool distributed to partners, not on partners reporting on distributions to beneficiaries. According to this measure only 64,386 people had been reached. Although the actual number reached in reality is actually much higher, partner reporting did not allow this to be demonstrated up until September 2014. / Distribution of fuel efficient stoves delayed (but expected to achieve full results at the end of project period, March 2015) and results on fishing kits, due second phase.	B

Output Title	Support to enabling activities that strengthen response capacity
Output number per LF		2 (for South Sudan).	Output Score	A
Risk:		High	Impact weighting :	10%
Risk revised since last AR		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by 31st December 2014)	Progress (i.e. meeting expectations)?	Score
Numbers of passengers transported in humanitarian air operations (12% attributable to DFID)	9,000	On target as overall 6,849 passengers are transported monthly, which is beyond UNHAS’s 5000 monthly target.	A
Tonnage of light cargo transported (12% attributable to DFID)	36 MT	25 Metric tonnes (MT) per month is the overall UNHAS target. A total of 150 metric tonnes has been delivered so far. DFID targets are likely to be met (which take a proportionate attribution of this).	A
Number of field based staff provided by the Standby partnership agreements attributable to DFID funding	30	30 posts filled across multiple sectors. Budget expected to be used by March 31, 2015. Good oversight and management by CHASE OT/London.	A

Region

## C: DETAILED OUTPUT SCORING for the region

Output Title	Support is provided to South Sudanese refugees in Ethiopia, Kenya, Sudan and Uganda
Output number per LF		1	Output Score	A +
Risk:		High	Impact weighting	30%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones (by 31st December 2014)	Progress (i.e. meeting expectations so far)?	Score against indicator
Ethiopia – Number of South Sudanese refugees reached with DFID funded assistance and protection	230,000 people	WFP has almost reached its target (i.e. delivering food to 190,000 out of 200,000 refugees) / UNICEF was on track with some minor delays in construction of schools, drilling of two boreholes and protection due to risks around flooding that eventuated and that DFID had foreseen and some earlier capacity constraints. A two month no cost extension would ensure targets were met. Some preliminary results around the DFID support are illustrated below: / It had assisted 24,000 refugee children (grade 1-4) with education and had trained 639 primary school teachers (both refugees and host communities) as well as provided school supplies, school furniture and textbooks. / 30,331 children had received psychosocial support through participation in 12 Child Friendly Spaces. / Nearly US$235,000 worth of essential medical supplies and commodities (including cold chain accessories, sand spare parts, tents, delivery kits, disinfectants, chlorine, etc.) had been procured. Distribution of the supplies was effected through the Regional Health Bureau and priority was given to health facilities around the refugee camps. A total of 40,000 long-lasting insecticidal nets had also distributed to refugees which benefited an estimated 80,000 people. In addition, a total of 120 health professionals in Gambella had been trained on Integrated Community Case Management. The health interventions under the DFID grant had so far benefited a total of 245,000 people. / Nutrition interventions were progressing as planned. / UNHCR had not yet submitted a preliminary set of full results but generally were on track. The number of shelter kits distributed was slightly lower than planned.	A+ - moderately exceeds expectation
Kenya – number of South Sudanese refugees reached with DFID funded assistance and protection	39,800 people	Interim reporting illustrates UNHCR are exceeding expectations. UNHCR has been able to reach 42,872 new arrivals in Kakuma. Specific DFID targets are also on track (e.g. 27,757 shelters had been built by September; the balance of 347 household latrines are currently under construction; a new transit and reception centre has been established; vaccination coverage is 100% (for 0-15 year olds for measles and polio) and routine immunisation coverage was estimated at 96% (well above 80% to be effective) and NFIs have been purchased to assist more than 10,957 households (and each refugee has received 100% of basic household items). / Education results exceeded expectations with more than 11,000 children enrolled into primary school. But despite this progress, 43% of primary children are still without access to education (existing space cannot cater for further enrolments). Four child friendly spaces were made operational and 3,156 children attended activities on a weekly basis.	A +
Sudan – number of South Sudanese refugees reached with DFID funded assistance and protection	40,000 people	WFP has provided South Sudanese refugees with emergency general food distribution for 40 days over a period of 6 months. To date, WFP have reached their target of providing 47,728 refugees (51% women, 72% children) with food assistance, improving the quality of food consumption to households within a 4 month distribution period. WFP has assisted some these refugees with 3,165 metric tonnes (MT) of emergency food assistance across White Nile and South Kordofan States. Of these, approximately 9,880 refugees have also been assisted through the emergency Blanket Supplementary Feeding Programme (58.5MT) and 1,402 through the Targeted Supplementary Feeding Programme (14.1MT) / UNICEF have coordinated interventions to support the refugees with water, sanitation, and hygiene (WASH) and education services for a period of eight months (July 2014 to February 2015). / WASH / 60,000 South Sudanese refugees and host communities (of these, 50% targeted are women and girls) in Sudan are now being provided with sustained access to quality WASH interventions. To reach this target, UNICEF is in the process of updating the water supply infrastructure in 3 camps as well as construct 3 solar powered water supply systems in 2 other states. Refugees and host community members are now being provided with access to sanitary means for excreta and solid waste disposal with the construction and repair of 2,000 latrines as well as being reached with hygiene promotion interventions. / Education / 5,100 South Sudanese refugees and host communities (of these, 50% targeted are girls) in Sudan will have safe access to quality educational opportunities. Construction and signing of contracts with MoE have just begun in order to prepare adequate learning spaces, teacher offices, and semi-permanent classrooms for school children. Of this target, 15,000 primary school aged children are to be enrolled and engaged in an education environment. So far, UNICEF has trained up to 334 education actors and 3,300 have benefitted from the distribution of teaching and learning materials. UNICEF has also formed 4 environmental societies in the camp locations to help promote health, hygiene, and a peaceful coexistence for refugee children. / UNHCR is on track with supporting 35,700 refugees in Sudan (of which 80% are estimated to have been living in Sudan since the 2011 secession) with emergency shelter support and Non Food Items. UNHCR will also be individually registering 45,000 South Sudanese refugees in an electronic database through the use of a biometric system. These targets are to be met by mid-March and no formal reporting has been received yet.	A +
Uganda – number of South Sudanese refugees reached with DFID funded assistance and protection	150,000 people	The response in Uganda has been strong, with good cooperation between the UN agencies, and a positive scale-up from international and national NGOs who did not previously have a strong presence in the hosting area. / DFID funding to UNHCR targeted 50,000 people with shelter and 70,000 with core relief items by December 2014. Reporting was not due in time for this annual review, but DFID field visits conducted in the course of 2014 suggest good progress in these areas. / WFP provided a report in December covering their activities with the first tranche of funding. They responded well to challenges faced with the identification of a partner for General Food Distribution, and by the time of reporting had fed 119,650 people, all new arrivals registered by that time. Supplementary feeding activities had not begun by the time of reporting so data were not available on their progress. / UNICEF reports a total of 33,000 refugees have been provided with access to quality water (20,000 had been the original target in the DFID submission for example). / Water trucking was carried out for the first three months of the emergency in transit and reception centres, 25 boreholes were constructed. UNICEF has establishment of 25 early learning centres (i.e. half of the expected target) in Arua and Adjumani (15 permanent and 10 community/home based). Not all centres are operational, but in September more than 5,000 children accessed the services. / UNICEF had established 77 therapeutic feeding centres treating more than 3,131 children. An additional 42,138 children and 34,278 pregnant and lactating mothers had received folate and/or vitamin A. All food for nutrition pipelines had been procured.	A

Summary of responses to issues raised in previous annual reviews (where relevant)
N/A

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

Value for money assessments of DFID’s humanitarian response take into account three components namely: cost, quality and speed/timeliness. It is vital to consider all three as there are trade-offs between them. For example, higher costs associated with air transport due to impassable roads is justified in the context of South Sudan.

Where possible, some costs have been minimised by providing direct support to large pipelines (of food and non-food assistance) which helps to improve value for money of the overall humanitarian response. DFID’s commitment to the CHF is also another means in which to reduce costs associated with the administration of individual grants to each NGO. Importantly, it offers a common strategic direction if managed well – and helps to prioritise which geographic areas that require urgent targeting.

Transport
Transport costs are high in South Sudan due to poor road networks, dispersed populations and reliance in the rains upon air craft and helicopters. Insecurity and poor infrastructure in country means that humanitarian staff travel is often restricted to UNHAS and/or establishing independent fleets of transport and air charters. DFID funding to WFP/UNHAS to develop and maintain a common logistics service helps reduce this cost driver and in addition helps to ensure a coordinated approach to the delivery of assistance.

Preparedness and pre-positioning
Adequate support early on for pre-positioning activities in South Sudan, will continue to keep costs down as will using and maintaining the road networks compared to air. Other likely areas of savings include DFID support to the livelihood sector i.e. use of vouchers, provision of seeds and livelihood kits so that IDPs can, even for a season – partly support themselves or complement the assistance they have been given. Should the conflict continue into 2015 – agencies may wish to consider alternative shelters (to save money in the medium term).

Looking ahead, there may be a case to extend rehabilitation of basic services in urban areas, as some agencies are planning in 2015. However the current security situation does not allow for this to happen across the three conflict affected states yet.

Coordination
The humanitarian cluster system is in place and the overarching humanitarian architecture appears to provide value for money by coordinating the assistance effort. The concept of having co-leads (one UN and one INGO) per cluster helps to ensures an equal responsibility across actors (the UN being in most providing a policy lead and INGOs being more operational). However the response relies heavily on consultation and appears heavy in process – with paperwork demands at all levels (internal to the organisation and from donors). Where possible, joint working, joint targets and monitoring might help contribute to a more efficient operation.

 Assessment of whether the programme continues to represent value for money

Yes. There is good evidence that early response to humanitarian crisis are more cost efficient than responding late, which supports the case to invest in preparedness including pipeline support and prepositioning as well as supporting rapid responses (for example through the CHF). The Economics of Early Response and Resilience: Lessons from Niger (TEERR) [9] study found that in Niger the cost per capita of aid through a ‘late response’ is $230 versus $119 for an early response. In addition, taking into account losses avoided by an early response, the totals change to $932 per capita for the late response and still only $269 for the early response.
[9] “The Economics of Early Response and Resilience: Lessons from Niger,” by Courtnay Cabot Venton and Lorraine Coulter. June 2013.

Although this is not direct evidence for South Sudan, there is complementary evidence from other parts of Africa suggesting that early action leads to fewer economic losses, and to financial savings. For example, early action preventing an acutely malnourished child from becoming severely acutely malnourished cuts the cost of treatment from an average of $230 per child to $100.[10]
[10] “Value for Money in Humanitarian Response – Final Report,” by Simon Hale and Rachel Kessler. Coffey – International Development. July 2012.

Quality of financial management

South Sudan: DFID South Sudan disbursed £133.2 (89%) of the £149.5m approved by Ministers in 2014. £4.5m, allocated to Sudan in the first tranche in February 2014, was returned to the centre as was not going to be spent in 2013/14. The remaining balance will be released over 2015 as some projects are scheduled to run through to December 2015.

Regional spend: DFID country offices disbursed £46.4m (100%) of the allocation in 2014.  No balance remains to be released over 2015 but some no cost extensions are likely, due to minor delays in some areas.

Financial reporting is due at different stages with different partners. The first final reports were received at the end of December 2014 (see programme tracker for details).

E: RISK (½ page)

Overall risk rating: High for South Sudan and the Region

This programme is rated as high risk. This is because of the volume of funds, difficulty for DFID SS staff to travel outside Juba and the security challenges throughout the country. Mitigation measures include:
- Providing timely support to pre-positioning assistance in safer areas
- Pushing for greater access
- Investing in rapid response teams through the CHF
- Spreading risk and reach by channelling support through multiple channels
- Bolstering programme management capacity to help track and monitor reporting and results.

A detailed risk matrix will be updated as part of the Business Case. The main risks associated with the programme include:

Conflict leading to a suspension of programming or limited humanitarian access. The principle risk derives from conflict inside South Sudan including intimidation and harassment on aid personnel – which in the past has resulted in the scaling down of services. Furthermore, intercommunal tensions between the youth in UN bases (PoC sites) continue to disrupt humanitarian operations and potentially between refugee and host families in the region.

DFID partners will need to assess these risks further through monitoring and adapt programmes accordingly (e.g. UNHCR in the region provides assistance to some host communities as well as refugees, and the ICRC in South Sudan provides water to all affected groups and in urban areas). The UN has prepositioning sites in both Government held and opposition areas and monitors the movement of front lines. However DFID will need to also ensure that civilians potentially trapped in opposition areas, receive adequate levels of assistance (without having to walk cross line and in doing so, into an insecure area).

Additional risks for operating partners include poor market functionality as a result of insecurity (though this can also be caused by low production or supply chain ruptures) and flooding during the rains.

Financing gaps undermining the impact of UK funding: DFID has sought funding to cover critical pipeline gaps and meet essential needs, to mitigate this risk. Wider financing gaps are still a challenge both for South Sudan and against the UN regional appeal. In March-May 2013 DFID developed a lobbying plan where Ministers did a series of calls and meetings to influence the international community and encourage further funding to the appeals.

Fraud or theft may hamper programme delivery: DFID has selected partners who have experience of delivering in the region, and is currently carrying out local due diligence assessments, due to be finalised in February 2015, with many of its UN partners. Looting and theft are a big risk and are mitigated through UNMISS Force Protection, WFP reducing the number of warehouses they preposition supplies in (in the conflict states) and FAO are introducing a mobile phone tracking system to better monitor their stock. Further DFID have used the Humanitarian Country Team (HCT) to raise concerns of fraud and corruption and to emphasise the need for transparency, zero tolerance, and continuing work to strengthen systems. DFID also fund a consultant working with the CHF to strengthen their risk management systems.

Shortages of staffing and high turnover. Competing crises around the world will continue to impact on staff available for South Sudan both inside the UN, NGOs and donors (including DFID). For institutional memory purposes, it will be important to try and maintain a base of humanitarian experts that can continue to be used for South Sudan (and the region) and who are familiar with the context and conflict dynamics.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Yes. Although there have been some delays both in elements of the programme, and in some of the reporting provided (as noted above) as a whole the programme is delivering against the planned timeframe.

Performance of partnership (s)

This has been covered throughout the report, given DFID South Sudan and DFID in the region relies solely on its partners to deliver the programme. Performance is on track. There are some areas going forward that will require more detailed monitoring. Partners selected have a proven track record with DFID globally and receive larger institutional funding for core business, on an annual basis. It is important to note that local due diligence is being carried out now, across all DFID multi-lateral partners working on the humanitarian response in South Sudan. Host governments in the region are an important partner regarding refugee care and assistance and for the most part have played an exemplary role in leading with the UN and donors on the overall humanitarian response.

Asset monitoring and control

DFID has selected partners who have experience of delivering in the region, and is currently carrying out local due diligence checks with UN partners. UN partners are monitoring and reporting individually to donors on possible asset losses at the project level. There were significant losses of assets through looting etc. after the conflict broke out in December 2013 – the process for reporting and cataloguing these is being followed, and detailed risk mitigation strategies for avoiding further substantial losses have been developed by each partner.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

N/A
H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

There has not been a recent external evaluation and given access constraints and the complex context, it is not advised a full external evaluation be undertaken yet. Without prior knowledge of the context, it would be difficult in a short time frame to undertake a meaningful evaluation particularly given security and access constraints. Lesson learning and monitoring is better off coming from those directly involved in the response (with expertise from wider DFID and other agencies being drawn upon for additional advice, support and leadership when necessary).

DFID field/monitoring visits provide, for now at least, the best way to check if projects are on track (both through observation and direct questioning of beneficiaries). Although difficult, in the current environment, these are taking place where possible (see monitoring arrangement section below). The Regional Humanitarian Adviser is probably well placed to continue to provide oversight on performance across the region.

Monitoring progress throughout the review period

Methodology of the Annual Review

This review has been completed by an external consultant over a 27 day period including 1 week in Juba and 1 week in Kampala The report extends for the period from January 2014 to December 2014. The review is not an “end review” nor “evaluation” – but rather it is a review of progress to date. Findings draw on both qualitative and quantitative information, where possible. This review utilised general reporting and situation reports from partners, interim reports where they have been submitted, the Rapid Response Facility review, DFID’s Intervention Review sheets per tranche/agency which have all been completed, submissions for each tranche, the old Business case, two recent PCRs, minutes and emails from key meetings around issues relevant to the projects, a sampling of proposals submitted to DFID, back to office reports and samples of annual reviews carried out elsewhere (i.e. Sahel, Eritrea and Kenyan refugee response). Key informant interviews were conducted with humanitarian advisers in the region.

DFID’s own monitoring arrangements

DFID monitor the programme through regular field visits to all programmes. This proved more difficult for South Sudan due to heightened levels of insecurity, but 9 visits took place in South Sudan, and at least 3 visits were completed by humanitarian advisors based in the region during 2014 and detailed trip reports were made available. DFID staff attend regular donor and cluster meetings and humanitarian advisors meet regularly (i.e. each partner each week) with partners and donors to discuss programme successes and challenges. DFID sits on the advisory board of the CHF.

The AR recommends that field visits and schedules for South Sudan be designed to ensure that all projects receive a visit throughout the year (at least once). Consider utilisation of the DFID Regional humanitarian advisor for South Sudan inputs if required.