Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: State Building & Service Delivery Grant to the Palestinian Authority in the Occupied Palestinian Territories
Programme Value: 129,500,000 (£127,767,000 actual)		Review Date: 18/02/15
Programme Code: 202564	Start Date: 02/06/11	End Date:31/03/16

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A	A
Risk Rating	High	High	High

Summary of progress and lessons learnt since last review
	Output	Score	Weighting %
1	Results Funding – Public Services bought by DFID support	A	60
2	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient	B	25
3	Development effectiveness – aid to the PA is more predictable and results-focused	B	15

Lessons learned since last review

Conflict and instability hinders state building. The Gaza/Israel conflict during summer 2014 resulted in the deaths of 2,205 Palestinians including 521 children and 283 women. Seventy one Israelis were killed, including four civilians (OCHA 2014). The PA continues to face the challenges of reconstruction in Gaza following the conflict. Donor pledges for reconstruction made in Cairo in September 2014 are yet to materialise and whilst the Gaza Reconstruction Mechanism is delivering, there are financial and logistical challenges to scaling it up to respond to need. The Gaza/Israel conflict has had an impact on the Palestinian Economy. The 2014 escalation of violence in Gaza has dampened economic activity and therefore revenue generation. This has also contributed to the increase in the stock of arrears.

The Palestinian Authority (PA) is finding it increasingly difficult to sustain and advance reforms without political progress. The PA’s progress against the World Bank’s economic related indicators has decelerated. The PA will find it increasingly difficult to maintain policies to control expenditure in the face of worsening prospects for peace. The PA needs stability, sustained and full receipt of its clearance revenues from Israel (in line with its legal obligations) and a lifting of occupation related restrictions to grow its economy and continue to pursue reforms.

Donors are responding by strengthening their monitoring of reforms. Donors recognise the difficult environment the PA is operating in and want to better understand where reform is progressing well and where progress is slowing. The EU and the PA are developing a framework that will help monitor a number of key reform areas.

The Business Case vision for the Efficiency Action Plans (EAPs) was too ambitious. The Business Case outlined the use of EAPs for Ministries of Health and Education as a basis for our value for money assessments. The approval of the EAPs were delayed by PA Ministers due to the delays stemming from the appointment of a new Cabinet. The EAPs were then adopted by the Ministries at a slower pace than anticipated. The level of ambition for the EAPs was set too high for the fragile context of the OPTs. As a result the EAPs have not provided the data originally intended for the vfm assessments. The EAPs have however, put value for money ‘on the agenda’ and recent work from the Ministry of Health indicates that the PA may have generated efficiency savings of $3m (see vfm section). We will revise our vfm measures to more accurately and realistically reflect the work that is currently being undertaken by the Ministries and reflect this in our next review.

Summary of recommendations for the next year:

R0	Revise the log frame to reflect an extension to the programme from April 2015 to March 2016.
R1.1	Ensure the Terms of Reference for the independent evaluation of the SBG will examine the role of service delivery targets in direct financial assistance, capture lessons on what has worked well in this programme and suggest options for incorporating service delivery targets in any successor programme to the SBG.
R2.1	Verify the final results from indicator 2.1 on release of the World Bank’s Implementation Completion Report and report in the February 2016 annual review.
R2.2	Update indicator 2.2 in the 2015/16 log frame to better reflect the PA’s use of the EAPs. (Log frame will be updated by March 2015).
R3.1	Ensure that the SBG evaluation and design for any successor programme fully considers the role of existing World Bank and EU results frameworks to help the PA to develop a coherent reform agenda. Donor supported frameworks should align with PA’s Palestinian National Development Plan.
R3.2	Redefine indicator 3.3 to focus on the EU results framework that is currently being developed and will begin implementation in April 2015. (Logframe will be updated by March 2015).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202564/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202564/documents/

Outline of the programme

Need
At a time when the Palestinian economy is contracting by 4% (2014) and the PA faces losses in revenues from Israel’s with-holding of clearance revenues, donor aid is required to support the PA to continue paying salaries to enable the delivery of services in a timely, efficient and effective manner. Several studies have been made of the potential economic, educational and health repercussions of PA collapse. It is likely that there would be a broad decline of services in the sectors of health, education, communications, water and energy, the unemployment rate would reach unprecedented levels and internal security could be affected.

Outcome
Support to the Middle East Peace Process is a high priority for the UK Government. The UK’s goal is the creation of a sovereign, independent, democratic, contiguous and viable Palestinian State living in peace and security side by side with Israel. We continue to support the work of the PA under the leadership of President Abbas and Prime Minister Hamdallah, which remains a vital element of efforts to achieve a two-state solution. As well as providing education, health, policing and other vital services to the Palestinian people, the PA represents a partner for peace with Israel.

The project’s purpose is to support the Palestinian Authority to provide essential services to Palestinian citizens through the delivery of key state-building reforms and payment of salaries. Our support will help to address the chronic shortfall in funding for the PA resulting in part from the on-going conflict, and restrictions on movement and access in the Occupied Palestinian Territories (OPTs). These restrictions act as a brake on the Palestinian economy and the PA’s ability to raise revenues. If this funding shortfall is not addressed, the PA will not be able to pay public worker salaries and continue delivering essential services. Unemployment is high in the OPTs, and around one third of Palestinian households are dependent on a public sector wage earner.

Impact to date
The UK’s support has enabled the PA to continue delivering services to Palestinians and make impressive reforms in a number of state-building areas including security and Public Financial Management. The PA’s institutional readiness for statehood has been recognised by the international community including the UK. In 2011, the World Bank reported to the Ad Hoc Liaison Committee (AHLC) that the PA’s capacity to “fulfil state functions compares to capacity in MENA and other countries, and shows that it is often comparable and sometimes superior.” This message was also echoed by the UN and IMF in their reports to the AHLC. Subsequent reports and assessments continue to affirm the PA’s institutional capability but warn that the fragility of a political horizon puts these gains at risk.

The actual total amount disbursed to the PA since 2011 is £127,767,000. The disbursement schedule to date is as follows: £30m in 2011/2012 (actual); £34.1m in 2012/13 (actual); £41.6m in 2013/14 (actual); £22m in 2014/15 (actual). Out of the potential £12m ‘Results compact’, £10.267m was disbursed. Of the £200,000 allocated for an independent evaluation and results framework, £110,000 has been allocated for an independent evaluation; and £29,900 was allocated for an assessment of the PA accounts that will feed into the evaluation.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The outcome statement is: To improve the Palestinian Authority's management of its financial systems and to provide better access to services for the Palestinian public.

The overall outcome assessment is that the PA continues to make progress against service delivery targets. Public Financial Management reforms also continue but are increasingly difficult in the context of violence (Gaza/Israel 2014), easing of restrictions and absence of political progress.

#	Indicator	Milestones 2014 (Jan to Dec)	Actual	Comment
1	Education: Primary net enrolment rate for boys (M) and girls (F) (%)	97.2% (M) 97.9% (F)	96% (M), 96.8%(F)	Net enrolment rates have picked up significantly since the last AR. The PA’s previous targets were ambitious, and for the new PNDP, the PA has assigned new targets for enrolment in basic education, which are more realistic (94.1%M, 96.9%F). It should be noted however that there are no figures for Gaza, and without an end to the occupation it will be hard for the PA to meet the outcome target under the current circumstances.
2	Education: Mean score obtained by students (boys and girls) in Monitoring Learning Achievements in Maths (grade 8) and Arabic (grade 7)	Arabic / 62.5(M) 62.5.(F) / Maths / 53 (M) 53(F)	Arabic / 56(M), 58(F) / Maths / 36(M), 45(F) / [2013]	Data shows that there has been a steady improvement on scores obtained since 2011 baseline and 2012 achieved data. However, this still falls short of the PA’s own targets for those years as indicated in the milestones.
3	Health: Percentage of deaths caused by cancer, cardiovascular disease and diabetes	50%	51.3% [2013]	Data gathered from the Ministry of Health annual report published in 2014 has shown a positive trajectory from 2012 where the rate was 57%.
4	Security: Proportion of the public who are satisfied with the performance and services of the security establishment (%)	55%	No updated data available	Data on the indicator was reported as difficult to measure in the last AR and continues to be so. We were waiting for the publication of the PNDP 2014-17 to update this indicator. There is a PNDP indicator measuring “% of public trust in the security establishment” that we recommend as a replacement Before confirming this replacement, we will confirm the baseline with the Palestinian Centre Bureau of Statistics.
5	Fiscal sustainability: Net present value (NPV) of money saved for the PA by reforms in DPG Matrices 2011-2014 and reforms promoted by education and health efficiency technical assistance ($m)	-	Data will be available from the independent evaluation scheduled to be completed by December 2015.	Output recommendations will address the need to select better indicators to monitor service delivery efficiency gains. The independent evaluation of this programme will investigate effectiveness of spending and provide data to address this outcome indicator in the 2016 Annual Review (see evaluation section below).
6	Public financial management and accountability (PFMA): Fiduciary risk rating for PA PFMA system.	High	High	A DFID Fiduciary Risk Assessment (FRA) was conducted in 2014 drawing on the World Bank led Public Expenditure and Financial Accountability assessment (2013) and the EU Court of Auditors report (2013). The overall fiduciary risk level remains ‘High’, as in the 2010 FRA, but with a positive trajectory for change due to improvements in the PA’s PFMA systems. The overall corruption risk remains ‘Substantial’ as in the 2010 FRA. The oversight and accountability scores were low (and brought overall scores down) due to the lack of a functioning Parliamentary mechanism following the PA/Hamas split in 2007.

Overall output score and description

The programme has scored an A in this review.
	Output	Score
1	Results Funding – Public Services bought by DFID support	A
2	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient	B
3	Development effectiveness – aid to the PA is more predictable and results-focused	B

Key lessons

The Business Case vision for the Efficiency Action Plans (EAPs) was too ambitious. The Business Case vison for the Ministries of Health and Education EAPs was that they would provide the basis for our value for money assessments. The approval of the EAPs was delayed by PA Ministers due to the delays stemming from the appointment of a new Cabinet. The EAPs were then adopted by the Ministries at a slower pace. The level of ambition for the EAPs was set too high in the Business Case. As a result the EAPs have not provided the data originally intended for the vfm assessments. The EAPs have however put value for money ‘on the agenda’ and recent work from the Ministry of Health indicates that the PA may have generated efficiency savings of $3m (see vfm section). We will revise our vfm measures to more accurately and realistically reflect the work that is currently being undertaken by the Ministries and reflect this in our next review.

The PA continues to deliver services but reforms are becoming increasingly fragile. The pace and durability of these reforms however, become increasingly fragile the longer occupation imposed restrictions prevent the Palestinian economy from growing in a sustainable manner. A contracting economy, increasing unemployment, volatile donor contributions, conflict and lack of political horizon make it difficult for the PA to grow a job led economy and raise sustainable domestic revenues. The impact of the Gaza/Israel conflict in 2014 is still being felt with the PA attempting to deal with over 100,000 Gazans still displaced. Without continued financial and political support from the international community, the PA’s hard won state building achievements will become increasingly fragile.

Key actions

The UK will continue to support the PA through financial year 2015/16 with an allocation of £25m . The exact results to be achieved are being finalised with the PA and will be agreed before the first tranche is made in April 2015. The UK will continue to use the World Bank Palestinian Reform and Development Plan-Multi Donor Trust Fund outlined on page 9 to support agreed fiscal management reforms.

Has the logframe been updated since the last review?

The log frame has not been updated since the February 2014 Annual Review. In line with the recommendations from this (2015) review, an updated logframe will take effect from March 2015.

C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Results Funding – Public Services bought by DFID support
Output number per LF		1	Output Score	A
Risk:		High	Impact weighting (%):	60
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones	Progress
1.1	Education: Number of non-refugee children supported by DFID in primary education (grades 1 – 6)	5,751 (2,889M 2,862F)	5,788 (2893M 2895F)
1.2	Education: Number of non-refugee children supported by DFID in lower secondary education (grades 1 – 6)	1,731 (860M 871F)	1,965 (982M 983F)
1.3	Health: Number of children under 5 years old immunised for measles.	1,916	3,747 (MMRI and MMRII)
1.4	Health: Average number of daily medical consultations per doctor in general PHC clinic	47	55
1.5	Health: Proportion of Medicines on the essential drug list that are reported at zero stock levels in the West Bank (WB) and Gaza (G) central drug stores (%)	20%(WB) 20%(G)	26% (WB) 26% (G)
1.6	Social Protection: Number of individuals covered by DFID-supported cash transfers	7,283	10,393

Key Points
The PA has surpassed the majority of the milestone targets including in health, education and social protection:

1.1 and 1.2: In education the progress against the milestones shows that the PA has slightly overachieved on both primary and secondary education targets.

1.3: The PA no longer administers measles shots separately, but instead includes them within the Measles Mumps and Rubella (MMR) vaccine to children at both 12 (MMR I) and 18 months (MMR II).

1.4 and 1.5: In health, the average number of daily medical consultations per doctor in general PHC clinic (1.4) is steadily above the target. However, the health indicator (1.5) on drug shortages shows that there was an increase of medicine shortages compared to figures from 2013. Therefore the 2014 milestones were not achieved. To explain, in the West Bank, the shortages are mainly due to the budget problems of the Palestinian Authority. In Gaza, medical stocks fared better but only temporarily due to the donations of medicine during and after the war in the summer. Gaza continues to suffer shortages due to the closure of the Rafah border crossing since July 2013.

1.6: Social protection (1.6): The PA’s Social Protection Strategy for 2014-16 has a target to provide cash assistance to 10,972 (1.57% of the total number of individuals receiving cash transfers). In our measurement of progress towards that target, we have a milestone of 7,283. In 2014 the PA delivered cash transfers to 10,393 households, therefore overachieving on that target.

Summary of responses to issues raised in previous annual reviews (where relevant)
The previous review recommended finding ways to reduce the cost of drugs. The increased humanitarian pressures following the Gaza/Israel conflict in 2014 and have limited the scope for significant efficiency reforms in drug procurement (see 1.5) above. The PA has however generated efficiency savings elsewhere in the health sector (see vfm section).

Recommendations
R1.1: Ensure the Terms of Reference for the independent evaluation of the SBG will examine the role of service delivery targets in direct financial assistance, capture lessons on what has worked well in this programme and suggest options for incorporating service delivery targets in any successor programme to the SBG.

Output Title	Policy Leverage – improved PA systems and fiscal discipline, and spending more efficient
Output number per LF		2	Output Score	B
Risk:		Medium	Impact weighting (%):	25
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones	Progress
2.1	Public finance reforms: Proportion of planned reforms in World Bank annual Development Policy Grant (DPG) Matrices that are over 50% completed (%)	70%	55%
2.2	Public service efficiency reforms: Extent of completion of PA action plan for increasing efficiency of public spending on education and health (%)	70%	58%
2.3	Accountability reforms: Number of high quality quarterly and annual monitoring reports on the Palestinian National Development Plan each year that meet agreed quality criteria.	4	4

2.1: We assess that the PA has achieved 50% of the targets specified in the World Bank’s DPG matrix in the following reform areas; improved public procurement; improved cash planning and monitoring; improved access to information and leasing (as a proxy for business climate). Progress has been limited in the areas of controlling the wage bill and increasing domestic revenues. There are several explanations. The 2014 escalation of violence in Gaza has dampened economic activity and therefore revenue generation. The wage bill has grown because the freeze on net lending has been lifted, and because pay scales have been revised, meaning that promotions have taken place and resulted in the same stock of civil servants costing more. The World Bank will formally measure reforms achieved by the PA against the DPG Matrix in April 2015 through their Implementation Completion Report (ICR).

2.2: Both the Ministry of Education (MoE) and Ministry of Health (MoH) Efficiency Action Plans (EAPs) list activities related to efficiency measures incorporated in annual work plans and programme budgets; reviewing and simplifying financial regulations; adopting a programme budget structure to align the budget more closely with the delivery of their main services; identifying major cost drivers and reporting trends; and taking measures specific to the Ministries to implement these efficiencies. The EAPs were adopted by the Ministries at a slower pace than anticipated, however, as the previous Annual Review indicated, technical assistance to the MoH in implementing its EAP has been effective, and the MoH has made good progress such as identifying cost drivers and developing efficiency inputs to various national health service sections. The MoE has also seen progress against its EAP since the last AR in areas such as adopting efficiency priorities in their new Education Strategy 2014-19 including management reform that constitutes a major efficiency intervention. The implementation of the activities has improved since the last AR by 10% overall. However, both Ministries are still slightly under-performing against the milestone.

2.3: Following the Gaza/Israel conflict in the summer of 2014, MoPAD produced a Gaza reconstruction plan that provided the basis for the Cairo pledging conference in September 2014. MoPAD also produced a new Palestinian National Development Plan 2014-2016 based on extensive reviews of the previous plan and produced two high quality reports for the scheduled Ad Hoc Liaison Committee (AHLC) meeting in March and September 2014. The March AHLC was cancelled and consequently the report was not circulated (only published reports are captured in above). A PNDP 2011-2013 report was also published (but has to be translated to English). We recommend that the 2015 target is reduced to three which is an appropriate number of reports and includes two scheduled reports to the AHLC and one PNDP monitoring report.

Summary of responses to issues raised in previous annual reviews (where relevant) The 2014 Annual Review result for indicator 2.1 was verified using the World Bank’s Implementation Completion Report in May 2014. The 2014 Annual Review recommended supporting the PA to improve the quality of its financial accounts. A DFID funded World Bank PFM Expert provided technical assistance to the PA. The Expert led five TA missions to support the PA in improving the quality and timeliness of the financial statements.

See 2.2 above for details on EAPs.

Recommendations
R2.1: Verify indicator 2.1 on release of the World Bank’s ICR and report in the February 2016 annual review.
R2.2: Update indicator 2.2 in the 2015/16 log frame to better reflect the PA’s use of the EAPs. (Log frame will be updated by March 2015).

Output Title	Development effectiveness – aid to the PA is more predictable and results-focused
Output number per LF		3	Output Score	A
Risk:		Medium	Impact weighting (%):	15
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

	Indicator(s)	Milestones	Progress
3.1	Aid predictability - UK: Proportion of disbursements released by DFID according to the amount and month specified in the UK-PA Memorandum of Understanding, unless due to a breach of conditionality (%)	75%	75%
3.2	Aid predictability - international: Proportion of scheduled aid reported as disbursed in government accounts through a reliable information system (%)	65%	61%
3.3	Results-focus: Extent to which a comprehensive results framework has been developed and implemented for the PRDP Trust Fund.	4 (4 - Results framework is being reported upon annually)	4 (4 - Results framework is being reported upon annually)

Key Points
3.1: The UK made four payments to the PA during financial year 2014/15. Three of these payments were made according to the agreed schedule (£5m in May, £5m July, £10m in October and £2m in December). The fourth payment of £2m was made in December 2014 rather than January 2015. We decided to bring this payment forward to ease the PA’s fiscal pressures. This was agreed and welcomed by the PA.

3.2: The Ministry of Planning and Administrative Development (MoPAD) obtains data from the donor community on 2014 in early 2015. The current data capture rate is 61% but not all donors have completed their returns. Based on commitments, MoPAD anticipates that the final rate of data capture will be approximately 79% and will be able to confirm by March 2015. To note, this percentage includes both humanitarian aid and budget support.

3.3 The UK has been contributing to the development of an EU Results Framework that will take effect from April 2015. This results framework will complement the World Bank’s Development Policy Grant framework which the World Bank uses to assess the PA’s progress against pre-agreed reform targets. For the purposes of scoring, we have replaced the WB framework with the EU framework, which is in an advanced draft, and planned to be approved by the PA and EU by March 2015 and ‘go live’ in April 2015. The UK is leading on contributing to the development of specific targets related to Public Administration.

Summary of responses to issues raised in previous annual reviews (where relevant)

See 3.1 and 3.2 above.

The UK continues to hold formal dialogue meetings with the PA to ensure that both the UK and the PA are adhering to the commitments agreed in the joint Memorandum of Understanding. The next meeting will take place in March 2015.

Recommendations
R3.1: Ensure that the SBG evaluation and design for any successor programme fully considers the role of existing World Bank and EU results frameworks to help the PA to develop a coherent reform agenda.

R3.2: Replace indicator 3.3 with EU results framework (Update log frame by March 2015).

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance of the programme

The primary cost drivers that were identified in the Business Case were concerned with the procurement of consultants for the Performance Tranche, Results Framework and the Independent Evaluation. Previous Annual Reviews have stated that it has not proven necessary to bring in a consultant to assess the Performance Tranche.

An additional cost driver is the management charge imposed by the World Bank for managing the multi donor trust fund. This fee depends on the overall volume of UK contributions to the fund. We currently anticipate that this fee will be 0.5% until the fund arrangement expires in 2017. The is also the Trust Fund administration fee, which represents 1% of the contribution.

VfM performance compared to the original VfM proposition in the business case

The business case proposed tracking the following VFM measures to compare costs of basic services delivered by the PA compared to UNRWA::

- Economy: input unit costs in the West Bank and Gaza for medicines and salaries.
- Efficiency: output unit costs for (i) cost per outpatient visit to a primary healthcare clinic and (ii) cost per child in primary education.
- Effectiveness: the business case proposes calculating the net present value of the programme as part of the independent evaluation.

The source of the data for economy and efficiency was to be the Efficiency Action Plans (EAPs) for health and education which were completed with support of DFID funded technical assistance. These plans have helped the PA to identify areas to improve efficiency but the pace and manner of the PA’s adoption have developed differently to the vision outlined in the Business Case. Delays in approving the EAPs following Cabinet changes and political uncertainly for much of 2014 (breakdown in negotiations, reconciliation, Gaza/Israel conflict) has slowed down Ministerial decision making. Systematic collection of efficiency data and comparison to UNWRA costs have proven too complex at this stage of efficiency work.

DFID’s Palestinian Governance Programme (PGF) has been working with the Ministry of Health (MoH) in particular, gathering key data in order to develop robust indicators in a list of efficiency priority areas agreed with MoH. Outside medical referrals (to non-MoH hospitals) for tertiary health services are a major, rising and unsustainable financial burden. The issue emerged as a policy priority in 2014. With a view to using cardiac catheterisation as a pilot area, DFID’s programme supported the development of referral policies. These were approved by MoH and distributed to all cardiology treating, referring and referral-receiving facilities in the first half of 2014.

Partial and preliminary data for 2014 suggests there could be significant savings in this specific clinical area, although findings should be treated with caution at this stage. It is estimated that for 2014 (first 9 months), the average referral cost for catheterisations in the West Bank has been reduced by 8.1% compared to 2013. If the average cost had been at the same level as in 2013, this would have cost the PA a projected additional US$ 1m in 2014. The MoH is also on track (also first 9 months) to carry out 30% more catheterisations itself in 2014 than in 2013. If it keeps up this rate for the last three months of 2014, then it will have carried out an additional 648 procedures, which if these had been referred instead would have cost a further NIS 6.4m, a little under US$2m.

We will verify these results once the final quarter’s data has been released.

The business case envisaged an independent evaluation to take place in 2013/14. The evaluation will provide an opportunity to test the effectiveness of the programme to the degree benefits can be monetised further (see section H for further details on the evaluation).

Assessment of whether the programmer continues to represent value for money
The project continues to perform and is delivering the expected Outputs with an overall score of A. Given the difficult fiscal and political environment, the importance of this cannot be underestimated. Maintaining access to public services at the current high level is an important objective both for reducing poverty and continuing to demonstrate that the PA is an effective governing authority for Palestinians.

Quality of financial management

World Bank
The Palestinian Reform and Development Plan-Multi Donor Trust Fund (PRDP-MDTF) pools different donor funds into one administrative mechanism. This reduces the transactions costs for the PA and for the participating donors, and clearly links support to reform progress and provides regular and reliable disbursements to support priority recurrent and project expenditures in the budget. The Development Policy Grant (DPG) and its results framework were agreed with the PA in consultation with development partners. As such, the World Bank agrees reforms with the PA annually. The results matrix was developed to monitor progress under the DPG, and also to monitor the implementation of the MDTF, aligned with the National Development Plan. The DPG and the PRDP-MDTF support the implementation of selected key objectives of the PA’s strategy. The UK has an agreement with the Bank to use the PRDP-MDTF up until August 2017.

The PRDP-MDTF is audited by the World Bank’s external auditors following standard World Bank Trust Fund management practice. There is also an annual audit conducted by external auditors, paid for by the World Bank as part of the cost of administering the PRDP-MDTF. The PA produces progress reports on the National Development Plan to the World Bank at the end of each calendar quarter. The PRDP-MDTF then disburses after each calendar quarter upon receipt of the PA’s reform progress report. Progress reports can be delayed, and as a result, disbursement by the WB to the PA will also be delayed.

Date of last World Bank Implementation Completion Report	May 2014
Date of last World Bank quarterly report	October 2014
Date of last World Bank financial report	August 2014 (WB)
Date of last audited annual statement	August 2014 (WB)

Link to PRDP-MDTF website:
http://web.worldbank.org/WBSITE/EXTERNAL/COUNTRIES/MENAEXT/WESTBANKGAZAEXTN/0,,contentMDK:21779811~pagePK:1497618~piPK:217854~theSitePK:294365,00.html
Link to PRDP-MDTF quarterly reports: http://web.worldbank.org/WBSITE/EXTERNAL/COUNTRIES/MENAEXT/WESTBANKGAZAEXTN/0,,contentMDK:21878744~pagePK:1497618~piPK:217854~theSitePK:294365,00.html

Palestinian Authority
The latest audited annual accounts of the PA are for 2010 financial year. The 2010 financial statement was sent for audit in January 2012, but had to be repeatedly revised. The State Audit and Administrative Control Bureau (SAACB) sent a Management Letter to the MOF in August 2012 containing 133 observations. With technical support from the UK, the MOF has now completed the 2011 financial statements which will be sent the SAACB.
E: RISK (½ page)

Overall risk rating: High

The overall risk of the programme is still judged as High. This is due to the external risks which can affect the programme (e.g. failure of MEPP, conflict and civil unrest in the OPTs and Israel).

Annex A provides a complete update to the Risk Matrix.

Overview of programme risk

In addition to updating the risks in the original Business Case, we have also identified the following emerging risks or those that are particularly pertinent at this time:

Prospects for a return to negotiations in the near future are currently slim. Israel will have elections in March 2015 and the PLO has indicated that it will hold a congress in the near future. Changes in leadership may bring opportunities but unlikely in the short term.

The PA has done well to continue delivering services but progress on reforms is and will continue to be difficult unless political progress is made. World Bank and the UN have been delivering this through their reports to the Ad Hoc Liaison Committee meetings for some time now.

The most serious threat to the PA’s ability to continue delivering services (including security) is Israel’s withholding of clearance Revenues. Israel announced a freezing of the transfer of half a billion shekels ($130m) in tax revenues collected on behalf of the Palestinian Authority. This is in contravention of its legal obligations. These funds compose 70% of the PA’s revenue base and are worth the entire wage bill. PA civil servants were not paid their December 2014 salaries due at the beginning of January 2015 but paid 60% later in the month. The PA’s ability to operate without timely and sustained receipt of these revenues is extremely limited. The UK and others continue to urge Israel to fulfil its legal obligations to continue transferring these revenues in a timely and consistent manner.

Security cooperation between Israel and the PA has been key to stability in the West Bank and the reduction of terrorist attacks within Israel. The PA and the Palestinian leadership have continued to cooperate with Israel even during peaks of tension in 2014. Payment of civil service salaries including PA security personnel is dependent on sustained receipt of Clearance Revenues as outlined above.

2014 saw sustained violence in the West Bank and the Gaza/Israel conflict. The Gaza/Israel conflict resulted in the deaths of 1,483 Palestinian civilians, of whom 521 were children. Whilst the West Bank and East Jerusalem have not seen the tensions experienced in 2014, the overall security situation remains volatile. We share the UN’s assessment that without tangible progress on Gaza, it is very likely that violence will return. We continue to monitor the situation closely and encourage all parties to help Gazans recover from the devastation resulting from last summer’s conflict. Our funding to UN agencies is helping to mitigate the worst effects of the violence.

Outstanding actions from risk assessment

Risks continue to be treated in line with the Risk Matrix (annex A).

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

Output indicator 3.1 provides detail on the delivery against timeframe.

Performance of partnership(s)

The World Bank continues to operate the PRDP Trust Fund effectively and efficiently. In 2012 they altered their financial procedures to enable donor funds to be transferred more quickly. The Bank continues to charge 1% of the contribution to administer the Trust Fund. In January 2014, the World Bank began procedures to extend the Trust Fund for another three years, which resulted in the payment of an additional fee by all donors, proportional to their contribution, starting February 2014 and ending August 2017.Alldonors, including the UK, have agreed to this amendment.

As previously outlined, the UK’s relationship with the PA is governed by a robust MoU which centres on mutual accountability, good governance, transparency and commitment to non-violence. The next formal MoU Dialogue meeting will take place in March 2015 and will be an opportunity to reflect on this annual review and raise key issues such as the PA’s performance on primary education. The dialogue will also be an opportunity for the PA to hold the UK to our commitments on aid effectiveness.

An assessment of the PA’s progress against DFID’s Partnership Principles is conducted prior to each quarterly disbursement (see G below).

There are more details relating to the PRDP-MDTF contained within the links provided in section 2.2

Asset monitoring and control

No assets have been or will be procured under this programme.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

We assess the PA against DFID’s Partnership Principles before every quarterly disbursement. We also assess the PA’s commitment to these principles annually through a formal meeting with the PA. This was last undertaken in March 2014 where we commended the PA for its good progress against a number of indicators (such as financial management and tackling corruption) whilst also raising a number of issues including: urging the PA to take a more transparent and affordable approach to prisoner payments; asking about actions taken to tackle incitement; and emphasising our zero tolerance approach to human rights abuses in the Palestinian security forces.

As part of negotiating an extension to our current MoU we will have a formal conversation with the PA to re-confirm the Partnership Principles since the appointment of the Interim Technocratic Government. However, we continue to have high levels of confidence in the PA given the PM and key Ministers remain unchanged.

Commitment to additional discretionary Partnership Principle: We consider that the track record of the Palestinian leaderships shows their genuine commitment to non-violence and a negotiated two-state solution. We believe that the Palestinian Authority under President Abbas and Prime Minister Hamdallah is a firm partner for peace, they remain clear that they continue to work to achieve peace.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

Terms of Reference (ToRs) have been published to procure an external team of evaluators to complete an independent evaluation of this programme by the end of 2015. The results of this evaluation will contribute to the design of any successor programme.

The ToRs are based on the Organisation for Economic Cooperation and Development (OECD) methodology for evaluating budget support. The evaluation will also look specifically at:

Economy: How the management fees of the World Bank compare to other multi-donor trust funds and consultancy firms.

Economic return: The potential range for the economic return, from varying those assumptions for which there is weak evidence. An appropriate level of detail will be agreed during the inception phase of the evaluation.

Monitoring progress throughout the review period

The programme is managed by a team of officials from across the DFID OPTs team led by the Governance and Security team leader. The team completed this review drawing on evidence from a range of sources including the PA, implementing partners and open sources. Programme results and risks are interrogated on a quarterly basis. In line with DFID’s SMART Rules, a delivery plan was completed in January 2015.

The programme was a key area of focus for the UK International Development Committee (a Parliamentary select committee) in March 2014. The full report can be accessed via the International Development Committee’s website.

The programme was also examined as part of DFID’s routine internal audit in December 2014.

DFID maintains regular contact with the PA at both Ministerial and official levels to discuss the ‘health of the PA’ and its ability to continue delivering services and implement reforms. These meetings are conducted bilaterally and also through established donor structures.

The UK works with a range of civil society groups including through our own programme ‘Supporting Stability and Promoting Democracy’ to understand Palestinian feedback on the PA’s ability to deliver services and implement reforms.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to iprogrammessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against vfm measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc.) / The Annual Review process