Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: CLIMATE RESEARCH AND INFORMATION SERVICES IN SOUTH ASIA (CRISSA)
Programme Value: £2,600,000.00		Review Date: 17 Nov to 31 Dec 2014
Programme Code: 202125	Start Date: Sept. 2010	End Date: Sept. 2015

Summary of Programme Performance
Year	2011	2012	2013	2014
Programme Score	A+	B	B	A
Risk Rating	Medium	Medium	Medium	Medium*

*As in the current log frame. Increase to High is recommended in this Annual Review.

Summary of progress and lessons learnt since last review

During the current review period, there has been significant progress in the ongoing studies with several outputs either at an advanced stage of completion or undergoing peer review. A scoping exercise on the challenges and opportunities around green growth initiatives was completed, and a dissemination/ outreach strategy has been commissioned (the draft report is under review).

The key lessons have been the following:
- Focussed efforts to disseminate CRISSA outputs to a range of stakeholders is critical for achievement of programme level outcomes. The enhancement of coordination and coherence of research funding is challenging, and it is unlikely that publication of project outputs alone would achieve this. The CRISSA dissemination strategy (under review) will attempt to support partners in outreach and dissemination and will possibly include proactive engagement with potential funders.
- The programme has been producing significant research-based evidence on a range of climate related issues, and it is important that these feed into DFID country programmes wherever relevant. While several CRISSA outputs have been with Climate Advisers in the country offices (and their feedback sought), it has been strongly felt that CRISSA outputs can be strengthened if these are systematically validated through lessons emerging from climate funding at the country/ regional level.

Summary of recommendations for the next year

1. The project log frame should be revised based on the specific recommendations of this review. Overall the risk rating should be increased from Medium to High and SARH should review the mitigating actions every 3 months to assure itself that they are appropriate for a project with a high risk rating. (by February 2015)
2. The dissemination strategy should be finalised and a plan of implementation developed (by March 2015)
3. SARH should continue to closely monitor the active projects and seek periodic feedback on the uptake plans (till September 2015 when the programme ends). SARH should maintain a record of uptake activities and publications for at least one year after the programme end date.
4. SARH should maintain close contact with Asia Regional Team (ART) and Energy, Climate and Growth Unit (ECGU) to assess the need to continue with climate research funding and draw up a plan either to design a follow-up programme or to provide technical inputs to programmes designed by the other teams.
A. Introduction and Context (1 page)

DevTracker Link to Business Case:	Business Case and Summary3717461
DevTracker Link to Log frame:	Logical Framework4783824

The CRISSA programme had an original budget allocation of £1.5 million from September 2010 to March 2013. An updated Business Case was approved in August 2011 with an additional funding of £1.1million (total budget £2.6 million) over 4.5 years (2010-2015). A 6 month no-cost extension has been given to the programme extending the end date to September 2015. CRISSA was designed as an ‘umbrella’ programme under which a number of specific projects are supported. This support was initially intended to cover four areas of activity: coordination and strategic dialogue among funders of research; commissioning high quality evidence reviews of key subjects of policy importance; commissioning small-scale research addressing key topics; and, building capacity of South Asian climate researchers to publish papers in high impact journals. However the programme has significantly evolved over its lifetime based on assessment of intermediate results and recommendations of previous annual reviews. The CRISSA logframe (as revised in June 2014) modifies the first outcome to coordination with (rather than of/among) funders while retaining the evidence creation and capacity building objectives. However the capacity building objective is now tagged with a longer term target (beyond the project timeframe) as it has been realised that it is unrealistic to expect that the capacity building activity (organisation of ‘writeshops’) would result in significant increase in numbers of publications unless the quality of the generated evidence is enhanced.

SARH plans significant dissemination activity during the next few months and till the programme-end to consolidate the programme outputs and achieve the logfarne outcomes.

There are currently 4 live projects under CRISSA

- Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change: Asian Development Bank
- Glacier Monitoring in the Himalayas using Unmanned Airborne Vehicles (UAVs): University of Utrecht
- Calibrating above and below snow line precipitation as inputs to mountain hydrology models: University of Utrecht
- Climate Change and Groundwater Resilience: British Geological Survey

Two projects that have concluded this year are :

- Scoping Green Growth Challenges and Opportunities in South Asia: Oxford Policy Management
- Support for Special issue of Climate and Development Journal: International Institute for Environment and Development

In addition to these, a dissemination strategy for the programme is under development, and a firm specialising in development communication has been engaged to review project outputs and recommend modes of dissemination and outreach.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

There has been some progress towards the stated programme outcome - more coordinated and coherent regional approach to research.

The first outcome indicator is ‘level of duplication of research efforts’ and the 2015 milestone is ‘regional research priorities discussed among national and international donors (2015)’. The currently active CRISSA projects are expected to deliver outputs by mid-2015 and a comprehensive dissemination strategy to reach out to a wide range of stakeholders, including national and international donors is now being developed (the first draft of the strategy is under review). The strategy will include presentation of CRISSA outputs in national, regional and international conferences and preparation/ dissemination of policy briefs (or other summary documents) for the policy-maker and donor community, and will be implemented over 2015.

The second outcome indicator is ‘improved evidence base available to decision makers from jointly funded research and high quality evidence reviews’ and 2015 milestone ‘key research and reviews produced that are disseminated and discussed with decision-makers.’ CRISSA projects continue to generate high quality evidence and SARH is making focussed efforts to make these available to decision-makers in appropriate formats.

Overall output score and description

A (Outputs met expectation). The programme is on track to deliver the outcomes in the final year (2015), subject to the risks identified in this report.

Key lessons

A key lesson has been the reinforcement of the need to engage with various levels of stakeholders (including those outside the academic community) at various points of the project cycle.

The draft dissemination strategy has identified the key dissemination tools and channels for a range of stakeholders and it is expected that the evidence generated by CRISSA projects will feed into policy processes through a range of pathways. While CRISSA projects have in-built dissemination plans in every case, it is unlikely that these alone will achieve the desired impact. For example, it is desirable that CRISSA investigators based in the region present their findings in regional (as distinct from national) events wherever opportunities exist. The strategy includes a calendar of events (global, regional and national) that CRISSA investigators can participate in; however distilling research findings to suit a regional audience would be critical for the process to achieve high impact.

Key actions

1 The dissemination strategy is to be finalised by Feb 2015 and a plan is to be put in place for implementation of the strategy.

2 Close engagement is to be maintained with partners whose projects are nearing completion and appropriate project-specific dissemination channels are to be suggested (over 2015)

3 Discussion is to be held with Energy, Climate and Growth Unit (ECGU) and Asia Regional Team (ART)on issues of complementarity with the CRISSA programme. More specifically, linkages with the SAPs (State Action Plans) on Climate Change in Odisha and Bihar are to be discussed with ECGU (in the context of the Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change study).since these are receiving DFID support.

Has the log frame been updated since the last review? Yes
## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Coordination with research funders
Output number per LF		1	Output Score	A
Risk:		Medium *	Impact weighting (%):	20
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

*As in the current log frame. Increase to High is recommended in this Annual Review.

Indicator(s)	Milestones	Progress
Enhanced multi-country coordination in climate research	Enhanced multi-country inputs in climate research (No of multi-country or regional research programmes with multi-donor inputs) (2015)	Five CRISSA projects are multi-country, and based on collaborative arrangements among northern and southern institutions. Several project outputs (joint journal papers. workshops) reflect this collaboration. The dissemination strategy (now under development) will also target regional stakeholders.
Increased sharing of research outputs among funders	Research outputs and policy briefs formally shared in an appropriate forum (2015)	The ideal dissemination channels for each project are being identified as part of the dissemination strategy. Several research outputs have been shared through workshops, publications or blogs in the course of this year. Meetings with selected funders have benefited this process.

Key Points

The programme shows satisfactory progress against the milestones. Several projects (Climate Change and Groundwater Resilience, Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change, and Calibrating above and below snow line precipitation as inputs to mountain hydrology models) are at an advanced stage and significant results are expected to come in over the next few months. No milestones are indicated in the current review period; but the projects are on track (with minor exceptions due to reasons outside the project’s control) and it is expected that the 2015 millstones will be reasonably achieved. If may be however required to fine-tune the indicators/ milestones in the light of experience gained during the year, and some recommendations for this are being made in a subsequent section.

The Climate Change and Groundwater Resilience project presents a good example of multi-country coordination in climate research. The project aims to develop a typology of groundwater resources in the Indo-Gangetic basin and a set of country-specific case studies (Pakistan, Nepal. India, Bangladesh). Drafts of these outputs are currently undergoing peer review. The Annual Review team met one of the local partners (Matin Ahmed, Dhaka University) who expressed satisfaction on the collaboration arrangement and appreciated the facilitative role played by British Geological Survey.

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous AR expressed some concern on the lack of progress against this output. A key reason was absence of specialist staff within SARH to manage the programme (for a part of the review period) leading to discontinuities in technical leadership. A Research Specialist (A2) with background in climate and environment has been in place since February 2014, and issues related to coordination have been largely mitigated. Discussions have also taken place with Energy, Climate and Growth Unit (ECGU) and Asia Regional Team (ART) on issues of coordination and a number of research outputs have been formally reviewed by members of these teams. .

Recommendations

It has been realised that the enhancement of multi-country inputs in climate research (beyond the CRISSA projects) is contingent on a range of external factors outside the control of the programme. It is recommended that the milestone is rationalised, and interpreted as inputs within the CRISSA context. Hence the milestone could be rephrased to ‘Enhanced multi-country inputs in CRISSA projects’

It is recommended that the risk rating be changed from ‘Medium’ to ‘High’. Successful coordination with research funders assumes sufficient receptivity and coherence with programmatic priorities of other funders which are beyond the control of the programme. Moreover, CRISSA is a regional programme and targeting regional funders is an additional challenge. The risk could be partially mitigated by a strategy of engagement with research funders (as part of the dissemination strategy); however we believe that the residual risk will still be High. SARH will review the mitigating actions every 3 months to assure itself that they are appropriate for a project with a high risk rating.

Output Title	Quality of evidence base available for policy makers and programme managers
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	50
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Evidence on the needs of users with regard to climate information	WRI Review disseminated (2014). The review of user needs (of climate decision makers) was intended to shape upcoming investments in (climate) research and information systems in South Asia (to deliver information useful to decision makers)	The content of the review has been shared and discussed with several potential users. The CRISSA dissemination strategy may include further plans to disseminate outputs related to user needs.
Rigorous research findings available on key topics on policy and programming importance	Research outputs and policy briefs formally shared in an appropriate forum (2015)	Several research outputs (seven peer-reviewed papers, one final project report and four interim reports) of the CRISSA have been produced during the year and some dissemination activity has also been carried out. It is expected that research outputs for the full set of CRISSA projects will be available by mid-2015 and these will be shared in various forums.

Key Points

The WRI review (2011) produced a large number of generic recommendations and the document itself was somewhat unwieldy for the purpose of gathering focussed feedback. However, the process of identification of user needs fed into the design of the CRISSA programme. The Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change study, for example, responds to the felt need of developing an integrated approach to flood management based on a mix of structural and non-structural interventions

During the year, seven peer-reviewed papers were published by programme partners and several more have been submitted or under development, In addition, a special issue of Climate and Development funded by CRISSA was published in November 2014. The issue comprised a set of 12 papers on the theme ‘Mainstreaming Community-based Adaptation). A dissemination event for the Bangladesh component of the Climate Change and Groundwater Resilience project was held in Dhaka in November 2014 which had good participation from the relevant government departments. Two peer reviewed papers are under development under the project. It has been suggested that at least one of them should deal with multi-disciplinary/ multi-sectoral issues while the other could deal with more technical issues.

During the year, a scoping study on green growth challenges and opportunities was commissioned. The study provided a useful summary of green growth issues in the region, largely for policy-makers and non-expert audiences. The report was shared with climate advisers in the region and received favourable feedback. However it was felt that the constraints (to green growth implementation) that were identified in the report were rather generic, and it would have useful if these were supplemented by specific examples, wherever practicable.

The output indicator ‘High quality systematic reviews produced on key subjects on policy relevance’ was dropped at the time of revision of the logframe as this was considered no longer relevant to the programme. A separate Systematic Review Programme has been launched by SARH, and the process of sourcing appropriate review questions/ themes from Country Offices in the region is now on. If a review question/ theme on climate and environment registers sufficient demand, it will be included in the next call (or a subsequent call).

Summary of responses to issues raised in previous annual reviews (where relevant)

The previous review raised concerns relating to inadequate engagement with Asian Development Bank on the Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change project. SARH had a meeting with the ADB team in February 2014 in which the new technical lead was formally introduced. Subsequently there has been regular communication between SARH and ADB, and the inception and progress reports for the current phase have been reviewed by SARH. A visit to Odisha was also carried out to interact with the state-level study team. With regard to the Climate Change and Groundwater Resilience study, the previous review commented that ‘consideration of policy applications and dissemination will need to be sensitively done.’ Care is being taken to ensure that messaging issues are duly addressed and any potentially sensitive issues are discussed between DFID and the partner before dissemination. This has been done through specific requests to partners to share dissemination material (including blogs) before they are made public. This comment applies to all active CRISSA projects in varying degrees. .

Recommendations

The indicator ‘evidence on the needs of users with regard to climate information’ is relatively less relevant at this point when CRISSA is in its final year. It is recommended that evidence on ‘felt relevance’ of CRISSA outputs be rather sought, and the log frame indicator/ milestone appropriately revised.

Output Title	Capacity of south Asian climate community to produce high-quality and influential research
Output number per LF		3	Output Score	A
Risk:		High	Impact weighting (%):	30
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress
Number of papers on climate science published in high impact journals with South Asian lead or sole authors	10 papers published or accepted (2020)	While this is a longer term (beyond the programme duration) target, there has been good progress in the current year. Two journal articles attributable to CRISSA projects have a South Asia lead author. Two of the papers in a CRISSA funded special issue of Climate and Development are led by South Asian authors.

Key Points

Several CRISSA projects are multi-country with collaborative arrangements with/among South Asia institutions. It is expected that several project outputs will be jointly authored - with South Asian authors taking the lead in situations where the output is built on case-studies from the region. Significantly, 17 of the 37 authors of the Climate and Development special issue are from the south, though they are not necessarily the lead authors.

The capacity-building objective is more likely to be achieved through this route (collaborative research) rather than through capacity-building workshops (‘writeshops’, as in the original logframe) which presuppose that the constraints (for development of peer-reviewed material) relate to lack of writing skills rather than the quality of research itself.

Summary of responses to issues raised in previous annual reviews (where relevant)

In response to the previous annual report, support to capacity building workshops has been discontinued and the corresponding log frame output/indicator has been dropped.

Recommendations

It is suggested that the indicator be interpreted more broadly. It would be worthwhile to count the number of papers based on collaboration of northern and southern authors irrespective of who the lead author is. The present indicator (South Asian lead or sole) should be broadened to cover first and second authors since multi-author papers are increasingly becoming a norm.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance
Consider the specific costs and cost drivers identified in the Business Case
Have there been changes from those identified in previous reviews or at programme approval. If so, why?

The underlying cost drivers (as identified in the business case) are associated with the undertaking of new research, evidence reviews and capacity-building. There have been no changes in these except the discontinuation of specific funding for capacity-building.

VfM performance compared to the original VfM proposition in the business case
Performance against vfm measures and any trigger points that were identified to track through the programme

The original VfM proposition meant to assess VfM through measuring the quality of outputs and their influence (through pathways to impact). The project continues to produce high quality research outputs. The pathways to impact are however complex and a strategy is being developed to measure ‘first order’ impacts through feedback from the potential users of evidence.

Value for money in procurement has been ensured during the review period. For two contracts that were issued during this period (Scoping Green Growth Challenges and Opportunities in South Asia and Dissemination strategy), competitive procedures were followed with due consideration to cost issues. The Glacier Monitoring in the Himalayas using Unmanned Airborne Vehicles (UAVs) study was awarded to the University of Utrecht on single source basis to take advantage of existing collaborative arrangements (with ICIMOD) and the unique combination of specialised knowledge among research team members in a niche area of scientific work.

All contracts issued during the period were output-based with a number of well-defined intermediate milestones/ deliverables, and payments were linked with these. In case of ongoing grants with input-based arrangements, narrative reports were requested from partners along with their quarterly financial reports.

Assessment of whether the programme continues to represent value for money
Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?

The programme continues to represent good value for money, producing high quality outputs or showing good progress towards outputs expected in the next year. Local partners have, in general, placed a high value of the benefits of the collaborative arrangements, and have suggested that this is a cost-effective in situ capacity building process.

Quality of financial management
Consider our best estimate of future costs against the current approved budget and forecasting profile
Have narrative and financial reporting requirements been adhered to. Include details of last report
Have auditing requirements been met. Include details of last report

The Project Officer keeps track of the forecasts and payments for each project and is responsible for follow up with suppliers for invoices and reports keeping the Technical Lead informed. The financial forecasts for each of the projects are on track.

The quest numbers of key reports are provided below for ready reference.

Project title	Detail	Quest no.
Calibrating above and below snow line precipitation as inputs to mountain hydrology models	Progress report November 2014	4734681
Climate Change and Groundwater Resilience	Quarterly Report	4734236
Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change	Quarterly Report	4719951
Scoping Green Growth Challenges and Opportunities in South Asia: Oxford Policy Management	Final Report	4667283
Special issue of Climate and Development Journal	Annual Audit Report	4610158
Glacier Monitoring in the Himalayas using Unmanned Airborne Vehicles (UAVs)	Progress Report	4588222

E: RISK (½ page)

Overall risk rating: Medium (As in the current log frame)

Overview of programme risk

The business case assigns a medium risk to the programme.

However given the high outcome-level ambition of the programme, it is recommended that the risk level is increased to high. Several factors that may impede the achievement of outcome targets are relate to the external policy environment and are largely beyond the control of the programme. This includes the receptivity of other funders and their broader funding priorities, and in case of bilateral agencies, the agreed arrangements with partner governments. In some cases (Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change), the project outputs rely on data to be sourced from government agencies which are somewhat hard to access. Likewise, the project outcomes in a few cases are tagged to longer term processes such as the setting up of River Basin Organisations (RBOs). In the latter situation, continuous engagement with the partners will be necessary to ensure that the outputs deal adequately with governance and institutional issues, and do not remain restricted to providing theoretical frameworks.

The overall programme risks are thus largely of a management nature (at the programme level) where the translation of project outputs into broader outcomes (such as coordinated and coherent research approaches) needs significant effort beyond ensuring high quality project outputs. The key mitigation measure has been the development of a workable dissemination and outreach strategy for the CRISSA projects that includes engagement with a set of research funders. However, in the given timeframe (end of the programme), achieving significant tangible results in terms of the outcomes remains a challenge, and hence we anticipate that the residual risk would still be High. SARH will review the mitigating actions every 3 months to assure itself that they are appropriate for a project with a high risk rating.

Outstanding actions from risk assessment

None

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.

The programme is currently on track. A 6 month no cost extension has been given to the programme extending the end date to September 2015. This extension was made to allow the programme to facilitate the successful completion of two high impact projects and would offer an opportunity to engage more effectively with donors and policy makers, based on the technical outputs of the funded projects. There has been no revision to the overall cost of the programme.
The project spend on ARIES shows that the project is on track against the forecasts for the review period. The team is doing well with forecasts through regular review and close tracking of accountable grants and contracts. So far, the programme has spent around 75% of its allocation since the start of the programme. Of the remainder (£ 655,839), £ 517,383 is committed to be spent on on-going studies and plans are in place for the remaining funds. It is expected that a part of these will be used for implementation of the dissemination strategy. There has been a request for a 3 month no cost extension to the Calibrating above and below snow line precipitation study but that will not affect the overall timescales or cost of the programme.

Performance of partnership (s)
How well are formal partnerships/ contracts working
Are we learning and applying lessons from partner experience
How could DFID be a more effective partner

There has not been any issue with contracts and partnerships so far except the need to allow a no-cost
extension in one case (Calibrating above and below snow line precipitation study) to accommodate a minor change in the work plan.

Asset monitoring and control
Level of confidence in the management of programme assets, including information any monitoring or spot checks

No assets have been purchased under any of the projects during the period covering this annual review. Asset registers are periodically shared by partners as part of the reporting requirements. Physical monitoring and spot checks of existing assets (mostly high precision scientific instruments) have not been possible during the review period as they are located in remote places; however, their precise locations (geo-coordinates) have been reported by partners in relevant cases. Issues relating to the maintenance of assets have been discussed with project partners. In one case (Climate Change and Groundwater Resilience), preliminary discussion on asset disposal has also taken place.

G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

None.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

No formal evaluation has been currently planned for the programme. However, the dissemination strategy includes possible ways of assessing the programme impact, including requesting direct feedback from a range of stakeholders.

Monitoring progress throughout the review period

During the review period, a visit was made to Odisha to interact with state-level partners of the Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change study and to Dhaka to meet with the local partners of the Climate Change and Groundwater Resilience study. Telephonic conversations were held with the Principal Investigators of Climate Change and Groundwater Resilience , Glacier Monitoring in the Himalayas using Unmanned Airborne Vehicles (UAVs) and Calibrating above and below snow line precipitation as inputs to mountain hydrology models studies. Some feedback was also sought from government officials during the field visits through face-to-face meetings. Project outputs and progress reports from partners were carefully reviewed. Greg Briffa (Team Leader, ECGU, DFID India) joined the Odisha visit and Mr Liakath Ali (Climate and Environment Adviser, DFID Bangladesh) fed back from a dissemination event of the Climate Change and Groundwater Resilience study in Dhaka. Sarah Lester (Regional Climate Adviser, Asia Regional Team) provided a desk review of the Scoping Green Growth Challenges and Opportunities in South Asia study.

Additional details on specific projects are available in the aide memoire (Quest no 4815632) and consultants’ report (Quest no 4815662) of the Odisha visit for review of the Operational Research to Support Mainstreaming of Integrated Flood Management under Climate Change study (Quest no 4815662) and a review note on the Scoping Green Growth Challenges and Opportunities in South Asia study (Quest no 4815648).