Annual Review

Title: Health research – filling the gaps in evidence in infectious diseases, health systems and vulnerable groups
Programme Value £ (full life): £32.5 million		Review Date: April 2019
Programme Code: 300352	Start Date: 16/05/17	End Date: 31/03/2024

Summary of Programme Performance
Year	2018	2019
Programme Score	C	B
Risk Rating	Severe	Major

DevTracker Link to Business Case:	Not yet published due to ongoing competitive process
DevTracker Link to Log frame:	Not yet published due to ongoing competitive process

A. Summary and Overview

Description of programme
The UK will provide up to £32.5 million from 2017/18 to 2023/24 to support research to provide the latest evidence on how best to address some of the remaining challenges in global health.

Following extensive internal and global consultation, the following areas were identified as being gaps and an opportunity for the UK to intervene, given our relative strengths:

1. Tackling infectious diseases
2. Building stronger and more resilient health systems,
3. Improving the health of the world’s most vulnerable, including sexual and reproductive health, mental health and maternal, newborn and child health
Following approval of the business case, a competitive procurement process was planned to identify the best research partners for each of the research areas, with funding expected for several programmes, to be managed by consortia of researchers (Research Programme Consortia, RPCs). The consortia’s proposals will help determine the most appropriate and effective research to be undertaken and the expected results.

The consortia will deliver evidence in the priority areas, demonstrate how these can be delivered in different contexts, and facilitate incorporation of evidence into policy and programming in low income countries, to benefit the poor. Results will help provide answers to the most pressing global health challenges and will contribute to DFID’s own health strategy, policy and programming.

The intended impact of the research is improved health of some of the poorest and most vulnerable including through more efficient and resilient health systems. The outcome is that policies and programmes in relevant areas are better informed, with stronger leadership and partnerships.

The intended outcome of this initial procurement period was for an inception period to have started following the contracting of the new RPCs.

Summary supporting narrative for the overall score in this review
Procurement was expected to take place in 2017 and then scheduled to start in the 2nd quarter of 2018. As a result of delays, the Selection Stage Questionnaire (SSQ) was finally issued October 2018 and the procurement process is now expected to be completed September 2019.

Recommendations for the year ahead
- The procurement process to proceed in line with the latest procurement timetable.
- Once procurement is complete, the end-date of the business case to be amended to align to the timelines for the contracts.
## B: DETAILED OUTPUT SCORING

Output Title	Procurement process completed and RPC contracts in place
Output number per LF		1	Output Score	B
Impact weighting (%):		100%	Impact weighting % revised since last AR?	n/a

Indicators	Milestone	Progress
Terms of reference for 3 lots, and RPC funding modality agreed	Sourcing strategy to be agreed by June 2018	Milestone met: / Approved June 2018
All documentation finalised and competition opened to the market	SSQ documents issued by June 2018	Milestone not met: / SSQ documents issued October 2018
Procurement complete and contracts in place	Contracts signed by March 2019	Milestone not met: / Procurement still under process

Provide supporting narrative for the score
The commercial process started prior to approval of the business case with an early market engagement event in the last quarter of 2016. As the business case was approved, DFID was undertaking a supplier review. This stalled the expected procurement process whilst revised processes and procedures were put in place.

In the period from March 2017 when draft terms of reference (ToR) were first shared with the procurement and commercial department, a series of detailed discussions were held with procurement and legal advisors to determine the best route to market and resource implications. The overall approach was approved in October 2017.

The ToR were further revised with input from procurement and other DFID colleagues to reflect emerging priorities. The procurement and commercial department steering board accepted the procurement requisition in January 2018. Since then, officials worked together to develop the sourcing strategy, a process that was challenging and complex. The sourcing strategy was approved in June 2018 and the 1st stage Selection Stage Questionnaire (SSQ) was issued in October. With some further delays, the Invitation to Tender stage is underway and is expected to be completed in the 3rd quarter of the year.

Lessons identified this year, and recommendations for the year ahead linked to this output
The supplier review and subsequent internal discussions contributed to the delay in the initial procurement process. The effect of a change in procurement policy environment on the initial assumptions was not well enough anticipated. The outcome of all the work that has taken place is that, if these lessons are effectively codified, the procurement process for future new research programme consortia should be more straightforward and efficient.

Recommendation
The procurement process to proceed in line with the latest procurement timetable.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year
The theory of change for research programmes of this type is well established and the one for this programme aligns to that of the overall health research portfolio, which includes the DFID research elements of the Ross Fund Portfolio. The basic inputs are research, scientific expertise, and influencing and partnership activities. Researchers will use existing evidence to guide the development and evaluation of relevant interventions. The programme will provide robust evidence about how to integrate and scale up these interventions. The individual programmes will develop key partnerships with a range of academics, policy makers, service delivery organisations, communities and NGOs.

To ensure the research is used and has an impact, the researchers will invest in capacity development and research uptake activities to increase the dissemination of results in public policy discourses. The expectation is that these combined outputs will create momentum and improve systems and service delivery in focal countries and beyond. These outcomes should in turn lead to the desired impact of improved health of some of the poorest and most vulnerable.

There is no change to the external context that would challenge the theory of change or the underlying assumptions at this stage.

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead
The procurement process has been significantly delayed so that the actual start of research projects will be much later than anticipated. A new procurement timeline has been agreed and is expected to be completed by September 2019. The expected programme outcome should be achievable although at a later date. Given the delays in procurement, there will be a gap between the end of the current RPCs (largely completed in Q4 2018 and Q1 2019) and the new ones commissioned through this programme.

Explain major changes to the logframe in the past year
The logframe was amended at the time of the annual review last year so that the indicators better captured the revised procurement process including new timelines.

Describe any planned changes to the logframe as a result of this review
The current logframe is for the procurement period only. A logframe for the implementation period has been drafted. Each research consortium/supplier will be required to develop a specific theory of change and logframe for their component during their research project inception phase, aligned to the health research team results framework.

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year
Overall VfM measures for the programme can only be developed once funding is awarded and the composition of the portfolio is clear.

Achieving VfM starts with choosing the right problems to be addressed and using the best methodology to tackle them. The next stage will be assessing VfM through the competitive tender exercise. At the full proposal stage, the quality of the research will be assessed through external and internal peer review by technical experts, and the commercial evaluation will review proposed budgets to ensure costings are proportionate and in line with the rest of the market. We will be actively monitoring the impact of the procurement delay on the engagement of research institutions with the call, and implications for managing this and subsequent research calls.

The key cost drivers of implementation research are the people required to carry out the research, including their travel and subsistence. There will be an assessment of the bidders’ ability to conduct high quality research and likelihood of achieving research outputs i.e. effectiveness. These together will give a measure of cost-effectiveness

Potential VfM indicators were proposed in the business case (not yet published because of commercial sensitivities). Final indicators will be agreed during the inception phase for each consortium. These will be monitored on an annual basis using benchmarking and comparison to the baselines.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio
The planned areas of research will fill gaps in evidence and should contribute to the expected outcome and impact. Recent market analysis has confirmed the need for research in these areas previously identified, so the competition is still valid.

Recommendation
Once procurement is complete, the end-date of the business case to be amended to align to the timelines for contracts.

E: RISK

Overview of programme risk and mitigation
It is expected that, based on previous experience, each RPC overall risk will be major, because of the challenge of establishing new consortia, predicting results and the need to work with policy makers to ensure results are put into policy and practice. Partnerships are necessary to drive success but increase the delivery risk. Mitigating actions, identified from previous experience, reduce the overall risk and net risks may vary amongst the different projects. Potential benefits are high and mean the likely risk category is within DFID’s risk appetite.

Last year, the risk of the programme delivering on time was increased to severe as a result of the significant procurement delays. As the process is now underway, this has reverted to major (although the original timeline will need to be revised). We will monitor whether the procurement delay and subsequent gap between programmes will have an impact on the range and quality of the engagement of research institutions with the call.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues
Partners have not yet been selected. As noted above, the procurement process has been delayed and is now expected to be completed by September 2019.

DFID’s own forecasting has been adjusted to take into account the changing timelines.

Date of last narrative financial report(s)	n/a
Date of last audited annual statement (s)	n/a

G: MONITORING, EVIDENCE & LEARNING

Monitoring
The single business case will apply to a number of separate potential RPCs. DFID will manage these as separate components within one overall programme, once consortia are contracted.

Each consortium lead partner will develop a logframe during the inception period. There will be a break clause in each contract at the end of the inception period to allow a review of performance to date and a decision will be made on whether to progress to full implementation.

During implementation, the partner will upload results on to ResearchFish[1]. Regular narrative and financial reports will be analysed by health advisers and programme managers. These will focus on progress towards results and will align with the health research team’s results framework.
[1] https://www.researchfish.net/ an electronic system for funders to track the outputs and outcomes of research they fund

A component annual review will be done of each RPC. Their individual progress and results will be summarised into an overarching annual review on DFID’s system.

Evidence
The DFID health research team has developed an overarching team results framework that will inform the annual reviews of each RPC. The team will arrange an overall evaluation of the RPCs after the second full year of implementation, to look at the potential impact of the research, to ensure lesson learning can inform the design of the remaining period of RPC funding, provide evidence to DFID about the functioning of the RPC model and highlight added value of cross-cutting themes. Details about the evaluation will be developed in line with the team’s evaluation strategy and DFID’s evaluation department, if appropriate. Funding for the evaluation is available within the health team’s budget.

Learning
See under Output 1

Progress on recommendations from previous reviews
There were two recommendations last year:

The procurement process to proceed in line with the latest procurement timetable.
This was not achieved

Once procurement is complete, the end-date of the business case to be amended to align to the timelines for the contracts
This awaits the end of procurement

These recommendations are carried over to this review.