# Annual Review – April 2018 to March 2019

Title: Strengthening research systems for poverty reduction in East Africa
Programme Value £ (full life): £14,400,000		Review Date: May 2019
Programme Code: 204571	Start Date: 23rd April 2013	End Date: 31st March, 2020

Summary of Programme Performance
Year	2015	2016	2017	2018
Programme Score	A	A	A	A
Risk Rating	Medium	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-204571/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-204571/documents

## A. SUMMARY AND OVERVIEW

This is a light touch annual review for a programme which has a track record of consistently strong performance, continuing to meet stated objectives and log frame milestones.

Description of programme

Strengthening research systems for poverty reduction in East Africa (known as SEAK) is a research capacity strengthening programme led by DFID’s East Africa Research Hub (EARH). The hub is part of the Evidence Department within DFID’s Research and Evidence Division (RED). The SEAK programme aims invest up to £14.4m in four initiatives designed to promote more effective research leadership and country government and private sector investment in science, technology and innovation. These are:

- Output 1: Strengthening National Science Granting Councils: Strengthening the effectiveness of government and donor investments in research through technical support to the Science Granting Councils in sub-Saharan Africa. This is through a co-funding partnership with Canada’s International Development Research Centre and South Africa’s National Research Foundation. The initiative supports Science Granting Councils on effective research granting; research budget allocations; measuring research results and co-financing for research on poverty reduction which promotes effective links with the private sector in each country.
- Output 2: Strengthening Research Leadership: Strengthening research leadership through development grants for the next generation of Africa’s research leaders; strengthened research institutions and strong international collaborations. This is through a co-funding partnership with Wellcome Trust for health and population research leadership, and support for a long-term partnership platform for research leadership between Bill and Melinda Gates Foundation, Wellcome Trust and DFID. The initiative supports the Alliance for Accelerating Excellence in Science in Africa (AESA) platform and the Developing Excellence in Leadership, Training & Sciences (DELTAS) initiative, managed by AESA.
- Output 3: Targeted support to Research Capacity in Somalia: Strengthened research leadership in Somalia through a small-grants mechanism with the multi-donor Somalia Stability Fund to expand the initiative to include research capacity development. This component has been completed and is not part of this review.
- Output 4: Learning What Works: Understanding knowledge systems and what works to promote science technology and innovation in Kenya, Tanzania and Rwanda. This is a study to inform effective investments in science, technology and innovation by Kenya, Tanzania and Rwanda and their external partners. The objectives of the study include describing the knowledge systems and actors in each country; providing appropriate international evidence of what works in innovation and research system approaches; and proposing practical actions and recommendations for effective investments in science, technology and innovation by these countries and their partners.

Recommendations for the year ahead

The recommendations for the year ahead are summarised below:
	Recommendation	Rationale	Timeframe
	Output 1: Science Granting Councils
1	Define clear gender equity targets for the Gender Mainstreaming Framework and Action Plan and implement them.	To clarify how results obtained from the monitoring framework that is being rolled out will be interpreted.	July, 2019
2	SGCI to provide guidance to SGCs on intellectual property rights.	To support SGCs in maximising public benefit from any transfer of intellectual property rights.	Dec, 2019
	Output 2: Research Leadership
1	AESA to report explicitly against annual review recommendations and log frame indicators in the annual report and clarify on what is and what is not part of the DELTAS programme (should ideally be addressed in revised annual report for this year).	To facilitate monitoring of progress against the previous recommendations and differentiate what is being delivered by this funding from related projects.	Jan, 2020
2	AESA to improve recognition of funding in DELTAS outputs and have a system of monitoring this.	To: 1) ensure that UK investment in international development has a visible profile, helping to make the case that UK taxpayer money is well spent; 2) enable research users to understand who has funded DELTAS research; and 3) Enforce compliance with standards on transparency and disclosure of funding sources when publishing research.	October, 2019
3	AESA to finalize its equity, gender and inclusion strategy and a workplan plan for mainstreaming this across its collaborating DELTAS programmes.	To promote and support gender-equitable career pathways.	October, 2019
4	AESA to develop and share guidelines for policy and community engagement with DELTAS programs.	To provide clear guidance on goals and expectations on how to maximise knowledge translation and uptake from the first phase of DELTAS and strengthen this aspect of the theory of change.	September 2019
5	AESA to provide support to DELTAS directors and promote lesson sharing on developing strategies for ensuring long-term financial sustainability beyond core DELTAS funding.	To strengthen capacity for financial sustainability across the DELTAS initiative.	Dec, 2019
	Output 4: Learning What Works
1	The KSI team to provide a work-plan for translating, packaging and disseminating clear outputs to key stakeholders in the 3 countries, with a sharpened focus on practical/actionable recommendations	To ensure that any useful outputs of the study are appropriately disseminated to reach those who may be able to benefit from the findings	July, 2019
2	The EARH to promote synergies by facilitating sharing and learning opportunities across initiatives and identifying forums for dissemination of program outputs.	To promote coherence and maximise gains and impact.	Dec, 2019

Summary supporting narrative for the overall score in this review

The “Strengthening research systems for poverty reduction in East Africa” programme is coming into its final year of implementation. The various components of the programme have reached maturity and are delivering well against the log-frame objectives and are likely to significantly improve research production and research use in many African countries.

As detailed in the sections below, the programme outputs are meeting or exceeding their targets. Indeed, DELTAS has already achieved the end of programme target for output indicator 2.2 regarding the number of post-docs, PhDs and Masters trainees supported. Therefore, the recommendation for the overall score is A.

## B: DETAILED OUTPUT SCORING

Output Title	More effective research investments by Science Granting Councils in East Africa
Output number per LF		1	Output Score	A+
Impact weighting (%):		30%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 1.1
Number of high-quality research competitions	At least 3 participating SGCs conduct high quality research competitions (1 new SGC)	Completed: 4 SGCs have conducted research competitions using “good practice guidelines” to date. There are 2 new SGCs for 2018: Mozambique’s Fundo Nacional de Investigacao (FNI) and Namibia’s National Commission on Research, Science and Technology (NCRST).
Output Indicator 1.2
Documented examples of SGCs adjusting research programmes and prioritising investments based on international evidence and comparative indicators	At least 5 SGCs have modified their data collection instruments/ tools and received training on data collection, analysis and use for the design of research programs and budget allocation analysis	Completed: 6 SGCS, councils from Botswana, Burkina Faso, Ethiopia, Rwanda, Senegal and Zambia have modified their data collection instruments and received training on data collection, analysis and use. Rwanda and Ethiopia have used a modified instrument to conduct surveys, while Uganda and Burkina Faso are still planning their surveys.
Output Indicator 1.3
Documented numbers and examples of strategic partnerships with private sector	At least 4 participating SGCs engage in new partnerships with private sector (2 new SGCs)	Completed: 4 SGCs (from Uganda, Ghana, Malawi and Mozambique) have engaged in activities involving the private sector to date. 2 new SGCs (from Malawi and Mozambique) have engaged in private sector partnerships during the current reporting period in the context of launching calls for projects proposals.
Output Indicator 1.4
Numbers and examples of increased coordination activities between science granting councils in East Africa.	At least 4 new cooperation agreements for joint activities signed by participating SGCs (2 new)	Completed: 4 new cooperation agreements were signed during the current reporting period: Uganda and Côte d’Ivoire (March 2018); Senegal and Burkina Faso (March 2018), Zimbabwe and Mozambique (February 2018); and EAC cooperation (Kenya, Uganda, Tanzania and Rwanda) (March 2018).

Science Granting Councils: This output seeks to promote more effective research investments by Science Granting Councils (SGCs) in East Africa. The Science Granting Councils Initiative in sub-Saharan Africa (SGCI) supports 15 SGCs through a co-funding partnership between DFID, Canada’s International Development Research Centre (IDRC), and South Africa’s National Research Foundation (NRF). Four Collaborating Technical Agencies (CTAs) are in place and leading on each of the initiative’s four themes under the direction of the joint IDRC and NRF Initiative Management Team (IMT). The lead CTAs are: SARIMA (Southern African Research and Innovation Management Association), ACTS (African Centre for Technology Studies), NEPAD (New Partnership for Africa’s Development) and ATPS (African Technology Policy Studies Network). Each lead CTA collaborates with several other organizations.

The annual report explicitly reports progress against log frame indicators and it is clear that all milestones associated with Output 1 have either been met or exceeded.

Indicator 1.1 measures the number of high-quality research competitions conducted, with the aim of improving the capacity of SGCs to manage research. Four SGCs have conducted research competitions using “good practice guidelines” to date, exceeding the log frame target of three competitions.

The milestone also has a goal of one additional SGC and in 2018 two new SGCs fulfilled the milestone: Mozambique’s Fundo Nacional de Investigacao (FNI) and Namibia’s National Commission on Research, Science and Technology (NCRST).

Indicator 1.2 measures the ability of SGCs to adjust research programmes and prioritise investments based on international evidence and comparative indicators and requires that at least five SGCs modify their data collection instruments and receive training on data collection, analysis and use for the design of research programs and budget allocation analysis. Exceeding this milestone, six councils from Botswana, Burkina Faso, Ethiopia, Rwanda, Senegal and Zambia have modified their data collection instruments and received training on data collection, analysis and use. Rwanda and Ethiopia have used a modified instrument to conduct surveys, while Uganda and Burkina Faso are still planning their surveys.

Indicator 1.3 measures documented numbers and examples of strategic partnerships with private sector with the aim of increasing knowledge exchange between SGCs and the private sector and requires that cumulatively, at least four participating SGCs engage in new partnerships with private sector (two new SGCs). Uganda, Ghana, Malawi and Mozambique SGCs have engaged in activities involving the private sector to date and two new SGCs (Malawi and Mozambique) have engaged in private sector partnerships during the current reporting period in the context of launching calls for projects proposals.

Indicator 1.4 measures numbers and examples of increased coordination activities between SGCs, requiring at least 4 new cooperation agreements for joint activities signed by participating SGCs. Meeting the milestone, four new cooperation agreements were signed during the current reporting period: Uganda and Côte d’Ivoire (March 2018); Senegal and Burkina Faso (March 2018), Zimbabwe and Mozambique (February 2018); and EAC cooperation (Kenya, Uganda, Tanzania and Rwanda) (March 2018).

Lessons identified this year, and recommendations for the year ahead linked to this output

Define clear gender equity targets for the Gender Mainstreaming Framework and Action Plan and implement them.

Recommendation 4 from the previous annual report is to develop and implement a system to monitor progress of the Gender Mainstreaming Framework and Action Plan. Progress has been made in this area with the framework and action plan, which was developed in 2017 being updated in 2018 in incorporate monitoring and evaluation approach. However, it was not clear from reading the report whether specific gender equity targets had been set and therefore whether it would be clear how to interpret the results produced by the monitoring framework. If this is the case, then SGCI could define goals for gender equity and set out how it will achieve these goals.

SGCI to provide guidance to SGCs on intellectual property rights

The annual report articulates an interest in supporting SGCs to engage the private sector on the back of the “public-private sector partnerships” paper. Public private partnerships have the potential to be highly beneficial. In research one potentially problematic area in public private partnerships is that of intellectual property. SGCI could support SGCs by providing guidance on public private partnerships in research with a particular focus on handling intellectual property in such a way that taxpayers sufficiently benefit from any transfer of commercial intellectual property rights.

Output Title	Capacity built for research leadership in collaborating partners
Output number per LF		2	Output Score	A
Impact weighting (%):		40%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 2.1
Number first author publications in peer-reviewed journals (with % by women researchers) by collaborating partners	Number publications (with % women)	Completed: 349 first-author publications (151 (43%) by women) in peer-reviewed journals by DELTAS research fellows in 2018
Output Indicator 2.2
Numbers of (i) post doc (ii) Masters (iii) PhDs (iv) graduate internships supported (with % of women)	Numbers of (i) Masters (ii) PhDs (iii) post docs enrolled & supported (with % women) / Overall programme targets of (i) >220 Masters (ii) > 170 PhD and (iii) >95 post docs of which 11.5% of each attributable to DFID	Completed: Cumulative enrolment as of December 2017: / 261 Masters (49% women) / 297 PhD (51% women) / 106 Postdocs (43% women) / 10 Senior Researchers (20% women)
Output indicator 2.3
Joint platform to support research leadership established and on sustainable financial footing	Additional donor funding secured for granting	Completed: See table below for breakdown of consortia funding.

Research Leadership: This output seeks to build capacity for research development among collaborating partners (graduate students, postdoctoral scholars and research fellows in participating research institutions). It is implemented by the Accelerating Excellence in Science in Africa (AESA) at the African Academy of Sciences (AAS), through the Developing Excellence in Leadership, Training and Science in Africa (DELTAS Africa) initiative, with the support of the Wellcome Trust and the UK’s Department for International Development (DFID).

Milestones associated with Output 2 generally do not have specific qualitative targets which is a limitation to monitoring programme performance. However, the outputs are substantial and increase year on year.

Indicator 2.1 measures research outputs in terms of first-author publications in peer-reviewed journals by DELTAS fellows. The programme considers this indicator as a demonstration of the application of the research training and supervision in building the capacity of fellows to generate research that can be used in decision-making. The first-author of a manuscript is assumed to have a lead role in conceptualising the study topic, conducting the research and writing the paper. Therefore, this is considered to reflect the ability of fellows to take on a leadership role in the production of internationally competitive, African-driven research. There is a slight limitation in this assumption in that it is certainly possible to have senior authors or supporting mentors hand-holding or micro-managing junior researchers to achieve first author publications. Nevertheless, even in these cases first authorship will improve the leadership potential of the lead junior researcher.

Overall, 349 papers were published in peer-reviewed publications in which a DELTAS collaborator was listed as a co-author, a substantial increase from 81 papers in the previous year. Of these 349 papers, 151 (43%) were first-authored by women. While gender parity has not been achieved on this indicator, there is considerable improvement since the previous year. Nevertheless, there remains a need for a better understanding of how this is manifested within the DELTAS initiative to design appropriate strategies to support equitable career pathways for female fellows.

However, it is notable that many the papers counted toward this indicator did not explicitly recognise DFID and Wellcome Trust funding in the funder acknowledgements. This is either a problem of incorrect attribution of papers as DELTAS-related outputs or a short-coming in best practice for disclosing funding sources for peer-reviewed research.

Figure 1: DELTAS Africa publications with DELTAS Fellows as First Author

(Source: DELTAS Annual Report April 2019)

Indicator 2.2 measures the number of graduate students and fellows enrolled in DELTAS. This contributes towards building a critical mass of highly trained and capable research leaders in Africa. The overall programme targets for this indicator of (i) 220 Masters (ii) 170 PhD and (iii) 95 post docs have now been met, over a year before the end of the programme.

Table 1: Summary Recruitment from Master to Senior Research Fellows Level across DELTAS Africa programmes

(Source: DELTAS Annual Report April 2019)

Indicator 2.3 aims to track financial sustainability of the DELTAS partners. The table below outlines the grant funding obtained by the various consortia and, in most cases, demonstrates an ability to attract funding from a range of sources. The reasons some consortia are not reporting much additional funding should be investigated and understood.

Table 2: Number and amount of New grants attracted by DELTAS Africa grantees

(Source: DELTAS Annual Report April 2019)

Lessons identified this year, and recommendations for the year ahead linked to this output

Report explicitly against AR recommendations and log frame indicators in the annual report and clarify on what is and what is not part of the DELTAS programme (should ideally be addressed in revised annual report for this year).

The annual report is thorough and comprehensive however it would be useful to explicitly report against the relevant recommendations of the previous annual review. This will facilitate monitoring of progress against the previous recommendations. In addition, there are several things included in the annual report which are not funded through this programme, for example, the Research Management in Africa Programme (REMPRO). It is useful to note synergies with related work in the annual report, but it should be clear what is being delivered by the funding from this programme and differentiate this from related projects.

Improve recognition of funding in DELTAS output and have a system of how to monitor this.

As noted above, many the papers counted toward this indicator did not explicitly recognise DFID and Wellcome Trust funding in the funder acknowledgements. This is important both so that UK investment in international development has a visible profile, helping to make the case that UK taxpayer money is well spent, but also so that research users can understand who has funded a piece of research. Transparency in disclosure of funding sources is a well-established norm in publishing research and most quality journals should require a statement on research funding. It is important that DELTAS researchers appropriately disclose funding sources for both these reasons.

AESA to finalize its equity, gender and inclusion strategy and a workplan plan for mainstreaming this across its collaborating DELTAS programmes.

Some progress has been made in several respects including the establishment of a gender and diversity team at the AAS, and the development of a concept note for funding to support the roll-out of several priority activities linked to gender, equity and inclusion. It will be important to finalize the comprehensive strategy and workplan, ensuring that it sufficiently incorporates a clear and coherent framework for gender-equitable scientific career progression.

AESA to develop and share guidelines for policy and community engagement.

The DELTAS Africa initiative has an explicit objective on ‘Scientific Citizenship’, which mandates DELTAS grantees to carry out policy, public and community engagement activities. The initiative has made some progress in promoting more active implementation of community and policy activities by researchers. However, guidance for researchers and articulations of expectations appears to be limited or inconsistent. AESA should develop and share guidelines on community and policy engagement to provide clear guidance on goals and expectations on maximising knowledge translation and uptake from the first phase of DELTAS, thereby strengthening this aspect of the theory of change.

AESA to provide support to DELTAS directors and promote lesson sharing on developing strategies for ensuring long-term financial sustainability beyond core DELTAS funding.

Whilst various consortia across the DELTAS initiative have demonstrated an ability to attract funding from a range of sources, some consortia have not reported additional funding and the reasons for this are not clear. Strengthening financial sustainability beyond core funding is an important long-term goal across the DELTAS initiative, and it will be important to ensure that effective strategies are shared and institutionalized.

Output Title	Increased research capacity in collaborating partners in Somalia
Output number per LF		3	Output Score	N/A
Impact weighting (%):		10%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 3.1
Number of training sessions/events delivered	N/A	N/A
Output Indicator 3.2
Number of policy dialogue events (with documented examples)	N/A	N/A

Somalia Research Capacity: This component was completed in the previous year and assessed as part of the last annual review. There were no related milestones this year.

Output Title	Learning on what works and what does not in strengthening research systems in East Africa
Output number per LF		4	Output Score	A
Impact weighting (%):		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
Output Indicator 4.1
Number of knowledge outputs on research system strengthening in East Africa (e.g. political economy analysis; research synthesis; commissioned studies)	SGCI: At least 4 knowledge outputs produced (2 new) / KSI: Independent research interim reports for 3 countries	Completed: A total of 5 outputs have been produced by the SGCI to date. Three new outputs for 2018 are: (i) Public-private partnerships in research and innovation: opportunities and barriers for African Science Granting Councils – submitted to Research Policy; (ii) Open innovation and innovation intermediaries in sub-Saharan Africa – accepted by Sustainability journal; (iii) Gender in STI: A review of Africa’s Science Granting Councils Initiative. / Partially Completed: The programme start date was delayed at the procurement state, so timeline for the research outputs was adjusted accordingly. Draft reports for three countries are due in June/July 2019. However, an inception report has been produced from the KSI project and the annual report includes some country-specific analysis.
Output Indicator 4.2
Number communication (i) outputs and (ii) events on what works on research system strengthening	SGCI At least 5 communication events held (1 new) and at least 2 policy briefs produced (1 new) / AESA/DELTAS: Annual Forum held	Completed: A total of nine communication events have been held to date. Four new events held in 2018 are: Regional Meeting (July, Ghana); 2018 Annual Forum (November, Côte d’Ivoire); Workshop on “Leadership, Gender and Research Excellence in African Universities” (October, Kenya) and SGCI-DFG meeting (March, Rwanda). One new policy brief produced in 2018 is: “Towards effective public-private partnerships: A perspective for African Science Granting Councils”, bringing the cumulative total to two policy briefs. / Completed: DELTAS convened the Grantees Annual Meeting in Johannesburg, South Africa.

Learning What Works: This output seeks to promote learning on what works and what does not work in strengthening knowledge systems in East Africa.

Milestones associated with Output 4 have been met.

Indicator 4.1 measures an increase in the number of knowledge outputs related to research systems strengthening in East Africa. Three new knowledge products were produced by SGCI: (i) Public-private partnerships in research and innovation: opportunities and barriers for African Science Granting Councils – submitted to Research Policy; (ii) Open innovation and innovation intermediaries in sub-Saharan Africa – accepted by Sustainability journal; (iii) Gender in STI: A review of Africa’s Science Granting Councils Initiative.

The University of Greenwich and partners including the African Centre for Technology Studies (ACTS) are undertaking a study on Knowledge Systems and Innovation (KSI) in Kenya, Rwanda and Tanzania. The target was for interim reports for each of the three study countries. The programme start date was delayed at the procurement state, so timeline for the research outputs was adjusted accordingly. Draft reports for three countries are due in June/July 2019. However, the implementing partners have produced an inception report which sketches out some of the intended methods and an annual report which includes interim analysis disaggregated by country.

Indicator 4.2 measures an increase in communication outputs and events on what works on research systems strengthening. Exceeding the milestone, four events were convened by SGCI and AESA during the reporting period. These are: Regional Meeting (July, Ghana); 2018 Annual Forum (November, Côte d’Ivoire); Workshop on “Leadership, Gender and Research Excellence in African Universities” (October, Kenya) and SGCI-DFG meeting (March, Rwanda). One new policy brief produced in 2018 is: “Towards effective public-private partnerships: A perspective for African Science Granting Councils”. AESA organized the 2018 DELTAS Annual Grantees meeting in Johannesburg South Africa.

Lessons identified this year, and recommendations for the year ahead linked to this output

Present a workplan for translating, packaging and disseminating clear outputs to key stakeholders in the 3 countries, and sharpen focus on practical/actionable recommendations

It will be important to ensure that any useful outputs of the KSI study are appropriately disseminated to reach those who may be able to benefit from the findings. The KSI study should ensure that in addition to completing the research to schedule, it outlines a workplan for disseminating the research and monitoring its impact. This should include close collaboration with related DFID initiatives on research capacity strengthening.

The EARH to promote synergies by facilitating sharing and learning opportunities across initiatives and identifying forums for dissemination of program outputs.

Strengthening a knowledge system requires strong buy-in and effective leadership by country governments and key partners in each country. In line with the 2018 Annual Review recommendation, the EARH has developed a plan to promote synergies in the dissemination of programme outputs and learning across initiatives. The EARH should implement this plan and identifying forums to maximise dissemination of program outputs.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change and any major changes in the past year

There were no major changes in the programme’s theory of change in the past year. The original theory of change (TOC), as per the business case, is based on the underlying TOC in DFID’s Research Capacity Building Paper (2014). According to this paper, building capacity of knowledge producers, brokers and users within a wider enabling environment will result in evidence being used to inform and appraise the actions of government, the private sector, NGOS and citizens. This use of evidence leads to better public services and policy and contributes to innovation and economic growth. The Programme’s Overarching Theory of Change (Annex 1) is adapted from the ‘Triple Helix’ thesis that the university-industry-government relationship is the basis for innovation and development in a knowledge-based economy. Arrangements and networks among these three institutional spheres provide the transaction space to support evidence-based policy and innovation processes. The Triple Helix analytical framework has been applied to systems of innovation for industry and growth. In this adaptation, the industry sphere has been extended to encompass other areas of development and wider users of new knowledge within the research system. High-level change in the three institutional spheres, as envisaged in the TOC, will require the identification and promotion of synergies across the programme’s four initiatives

Progress towards outcomes

Overall, this programme “Strengthening research systems for poverty reduction in East Africa” is performing well and delivering change in accordance with its theory of change. The specific log-frame outcome targets for this year are presented below.

Indicator(s)	Milestone(s) for this review	Progress
Case studies to show how evidence, exchange and support has informed research allocation and grants management by science granting councils.	All 5 national political economy case studies completed (baseline). Second phase of political economy case studies commissioned. 4 SGC examples of how evidence, exchange and support has informed research allocation and grants management	Completed
Case studies to show how high-quality researchers have been developed and are engaged with policy and how to promote equitable career pathways for internationally competitive African researchers including women and other under-represented groups	Independent learning data collection and interim reports	Completed
Case studies document how learning outputs have been taken up by science granting councils and research leaders in East Africa	5 SGCs take up learning outputs	Completed

## D: VALUE FOR MONEY

Assess VfM compared to the proposition in the Business Case, based on the past year

Overall, the programme represented good value for money.

Milestones are being met and/or exceeded, and implementing partners are largely delivering according to their agreed work plans, and within agreed budgets. The DELTAS/AESA co-funding mechanism has meant that the programme continues to benefit from a dilution of costs, and overall programme effectiveness through additional funding and new workstreams. The decision to fund the AAS Research Management Programme (ReMPRO) up to the March 2020, from a different DFID RED programme demonstrates efficiencies and interlinkages across DFID research and evidence programmes and underpins the need and opportunity for further collaborations and co-funding endeavours.

There have been no significant changes to cost-drivers over the past year, and the finding remains valid. The main cost-driver for implementing partners are personnel costs, trainings and conferences; travel and subsistence costs also account for a significant percentage of programme costs. Overall, these costs have variously been impacted by events outside the control of the programme, these include, inflation and exchange rate fluctuations. For instance: the SGCI budget allocation for monitoring and evaluation was raised in 2018 to allow for case studies and the second phase of the political economy studies to be undertaken in 2019; this was funded through the exchange rate gains.

This review has assessed the performance of the programme under the four value for money metrics; Economy, Efficiency, Effectiveness and Equity.

Economy

Research Leadership: All the CTAs continued to observe their organisations’ procurement rules. For example, services are procured based on competitive quotations. At IDRC, the CTAs receive grants in instalments following analysis and approval of technical report and financial reports.

CTAs have often conducted training workshops instead of relying on consultants. NEPAD used local experts from agencies such as National Statistics Offices and Ministries of Trade in its training events. CTAs have also adopted joint training events to reduce travel and accommodation costs. Examples include the October 2018 joint workshop in Botswana that also emphasised the inter-connectedness of the SGCI thematic areas.

Efficiency

Science Granting Councils: Collaborative approaches that ensure efficiency are evident. The 2018 Annual Forum was co-organized and co-financed with PASRES as the host Council. This was efficient, allowing cost-sharing and making it possible for the delegates to participate in the different meetings that were organised in the same week. The Masterclass discussions were enriched by perspectives from a wide range of delegates. Holding the Forum alongside other meetings facilitated networking among the Councils and with other stakeholders.

The Councils have hosted training sessions in their premises, and some training events have been conducted back-to-back with other meetings as a cost-saving measure. For example, SARIMA held training workshops alongside 2018 Regional Meeting and the Annual Forum.

Research Leadership: To address rapid growth, AAS recently restructured its organisation into four functional directorates. A recent review of AESA deemed this new structure as logical and mentioned that it clarified how several initiatives linked to AESA, such as CARI, the think tank function and GFGP, fit within the broader context of the AAS. The review also stated that links across the directorates seem effective.

Understanding Knowledge Systems: the KSI programme has excellent engagement performance with key stakeholders. These engagement activities provide opportunities to further align project objectives, enhance regional coordination and ensure lesson learning. Examples include: the African Centre for Technology Studies (ACTS) has through its leading researchers, been involved in initiatives and fora with the potential for collaboration and dissemination of KSI project results. Notably, one of the KSI researchers at ACTS was appointed to lead a high-level panel of the African Union on Green Innovation, a very strategic engagement that will promote linkages by providing a framework to channel KSI project outputs.

The KSI lead researcher has continued in his role of mentor to the Nigerian institution, National Centre for Technology Management (NACETEM) under the Global Development Network (GDN), Doing Research Programme. This role will seek to broaden discussions of this network beyond research systems.

Effectiveness

Science Granting Councils: The SGCI has continued to catalyse additional strategic partnerships and collaborations that enable strengthening of the collective global voices of Africa’s Councils in leveraging private sector partnerships e.g. Malawi’s National Commission for Science and technology (NCST) and Mozambique’s Fundo Nacional de Investigacao (FNI) engaging with private sector actors. In addition, the SGCI supported the establishment of Ghana Innovation and Research Centre (GIRC) that was launched during the SGCI Regional Meeting in July 2018.

The SGCI is facilitating the institutionalisation of capacities built by producing various documents such as a Standard Operating Procedure (SOP) on research and grants management, a template for cooperation agreements and a social media how-to-guide that can be accessed by all Council staff through the SGCI website. Training materials including presentations are also shared on the website.

The SGCI also developed a strategy to facilitate and monitor uptake of knowledge outputs by participating Councils. The strategy that defines the approaches used by the CTAs to promote and monitor uptake of these outputs is currently under implementation. The SGCI generates several knowledge products including commissioned papers and policy briefs.

Research Leadership: The use of adaptive and flexible programming is set to ensure effectiveness. The decision to fund the AAS Research Management Programme (ReMPRO) up to the March 2020, is critical in creating and sustaining enabling research environments for the flourishment of research and the development of sustainable systems, which can be maintained by their host institutions. Under strand 2 of the programme, there will be efforts to find mechanisms to help ensure that institutions can support their own research management functions, regardless of funder or government support; and aligning funder policies towards meeting indirect costs.

The fact that this funding has come from a different DFID RED programme demonstrates efficiencies and interlinkages across DFID research and evidence programmes and creates opportunities for further collaborations and co-funding endeavours.

This year, 449 new trainees joined the DELTAS Africa programme. This brings the total number of trainees recruited from the inception of the programme to 1439 across all the different levels of training offered by the programme. A total of 29 new research collaborations/partnerships were established across all DELTAS Africa networks. 130 engagement activities were organized across all networks of which 72 were policy activities. In all, it is estimated that over 300,000 people were reached through these activities. 102 DELTAS fellows received training in community and public engagement (CPE). Over 4000 different research outputs were produced and disseminated, and it is estimated that >4,000,000 people were reached through these dissemination activities.

DELTAS Africa grantees continue to improve the research environments in which DELTAS Africa research is being carried out at both lead and partner institutions through a variety of interventions including procurement of state-of-the-art lab equipment, improved physical infrastructure, research resources and research quality management tools.

Understanding Knowledge Systems: In the KSI project, commendable progress has been made in the forging of country level linkages and relationships, which are working well. Country level ownership is already evident. Of note, COSTECH in Tanzania has been so motivated by the project that it has expressed interest to do a similar exercise to conduct its own extensive mapping of Tanzania’s STI ecosystem.

Equity;

Equity is about maximising opportunities for all – including marginalised individuals.

Science Granting Councils: The SGCI has developed a robust Gender Mainstreaming Framework and Action Plan. In 2018, the IMT updated the framework to incorporate a monitoring and evaluation approach, suggesting indicators to track gender work in SGCI. A section on ‘gender’ was introduced in the CTAs technical reports template, where they are expected to provide details about their work on gender. The SGCI’s expectations on gender mainstreaming were discussed with the CTAs at the Pretoria meeting in May 2018 (Appendix 5). As a result of this conversation, the CTAs’ reporting on gender elements (that goes beyond providing sex-disaggregated data) has greatly improved.

Research Leadership: In the recent AESA review, (67%) of AESA programme managers survey respondents reported good responses to programme calls, and two-thirds agreed or strongly agreed that ‘information about the AESA initiative and funding opportunities is readily available to the African science community’. Some programmes were devoting time and resources to increase awareness of calls. For example, GCA has conducted pre-call webinars.

Explain whether and why the programme should continue from a VfM perspective, based on its own merits and in the context of the wider portfolio

From a value for money perspective, the programme should continue, both based on its own merits as outlined in this review and in the context of the wider DFID portfolio and commitments. In line with the business case proposition, this programme continues to meet the UK’s commitment to research capacity building for development. The programme has continued to bridge the evidence gap on what works to strengthen national research systems in low income and low-middle income countries and is catalytical in driving change in beneficiary country’s research ecosystems.

## E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The overall programme risk rating remains ‘Moderate’. An additional risk category – safeguarding was added to the risk framework and mitigating actions identified. The team has mapped out the risks framework online and reviews and updates this on a quarterly basis.

As the programme is moving to closure phase the team will need to ensure that delivery is on track and mitigate the likely risk of underspend that would be occasioned by slow implementation. The EARH will need to undertake a review of partners’ workplans to ensure they have realistic/achievable milestones and continue monitoring implementation progress.
Programme Risk Register: The risk register below sets out a summary of the most significant risks to the programme at the time of this review
## F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues

The EARH has developed strong partnerships with each of the implementing partners and there is a good co-operation narrative. The team have regular meetings with partners.

Both Wellcome Trust (Research Leadership) and IDRC (Science Granting Councils), as with the previous year and in line with DFID practice, continued to submit Requests for Funds on a quarterly basis for the period under review. All their requests included a report on the actual expenses incurred in the quarter being reported on and the forecast of funds needed for the next quarter. Both partners also reported expected adjustments which enabled the EARH to accurately forecast its disbursements for the programme. In addition, payments to CTAs continue to be disbursed in instalments depending on the risk level of the CTAs, and approach that demonstrates good value for money.

In seeking continuous improvement, AAS continued the process of identifying and developing more relevant grant management policies, in consultation with Wellcome Trust and other partners. In 2018, over 50 new policies were developed and approved for use by the AAS senior management team. AAS further sought to explore best value in terms of its grants management systems and sent two staff members to the annual CCTech Users’ Forum in the UK in September 2018. Recommendations on how best to maximize the use of the AAS Ishango Grants systems have been made and are being implemented. AAS has also recommended that all DELTAS lead institutions undergo GFGP certification as a means of ensuring improvements in research management environments under which the DELTAS Africa programmes are led. There are plans to roll-out the GFGP to other DELTAS partner institutions.

The Understanding Knowledge Systems contract grappled with tax issues after the first milestone delivery. These issues were resolved, and delivery has been majorly on track. The project has however, flagged that it is running behind by a month due to inception phase challenges. Mitigating actions - including a proposed costed extension, are being explored.

Due diligence and financial controls

There is sufficient assurance that partners are adhering to their organisations’ internal control frameworks. The programme risk framework now includes mitigation strategies for safeguarding risks and the team has shared DFID’s safeguarding policies and requirements with partners. Spend is in line with agreed contractual obligations and requirements. Milestone/results-based payment ensures that agreed-to delivery requirements are met.

Asset monitoring and control

All assets purchased with DFID money have been monitored as per the agreements put in place with funding partners.

Summary of funding

Spend to date per partner is shown in the table below. Spend is in line with expectations outlined in the business case. There has been robust forecasting and partners are proactively engaging with DFID.

Initiative	DFID contribution	Total funds disbursed by DFID	Partner Funding	Total programme
Science Granting Councils: / Science Granting Councils Initiative	£5,404,347	£3,558,829	£1.1m (Canada’s IDRC) / £1.1m (South Africa’s NRF)	£7.6m
Research Leadership: Accelerating Excellence in Science in Africa (AESA) / And / Developing Excellence in Leadership, Training and Science Initiative (DELTAS)	£6,850,000	£6,228,456	£1 m (Wellcome Trust) / £1m Bill and Melinda Gates Foundation / £54m (Wellcome Trust)	£3m / £60m
Somalia Research Capacity: / Research capacity strengthening (Somalia) through The Somalia Stability Fund (SSF)	£1,032,544	£1,032,503	£0.24 million (Somalia Stability Fund)	£1.4m
Learning What Works: Understanding knowledge systems and what works to promote science technology and innovation in Kenya, Tanzania and Rwanda.	£ 541,584	£347,825	Nil	£541,584

Date of last narrative financial report	KSI April 2019 / SGCI March 2019 / AESA/DELTAS April 2019
Date of last audited annual statement	Wellcome Trust: December 2018 / IDRC: October 2018

## G: MONITORING, EVIDENCE & LEARNING

Monitoring

The East Africa Research Hub (EARH) continually monitors all SEAK programmes through coordinating meetings and calls with both co-funding organisations and implementing partners.

The programme’s Senior Responsibility Owner (SRO) is a member of the SGCI Executive Committee alongside IDRC and South Africa’s NRF, and represents DFID in the Partner’s Advisory Group for AESA, which includes Wellcome, NEPAD, Bill and Melinda Gates Foundation and the African Academy of Sciences. During the reporting period, EARH staff also attended the SGCI Annual Meeting in Zambia, the AESA Research Management Consultation and the AESA Risk Management Workshop.

This Annual Review was undertaken by Tom Drake, an Evidence Broker in Evidence into Action team and SRO on related research capacity strengthening projects; Maryanne Kuria, EARH Programme Manager and Leah Mwai, EARH Research Specialist. The following meetings, site visits and consultations were conducted with programme partners, beneficiaries and stakeholders, to obtain their feedback in preparation for this review.

Project	Stakeholders	Date	Consultation Type
SGCI	Heads of 15 research councils supported through the SGCI programme	05/04/2019	Closed door session with Heads of research Councils
SGCI	Initiative Management Team (IDRC & NRF)	9/04/2019	Meeting/Call
DELTAS/AESA	Head International Operations and Partnerships, Wellcome Trust	18/04/2019	Meeting/Call
KSI	Study Principal Investigators	23/04/2018	Meeting/Call

Evidence
Research Leadership: The planned mid-term review of the DELTAS initiative was undertaken and provided insights and practical examples on strengths and areas of improvement. An end term review is planned in early 2020. This review should include a comparative analysis on different approaches to capacity building and promoting scientific career progression.

Science Granting Councils: The SGCI convened two joint Monitoring Evaluation and Learning workshops during this reporting period. The first workshop held alongside the 2018 Regional Meeting (4-6 July, Accra, Ghana) was attended by the Collaborative Technical Agencies (CTA’s), Councils and the IMT. The CTAs and the Councils shared specific “stories of change” in the context of the SGCI Logframe indicators for Themes 1-4 and the Evaluative Learning Framework (ELF) system of “acquiring”, “adapting” and “applying” of knowledge. A second workshop was convened alongside the 2018 Annual Forum and attended by Councils, POA, funders and the CTAs. This workshop was an opportunity for the CTAs to present progress made against the SGCI Logframe targets. As well, the CTAs and the Councils narrated specific “stories of change”. The Councils provided useful inputs to these stories and highlighted other stories that had not yet been documented.

Learning What Works: The commissioned EARH study Understanding knowledge systems and what works to promote science technology and innovation in Kenya, Tanzania and Rwanda is currently underway (see output 4 above).

Learning

Science Granting Councils: SGCI generates knowledge products that include commissioned papers, policy briefs, and books. For instance, a state-of-the-art paper is commissioned every year to inform a Masterclass held during the Annual Forums. The Initiative Management Team (IMT) and the responsible Collaborating Technical Agencies (CTAs) have developed a strategy that defines approaches to facilitate and monitor the uptake of these knowledge outputs. All products are shared electronically with the Councils, CTAs and other stakeholders in a timely manner. The products are also published on the SGCI website to facilitate easy access. All stakeholders are immediately informed about new materials on the website.

During the reporting period, the Southern African Research and Innovation Management Association (SARIMA) incorporated elements of the “Research Excellence” paper in its guidelines for implementing good research competitions. The learning and principles espoused in the “Research Excellence” and ‘Public Private Partnership’ (PPP) papers informed the design, review, assessment and selection of the proposals/projects, and were used to identify knowledge gaps to be addressed by upcoming commissioned studies. This learning was also incorporated in the selection of theme for the 2018 Annual Forum.

Research Leadership: The DELTAS program has a Learning Research Programme (LRP), managed by the Capacity Research Unit (CRU) at Liverpool School of Tropical Medicine. The LRP comprises four thematic research strands, three of which are completed within the frame of a PhD fellowship. During the reporting period, the LRP produced its third annual report presenting findings on each strand that will inform decision-making in the following areas:

1. Enhancing women’s career advancement in academic and/or scientific institutions
2. Facilitating an equitable distribution of post-graduate training opportunities across sub-Saharan Africa
3. Enhancing researchers’ and/or research institutions’ knowledge translation capacity
4. Enhancing consortia outcomes through effective programme management

# Progress on recommendations from previous reviews

	Recommendation	Progress	Due
	Output 1: Science Granting Councils
1	SGCI to develop and implement a systematic approach for monitoring Collaborating Technical Agencies (CTAs) and consultants, to facilitate real-time feedback loops	Completed	Dec, 2018
2	SGCI to support Councils in developing strategies for institutionalising capacity gains	The recommendation has been adequately responded to, but efforts should continue, see current review recommendation.	Dec, 2018
3	SGCI to support sharing of experiences and lessons about strategies for effective engagement with government policy/ decision makers, regarding increasing investments in science for national development	Completed	Mar, 2019
4	SGCI to develop a system to monitor the implementation of the Gender Mainstreaming Framework and Action Plan and promote inclusion of disadvantaged groups	Good progress but needs further work to define and achieve goals. See current review recommendations.	Dec, 2018
5	SGCI to support the SGCs to develop individualised annual or bi-annual action plans and facilitate self-assessment against these objectives	Completed	Mar, 2019
	Output 2: Research Leadership
1	AESA to submit to the Partner’s Group a report on the lessons and outcomes of the Wellcome internal audit	Completed	Jan, 2019
2	AESA to submit a funds-flow diagram of the DELTAS initiative delivery chain as part of risk management	Completed	Jan, 2019
3	AESA to develop and submit to the Partner’s Group a strategy for promoting gender mainstreaming and advancement of female researchers	Progress has been made but further work is needed to finalize and mainstream the gender strategy and workplan. See current review recommendations.	October, 2019
4	AESA to provide guidance to DELTAS Programme Directors on how to document policy impact and produce relevant case studies for the next DELTAS Annual Report	Good progress but needs further work to define and achieve goals. See current review recommendations.	Mar, 2019
5	In consultation with the DELTAS Learning Research Programme team (LRP), AESA to: 1) review evidence on promoting sustainable career pathways, 2) provide guidance to DELTAS Programme Directors on implementing effective approaches, and 3) document progress in the next DELTAS Annual Report	Completed	Mar, 2019
6	In consultation with the LRP team, AESA to explore opportunities for generating and strengthening evidence on the effectiveness of DELTAS capacity building interventions and training models	Progress has been made but more work is needed to analyse and formulate recommendations for future programming. See current review recommendations.	March, 2019
	Output 4: Learning What Works
1	SGCI to implement a systematic approach for facilitating and monitoring uptake of knowledge outputs	Completed	Dec, 2018
2	AESA to promote and monitor uptake of LRP recommendations and document this in the DELTAS Annual Report	Completed	Dec, 2018
3	AESA to promote real-time lesson sharing between DELTAS grantees	Completed	Dec, 2018
4	EARH to develop a plan to promote synergies in the dissemination of programme outputs and learning across initiatives	Completed	Mar, 2019

# Annex 1: Programme’s Overarching Theory of Change

# Annex 2: Research Leadership: DELTAS Africa Theory of Change

# Annex 3: Science Granting Councils: SGCI Theory of Change

Assumptions
- Private sector’s interest to engage with academia and research institutes
- SGCs are committed to sustaining partnerships with each other
- Policy and decision makers are responsive to research-based evidence
- Researchers have capacity to position their research for uptake
- Expenditure on STI by governments continues to increase
- Governments continue to support and empower SGCs
- Regional cooperation continues
- Political will to support science and innovation continues
- Other science system actors are equally empowered
S = short-term
M = Medium-term
L = Long-term

Effective science granting councils that will strengthen national science systems, and lead to nationally led research that contributes to development in East Africa and other participating countries
 (L)

More effective research investments and strengthened research leadership for development in East Africa and other participating countries
(M)
Strengthen ability to establish partnerships among SGCs and with other science system actors:
- Collaborative agreements with demand-led joint activities
- Learning Forums
- Virtual Hub
More effective research management practices among SGCs: Improved ability to identify and set research priorities that meet local needs, develop competitive research calls, manage fair and transparent adjudication processes, and manage and monitor research (S)

Strengthen ability to manage research:
Customized regional training courses in STI policy analysis and priority setting, grant-making systems and procedures, on-site coaching, and on-going access to expert advice
Strengthen ability to design and monitor research, and to formulate and implement policies based on robust STI indicators:
- Onsite customized training on linking R&D/ innovation to development plans
- Support SGCs to collect micro-level datasets
- Train SGCs on use of data for priority –setting and allocation analysis
Strengthen ability to support knowledge transfer to the private sector:
- Research evidence enables alignment of research with demand
- ldentify research priority areas with selected SGCs
- Work with SGCs to launch proposal calls in priority areas, provide co-funding for research calls.
IDRC-DFID-NRF (funding and reporting agreements are agreed upon and signed)

Buy-in and ownership of the selected SGCs to participate effectively, and agree on a 5-year engagement strategy.

Selection of Collaborating technical agencies to deliver core programme activities
Inputs
Outputs
Outcome
Impact
Activities
Increasingly coordinated and networked SGCs: Coordination improves synergies with other science system actors; networking enables interactive learning; collaborative agreements between SGCs will enable joint projects on regional priorities (S/M)
Increased knowledge transfer to the private sector: Research evidence enables SGCs to develop policies that strengthen links with private sector actors and promotes innovation (M)
Increased use of STI indicators to design and monitor research programs, and to formulate and implement policies
Research evidence improves the capacity of SGCs to manage research programs. Improved capacity to identify and prioritize future STI needs contributes to building resilience of science systems.
- Core research management capacities exist among SGCs
- Participating SGCs are committed to engage in activities and self-improvement
- SGCs are interested in forming partnerships
- Buy-in and support from relevant government Ministries or Departments
# Annex 4: Science Granting Councils: Science Granting Councils Initiative partnership chain mapping

Science Granting Councils
Countries	Science Granting Councils
Ethiopia	Ministry of Science and Technology (MoST)
Kenya	National Commission for Science, Technology and Innovation (NACOSTI)
Rwanda	National Commission for Science and Technology (NCST)
Tanzania	Tanzania Commission for Science and Technology (COSTECH)
Uganda	Uganda National Council for Science and Technology (NCST)
Burkina Faso	Le Fonds National de la Recherche et de l’Innovation pour le Développement (FONRID)
Côte d’Ivoire	Programme d’Appui Stratégique à la Recherche Scientifique (PASRES)
Ghana	Ministry of Environment, Science, Technology and Innovation (MESTI)
Senegal	Direction du Financement de la Recherche et du Développement Technologique, Ministère de l'Enseignement Supérieur et de la Recherche
Botswana	Department of Research, Science and Technology
Malawi	National Commission for Science and Technology (NCST)
Mozambique	Fundo Nacional de Investigacao (FNI)
Namibia	National Commission on Research, Science and Technology (NCRST)
Zambia	National Science and Technology Council (NSTC)
Zimbabwe	Research Council of Zimbabwe (RCZ)

Collaborating Technical Agencies and partners supporting the Science Granting Councils

Project Number	SGCI objective	Collaborating Technical Agencies
108319	More effective research management practices among SGCs;	Southern African Research and Innovation Management Association (SARIMA); Central African Research and Innovation Management Association (CARIMA), West African Research and Innovation Management Association (WARIMA) and East African Research and Innovation Management Association (EARIMA).
108320	Strengthened abilities of SGCs to design and monitor research programmes based on the use of robust STI indicators;	New Partnership for Africa’s Development (NEPAD)
108349	Increased knowledge exchange with the private sector;	African Centre for Technology Studies (ACTS); Scinnovent Centre, STI Policy Research Organization (STIPRO) and Association of African Universities (AAU)
108460	Increasingly coordinated and networked SGCs.	Africa Technology Policy Studies (ATPS) and Scinnovent Centre
108138	Monitoring and evaluation	African Centre for Technology Studies (ACTS);

Other partners: Political economy studies are led by University of Sussex Science Policy Research Unit (SPRU) and African Centre for Technology Studies

# Annex 5: Research Leadership: Developing Excellence in Leadership, Training and Science (DELTAS Africa) Initiative List of Grants
Accelerating Excellence in Science in Africa (AESA) manages grants to:

DELTAS awards	Country	Lead and partner institutions
AMARI: African Mental Health Research Initiative	Zimbabwe	Dr Dixon Chibanda / University of Zimbabwe
A vastly underserved discipline in sub-Saharan Africa, mental health is becoming of increasing concern to governments with only limited intervention programmes available. Researchers will be trained to understand the burden of mental health within populations, as well as risk factors such as poverty and HIV. A strong focus will be on the development of community based intervention strategies with the aim of addressing the treatment gap that exists in sub-Saharan Africa.	Ethiopia / Malawi / South Africa / UK	Addis Ababa University & KCL / College of Medicine, University of Malawi / University of Cape Town / Kings College London / London School of Hygiene & Tropical Medicine / University College
Developing Excellence in Leadership and Genetic Training for Malaria Elimination in Sub-Saharan Africa (DELGEME)	Mali	Professor Abdoulaye Djimde / University of Science Techniques and Technologies of Bamako
Understanding the genetics of malaria parasites, and tracking malaria parasite migration and drug resistance, are two key ways that scientists can begin to develop new malaria drugs and vaccines and make progress with elimination programmes. Mali is to lead sub-Saharan Africa in becoming a leading bioinformatics hub for university-based research, vastly increasing the region’s ability to drive forward this vital research and representing a large part of the total malaria genomic capacity in Africa.	Gabon / Germany / Ghana / Kenya / The Gambia / Tanzania	Universite des Sciences de la Sante / Bernhard-Nocht Institute for Tropical Medicine / Noguchi Memorial Institute for Medical Research / KEMRI / Medical Research Council Unit / National Institute for Medical Research
Initiative to Develop African Research Leaders (IDeAL)	Kenya	Dr Samson Kinyanjui / KEMRI-Wellcome Trust Research Programme
IDeAL will train young researchers, form intern to postdoctoral level, across the whole spectrum of health research, from basic biology to health systems research. It will aim to keep scientists at African institutions through a defined programme of recruitment, supervision, mentorship, multidisciplinary approaches and clear career paths. It builds on a previous Wellcome Trust Strategic Award, which has attracted and trained more than 200 people since 2008.
Makerere University UVRI Centre of Excellence for Infection & Immunity Research and Training (MUII-plus	Uganda	Professor Alison Elliott / Uganda Virus Research Institute UVRI
Makerere University and the Uganda Virus Research Institute (UVRI) will offer fellowships for training African research leaders in bioinformatics, immunity and infectious diseases. Their research will focus on infectious diseases including parasitology, the interactions between infection and non-communicable diseases, and emerging and re-emerging infections – particularly zoonoses.	Uganda	Makerere University
		Makerere University College of Health
	UK	London School of Hygiene & Tropical Medicine
		University of Cambridge
Sub-Saharan Africa Advanced Training Programme for Leadership and Excellence in Biostatistics	South Africa	Professor Tobias Chirwa / University of Witwatersrand
Masters and PhD students will be trained to become experts in biostatistics addressing a gap in biostatistics across Africa. The Consortium will emphasise the use of open access data generated through demographic and health surveillance sites and health research in the region.	South Africa / Kenya	University of Kwazulu Natal / KEMRI-Wellcome Trust Research Programme
	UK	London School of Hygiene & Tropical Medicine
		University of Warwick
Sub-Saharan African Network for TB/HIV research Excellence (SANTHE	South Africa	Professor Thumbi Ndung’u / University of KwaZulu- Natal, K-RITH
The sub-Saharan African Network for TB/HIV research excellence will strengthen the scientific research base for two diseases that account for a major burden of morbidity and mortality in Africa. The network will expand basic, clinical and translational research programmes focussed on HIV and TB, developing African researchers and institutions.	Botswana	Botswana Harvard AIDS Institute Partnership
	Kenya	KEMRI-Wellcome Trust Research Programme
	Rwanda	Rwanda-Zambia HIV Research Group
West African Centre for Cell Biology of Infectious Pathogens (WACCBIP),	Ghana	Dr Gordon Akanzuwine Awandare / Noguchi Memorial Institute for Medical Research, University of Ghana
The programme aims to improve understanding of disease mechanisms for both communicable and non-communicable diseases by training research leaders in the fields of pathogen biology and human genetics. The new award will build on a World Bank grant to support the training of Masters and PhD students and will enable the addition of a post-doctoral programme.	Kenya		KEMRI-Wellcome Trust Research Programme
	Mali		University of Science, Techniques and Technology
	South Africa		University of Cape Town
	The Gambia		Medical Research Council Unit, The Gambia
	UK / USA		London School of Hygiene & Tropical Medicine / University of Cambridge / University of Oxford/WTSI / University of Pittsburgh
African Science Partnership for Intervention Research Excellence (Afrique One-ASPIRE),	Ivory Coast		Professor Bassirou Bonfoh / Centre Suisse De Recherches Scientifiques (CSRS)
Afrique One-ASPIRE will support West and East African scientists researching endemic zoonoses, with an emphasis on improving research training and supporting career pathways through Thematic Training Programmes. The programme will link emerging research institutions across East and West Africa, developing research capacity and training for the next generation of African scientists researching ecosystem health challenges at the human-environment interface.	Ghana / Senegal / Chad / Tanzania / Kenya / UK / Switzerland		Noguchi Memorial Institute for Medical Research, University of Ghana / Inter-states of Medecine and Veterinary School of Dakar (EISMV), Senegal / Institut de Recherche en Élevage pour le Développement (IRED) / Sokoine University of Agriculture / National Institute for Medical Research, / Nelson Mandela African Institution of Sciences and Technology / Kilimanjaro Clinical Research Institute– KCMC / Ifakara Research Institute / Biosciences eastern and central Africa (BecA) Hub / International Livestock Research Institute / University of Glasgow / Swiss Tropical and Public Health Institute
Malaria Research Capacity Development in West and Central Africa (MARCAD	Senegal		Professor Oumar Gaye / University Cheikh Anta Diop de Dakar
MARCAD will bring together leading researchers in West and Central Africa to help eliminate malaria. It will build on the previous achievements of the Malaria Capacity Development Consortium (MCDC) to provide PhD, early and senior post-doctoral fellowships in areas of research relevant to malaria elimination. It will focus on integrating individual training projects within existing research programmes in the following areas: the emergence of insecticide and drug resistance; changing malaria epidemiology; the maintenance of transmission hotspots; and the cost-effectiveness of interventions.	Ghana / Cameroon / Mali / UK / Denmark		Kwame Nkrumah University of Science and Technology / University of Yaounde / University of Sciences, Techniques and Technologies of Bamako (USTTB) / London School of Hygiene and Tropical medicine / Liverpool School Tropical Medicine / University of Copenhagen
The Consortium for Advanced Research Training in Africa + (CARTA+)	Kenya		Professor Catherine Kyobutungi / African Population and Health Research Centre
CARTA+ will build supportive research environments to develop a critical mass of multidisciplinary researchers that improve public and population health in Africa. It will seek to maintain the pipeline of high-quality doctoral candidates and graduates and foster career paths for high achieving fellows through post-doctoral positions and a range of mentorship and support.	Nigeria / Kenya / South Africa / Uganda / Malawi / Tanzania / Sweden / UK / Canada / Switzerland		University of Ibadan / Commission for University Education / KEMRI-Wellcome Trust Research Programme / University of the Witwatersrand / Makerere University / University Of Malawi / Ifakara Research Institute / University of Gothenburg / Umeå University / University of Warwick / University of Toronto / Swiss Tropical and Public Health Institute
Training Health Researchers into Vocational Excellence in East Africa (THRiVE-2), £5.3 million	Uganda		Professor Nelson Sewankambo / Makerere University College of Health Sciences
The programme will aim to transform East African universities into world class research hubs for key emerging health issues in the region. It will train and develop the scientific careers of PhD students and post-doctoral fellows. It will build on the successes of THRiVE-1 to create research leaders in infectious diseases, neglected tropical disease, neonatal and reproductive health and non-communicable diseases	Kenya / Tanzania / Uganda / UK		The International Centre of Insect Physiology and Ecology (ICIPE) / National Institute for Medical Research (NIMR) / Kilimanjaro Christian Medical College / Gulu University / Uganda Virus Research Institute / London School of Hygiene & Tropical Medicine / University of Cambridge

Other Programmes and initiatives managed by AESA other than DELTAS

- Climate Impact Research Capacity and Leadership Enhancement (CIRCLE) (supported by ACU and funded by DFID)
- Grand Challenges Africa (funded by Bill and Melinda Gates Foundation, and other partners)
- Good Financial Grant Practice programme (supported by Wellcome Trust, MRC UK and other partners)
- Human Heredity and Health in Africa (H3Africa) Initiative (supported by Wellcome Trust and GSK) and a STEM education programme (African Academy of Sciences)

# Annex 6: Somalia Research Capacity: Somalia Stability Fund partnership mapping

The Somalia Stability Fund is a multi-donor initiative managed by Adam Smith International

Project 1	Lead and partner institutions
Supporting the Delivery of High-quality Research in Somalia	Lead: Observatory of Conflict and Violence Prevention (OCVP), Somaliland / Partners: University of Bristol and / Transparency Solutions
Objective / To support the capacity of mid-career researchers to conduct high-quality social research across the Somali regions
Project 2	Lead and partner institutions
Ogaal-Xal Reeb (Knowledge for Change)	Lead: Rift Valley Institute (RVI), Kenya / Partners: University of Hargeisa and / Puntland State University
Objective / To develop competence in two Somali higher education institutes for training and research / through investments in human resources, research resources and in equipment and / facilities