Annual Review
Title: Connecting Classrooms through Global Learning (CCGL)
Programme Value £ (full life): £38m (£21m DFID contribution and £17m British Council contribution)		Review Date: / May 2019 (light touch review)
Programme Code: 300502	Start Date: May 2018	End Date: August 2021

Summary of Programme Performance
Year	2019 (May)	2019 / (Aug)	2020	2021
Programme Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	link here
DevTracker Link to Log frame:	link here

A. Summary and Overview (1-2 pages)

Description of programme (1/2 page)

Connecting Classrooms through Global Learning (CCGL) is DFID’s principal development education programme. It aims to result in more and better teaching of international development issues, with more children in the UK and overseas equipped to take action on sustainable development, while also helping to give them the transferable skills that will enable them to live and work in a global economy. The programme is co-designed, co-funded and delivered by the British Council, who will contribute £17m. DFID will contribute £21m.

CCGL focuses on children aged between 7 and 14 and supports partnerships between primary and secondary schools in the four nations of the UK and 30[1] priority countries in Sub-Saharan Africa, Asia, the Middle East and North Africa. By working directly with UK pupils, we are investing in a new generation of Global Britain ambassadors who are proud of the work the UK is doing to tackle global poverty. Through their participation, they will gain the skills, knowledge, attitudes and values they will need to live and eventually work in the global economy.
[1] In the Business Case, 30 developing countries were included in the programme. However, in April 2019, a question-mark arose over the inclusion of Burma. No partnerships have been formed with Burmese schools the British Council office in Burma has said they themselves are unable to provide the resources to manage the programme. At the time of writing this Annual Review, a decision is pending on whether schools and teachers in Burma will continue to participate in the programme.

CCGL has two major components:

1.	School partnerships: the programme will involve long-term partnerships between 4,500 schools and communities in the UK and developing countries, involving 3 million pupils. The programme facilitates both virtual and face-to-face partnerships between schools. It offers grants to fund projects between pupils and visits by UK and developing country teachers to their partner schools. Grant applications are assessed four times each academic year. Schools are encouraged to work in clusters with other schools local to them, both in the UK and overseas. This strengthens peer learning and support among teachers involved in the programme and allows joint visits both to the UK and overseas.

2.	Teacher training: The programme will train 60,000 teachers and school leaders in the UK and developing countries. This includes:
•	setting up and running equitable partnerships, which focuses on working together on the SDGs;
•	teaching and mainstreaming development education/global citizenship content, such as the SDGs;
•	teaching transferable skills, such as critical thinking and problem-solving;
•	ensuring that education is inclusive and of high quality.

The Business Case was approved in March 2018 and preparatory activities were initiated in May 2018. However, core programme activities - notably direct engagement with schools - did not begin until September 2018, in line with the start of the academic year. This start date also prevented overlap with the previous Connecting Classrooms programme which ran until the end of the 2017/18 academic year, as well as with the Global Learning Programme. This Annual Review is therefore a light-touch preliminary review to coincide with the anniversary of preparatory activities being begun. A full Annual Review will take place in August 2019 by which the first year of programme activities will have been completed (aligned to the academic year). Subsequent annual reviews will then take place each August.

Summary supporting narrative for the overall score in this review (1/2 page)

The programme is progressing in line with the original Business Case.

The programme has been scored an A. It is currently on track to meet its Year 1 (July 2019) milestones, and some milestones have already been exceeded. However, we cannot yet judge final performance until the end of the first full academic/school year. This assessment will be made in the full Year 1 Annual Review scheduled for August 2019.

Recommendations for the year ahead (1/2 page)

Over the next period, the programme should aim to:
1. Continue delivery and monitoring as per the Business Case
2. Explore opportunities for CCGL to make a stronger contribution to DFID’s policy objectives, with a particular focus on Education, Climate Change and Disability.
3. Ensure that both the DFID and British Council teams are suitably resourced to meet the demands of the programme.

Specific recommendations:

	Recommendations
1	Delivery and monitoring as per the Business Case
1.1	Identify geographic gaps in engagement by schools/teachers across the UK and develop and implement an action plan to tackle this. This should include a review of the role and activities of lead organisations and local advisors in each UK nation.
1.2	Take specific action to maximise participation by schools/teachers in areas of deprivation/disadvantage, in all four UK nations
1.3	Identify geographic gaps in engagement by developing countries and develop and implement an action plan to tackle this
1.4	Determine whether to continue the programme in Burma and, if not, decide how the funds allocated to Burma should be reallocated
1.5	Complete the review of the logframe by August 2019, with the new agreed logframe to be implemented from the start of Year 2 (Sept 2019)
1.6	Produce and implement a detailed Communications Plan, to include visit schedules, the website and branding
1.7	Ensure that all financial reports are provided to DFID in the required format, on time
1.8	Ensure that financial spend is forecasted accurately by British Council, that British Council inform DFID of any deviations as soon as possible and that any deviations are fully explained and justified
1.9	Ensure that all Assets are recorded accurately by British Council and reported to DFID in full in the required format
1.10	Ensure that all Quarterly reports are provided to DFID on time and with the requested detail. British Council may wish to review the processes and timelines for collating and checking data for the reports in order to minimise delays in their delivery.
1.11	British Council should proactively share data on the programme with DFID so as to minimise ad hoc requests for information. Data provided in the Quarterly Reports should be used to update a master data sheet on the programme, held by DFID, that will be the reference document for as many enquiries as possible. To ensure this data sheet is as accurate as possible, British Council should provide DFID with detailed data annexes in each Quarterly Report (content of the annexes has been agreed in principle but may be adjusted by mutual agreement going forward).
1.12	British Council to provide further information on activities to engage policy-makers/senior practitioners, provide explanations to the geographic polarisation of participation and provide and implement an action plan to ensure policy-makers from each programme country are engaged with the programme.
2	Policy Contribution
2.1	Incorporate key elements of DFID’s Education Policy, Safe to Learn and Safeguarding in teacher training materials and courses. Ensure that CCGL schools follow best practice in these areas and that the UK teachers, particularly during visits, support developing country teachers, school leaders and policy makers make progress in these areas.
2.2	Review the contribution of the programme to the challenge of Climate Change, including through thematic student projects and appropriate teacher training.
2.3	Ensure that the programme appeals to special needs schools and that pupils with special needs in mainstream partner schools are able to participate, supporting these schools and pupils to participate as necessary.
2.4	Review the teacher training offer on inclusive education, particularly for developing country teachers, and if required enhance the focus on disability and inclusion, including the access of disabled children to schools.
2.5	Ensure that monitoring of participation in the programme is disaggregated as far as possible, including by disability, so that the programme ensures its teacher training and partnership offer is as inclusive as possible.
2.6	Explore opportunities to expand the teacher training offer into Initial Teacher Training colleges/courses, in order to strengthen ability of new/future teachers to deliver development education.
3	Resourcing
3.1	British Council to review the resources allocated to the management of the programme: it is recommended that additional staff time be added to the programme
3.2	DFID to seek the more active engagement of Education Advisors, at central and country levels, in the programme. Dedicated advisory support is recommended.

Further recommendations for Year 2 may be added in the full Year 1 Annual Review (August 2019). The above recommendations will also be reviewed at this stage.

## B: DETAILED OUTPUT SCORING (suggest 1 page per output)

Output Title	Partnerships and International Collaboration / Sustainable, equitable and high-impact partnerships between UK and developing country schools/ networks of schools leading to peer-to-peer learning and increased quality of education
Output number per LF		1	Output Score	A
Impact weighting (%):		38%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
# UK and developing country schools develop and share best practice in active global citizenship and activities that develop the knowledge, transferable skills and attitudes students need to live and work in a global economy, through face-to-face partnerships (including reciprocal visits)	1,000 by July 2019	On track / 787 schools awarded partnership funding in Round 1 (October 2018) and Round 2 (January 2019). / Round 3 (March 2019) results are still being analysed, but will bring the total close to the 1000 target with one further Round in June 2019 (indicative results from Round 3 are that a further 130 awards will be made, making the total awards from Rounds 1-3 approximately 917).
# UK and developing country schools develop and share best practice in active global citizenship and activities that develop the knowledge, transferable skills and attitudes students need to live and work in a global economy, through online partnerships	1,000 by July 2019	On track / 987 schools as at 31/3/19
% UK and developing country schools that report their international face-to-face/online partnerships support the development of the knowledge, transferable skills and attitudes students need to live and work in a global economy	50% by July 2019	Exceeded milestone ahead of deadline / 75% UK and developing country schools that report their international face-to-face/online partnerships support the development of the knowledge, transferable skills and attitudes students need to live and work in a global economy

Provide supporting narrative for the score

Since the programme was launched in September 2018, there has been a steady uptake of the programme by schools. Initially the British Council targeted primarily those schools that had been involved in previous Connecting Classrooms programme, but engagement has now broadened out and schools without previous involvement are coming on board.

Schools across the UK have become involved, although there is some unevenness e.g. uptake in London and South East England is lower than elsewhere in England and lower than expected; uptake in Scotland was initially low, but has increased recently following the appointment of local advisors, although it remains below expectations. Overall, 503 UK schools are involved in the programme, of which 409 are in England, 52 in Wales, 27 in Scotland and 15 in Northern Ireland. Participation in Wales exceeds that expected, participation in England is on a par with that expected and participation in Scotland and Northern Ireland is below that expected. The British Council is in the process of undertaking a full gap analysis to identify where further support may be required. It will be particularly important to focus on areas of disadvantage which was a specific commitment in the Business Case and plans are already in place to take forward specific action in these areas; e.g. in Scotland, workshops and ambassadorial activity will be prioritised in the 9 Challenge Authorities.

As at 31st March 2018, there were participating schools in all but two priority countries: South Sudan and Burma. The lack of participation in South Sudan can be explained by the current country circumstances. In the case of Burma, the programme team was informed in April that British Council – Burma had taken the decision not to participate in the programme, due to insufficient funds at the local level (British Council offices overseas provide some of the funding towards the overall £17m British Council programme contribution); they are also stretched in terms of human resources, as they are implementing a new, large-scale DFID programme in-country. We are exploring whether we should continue to include Burma as a priority country under CCGL or whether the funds allocated for Burma (approximately £350K) should be reallocated to another priority country or whether an additional country should be added to the programme to replace Burma, keeping the total number of priority countries at 30. A decision on this will be made by July 2019 and reported in the full Year 1 Annual Review.

While all other priority countries do have participating schools, the level of participation varies considerably. There are 1479 participating schools in Sub-Saharan Africa - this includes over 200 schools in each of Nigeria, Tanzania and Zimbabwe, but less than 10 schools in each of Lesotho, Mozambique, Rwanda and Sudan. In Asia, there are 1174 participating schools, of which 524 are in Bangladesh and 412 are in Pakistan. 96 Afghan schools are involved in virtual partnerships. 418 schools in the Middle East and North Africa are engaged in the programme; all countries are involved, but the highest participation rates are in Lebanon (154 schools) and Palestine (120 schools); only 5 schools in Iraq and 6 schools in Jordan are currently participating in the programme. The British Council are in the process of analysing the reasons for the varied take up in order to target action for Year 2 (reasons could include, for example, local circumstances (conflict, natural disasters, etc), language barriers, resourcing issues, or buy-in from the Ministry of Education).

Demand for grants has been strong. Slightly lower figures in Round 3 (March) were as expected given the experience of the previous Connecting Classrooms programmes. British Council expect high numbers of grant applications in Round 4 (June), as this is the time of year when teachers are actively planning for the next academic year.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:

1. The programme is demand-driven and therefore it is not possible to pre-determine participation in the programme. However, the programme team can provide support to make schools aware of the programme and then to convert that awareness into participation. In Scotland, the impact of local support on school take-up was seen clearly during Year 1: there were delays in procuring local advisory support and in the early months of the programme take-up in Scotland was lower than expected (in the previous Connecting Classrooms programme, participation rates in Scotland were higher than in the rest of the UK); since local advisory support has been in place, however, take-up in Scotland has increased significantly.
2. Regular updates on programme progress and data (eg on grants, school numbers) are essential for the DFID team to effectively monitor and manage the programme and respond to public and ministerial requests. However, ad hoc requests for information take the programme team away from day-to-day programme implementation. In order to minimise ad hoc requests to British Council, a process has been established by which the majority of data should be updated, in detail, on a quarterly basis in the Quarterly Reports. DFID will then produce a master data reference sheet containing key information. While the majority of data will be provided in Quarterly Reports, DFID would also find it helpful if the British Council could proactively share data during the quarter when it is updated e.g. when the outcome of a grant round is decided.

The aims for both the remainder of the 2018/19 academic year and for Year 2 of the programme (August 2019-August 2020) should be to:
- Increase overall participation in the programme, in both the UK and overseas
- Address gaps in the geographic distribution of participation, both within and among countries
- Focus on areas of disadvantage in the UK in order to increase participation in these areas
- Ensure that special needs schools and teachers and pupils with disabilities are able to participate in the programme as fully as possible.

A decision needs to be made by July 2019 as to whether the programme will continue in Burma and, if not, how resources should be reallocated. There are 2 options: (1) provide additional resources to (an) existing programme country/ies; (2) open the programme in a new country.

Launch events to publicise the new programme were held as follows:
London – September 2018 – Secretaries of State for Development and Education
Bridgend – November 2018 – Secretary of State for Wales
Edinburgh – November 2018 – Secretary of State for Scotland
These events were important for raising awareness of the programme via social and print media, as well as for celebrating the successful partnerships in the host schools. A similar awareness-raising event is planned for Northern Ireland in summer 2019. There have also been a number of other school visits, by ministers and officials, designed to celebrate existing partnerships and encourage other schools to sign up e.g. Herefordshire, Portsmouth, Glasgow.

A detailed Communications Plan is currently under preparation in order to streamline all communications/awareness-raising opportunities for the coming year and maximise the return from events, social media, etc.. This will include decisions on branding of the programme and actions to maximise the usability of, and return from, the CCGL website.

Summary of recommendations:

1	Delivery and monitoring as per the Business Case
1.1	Identify geographic gaps in engagement by schools across the UK and develop and implement an action plan to tackle this. This should include a review of the role and activities of lead organisations and local advisors in each UK nation.
1.2	Take specific action to maximise participation by schools in areas of deprivation/disadvantage, in all four UK nations
1.3	Identify geographic gaps in engagement by developing countries and develop and implement an action plan to tackle this
1.4	Determine whether to continue the programme in Burma and, if not, decide how the funds allocated to Burma should be reallocated
1.5	Complete the review of the logframe by August 2019, with the new agreed logframe to be implemented from the start of Year 2 (Sept 2019)
1.6	Produce and implement a detailed Communications Plan, to include visit schedules, the website and branding
1.10	Ensure that all Quarterly reports are provided to DFID on time and with the requested detail. British Council may wish to review the processes and timelines for collating and checking data for the reports in order to minimise delays in their delivery.
1.11	British Council should proactively share data on the programme with DFID so as to minimise ad hoc requests for information. Data provided in the Quarterly Reports should be used to update a master data sheet on the programme, held by DFID, that will be the reference document for as many enquiries as possible. To ensure this data sheet is as accurate as possible, British Council should provide DFID with detailed data annexes in each Quarterly Report (content of the annexes has been agreed in principle but may be adjusted by mutual agreement going forward).

Output Title	Teaching Improvements / Teachers are equipped and better able to deliver transferable skills and global learning effectively
Output number per LF		2	Output Score	A
Impact weighting (%):		35%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
# teachers who complete online or face-to-face training through the programme	10,000 by July 2019	On track / 5,866 teachers trained to date. (of which 41% female, 59% male) / Further CPD is planned for May to July 2019 – British Council are confident that the 10,000 milestone will be met by the end of this school year (July).
% gain of teachers with increased confidence in teaching activities relating to active global citizenship and the development of key knowledge, transferable skills and attitudes amongst students	50% by July 2019	Exceeded ahead of deadline / 63%
% of teachers who confirm their teaching practice has been enhanced by the professional development opportunities offered by the programme	50% by July 2019	Data not yet available, will be included in the full Annual Review (requires follow up surveys)
# UK and developing country schools using high quality online resources that support the development of active global citizenship amongst students	7000 by July 2019	Exceeded ahead of deadline / 10,024

Briefly describe the output and provide supporting narrative for the score

A strong offer of Continuing Professional Development (CPD), in the UK and overseas, has been developed and implemented during Year 1. Face-to-face and online training had reached 5,866 teachers as at 31 March 2019; this was 59% of the Year 1 target. Given procurement delays, some of the CPD offer was slow to come on stream, but this has now been rectified. Courses are also commonly offered in several parts; in many cases some, but not all, of the stages had been delivered by 31 March; once the final modules of these courses have been delivered, CPD completion rates will increase significantly. Courses are already organised for the remainder of this academic year (May, June, July 2019) which should bring the total number of teachers trained to the target of 10,000 by the end of July.

In the UK, as at 31 March, in-depth CPD had been completed by 123 teachers; no Northern Irish teachers had, however, completed any training. Completion rates are predicted increase significantly between May and July, once teachers complete all the modules in a course and once additional courses, already organised, have taken place.

3323 teachers in Africa had completed training on 31 March. There is considerable geographic unevenness in completion of CPD, although this could be linked, in some cases, to the timing of the modules (e.g. if a large group of teachers have completed the penultimate but not the final module of a course it will not yet be recorded): no teachers in Lesotho, South Sudan or Sudan had completed a course and only one teacher in Malawi. At the other end of the scale, 710 teachers in Ethiopia, 690 in Uganda and 559 in Nigeria completed training. In Asia, 1562 teachers completed training, including 944 in Bangladesh; no teachers in India completed a training course. In the Middle East and North Africa, a total of 858 teachers had been trained, 460 (54%) of these from Lebanon; no teachers in Iraq or Palestine had completed courses by 31 March.

While in some cases this geographic distribution matches that of school participation, there are also some differences. For example, only 33 schools in Morocco currently participate in the programme, but 172 teachers have completed training, while in Palestine there is a high school participation rate, but no teachers have yet completed training. As with the geographic distribution of schools, British Council are analysing the participation of teachers in CPD courses and will take action as necessary to encourage participation.

Teacher participation is disaggregated by gender. However, it would be helpful if the data could be disaggregated also by disability (and potentially other criteria) in order to ensure that CCGL is as inclusive as possible. Disability data can however be difficult to collect as it relies on self-declarations by individual teachers. The British Council do collect data on the schools the teachers teach in: 17.3% of teachers participating in CCGL CPD courses stated that some or all of their pupils have special educational needs or disabilities; 108 teachers stated that all of their pupils had special educational needs or disabilities (ie they teach in a SEND school).

Qualitative data on the benefits teachers derive from the training is not yet available. Surveys of participating teachers are circulated after CPD courses. These will be received and analysed in time for the full Year 1 Annual Review in August 2019.

Teacher training has to date focused on teachers already practicing. British Council are starting to explore how the programme could support Initial Teacher Education (teacher training), for example by training future teachers in including development education within other curriculum subjects.

Lessons identified this year, and recommendations for the year ahead linked to this output

Lessons learned:

1. An important feature of the CCGL programme is the provision of accredited teacher CPD. This can help increase demand for CCGL courses over others offered by other providers. For overseas teachers, it can also be important to obtain certification that they have completed an accredited course delivered through the medium of English. There were procurement delays in arranging accreditation for CCGL courses (no response from the first call for bids), but City and Guilds has now been engaged. They are currently undertaking the necessary checks and designing their accreditation offer so CPD courses delivered from Year 2 onwards (academic year 2019/20) can be accredited; they are also considering whether they are able to retrospectively accredit courses delivered in Year 1.
2. Courses are delivered according to best practice. For example, courses are delivered in stages, with time for teacher application and reflection in-school between modules. This is an important strength of the CPD offer, but can mean that completion rate data looks to be off track. Care should be taken when drawing conclusions based on the data alone, without considering the nature and timing of the courses being offered.
3. As for Output 1, regular updates on programme progress and data (e.g. on CPD courses) are essential for the DFID team to effectively monitor and manage the programme and respond to public and ministerial requests.
4. Increased disaggregation of participation data would help to ensure that the CPD is as inclusive and targeted as possible.
5. Teachers will not participate in teacher training courses if they are not aware of them. The programme should therefore maximise every opportunity to publicise teacher training courses. This should be included in the Communications Plan currently being prepared.
6. Supply cover can be cited as a reason for non-participation in CPD. Schools can apply for a limited amount of supply cover within CCGL grant applications. The British Council currently consider that supply cover is adequate – while schools will welcome additional cover, the amount currently offered is considered balanced and proportionate.

The aims for both the remainder of the 2018/19 academic year and for Year 2 of the programme (August 2019-August 2020) should be to:
- Ensure that ongoing CPD is completed and all future courses are delivered as planned and completed by as many teachers as possible
- Address gaps in the geographic distribution of participation, both within and among countries
- Focus on areas of disadvantage in the UK in order to increase participation by teachers from these areas
- Ensure that teachers with disabilities are able to participate in the CPD programme as fully as possible.
- Ensure that future CPD supports policy objectives on inclusive education/disability, climate change, safeguarding and Safe to Learn.

Specific recommendations:

	Recommendations
1	Delivery and monitoring as per the Business Case
1.1	Identify geographic gaps in engagement by teachers across the UK and develop and implement an action plan to tackle this. This should include a review of the role and activities of lead organisations and local advisors in each UK nation.
1.2	Take specific action to maximise participation by teachers in areas of deprivation/disadvantage, in all four UK nations
1.3	Identify geographic gaps in engagement by developing countries and develop and implement an action plan to tackle this
1.5	Complete the review of the logframe by August 2019, with the new agreed logframe to be implemented from the start of Year 2 (Sept 2019)
1.6	Produce and implement a detailed Communications Plan, to include visit schedules, the website and branding
1.10	Ensure that all Quarterly reports are provided to DFID on time and with the requested detail. British Council may wish to review the processes and timelines for collating and checking data for the reports in order to minimise delays in their delivery.
1.11	British Council should proactively share data on the programme with DFID so as to minimise ad hoc requests for information. Data provided in the Quarterly Reports should be used to update a master data sheet on the programme, held by DFID, that will be the reference document for as many enquiries as possible. To ensure this data sheet is as accurate as possible, British Council should provide DFID with detailed data annexes in each Quarterly Report (content of the annexes has been agreed in principle but may be adjusted by mutual agreement going forward).
2	Policy Contribution
2.1	Incorporate key elements of DFID’s Education Policy, Safe to Learn and Safeguarding in teacher training materials and courses. Ensure that CCGL schools follow best practice in these areas and that the UK teachers, particularly during visits, support developing country teachers, school leaders and policy makers make progress in these areas.
2.2	Review the contribution of the programme to the challenge of Climate Change, including through thematic student projects and appropriate teacher training.
2.4	Review the teacher training offer on inclusive education, particularly for developing country teachers, and if required enhance the focus on disability and inclusion, including the access of disabled children to schools.
2.5	Ensure that monitoring of participation in the programme is disaggregated as far as possible, including by disability, so that the programme ensures its teacher training and partnership offer is as inclusive as possible.
2.6	Explore opportunities to expand the teacher training offer into Initial Teacher Training colleges/courses, in order to strengthen ability of new/future teachers to deliver development education.

Output Title	School Leadership / Participant schools across the UK and overseas strengthen their leaders’ skills and their curriculum’s focus on international dimension and global citizenship.
Output number per LF		3	Output Score	B
Impact weighting (%):		19%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
# school senior management teams support the integration of active global citizenship and key knowledge, skills and attitudes amongst students through classroom teaching and whole school initiatives	3,000 by July 2019	On track / 2,571 school leaders trained (33% female and 66% male) to support the integration of global citizenship and core/transferable skills in their schools
% school leaders who confirm their leadership practice has been enhanced and influenced by the professional development opportunities offered through the programme	50% by July 2019	Data not yet available, will be available next quarter and included in the full Annual Review.
# schools that receive formal accreditation through the programme in recognition of the quality delivery of active global citizenship activities in school/the community/internationally that develop the knowledge, transferable skills and attitudes students need to live and work in a global economy	3,000 (original) / 800 (revised April 2019)	Year 1 target lowered due to delays in starting this element / 468 schools awarded the International School Award / No teachers or School Leaders to date yet awarded accreditation for completion of in-depth training

Provide supporting narrative for the score

Training of school leaders is on track, but, as for teacher training, there is considerable geographic variation. 1345 leaders have been trained in Africa, but no leaders have been trained in Lesotho, Malawi, Sierra Leone, South Africa, South Sudan or Sudan and only one leader has been trained in each of Ghana and Uganda. Also as for teachers, however, this may be because leaders have not yet completed all the modules required for a course to register as completed. In Asia, 935 leaders have been trained, but only 2 in Nepal and none in India. In the Middle East and North Africa, 288 leaders have completed training, but none of these are in Iraq, Jordan or Palestine. Data has not been provided by the British Council to assess leadership training in the UK.

Qualitative data on the benefits leaders derive from the training is not yet available. Surveys of participating leaders are circulated after CPD courses. These will be received and analysed in time for the full Year 1 Annual Review in August 2019.

It was agreed in April 2019 to revise the Year 1 (July 2019) accreditation targets downwards, principally due to delays in procurement (see above under Output 2). The Year 2 and Year 3 (whole-programme) targets remain unchanged.

Lessons identified this year, and recommendations for the year ahead linked to this output

The lessons and recommendations for school leader training are the same as those for teacher training (Output 2 – see above).

Output Title	Policy Dialogue / Policy makers and senior practitioners in developing countries have better understanding of best practice (e.g. on inclusion) and implement this
Output number per LF			Output Score	B
Impact weighting (%):		8%	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
# senior practitioners and policy makers engaged with programme	200 by July 2019	Milestone exceeded ahead of time / 210 senior practitioners and policy makers engaged with the programme
% policymakers and senior practitioners reporting that the programme's activities fully support their needs	60% by July 2019	Data not yet available, will be included in the full Annual Review. / Evidence will be derived form surveys which start from now onwards.
% policy and decision makers reporting enhanced understanding of best practice in the priority themes addressed through the programme (eg. Inclusion, transferable skills, active global citizenship)	60% by July 2019	Data not yet available, will be included in the full Annual Review. / Evidence will be derived from surveys which are being launched in May 2019.

Provide supporting narrative for the score

While the July 2019 milestone for senior practitioner and policy-maker engagement has been exceeded ahead of time, much of this Output relies on qualitative data which is not yet available.

Additionally, there is significant geographic polarisation in policy-maker engagement. The majority of the milestone is made up by engagement in a very small number of countries: 100% of engagement in Africa is accounted for by Nigeria (36 policy-makers/practitioners); 96 out of 116 policy-makers reached in Asia are in Bangladesh, with the remaining 20 in Pakistan; in the Middle East and North Africa, only policy-makers in Jordan, Lebanon and Palestine have been reached and of these 81% are in Lebanon. The overall level of policy-maker engagement in Africa seems particularly low (36 out of the 210 total = 17%) given the number of participating countries (16 out of 30 priority countries are in Africa = 53%). This geographic distribution should be explored in greater detail by British Council and explanations provided, along with plans to ensure that policy-makers in all participating countries are involved in the programme.

The programme has reached 16 UK policy-makers, with participation from all four of the UK nations.

Lessons identified this year, and recommendations for the year ahead linked to this output

DFID has limited information from British Council on the activities being carried out under this Output. More detailed narrative in the Quarterly Reports is required, starting with Q1 2019/20 (April-June).

1.10	Ensure that all Quarterly reports are provided to DFID on time and with the requested detail. British Council may wish to review the processes and timelines for collating and checking data for the reports in order to minimise delays in their delivery.
1.11	British Council should proactively share data on the programme with DFID so as to minimise ad hoc requests for information. Data provided in the Quarterly Reports should be used to update a master data sheet on the programme, held by DFID, that will be the reference document for as many enquiries as possible. To ensure this data sheet is as accurate as possible, British Council should provide DFID with detailed data annexes in each Quarterly Report (content of the annexes has been agreed in principle but may be adjusted by mutual agreement going forward).
1.12	British Council to provide further information on activities to engage policy-makers/senior practitioners, provide explanations to the geographic polarisation of participation and provide and implement an action plan to ensure policy-makers from each programme country are engaged with the programme.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES (1-2 pages)

Summarise the programme’s theory of change and any major changes in the past year (1/2 page)

To date there has been no change to the Theory of Change which remains as approved in the Business Case (see diagram below).

Describe where the programme is on track to contribute to the expected outcomes and impact, and where it is off track and so what action is planned as a result in the year ahead (1/2 page)

It is too early to assess progress against the Impact. This will be assessed in the full Annual Report in August 2019. Evidence will be derived from:
-	Self-assessments by schools (launched February 2019)
-	Survey responses from students (launched February 2019)
Further evidence will be provided by the external evaluation (to be launched September 2019), which will be available for in-year monitoring and the Year 2 Annual Report.

Against the Outcome:

(i) 3,673 schools were delivering quality transferable skills and/or active global citizenship in the curriculum as ay 31 March 2019. Against a Year 1 milestone of 5,000, the programme is on track.

(ii) 87% school partnership activities had improved the teaching of active global citizenship as at 31 March 2019.

(iii) 64% schools in the UK are engaged in teaching that enhances transferable and core skills in the curriculum and ethos of the school (31 March 2019).

Explain major changes to the logframe in the past year (1/2 page)

With one exception (Output Indicator 3.3), no significant changes have been made to the logframe in the past year. However, the logframe has been subject to detailed review. An updated logframe should be agreed ahead of the full Annual Review in August. This updated logframe will be used from the start of Year 2 of the programme to coincide with the new academic year 2019/20.

In March 2019 it was agreed that, due to delays in procurement, the Year 1 (July) milestone for indicator Output 3.3 (Accreditation) be reduced to 800. The milestones for Year 2 and Year 3 (whole programme) will be unchanged.

Describe any planned changes to the logframe as a result of this review (1/2 page)

None.

## D: VALUE FOR MONEY (1-2 pages)

Assess VfM compared to the proposition in the Business Case, based on the past year (1 page)

Overall, the programme is performing in line with the key cost drivers in the business case. The British Council are taking all the necessary action to manage the cost drivers.

Economy:
- Staff costs: spend on staff costs currently represents 17% of the overall programme spend (vs VFM milestone measure of 23.5%)
- Management and M&E costs: spend represents a total of 7% of the overall programme spend (vs milestone measure of 9%, comprising 4% for management costs and 5% for M&E costs).
- Grant amount of £1,500 per school – maintained in line with the current programme

The above have been achieved due to close management and monitoring of staff time allocated to the programme, as well as closely monitoring and managing spend on management and M&E costs.

Evidence against efficiency, effectiveness and equity measures will be provided in the full Year 1 Annual Review in August 2019.
Based on the evidence available within the programme so far, and the measures being taken by British Council to manage key cost drivers in line with the Business Case, the programme continues to represent value for money. There are no suggestions for any changes to the VFM measures or trigger points.

E: RISK (½ to 1 page)

Overall risk rating: Moderate

Overview of programme risk

The British Council, supported by DFID, manage and monitor the overall risks of CCGL. A comprehensive risk register is maintained (see below). Risks are reviewed quarterly and the risk register updated accordingly.

The overall risk rating for the programme remains moderate, with no significant changes.

The main risks with major residual impact are those concerning travel of UK nationals overseas and the accompanying security risks, as well as the placing at risk of children/vulnerable adults through the programme’s main activities. The British Council ensure that teachers travel on pre-agreed dates in groups arranged by the British Council. They also follow FCO travel advice and carry out risk assessments before visits are given the go ahead by the Country Director.

The risk of overseas teachers absconding as part of the teacher visits to the UK remains a moderate risk. As a result of this, only schools that demonstrate commitment to the programme will be considered for travel grants, clusters of schools are encouraged to travel together reducing the opportunities for absconding.

Risk Category and Description	Gross Likelihood	Gross Impact	Mitigating Actions	Residual Likelihood	Residual Impact	Overall Residual Risk	Triggers	Owner
Safeguards
Security risks concerning teachers travelling from the UK to overseas	Possible	Major	Teachers travel on pre-agreed dates to country in groups arranged by the British Council / British Council follows FCO travel advice and carries out risk assessments before visits given go ahead	Possible	Major	Amber	FCO travel advice / Local advice from security officer at Post	British Council
Children / vulnerable adults are placed at risk through the programme’s activities	Possible	Major	We will ensure that contracts for implementing partners, issued by the British Council, are fully compliant with the SMART Rules.	Possible	Major	Amber	Any reports of abuse of children	British Council
Operational
Targets not reached due to conflict or natural disaster in participating countries	Possible	Moderate	Funds can be moved between countries/regions and targets transferred	Possible	Moderate	Amber	M&E results in quarterly reports	British Council
Delivery
Insufficient schools take up the programme due to workload/ curriculum pressures.	Possible	Moderate	Promote benefits of DEGL and school partnerships / Offer strong incentives for joining the programme, such as awards and accreditation. / Ensure burden on teachers of participating in the programme is minimised by streamlining registration and reporting requirements, and ensuring that teaching resources are easy to access and use. / Seek endorsement from Ministries of Education through the programme’s advocacy efforts.	Possible	Moderate	Amber	Number of schools behind target	British Council & DFID
Insufficient schools in disadvantaged areas of the UK take up the programme	Possible	Moderate	Target those areas with offers of support and outreach (e.g. resources that bring our work to life, speakers from amongst DFID staff, ICS/VSO returnees, Commonwealth Scholars etc.)	Possible	Moderate	Amber	Number of schools behind target in the quarterly report	British Council & DFID
The relationship between British Council and Delivery Partners becomes strained.	Possible	Moderate	Draw up clear terms of reference with roles and responsibilities, with regular review of how this is working by the Programme Management and Advisory Committees	Possible	Moderate	Amber	Issues raised by delivery partners/ / British Council and monitoring at the Steering Committee	British Council & DFID
British Council country offices unable/unwilling to participate in the programme	Possible	Moderate	British Council to seek early confirmation from their country offices that they will engage and have sufficient resources (human and financial) to do so	Possible	Low	Green	British Council information / DFID Education Advisors in-country	British Council
British Council and DFID have insufficient resources to implement, manage and monitor the programme	Possible	Major	BC to review resourcing for the programme / DFID to ensure programme team resources adequate / DFID to keep Education Advisors overseas informed of the programme and ensure their active engagement	Possible	Major	Amber	Delays in reporting, delivery actions, etc	DFID and British Council
Reputational
Absconding of developing country teachers	Possible	Moderate	Only schools that demonstrate strong commitment to the programme will be considered for travel grants; clusters of schools will be encouraged to travel together, reducing opportunities for absconding; teachers will be accompanied throughout their visit by their partner schools; UK hosting schools will receive written guidance on the risks of absconding, detection of warning signs, and reporting; pre-travel briefings will be given to ensure understanding of expectations and consequences of absconding; written permission for each teacher travelling will be obtained from the local Ministry of Education.	Possible	Moderate	Amber	Absconding of teacher	British Council
UK media portrays teacher/pupil visits as a waste of taxpayers’ money	Possible	Moderate	Promote the educational benefits of teacher/pupil exchanges through ministerial visits to school, proactive press stories etc. / Have strong defensive lines in place.	Possible	Moderate	Amber	Publication of negative article	British Council and DFID
Downstream supplier acts inappropriately or was not eligible for a contract	Possible	Major	Due Diligence checks for all countries have been completed but need to be expanded to cover all DFID requirements	Unlikely	Moderate	Amber
External Context
Country context is not conducive to the delivery of the programme	Possible	Moderate	Relevance of the offer strengthened by working closely with policymakers to develop contextually relevant training opportunities	Unlikely	Moderate	Green	Reports from local British Council offices / M&E results
Fiduciary
Programme funds are not used for the intended purpose, either by British Council staff or 3rd party suppliers, as a result of fraud, bribery or corruption	Possible	Moderate	British Council has in place robust anti-fraud and corruption policies and procedures, which all staff must adhere to as part of the organisation’s code of conduct / British Council accounts are audited by the National Audit Office on an annual basis / 3rd party suppliers are also subject to the above policies and procedures and British Council reserves the right to conduct audits	Unlikely	Moderate	Green	Reports from British Council finance officers / Issues highlighted through British Council finance checks and procedures / Reports from audits

British Council has carried out Due Diligence on all suppliers as part of its own robust processes regarding procurement and ongoing supplier management.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE (1-2 pages)

Delivery against planned timeframe:

Delivery against the planned timeframe set out in the Business Case remains on track, despite some slight delays in launching the UK CPD offer (January 2019 rather than Sept 2018) and the teacher accreditation offer (July 2019 rather than Jan 2019). The launch of the full accreditation offer was delayed due to the absence of any suppliers responding to the first procurement opportunity when it was advertised. This tender was subsequently reissued in early 2019 with City and Guilds in the process of being appointed and starting work. The expectation is that the overall target for teacher and school level accreditation will still be met in Year 2 and by the end of the programme in 2021.

Performance of partners and DFID, notably on commercial, and financial issues (1-2 pages)

Overall, partnerships are going well. All suppliers have been procured and contracted apart from the accreditation and evaluation study. Given the nature of the programme (training delivery over more than 30 countries), there is an extremely, and unusually, large number of Tier 2 suppliers. DFID due diligence (including enhanced due diligence) and safeguarding requirements have been embedded into pre-contract checks and as part of signed contracts. British Council have a payment plan agreed and in place with suppliers based on performance,	with review points built in and the option for termination of contract as required.

British Council has been exploring wider partnerships to strengthen the impact of the programme. For example, they have had initial conversations with the BBC and FIA Foundation to scope out the potential for cross promotion and synergy between their offers in Global Learning and the CCGL programme. The British Council have also further developed programme partnerships with Send My Friend to School and World’s Largest Lesson, through co-promotional activity. Partnerships and links with UK teaching bodies, such as the Teaching Councils, and with initial teacher training providers (universities) are being explored.

British Council continue to send DFID Quarterly reports to update on the activity of the CCGL programme to date. DFID introduced a new reporting template which has been a challenge, but British Council are now on track and delivering the reports generally in the timeline requested. They are urged to ensure that all future reports are delivered on time and with the full information and data required. They may wish to consider reviewing their processes for the collation and checking of data in order to minimise delays in delivering Quarterly Reports.

DFID and the British Council have been working together to reduce ad-hoc requests and work as a partnership to respond to Ministerial requirements. A key part of this effort is to ensure DFID team has the data it needs to hand, principally provided through the Quarterly Reports. DFID is also ensuring that the CCGL programme team work together with DFID Communications to deliver a joined up communications strategy.

The current programme governance structure is still the same as per the agreed Business Case. Various governance meetings have now been agreed to take place in May/June 2019. The Programme Delivery Board meet monthly throughout the quarter to discuss issues. Actions are regularly recorded on the Delivery Plan between BC and DFID.

Disability

British Council aims to deliver to outcomes relating to Special Education Needs through the teacher training and school leader training, learning through school partnerships and influencing at the policy level. The programme is monitoring participation by SEN schools and is addressing underrepresentation by targeting more SEN schools in UK and overseas. Current data on SEN schools include:

- UK SEN schools: 20 participating schools to date
- Overseas SEN schools: 10 participating schools to date
- 108 teachers and 16 school leaders who work in SEN schools have been trained to date.

Moving forwards, the programme should consider:
- Further enhancing training on inclusive education, including access of children with special educational needs and disabilities to school, through the CPD courses offered. This will be particularly important for those teachers who declare that there are no pupils with special educational needs or disabilities in their schools: this is either an issue of access (disabled children do not have access to school) or identifying pupils with special needs in a mainstream setting and providing them with any additional support they may require.
- Disaggregating data on participation by teachers with disabilities (where self-declaration provides sufficient data).

Climate Change

The programme contributes to Strategic Objective 2 of the 2015 UK Aid Strategy by supporting UK schools to work with schools in countries affected by conflict and by educating children on climate change.

The following climate change-themed classroom resources are available to schools to download and use with their overseas partner school:

- Responsible production and consumption
- Zero Waste
- Affordable, clean energy.

Discussions between DIFD and British Council are on-going to develop a new classroom resource on Plastics and Oceans which we will be will be able to share more detail on in the full Year 1 Annual Review in August 2019.

Financial performance

The British Council has a robust financial management system in place across all regions that is being used to monitor programme expenditure. They provide up to date and generally accurate forecasting figures to DFID monthly, although in the first year there have been some instances where invoices have come in that exceed the forecast by a significant amount (although the year-end figure was accurate). The request for payment is mostly on time a month after the quarter closes. The figures are largely correct. Overall, spend was in line with the expectations for the first year of the programme.

Spend for FY 2018/19 was slightly adjusted which has had a knock-on impact in the outer years, which have now been adjusted - the overall programme spend until 2021 remains £21 million.

The following forecast sets out anticipated future costs against current approved budgets as per the Business Case:

Forecast	2018-19				2019-20	2020-21	2021-22	All years
£	Q2	Q3	Q4	TOTAL	TOTAL	TOTAL	TOTAL	Total
Forecast spend	1,152,542	2,786,072	3,914,000	7,852,614	12,550,000	13,900,000	3,697,386	38,000,000
DFID proportion @ 55%	633,898	1,532,339	2,152,700	4,318,938	6,902,500	7,645,000	2,133,562	21,000,000

Date of last narrative financial report(s)	31/03/2019
Date of last audited annual statement (s)	N/A

Asset monitoring

Assets of £53,092 remained after the Connecting Classrooms programme (2015-2018). These have been transferred to CCGL and are recorded on the Asset Register. A formal letter to finalise transfer of these assets is in the process of being agreed between DFID and British Council. The assets are principally computers, projectors and similar IT equipment, which are used by trainers locally to deliver training as well as loaned to overseas schools so that they can fully participate in the programme – e.g. to allow video links with their UK partner school.

Spot checks on assets purchased may be carried out at any time by the global management team, using transaction reports on the Corporate Global Finance system to identify assets and seek reassurances that due process has been carried out.

Two new laptops were purchased in Tanzania (February 2019) to replace computer assets which were no longer functioning at the end of the Connecting Classrooms programme. No further new assets have been purchased to date under CCGL.

G: MONITORING, EVIDENCE & LEARNING (1-2 pages)

Monitoring (1/2 page)

In line with the Business Case, an independent evaluation of the programme will be procured in 2019 and begin in 2020. The TORs have been reviewed by DFID-appointed consultants whose feedback will now be incorporated into the finalised TORs. Once agreed, the aim is to go out to tender for a supplier to lead the study by end of May 2019. Further details of this review will be included in the full Year 1 Annual Review in August 2019.

In the UK, the programme is being closely monitored to ensure a geographical spread across and within the 4 UK nations. There is a particular focus on monitoring and take-up of the programme in locations of the UK as being areas of socio-economic deprivation. Further analysis and action being taken for the year ahead will be included in the Annual Review later this year.

Discussions have also taken place between DFID and British Council regarding additional requirements within DFID for disaggregated by data by disability.

Monitoring activities carried out to date include:
 South Asia - country teams made a series of visits to the field to ensure quality of delivery and collate information for centralised M&E processes. Spot checks have also been carried out to ensure trainers are delivering and providing programme support to participants as contracted.
 Scotland - a teacher reference group, attended by 6 practitioners was held at British Council Scotland in March 2019 in order for practitioners from different settings to trial the pupil outcomes, cluster and school handbooks. The feedback was used to refine the materials and ensure they were fit for purpose before publication.
 MENA - a field visit to UNRWA Marka School for Girls (linked to St Joseph’s Primary, London) took place in March 2019 with senior representatives from British Council and the Chief of education programme at UNRWA. The visit included attending classes and meetings with school principal, teachers and students who have been involved in the project activities and trainings to discuss the core skills trainings and the International collaboration impact on the learning and teaching process.

Evidence (1/2 page)

Feedback on the programme continues to be generally positive from a range of stakeholders: see below an example provided from the Bangladesh Education Secretary Md Sohrab Hossain.

Bangladesh Education Secretary Md Sohrab Hossain, chief guest at the launch of Connecting Classrooms in November 2018 in Dhaka stated, ‘The world has become more complex now and our younger generations need to have appropriate knowledge and skill to ensure a better future. Along with many education initiatives, ‘Connecting Classrooms’ will contribute to ensure that better future.’

Qualitative data is being gathered from teachers and school leaders who participate in CCGL training courses. This data is being collected as planned but the results will not be available until the full Annual Review in August 2019.

Learning (1/2 page)

Learning against each Output has been included above. Year 1 learning will be fully analysed in the Annual Review in August 2019, using the results of the qualitative surveys and the evaluation.

Progress on recommendations from previous reviews (1/2 page)

Not applicable - CCGL started in September 2018; this is the first annual review.
## Smart Guide

## The Annual Review is part of a continuous process of review and improvement and a formal control point in DFID’s programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed and the spending team needs to decide whether the programme should continue, be restructured or stopped. Teams should refer to the section on annual reviews in the Smart Rules and may also like to look at relevant Smart Guides e.g on Reviewing and Scoring Projects. When planning a review, re-read the 10 Delivery Questions in the Smart Rules and when writing the findings reflect anything relevant related to them.
The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in internal delivery plans.
The Annual Review assesses and rates outputs using the following rating scale. The Aid Management Platform (AMP) and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual output scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

## Teams should refer to the considerations below when completing this template. Suggested section lengths are indicative. Teams can delete spaces between sections on the template as needed, but the headings and sub-headings must not be altered or removed unless otherwise indicated in the template. Some reviews may need to be longer and others can be shorter (eg first year of a programme which has largely focused on mobilisation activities) – it is for the SRO and Head of Department to decide. All text needs to be suitable for publication. Bullets rather than full narrative may make sense for some sections.

A: Summary and Overview
Programme Code is the AMP I.D. number (same on Devtracker) / Enter risk rating (Minor, Moderate, Major or Severe) at the time of the review, taken from AMP / Describe the programme in 1-2 paras including what it is aiming to achieve. You might want to include headline points on changes in the operating context, partner performance, DFID management of the programme or other points relevant to the 10 Delivery Questions in the Smart Rules. / Describe –without repeating detail from Section B- progress in the past year and why the programme has scored as it has against the output indicators. Capture the key recommendations for the year ahead factoring in all the text from the report. You don’t need to include the detail of all lessons and recommendations from each output.
B: Detailed Output Scoring
Output Title, Number, Weighting, Indicators and milestones / Use the wording exactly as is from the current logframe. This will need to be entered on AMP as part of loading the Annual Review for approval. Indicate (Yes or No) if the impact weighting has been revised since last Annual Review and if Yes in which direction (up or down). Input progress against the milestone for this review
Output Score / Enter the rating (using the scale A++ to C) exactly as generated on the programme scoring calculation sheet
Provide a brief description of the output (unless obvious from the information in the box above) and supporting narrative for the score
Lessons and recommendations linked to this output. Some of these may inform or need to be included in the summary of recommendations on page 1. For anything that can’t be published please use the Delivery Plan
Repeat above for each Output in the logframe and add new sub-sections for additional outputs.
C: Theory of change and progress towards outcomes
Theory of Change (ToC). You might want to use a diagram to summarise it. You should flag any major changes in the past year. You should consider if the steps to achieving outcome and impact are still valid e.g. are the ToC logic, supporting evidence and assumptions holding up against implementation experience? Is there any new evidence which challenges the programme design or rationale? If relevant you might also want to flag any major changes since the programme started rather than just over the year in question.
Is the programme on track to contribute to the expected outcomes and impact? Review this in view of the overall programme score; but it is possible that outputs are being delivered but the envisaged outcomes or impact may not be achieved – or vice versa – and consider reasons for this. It is not unusual for programmes to be off track against at least some of the expected outcomes or impact: just set out what you plan to do about it. You should refer to the indicators in the logframe. Are there any unexpected outcomes emerging? Have there been any significant changes in the planned timetable for delivery of the programme? Are there any changes to expected outcomes or impact on gender equality compared to what was described in the approved Business Case?
Logframe. Describe major changes in the past year –including when they were made and why- and what their implications are for the programme. Ideally changes should not be made to any targets or indicators less than six months before they are being reviewed unless agreed with the Head of Department. All changes should be recorded as part of the programme’s documentation (there is a ‘change frame’ tab on the logframe template). If relevant you might also want to flag any major changes since the programme started. Flag any planned changes (impact, outcome, output etc) as a result of the review and once agreed at the approporiate level record them in the change frame tab.
D: Value for Money
VfM assessment compared to the proposition in the business case You should refer to VfM measures and metrics from the Business Case and/or previous annual review. Changes in cost drivers (e.g costs of major inputs) and the theory of change may be relevant. The assessment should encompass the 4 E’s of DFID’s value for money framework – economy, efficiency, effectiveness and equity, including gender equality (referring back to the relevant text in the approved Business Case’s Strategic Case may be relevant), disability and leaving no one behind.

Explain whether it makes sense to continue with the programme from a VfM perspective / Based on the above analysis of outcome and output attainment, theory of change, VfM and evidence analysis, is there sufficient evidence for the programme to continue, or should it be restructured or closed down? / You should also consider the programme as part of the wider portfolio in your department (e.g Business Plan) and if relevant for this document, DFID as a whole (e.g. Single Departmental Plan) or HMG as a whole

E: Risk

Provide an overview of the programme’s risk (noting the rating from page 1) and mitigation / Note the overall risk rating now as captured in AMP and on p1. Flag any changes to the overall risk environment/ context and how they impact on the programme, along with key risks that affect the successful delivery of the expected results. Use DFID’s standard risk terminology where possible eg categories of risk and risk appetite. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? Remember to take account of any relevant recommendations from Due Diligence Assessments on implementing partners. / Some relevant information may not be suitable for publication but ensure the risk register on AMP and Delivery Plan are updated as necessary following this review / Update on Partnership Principles. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four PPs over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
F: Delivery, Commercial and Financial Performance
Issues to consider for both the implementing partner(s) and DFID include: quality and timeliness of narrative reporting and audited financial statements; proactive dialogue on risks and updating of delivery chain maps; quality of financial management eg accuracy of forecasting; monitoring of assets. Consider also how DFID could be a more effective partner to help deliver the programme. / If there is a contract involved, set out: / Delivery against contract KPIs (and Terms and Conditions) / Compliance with the Supply Partner Code, where applicable, drawing on advice from PCD. / Compliance with the new cost and transparency requirements, where applicable (i.e. highlighting any profit variance and challenge and use of Open Book Accounting) / Performance of Partners. Where applicable, an annual summary of the new SRM scorecard assessment for each delivery partner involved in delivering this programme.
G: Monitoring, Evidence and Learning
Monitoring. / Summarise monitoring activities throughout the review period (field visits, reviews, engagement with stakeholders including beneficiary feedback) and how these have informed programming decisions. Where there is an external M&E supplier, how are they engaging with the programme implementer(s) and DFID. Briefly describe the Annual Review process itself including any inputs from outside the programme team (within or beyond DFID). / Evidence / Describe any changes in evidence and implications for the programme. Any relevant comments on the quality/breadth of the evidence. / Monitoring data, evidence and learning should consider the ‘Leave no one Behind’ agenda and as far as possible disaggregate information by age, sex, disability, geography (update geocoding information on AMP as needed) and other relevant variables. / Where an evaluation is planned set out what progress has been made. / Learning / What learning processes have been used over the past year to capture and share lessons, new evidence and know-how? / What are the key lessons identified over the past year for (i) this programme (ii) wider DFID and development work? / Any specific implications of that learning for this programme and priorities for follow-up in the year ahead may be best captured in the recommendations part of Section A / Do you have any learning aims for the programme for the coming year? / Progress on recommendations from previous review(s) / It is important to keep track of this. Some may not be publishable and feature in the Delivery Plan. But a brief update on progress against any recommendations from previous ARs (unless this is the first) should be provided