Project Completion Review – post April 2018

Title: Strengthening Emergency Preparedness and Response Programme (EPRP) in Kenya
Final Programme Value £ (full life): UK £2,915,000	Review Date: March 2019
Programme Code: 203768	Start Date: December 2014	Final End Date: December 2018

Summary of Programme Performance

Year	2015	2016	2017	2018
Programme Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.dfid.gov.uk/projects/GB-1-203768/documents
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-203768/documents

A. Summary and Overview
Description of programme and what it has achieved

Context: Kenya is prone to various emergencies that affect a large number of households. Most common among these are droughts (affecting mostly the Arid and Semi-Arid Lands (ASAL’s)), floods, disease outbreaks and urban disasters such as, terrorist attacks, fire outbreaks and election related violence.

The Emergency Preparedness and Response Programme (EPRP) implemented by the British Red Cross Society (BRCS) between 2014-2018, was designed to strengthen the Kenya Red Cross Society’s (KRCS) capacity on emergency preparedness and response. Specifically to: i) address gaps in KRCS’ systems and procedures; ii) embed and standardise ways of working; iii) enhance capacity of KRCS’s staff and volunteers in emergency management; and iv) promote a culture of learning. These activities were meant to contribute to reducing the impact of emergencies in Kenya.

Overall the programme scored an A, meaning ‘met expectations’. The main objective of EPRP was to build KRCS’ capacity and systems to respond to disasters in Kenya. This review finds that the EPRP met this objective as the KRCS was able to sufficiently respond to disasters such as floods that happened during the duration of the programme. For example, the KRCS would previously take three to four days to respond to disasters but, through the programme this has improved to a faster timeline of 24 hours. The programme reached 79% of people that were affected by disasters that affected more than 600 people.

Broadly, lessons learned from the programme were positive and include evidence to show that disaster preparedness is a better value for money approach than post disaster response approaches and that local capacity with the right training, is effective in responding to disasters. However, this review acknowledges that the programme mainly focused on building KRCS systems to respond to disasters, but more attention needs to be given to building Government systems to prepare and respond, including having in place disaster risk financing mechanisms.

In 2018, a Disaster Risk Management Bill was approved by the Cabinet and Senate (Upper House of Parliament) but is yet to receive National Assembly (lower house of parliament) approval. If passed, the law could ensure that GoK takes full responsibility for leading, coordinating and financing emergency response interventions. It is anticipated that the Bill could pass into law by the end of 2019. However, the procees is likely to experience delays due to a number of other bills that are also due for approval.

Description of Programme
The programme’s budget was £2.915 million over 2014-2018. This comprised a £965K contribution to the KRCS’s Disaster Management and Strengthening (DMS) Programme[1] and a £1,950 million contingency fund to enable quick, flexible support to emergencies. UK funding was channelled through the British Red Cross (BRCS), who provided technical assistance in financial management, reporting, programme design and implementation to KRCS. The programme was extended from May to December 2018 to contribute £1.2 million, unused from the contingency fund, to the KRCS for flood response.
[1] This programme helps improve the KRCS systems to prepare and respond to emergencies and help build GoK systems. ECHO, British Red Cross (BRCS) and the Finish Red Cross have provided wider support to the programme.

Some of the major disasters that happened during the programme period include: El Nino flooding in 2015, that affected 240,726 people; drought in 2017, where over 2.7 million people required food and nutrition assistance; violence related to the 2017 elections; flooding in 2018 and the Solai Dam tragedy[2], which displaced over 300,000 people; and several conflict and disease outbreaks.
[2] Floods following excessive rains in March 2018 preceded and led to the breaking of a privately-owned Dam near Solai. 70 million litres of water was released downhill and submerged homes over a radius of nearly 2 kilometres. In the aftermath 48 people were confirmed dead with over 2,000 people displaced.

In keeping with the UK’s commitments of “leave no one behind” and those made at the 2018 Disability Summit (co-hosted by the UK, Kenya and the International Disability Alliance), EPRP ensured inclusion of women and vulnerable groups including Persons with Disabilities (PWDs). This included through needs assessments and in the direct provision of assistance. Additionally, accountability to affected people was achieved through regular meetings with communities that led to collective decision making of relief assistance (what was required, how and when to receive it) and the establishment of effective complaints and feedback mechanisms that enabled beneficiaries to provide feedback about the assistance provided.

Major achievements of the DMS to which the UK contributed £965K included;
- KRCS was able to reach 79% of people reported to have been affected by emergencies described above. This marked a 34% increase from a target of 45% at the start of the programme.
- Development of effective Early Warning Systems (EWSs). These were used to disseminate early warning information to communities through a bulk short messaging service (SMS). Community members were able to further interact with the service to seek clarity on information provided through a toll-free line. A total of 1,591 calls were received between April 2017 (when the service was established) to December 2018.
- To further improve the EWSs,16 hazard and risk maps were published and disseminated. These helped in providing an analysis of risks throughout the programme.
- Improved efficiency. For instance, the KRCS Emergency Operations Centre (EOC) responded to 64% of disaster incidences that were recorded (up from 32% at the start of the programme). Also, upgrading of the Navision system[3] greatly improved the efficiency of the KRCS procurement and finance departments. This helped both departments generate prompt data for quick delivery of relief assistance.
  [3] The system generates instant reports on all financial and procurement matters. This increased control and accountability, for example all procurements can be tracked from issuance of Local Purchase Orders (LPOs) the delivery of commodities the KRCS warehouses.
- Improved capacity through the development of Standard Operating Procedures (SOPs). Six SOPs with clear roles and responsibilities were developed and disseminated to 286 staff and volunteers (32% female). At the end of the programme, 83% of KRCS staff reported improved capacity to prepare for emergencies, a significant improvement from the 53% reported at the start of the EPRP.
- A complaints and feedback mechanism was set-up to support community participation and accountability. A total of 395 complaints were received over 2015 to 2018, of which 84% were fully addressed within the KRCS SoPs.
- Coordinated joint assessments. 13 assessments were carried out and coordinated with GoK and other humanitarian organizations that included the UN agencies; UNICEF and UNWOMEN and various Non-Governmental Organizations (NGOs).
- Formation of the Red Cross Action Teams (RCATs). This innovation led to improved capacity of the Red Cross by having in place skilled volunteers to respond to emergencies. A total of 1,738 RCAT’s (38% female, 5% PWD) were recruited and trained in various roles such as search and rescue, psychosocial support, etc.
- A total of 270,372 people were reached with cash via a mobile digital platform (Mpesa) as compared to 20,000 in mid-2017. Cash was used to help families affected by disasters recover and rebuild their livelihoods.
- To support increased learning, KRCS published 17 articles (six external and 11 internal) and shared lessons learnt in 10 local and international forums.

The EPRP’s £1.950m contingency fund provided specific support to four emergencies -. These were:

El Nino floods: In 2015, Kenya received above normal rainfall that affected several locations in the North and Coastal parts of Kenya. UK support of £250K provided evacuation services, emergency shelter and medical supplies to affected people. As a result, 12,871 families (77,226 individuals[4]) were reached in Garissa, Wajir, Tana River and Taita Taveta counties. Additionally, the UK provided support to 67 camps for internally displaced persons (IDPs) and, in partnership with the World Food Programme (WFP), supplied 1,312 MT’s of food. In anticipation of good rainfall in some locations, 21,000 families (126,000 individuals) from farming communities were supplied with seeds for planting.
[4] This is based on an average of 6 individuals per household

Cholera outbreak: In 2015, 30 out of 47 counties in Kenya reported a total of 16,511 cases of cholera (including 254 deaths). The UK provided £200K to support prevention measures such as safe water and hygiene promotion to reduce the risk of transmission. Activities carried out by KRCS included decontamination of affected homes, distribution of water treatment chemicals and treatment. On treatment, KRCS set up 17 Cholera Treatment Centers (CTCs) in nine counties[5]. As a result, 482 cases were managed and discharged at the centres. Additionally, 1.4 million people including children in 123 schools were reached with cholera prevention information through the use of text messages. Furthermore, 509 KRCS volunteers were recruited, trained and equipped.
[5] Siaya, Migori, Baringo, Wajir, Tharaka Nithi, Garissa, Marsabit and Mandera.

Election preparedness: In 2017, Kenya experienced two election cycles. The General Elections in August 2017 and a Presidential re-run in October 2017. Historically, elections in Kenya are characterised by incidences of violence and displacement. In this regard, the Government of Kenya (GoK) had in place a contingency plan that projected approximately 300,000 people at risk. These planning figures were based on the 2007 heavily contested General Elections, where post-election violence led to the death of approximately 1,100 people and over 650,000 people were displaced. To prepare for the 2017 elections, the UK provided £300K to support KRCS to stockpile non-food relief items including tarpaulins, collapsible jerry cans, blankets, kitchen sets, portable latrine slabs and mosquito nets. Additionally, KRCS used UK funding to station over 100 staff and 1,000 volunteers in different locations to be ready to provide relief services. In the periods after both elections, KRCS provided emergency medical and evacuation services to 147 people (mainly injuries) affected by sporadic violence. Fortunately, wide spread violence and mass displacement did not occur and as a consequence, the majority of the stocks remained in store and were drawn upon during the 2018 floods.

Flooding in 2018: Kenya experienced severe flooding between March to May 2018, affecting 40 out of 47 counties. In May, KRCS launched a £3.5m appeal to deliver assistance to the first 150,000 [6]people displaced. The UK contributed £1.2m towards the appeal to support eight of the most affected counties[7]. As a result, 46,179 families (277,000 individuals[8]) were provided with temporary shelter, basic health & nutrition services and livelihoods recovery support. Specific results achieved included:
[6] KRCS has been mandated by Government of Kenya to provide assistance to the first 150,000 displaced of any disaster.
[7] Garissa, Isiolo, Tana River, Kilifi, Taita Taveta, Makueni, Kitui, Busia, Homa Bay, Siaya, Kisumu, Baringo and Kitui Counties.
[8] This is based on an average of six individuals per household

  1. 2,000 families (12,000 individuals) were provided with non-food items lost during the floods.
  2. 11 water supply systems were rehabilitated to restore clean and safe water to affected communities. Additionally,160 families (960 individuals) were provided with water pumps.
  3. 14,800 families (89,000 individuals) benefited from integrated health and nutrition services.
  4. 4,515 families (27,000 individuals) were provided with livelihoods recovery interventions that included repairs to irrigation systems and distribution of seeds and fertilizer.
  5. 2,010 families (20,060 individuals) received a one-off cash transfer through a digital mobile money platform (M-pesa) of Kshs. 13,100 (approximately £97) per family to restore livelihoods.
  6. 42 persons with disabilities were supported with assistive devices.

Follow up actions required following approval of this report:

- DFID to disburse the final payment of the programme.
- KRCS to provide 2018/19 annual audited financial statement.
- KRCS to provide quarterly reports on status of approximately £18K equivalent of unused non-food items (NFIs) at the close of this programme.
- DFID with wider British High Commission support to lobby for the Disaster Risk Management Bill to be approved by the National Assembly.
- Follow up with the DFID Kenya Governance and Security team on potential support for County Governments on capacity building on disaster management in any future devolution programming.

## B: DETAILED OUTPUT SCORING

Output Title	Increased KRCS capacity to prepare for disasters
Output number per LF		1	Output Score	A
Impact weighting (%)?		45%	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress	Indicator score
1.1 KRCS contingency plan developed and reviewed every 6 months	6 (1 plan developed and reviewed 5 times)	7(I plan developed and was reviewed 6 times)	A
1.2 Number of risk-hazard bulletins shared internally and externally	15	16	A
1.3 KRCS has systems and procedures to manage the funds raised from the public in order to respond to disasters.	1 (one guiding document)	1	A
1.4 Number of KRCS staff/volunteers (disaggregated by gender) trained and available to lead operations	67 (there was no baselines target for women)	122 (95 male and 27 female)	A++

Provide supporting narrative for the score

Key Points
This output’s main focus was to strengthen KRCS’ capacity to predict and where possible, prevent and mitigate the negative impact of emergencies. The output indicators are indicative of KRCS’ ability to prepare and launch a timely and appropriate response. This output is assessed to have met expectation and therefore scored an ‘A’.

  1. KRCS contingency plan developed and reviewed every 6 months: Contingency planning is an important step for risk management. During the programme period, a multi-hazard contingency plan was developed and reviewed bi-annually in March and September of each year. This indicator assessed the number of times the contingency plan was reviewed over the programme duration. With a target of five the indicator exceeded expectation as the plan was reviewed a total of seven times starting September 2015 and the last review happening in September 2018. However, the target was exceeded due to the programme end date being extended in May 2018. The contingency plan was developed collectively by KRCS’ headquarters, field and volunteer staff with the BRCS staff providing technical support. This was not only used by KRCS staff but was also a key reference document for the Government of Kenya (GoK) and other partners including UN agencies, donors, NGOs etc. In line with best practice, the plan was continuously monitored and tested through simulations. For example, emergency drills were carried out in 2015 and 2016 to determine if the plan was fit for purpose. This helped to capture key lessons that were used to inform the bi-annual review processes. One of the major findings of the simulation exercise was that the plan was mainly known to staff at headquarters. This helped the KRCS step up to disseminate and orient all field staff and volunteers of the contingency plan.

1.2 Number of risk-hazard bulletins shared internally and externally: 16 bulletins were developed and shared exceeding the set target of 15. This indicator is accessed as met expectations as the target was slightly exceeded because of the extension to the programme’s life span. The bulletins provided periodic analysis of impending risks and supported emergency preparedness. They were also used in the development and review of the multi-hazard contingency plan and were an important source of information for KRCS field staff and volunteers, and GoK and other key emergency responders. This review notes, that in some instances critical early warning information contained in the bulletins was not provided to communities. This compromised on their ability to prevent and mitigate the effects of a disaster.

1.3: KRCS has systems and procedures to manage the funds raised from the public in order to respond to disasters: In 2018, KRCS developed and approved a set of Disaster Fund Guidelines to help in manging funds received from development partners and for raising and managing funds from the public. Public fund raising is part of KRCS’s sustainability strategy and is intended to provide rapid support especially for small scale emergencies that often do not receive international assistance. The guidelines are anchored within KRCS’s Disaster Management Policy and all staff and volunteers have been provided with information regarding compliance. Although KRCS previously carried out public fundraising activities, this was happening with no set guidelines on how funds should be utilised. Without these, most funds were used for non-disaster related activities. The guidelines helped set a requirement that 10 percent of all funds raised should be used for disaster activities through a disaster management kitty. Since approval and roll out of the guidelines, 15 of KRCS’s 47 branch offices have raised an equivalent of £81K.

1.4: Number of KRCS staff/volunteers (disaggregated by gender) trained and available to lead operations: 122 (22% women) KRCS staff and volunteers from a target of 69 were trained to lead on emergency operations. As a result, KRCS has in place response team leaders stationed at the national and all branch offices. The over achievement of this indicator is attributed to complementary mentorship that was part of the design of the programme. Trainings were carried out through online and face to face courses. The on-line courses that were accessible to trainees include volunteer code of conduct, emergency needs assessments and personal safety. This were offered prior to face to face trainings that included practical courses such as on; first aid, communication, coordination and psychosocial support in emergencies. The trainings are standardised across the Red Cross movement and are ran by qualified trainers and staff. This helps to ensure quality of the trainings and consistency of the modules as the same content is available to all staff and volunteers.

Lessons identified this year linked to this output and recommendations for future programmes
Though the review acknowledges that KRCS has made commendable progress in the generation and dissemination of on early warning information through use of the risk-hazard bulletins, there is need to strengthen this further especially at community level. The DFID Humanitarian team while visiting communities affected by floods in 2018, were able to establish that most members did not receive any information of the impending flooding situation or of the overflow of the dams upstream. Without knowledge of the risks, most were unable to prevent or mitigate losses. This review recommends that KRCS put in place mechanisms to disseminate information generated in the risk bulletins to communities in an appropriate format.

Output Title	Increased KRCS response efficiency (time, money) and accountability
Output number per LF		2	Output Score	A
Impact weighting (%)?		35%	Impact weighting % revised since last AR?	N

Indicator(s)	Targets	Progress	Indicator score
2.1 KRCS has approved disaster response Standard Operating Procedures (SOPs) that it applies in emergencies.	SOPs developed	6 SOPs developed	A
2.2 Percentage of post-assessment responses which target the needs of 600 or more people where a formal feedback/complaint mechanism is set-up and implemented.	50%	64% / (16 out of 25)	A+
2.3 Percentage of post assessments responses which target 600 or more people where aspects of value for money is analysed.	50%	52% / (13 out of 25)	A

Provide supporting narrative for the score

Key Points
This output focuses on improved transparency and accountability: i) within the KRCS through the use of Standard Operating Procedures (SOPs) and Value for Money analysis; and ii) to beneficiaries through the use of a complaints and feedback mechanism. This output has been assessed as having met expectation and therefore scored ‘A’.

Indicator 2.1 KRCS has approved disaster response SOPs that it applies in emergencies: During the duration of the programme, six SOPs were developed on cash programming, mass casualty incidence, disaster management, emergency assessments, response preparedness and analysis, and livestock off-take. The SOPs were helpful in clearly setting out the roles and responsibilities for KRCS staff and volunteers. This enabled a structural re-organisation for both KRCS HQ and field operations and the SOPs have since been used as key reference documents in the management of emergencies. A case in point is the recruitment and training of specialised teams of volunteers. These teams known as Red Cross Action Teams (RCATs) are positioned at the KRCS branch offices and are the first line responders to any emergency. The teams comprise of roles such as psychosocial counsellors, first aiders, logistics, operational and search and rescue experts. Previously the KRCS would have to rely on staff from either their regional or headquarter offices. This in some cases would lead to delays in launching a response. The SOPs are in use in all 47 KRCS branch offices and to ensure their effectiveness the KRCS internal audit department conducts routine monitoring visits to evaluate utilisation of the SOPs.

Indicator 2.2 Percentage of post-assessment responses which target the needs of 600 or more people where a formal feedback/complaint mechanism is set-up and implemented: During the programme, KRCS responded to a total of 25 emergencies that targeted the needs of more than 600 people. Formal complaints and feedback mechanisms were set up and implemented for 16 emergencies (64% of the total and 14% above the target). To note, complaints and feedback mechanisms were not available to communities before the programme. Once set-up, the options to provide feedback included direct engagement with the communities through monthly community review forums and an anonymous channel through a toll-free line. A complaints register was also set up to track the complaints raised. This ensured that any feedback or complaints received were timely responded to. In addition, a dedicated staff (Accountability and Reporting Officer) was recruited to manage the system.

This review finds that KRCS’ capacity to engage with communities is enhanced within its operations leading to better delivery of assistance. For example, during the 2018 floods, a community-based methodology was used to identify beneficiaries for cash transfers. Additionally, under the shelter recovery programme following the 2018 flooding, which was financed by a £7.7m GoK contribution, recipients were consulted on the design, size, and type of materials for their houses.

Indicator 2.3 Percentage of post assessments responses which target 600 or more people where aspects of value for money is analysed: 13 out of 25 responses that targeted more than 600 people were assessed using the value for money matrix tool that was developed by KRCS. The tool is linked to the programme’s log frame and comprises criteria that can be monetised over different phases of the disaster management cycle, that include: i) mitigation (creation of awareness and community engagement); ii) preparedness (contingency planning, readiness of the response team, pre-positioning and early signs); and iii) response (activation of response, needs assessment and response coordination).
KRCS staff were trained on the matrix and how to use it by the British Red Cross. As a result, the use of the tool improved substantially from 33% noted in the 2018 DFID Annual Review to 52% by the end of the programme. A major change that the tool helped achieve, included the use of framework of agreements with KRCS suppliers to help guarantee the timely delivery of quality products. This review considers this a notable achievement given that KRCS was not using the value for money concept before EPRP.

Lessons identified this year linked to this output and recommendations for future programmes

There is need for KRCS to further improve dissemination of its SOPs. Although these have been accepted and rolled out up-to the branch level, the documents need to be made easily accessible. KRCS needs to explore ways of creating an on-line central registry that allows such critical documents to be easily accessible to volunteers especially given that that four out of six SOPs are meant to guide the volunteers in their ways of ways of working.

Output Title	Increased sharing of learning from KRCS preparedness and response operations
Output number per LF		3	Output Score	A+
Impact weighting (%)?		20%	Impact weighting % revised since last AR?	N

Indicator(s)	Milestones	Progress	Indicator score
3.1 Number of articles based on KRCS Disaster Management (DM) earning published in internal and external media	6	17	A++
3.2 Percentage of post-assessment-responses which target the needs of 600 or more people that are reviewed with reference to relevant Development Assistance Committee (DAC) criteria	80%	40% (10 out of 25 responses)	C
3.3 Number of fora (external) where KRCS DM lessons learned (positive and/or negative) are presented.	6	9	A+

Provide supporting narrative for the score

Key Points
This output recognises the need for learning and sharing as part of wider efforts of identifying and promoting use of best practices. KRCS exceeded targets under indicators 3.1 and 3.3. However, indicator 3.2 fell substantially below expectation as it later emerged that KRCS would not deliver as agreed due to limited resources. This output is assessed to have moderately exceeded expectation and therefore scored an ‘A+’.
Indicator 3.1 Number of articles based on KRCS Disaster Management (DM) learning published in internal and external media: A total of 17 articles were published including six papers that were shared externally. These include: 1) ‘From preparedness to rapid emergency cash transfer programming; Lessons learnt from Kenya Red Cross Society floods response’ and 2) ‘ Using Technology to Engage with Communities affected under El Nino’ both published in the IFRC website; 3) ‘KRCS Cash & Voucher programming process’; 4) ‘A buffer against drought (Use of equity bank to deliver cash to the most vulnerable communities in Turkana County)’; 5) ‘Use of Technology to reach vulnerable communities in hardship areas of Marsabit County’; and 6) ‘Kenya Drought Real Time Evaluation Findings’, all available at the Cash Learning Platform (CaLP) website: www.cashlearning.org.

11 articles were published internally through the KRCS E-Msalaba monthly newsletter. This indicator is assessed to have exceedingly met expectations and clearly demonstrates strong progress by KRCS in promoting a culture of learning. However, at the time of writing this review, DFID was not able to establish any examples of uptake of learning and how the articles may have had impact. However, the KRCS reported that the Bangladesh and Nigeria Red Cross Societies have improved their engagement and accountability with communities as a result of learning from the KRCS.

Indicator 3.2 Percentage of post-assessment-responses which target the needs of 600 or more people that are reviewed with reference to relevant DAC criteria: The DAC evaluation criteria[9] is an assessment that is used to determine the relevance of the response. KRCS experienced challenges meeting this indicator due to the high cost, time and capacity required to evaluate a response using the DAC criteria. To note, KRCS responded to 25 emergencies where more than 600 people were affected. 40% (representing 10 out of 25) were reviewed using the DAC criteria, whilst for all others an after-action review (AAR) approach was used. Use of the AAR[10] approach was recommended during the programme’s previous Annual Review as this was a simpler process.
[9] This is an evaluation that a set of five criteria used in assessing the relevance, efficiency, effectiveness, impact and sustainability of programmes.
[10] Is a structured review process for analyzing what happened?

The DFID team after close examination of the programme’s targets, concluded that the AAR – a structured review process of analysing what happened - would serve the same purpose as the DAC criteria in a less complex way. To note, that DAC was meant to give a much more in-depth analysis on the quality of the response based on its five criteria; relevance, efficiency, effectiveness, impact and sustainability. However, the AAR was able to provide a good analysis of what worked well and what did not. This helped the KRCS draw useful lessons for improvement, meeting the purpose for this indicator. The AARs were shared within KRCS for use by staff and helped change their emergency operations. For example, the decision to have community engagement forums as part of the feedback mechanisms and psychosocial experts as part of the response teams, were lessons generated by the AARs.

Indicator 3.3 Number of fora (external) where KRCS Disaster Management (DM) lessons learned (positive and/or negative) are presented. During programme implementation, nine forums were used to present lessons learned, majority from the articles outlined in 3.1 above. Some of these were: 1) The 8th African Evaluation Association International Conference (Kampala, Uganda in March 2017) where the ‘Evaluating[11] in Conflict and Fragile States; a case of KRCS’, was presented; 2) CaLP(Cash Learning Platform) East Africa Learning Event (December 2015 in Nairobi), where the ‘Institutionalization of CTP’ was presented; 3) CaLP level 2 training (in Harare, Zimbabwe, July 2016), where ‘From Preparedness to Rapid Emergency Cash Transfer Programming: Lessons Learnt from Kenya Red Cross Society flood response in the Huruma & Mukuru’ was presented;; 4) SAMEA Conference (Sandton, South Africa in October 2017) where the ‘Kenya Drought Response Real Time Evaluation Findings’ were presented. This helped increase KRCS visibility and in some instances, helped to raise additional funding for emergency responses.
[11] The paper explored the experiences by KRCS response teams during the twin epidemic (cholera & Chikungunya outbreak) in Mandera County.

In 2018, the UK, ECHO and US Office of Foreign Disaster Assistance were the biggest contributors to the KRCS floods appeal. Although this cannot be directly attributed to the lessons learned, it was a clear display of confidence of the three development partners of the KRCS capacity to deliver assistance. This capacity was partly as a result of utilisation of lessons learned. This review also notes that it was difficult to determine if the lesson learning had any other additional impact, however the KRCS reported that following sharing of lessons of their cash assistance programmes (partly supported by EPRP), they are providing technical assistance to similar Red Cross programmes in Ethiopia and Uganda. The need to provide such support was as a result of presenting lessons on cash programming in a number of external fora.

Lessons identified this year linked to this output and recommendations for future programmes
There is need for development partners to discuss and agree with implementing partners, the most suitable evaluation methodology – factoring in criteria such as value for money, objectives, existing evidence base etc. that are affordable and are ‘fit for purpose’. DAC evaluations proved costly (£15,000 each) and take time to complete.

## C: THEORY OF CHANGE AND PROGRESS AGAINST OUTCOMES

Overall assessment of whether the expected outcomes and contribution to target impact(s) were achieved

The outcome of the programme was ‘increased capacity of KRCS to prepare and respond to the needs of people affected by disasters’. This review assesses that the programme has achieved an overall score of ‘A’ met expectation.

This assessment is similar to an independent evaluation (commissioned by the KRCS) in 2018 that notes ‘The programme was strategic and relevant to the needs of the disaster affected populations, the priorities of the national and county governments as well as those of the partners. There was significant impact on its organizational systems, skills, knowledge and standardization of practice.’

Outcome indicator assessment

Outcome indicator 1	Baseline	Target	Achieved	Indicator score
Percentage of KRCS staff (disaggregated by gender) reporting improved capacity to prepare for disasters	Total: 0%	60%	83%	A++

Outcome indicator 2	Baseline	Target	Achieved	Indicator score
Percentage of population affected by disasters (reported to Emergency Operations Centre (EOC) reached by KRCS response	Total: TBD (baseline was not determined)	50%	64%	A

Outcome indicator 1: Percentage of KRCS staff (disaggregated by gender) reporting improved capacity to prepare for disasters. KRCS annual assessment carried out in June 2018, reported that 83% (76 male and 29 female) out of a target of 60% reported having improved capacity to prepare for emergencies. On the self-assessment staff were asked: (i) the extent to which their knowledge, skills and experience to prepare for different types of disasters has changed over time; and (ii) how the capacity of KRCS has generally changed to prepare and respond to disasters in the last three years. The significant increase in capacity can be attributed to investments that KRCS made in training of their staff throughout the programme. The various methods used included on-line, face to face, trainers of trainers’ approach, providing training at the regional and branch levels rather than nationally. The use of feedback received through post-training evaluations also led to the overachievement of the score. This indicator therefore scores an ‘A++’ outcome substantially exceeded expectation.

Outcome indicator 2: Percentage of population affected by disasters reached by KRCS response. This indicator captures the percentage of people affected by disasters who benefit from KRCS interventions. During the programme the Emergency Operations Centre (EOC[12]) recorded 6,958 incidences from the public that included fires, building collapses, road traffic accidents etc. Through EPRP support, this review finds that the EOC operations were strengthened. Reporting of incidences increased and quality of reporting greatly improved. This can be attributed to the training offered to KRCS staff and volunteers to collect, analyse and store information. Additionally, was the introduction of diverse ways of reporting incidences. For example, use of social media, a WhatsApp platform and a toll-free line. The increased awareness of volunteers and communities on use of the EOC also contributed to the increased incidences reported. There was coordinated flow of information amongst KRCS offices and staff and information sharing with stakeholders that ensured less duplication. The EOC is currently and recognised hub for disaster management operations and collaborates with other disaster focused agencies. For instance, in the 2018 floods the EOC worked with the National Disaster Operations Centre (NDOC) and the Kenya Defence Forces to provide evacuation services.
[12] This is a dedicated KRCS department that monitors disaster incidence via social media, mass media, toll free number etc.

The KRCS responded to 64% (4,453) of those reported. Despite this success, there were inconsistencies leading to possible cases of over or under reporting with a variance of plus or minus 10%. This happened in situations where multiple emergencies happened in one location or where a KRCS intervention had multiple components or where incidences were responded to by other actors including GoK, international agencies etc. The KRCS is working towards strengthening its documentation and reporting of the incidences. This indicator therefore scores an ‘A’ outputs met expectation.

To note, is that outcome indicator 2 only captures the numbers reached and not the quality of the response. During the programme a cumulative total of 6,609,753 million people were affected by disasters that affected more than 600 people. KRCS reached 5,267,598 million (79%). This marked a 34% increase from a target of 45% at the start of the programme. Although, KRCS increasingly met the needs of those affected by disasters, systematic improvements are required to continuously ensure and demonstrate that they are capturing the most in need in any emergency. Not all cases reported at the Emergency Operations Centre require this kind of assistance, hence the need for an indicator that captures the quality of the response.

Summarise the programme’s theory of change and major changes to it in the past year
The theory of change at programme design (see diagram below) envisaged an enhanced timely and effective KRCS response to small and medium scale emergencies. This would be achieved through: (i) an increased capacity of the KRCS to prepare and respond to disasters; (ii) a more efficient and accountable disaster response; and (iii) use of learning to improve its work and influence others.

INPUTS
OUTCOME
OUTPUTS

Establish a disaster surveillance system
Have clear policies, procedures and guidelines
Document best practise
An enhanced timely and effective Kenyan response to small and medium disasters

Increased capacity to prepare and respond to disasters
Efficiency and accountability in disaster response operations
Learning to improve work and influence others
The theory of change did not undergo any changes during the life of the programme and steps to achieving the outcome target remained valid throughout implementation. The theory of change hypothesised that having trained staff and volunteers who were able to respond to disasters, alongside functional systems (finance and logistics) and standardisation of practice, would enable timely and appropriate emergency responses. Following a disaster, this would also require the utilisation of 24hr and 72hr assessment tools and post-response assessments, including after action reviews. Together with beneficiary feedback, this would identify the most appropriate interventions to meet the needs of affected people and inform future responses. Additionally, improved and strengthened data collection and learning would allow for evidence-based learning for continued improvement of practice. Lastly, there was also an expectation that with robust systems and personnel, KRCS would be able to attract additional funding following building of its systems. This review finds that all the above assumptions were upheld.

The programme ensured that learning on topics such as gender mainstreaming and disability inclusion was incorporated into programme implementation. For example, 38% of volunteers recruited and trained were women, 119 volunteers were trained on disability inclusion and during response activities, deliberate effort was made to identify people with disabilities and provide them with appropriate assistance.

On value for money, the DFID Business Case assumed that this would be derived from investing in disaster preparedness, rather than post disaster responses. This review finds that this assumption was upheld with reports from the KRCS indicating that they were better prepared for example, for the 2017 elections as compared to previous election years. Through EPRP, KRCS was able to anticipate and pre-determine the needs of potentially vulnerable populations ahead of a disaster happening. For instance, ahead of the 2017 elections, the programme provided £300K to the KRCS to preposition non-food items and medical supplies to support 150,000 people if displaced. As a result, KRCS was able to respond within 24 hours to injuries and displacements. This when compared to a situation where one has to procure after a disaster has happened, could take up to 60 days especially for medical supplies. When compared to KRCS previous response times, this improved from 3-4 days prior to the programme.

Explain major changes to the log frame in the past year

There were no major changes to the log frame. During the programme, the log frame remained valid but only for the strengthening component of the programme. A key learning point that this programme takes forward, is that there should have been a separate output indicator for the contingency fund component of the programme. This would have enabled the programme to capture targets and achievements of the various responses that were supported. For instance, a separate results framework (see Annex A) was specifically developed for the 2018 floods but which should have been the case for other responses.

## D: VALUE FOR MONEY

Assess value for money compared to the proposition in the Business Case, based on the past year and during the lifetime of the programme

Overall, the programme represented good value for money scoring an “A”, meaning the programme met expectations. The Business Case noted that there is a strong evidence base globally that emergency preparedness and multi-year programming offer better value for money in meeting ongoing and anticipated needs, compared to annual post disaster approaches. This assumption as covered in the previous section proved to be true in the case of EPRP and the wider KRCS DMS programme.

At inception, the programme’s total budget was £2.5 million jointly financed by the Finnish Red Cross, ECHO, BRCS and DFID. DFID initially contributed £965K and at the end of the programme, the total DFID contribution was £2.9 million. This was as a result of additional contingency funding to: El Nino floods and cholera outbreaks in 2015 – totalling £450K; to election preparedness in 2017 totalling £300K and floods in 2018 totalling to £1.2 million. A decision to extend the timeframe of the programme by seven months was triggered by the 2018 floods and approved in May 2018.

Contingency funding provided to the various emergencies that happened during the programme duration, enabled the KRCS an opportunity to test its strengthened systems (developed under this programme) including SOPs developed.

Key costs
The programme’s main key costs were relief support (post emergency humanitarian aid) at 38%, personnel costs at 17% and training and simulation costs at 16%. The other drivers were admin support and associated costs; including security, monitoring and evaluation and staffing at 29%.

KRCS has a large geographical reach, covering all 47 counties in Kenya and with over 1,100 staff and volunteers (normally, volunteers are mobilised on a need to basis) across the country. The key cost drivers were broadly linked to location (some activities were in hard to reach counties), type of disaster, transport and security costs, accommodation costs and materials and supplies.

Management of these cost drivers was achieved through a number of approaches. For example: use of the trainers of trainers (ToT) approach (train a few to train others); using KRCS facilities rather than business facilities; holding trainings and simulation exercise within regions; use of pre-qualified suppliers; procurement through competitive bidding processes (where pre-qualified suppliers were not available); bulk procurement for commodities (especially for NFI’s); storage of commodities within regional hubs; and through use of GoK security services.

4 E’s of DFID’s value for money framework

Economy: Cost savings were obtained through smart procurement decisions. For example:

  - £22,360 was saved as a result of KRCS negotiating a downward transaction cost of £0.1 (Kshs.22) from the normal £0.2 (Kshs.33) with the mobile money service provider – Safaricom;

  - £120,676 was saved following negotiations for Safaricom to cancel all SMS associated charges for the provision of bulk messages and £15,800 through a tax waiver negotiated with the Kenya Revenue Authority for procurement of relief non-food items during the 2018 floods

  - £25,473 through direct cash transfers (using the Safaricom mobile money platform – M pesa) as compared to in-kind assistance. This was used as cash was determined to be cheaper and did not require additional logistic costs such as transportation and warehousing costs.

Efficiency: Overall, KRCS efficiency for providing emergency relief assistance has increased through use of more effective systems in their operations through for example:

  - The use of cash-based interventions in providing relief assistance. In places where markets were determined to be functional, the provision of cash ensured timely assistance and was appropriate by offering choice to the recipient.

  - The action of purchasing and holding non-food items stocks in the KRCS warehouses proved useful, as these were quickly deployed when needed. For example, stocks purchased ahead of the 2017 electioneering period enabled KRCS to provide assistance within 24hrs for the majority of the injury and displacements cases reported.

  - The SOPs developed by KRCS provided clarity on roles and responsibilities in emergency situations. This enabled quick and organised action by KRCS staff and volunteers. Additionally, the SOPs such as the ones developed for warehouse management, reduced wastage to a minimum, as only stocks that were needed (based on needs assessment) were released from the stores.

  - Use of KRCS RedRose system (an on-line registration portal) to register beneficiaries provided for speedy delivery as well as accountability of assistance provided.

  - The use of Navision, an online financial and stock management system, helped to fast track previously manual processes such as payment of staff allowances and to suppliers. In addition to proving an effective tool for accountability and transparency, approved transactions were completed within a day as compared to one week before introduction of the system.

  - Coordination of needs assessment processes through the use of the Kenya Initial Rapid Assessment tool (and its trainings) further reduced the duplication of processes by other humanitarian actors.

  - Use of the bulk messaging service (capable of sending out thousands of messages at one go) has greatly improved the dissemination of messages to communities and to KRCS staff, especially its volunteers.
Cost
effectiveness:	The programme was in most cases successful in preventing or mitigating the impact of emergencies, while also building KRCS local capacity to manage emergencies. This ensured that KRCS interventions were faster and more appropriate, contributing to saving more lives and alleviating human suffering.

79% of people affected by a number of emergencies over the programme period were provided with appropriate assistance, in most cases within 24hrs following an emergency. This was an increase of 34% compared to the baseline.

During the programme additional funding equivalent to £7.7 million was leveraged by KRCS from national and county governments, donors and corporate organizations to provide support to emergencies. To note, DFID’s support cannot solely be attributed to this achievement rather, a combination of various factors including improved capacity and systems within KRCS and the number of emergencies that happened requiring public appeal.

Equity:	The programme ensured the use of minimum standards for the protection of children, women, people with disabilities and the elderly.

Gender: Out of the 1,738 volunteers trained, 660 (38%) were women. The programme made deliberate effort to ensure that women were recruited as volunteers and were motivated to take on leadership roles through mentorship support. It is not clear how many women volunteers were recruited during the duration of the programme, but this review found that out of 130,000 KRCS volunteers across the country, 40% are women. Additionally, messaging to communities included messages on prevention and response to sexual gender-based violence (SGBV). For extremely vulnerable groups, dignity kits consisting of basic hygiene items such as sanitary pads, soaps, towels, toothbrushes etc were provided for both women and men.

Persons with disabilities (PWDs): Deliberate effort was made to ensure that PWDs were targeted and provided with appropriate assistance. For example, during the flood intervention in 2018, a total of 19 KRCS staff and volunteers were trained on disability inclusion and this was cascaded to an additional 100 volunteers. In the establishment of the specialized Red Cross Action Teams, there was a requirement that 5% be members who are PWDs. Activities also included supporting 42 persons with disabilities with assistive devices.

Vulnerable populations: During the programme, vulnerable groups were mainly identified as those with special needs such as PWDs and the elderly. This also included people who were not able to access health services after an emergency had happened. Targeting of this groups was done through a community-based approach (where community members were part of identifying who was most affected). This was confirmed through a post emergency monitoring exercise where 99% of respondents interviewed as having been recipients of assistance during the 2018 floods, felt there was no bias in the targeting and delivery of assistance. Aditionally, 152 integrated health and nutrition outreach services were carried out during the 2018 floods, where medical services were provided in communities that were most affected.

Despite the successes above, the review notes that more needs to be done, including: -

- A bigger push towards government led responses through concerted efforts by key stakeholders and development partners.
- Development of methodologies that can holistically measure the quality of KRCS’ responses.
- The need for KRCS to prioritise value for money reporting gaps so as to better understand efficiency of cash programming. Refer to section G: Progress on recommendations from annual reviews for this programme.

E: RISK

Overview of programme risk (noting the rating from page 1) during the past year and over the life of the programme

The EPRP was implemented over four years and identified risks were assessed as ‘moderate’ throughout. The majority of risks identified such as fraud in mobile cash transfers and election related violence leading to mass displacement and injury, did not occur. Moreover, inadequate mobile phone network coverage did not affect cash transfers as KRCS was able to deliver cash through contracted vendors to beneficiaries in areas where this was a challenge. To mitigate against fraud and to ensure only targeted people received the cash, beneficiaries were registered through a biometrics system. Severe floods in 2018 posed significant risk to the programme in terms of the capacity of KRCS and others to manage the impact. However, as this happened in the final year of the programme, KRCS’ systems were at an advanced level to cope effectively. KRCS has policies in place on Child Protection Policy and Protection Against Sexual Exploitation and Abuse. These policies are designed to help protect KRCS staff, volunteers and beneficiaries against harm and exploitation, while ensuring reported cases are handled effectively.

To effectively manage identified risks, the DFID Humanitarian Team had in place a robust risk management strategy. This was implemented through a series of actions and activities that included:

Funding to KRCS was through BRCS in tranches and arrears. This meant that UK support totalling £2.9 million was paid following delivery of agreed results.

Consistent engagement with the BRCS and the KRCS, including through cross-DFID office/agency field visits and regular meetings following reporting. For example, in September 2018 the DFID Humanitarian and Governance & Security teams visited Bomet County and in November 2018, the DFID Humanitarian team including the Human and Social Development Group Head visited Kilifi and Tana River counties, jointly with ECHO and the British and Kenya Red Cross. The visits helped ensure that activities supported under the programme were aligned to other DFID support and were also useful monitoring visits.

DFID programme staff also ensured continuous review of the risk matrix, escalation of risks and timely resolution. However, some of the risks led to delays even after solutions were found. For example, during the May 2018 floods, KRCS faced challenges in procurement of relief non-food items and medical supplies, mainly due to excessive demand. This challenge was escalated to the programme SRO and solutions agreed included for KRCS to use its own stocks of non-food items and later use UK support to replenish, once items were available in the market. KRCS’ learning from this, led to a change in their own procurement policy, for example enabling their pre-qualified suppliers to reserve a number of stocks for future use.

Reporting from BRCS on the programmes’ progress has been consistent and timely. This enabled DFID’s Humanitarian Team to identify and mitigate risks in a timely manner with the Red Cross. Additionally, the use of the risk bulletins helped in the periodic review of contextual risks to trigger the contingency fund.

The only outstanding risk of the programme is the challenge for KRCS to sustain gains achieved. This is due to inconsistent fund flows. This review identifies a number of potential actions to address this including: i) collective action amongst all stakeholders to help reduce duplication of key disaster management processes, including assessments and in the direct delivery of relief interventions; and ii) the passing of the legal frameworks that include the 2018 National Disaster Management Bill that seeks to coordinate all interventions and agencies that focus on the prevention and mitigation of disaster impacts in Kenya. The Bill received Senate (Upper House of the Parliament of Kenya) approval in 2018 and proposes the systematic coordination of all disaster response activities including national and county responsibilities and funding mechanisms to better prepare and deliver relief assistance. For instance, the Bill seeks to establish a Disaster Risk Management Fund where National Government will be setting aside money annually as well as a Country Government kitty for the same. At the time of writing this review, the Bill is in discussion at the National Assembly (Lower House of the Parliament of Kenya).

Update on partnership principles
No DFID funding was channelled through government financial systems. As such, DFID Kenya judged that the partnership principles did not apply in the detailed management and monitoring of the programme.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial, and financial issues

The DMS programme, jointly funded by DFID, ECHO and the Finnish Red Cross was managed by BRCS and implemented by KRCS. BRCS was responsible for the management and implementation of the programme and worked with KRCS as the implementing partner. BRCS’s role also included results reporting and financial management across the programme.

The EPRP, a component of DMS, was approved in December 2014 to enhance timely and effective responses to small and medium sized emergencies in Kenya. At inception, the programme’s budget was £965K with the figure rising to £2.9 million as a result of contingency funding to: El Nino floods and cholera outbreaks in 2015 – totalling £450K; election preparedness in 2017 totalling £300K and floods response in 2018 totalling to £1.2 million. A decision to extend the timeframe of the programme by seven months was triggered by the March – May 2018 floods and approved in May 2018. During the programme, no assets were acquired using DFID funds.

Overall financial management was satisfactory with milestone-based disbursements made quarterly in arrears. Programme spend to date is £2,069,723 representing approximately 70% of the total budget. The balance of approximately 30% is to be paid in arrears following satisfactory completion of the programme.

Forecast Vs Spend summary

Total programme budget	£2,915,000
	2014/2015	2015/2016	2017/2018	2018/2019
Forecast	£575,364	£437,637	£412,618	£1,489,381
Actual Spend	£574,364	£437,631	£382,514	£1,519,491

The KRCS through BRCS, has been able to report and offer clarification on all financial reports presented. Financial forecasting was timely and to a large extent near accurate. However, the flood response forecasts were inaccurate due to the procurement challenges highlighted earlier. However, this did not significantly affect DFID’s annual forecast and spend. No significant issues were raised in the independent audit reports during this period. The auditor’s opinion was unqualified implying that KRCS presented fairly, in all material respects, the actual expenditure incurred for the programme. The due diligence assessment confirmed that adequate systems were in place, thus scored a ‘low’ rating. The overall fraud risk rating on the programme was ‘moderate’.

The programme implementation had a slow start as envisioned in the Business Case, with full implementation starting in June 2015. This was informed by a lesson learnt from a similar DFID supported programme in Uganda. This was to enable the parties involved to be realistic over timescales to design and incorporate new systems, the need to further strengthen value for money measures and to not underestimate the risks to the programme.

Overall, this review finds implementation to have been timely and of good quality. During implementation, there were several emergencies that required KRCS action. This did not have significant impact on implementation of the KRCS capacity strengthening component of the programme, mainly because DFID working with the BRCS and KRCS teams, ensured risks were foreseen and resolved on time. The review notes that with a series of consecutive emergencies, the need for staff to assist whilst also implementing the strengthening component, in some instances minimised the efficiency and effectiveness of the programme. For example, during the 2017 elections, most KRCS staff and volunteers were deployed to areas away from their usual work stations, meaning they were not available to continue the day to day work on systems strengthening.

The use of KRCS as an implementing partner, ensured that optimum benefits were achieved. Reasons include; KRCS’ expansive network across the country supported reach to the most vulnerable and affected, and KRCS auxiliary role to GoK meant that they could engage and influence county governments’ policy framework on emergency management.

During programme implementation, a number of challenges were identified. These included: shortage in personal protective equipment and other equipment to deliver emergency assistance; delays in supply shipments and/or logistical bottlenecks due to market fluctuations; and a lack of sustainable income generating activities that leave the Red Cross dependant on aid. Such challenges exposed the programme to potential delivery risks such as those that have been identified for the 2018 floods. Staff turnover was also identified as leading to loss of institutional memory. In particular, this led to delays especially in DFID receiving final reports for the programme.

DFID maintained a close relationship with BRCS and this enabled quick resolution of programme risks. For example, during the floods, a decision to give cash to beneficiaries was made following a market analysis that on viability of cash, rather than provide in kind support. Also, DFID joined up with other development partners supporting the DMS programme to share learning and ensure accountability. For example, field visits were jointly carried out with ECHO to monitor the programmes progress and impact.

Sustainability: KRCS is a recognized first line responder to emergencies in Kenya and has over the years built its capacity to prepare and respond. Initially relying on donor funding, KRCS has evolved to now partnering with GoK and various private sector institutions. Some achievements that demonstrate this include;

- In 2018, KRCS received funding equivalent to £7.7 million from GoK – a first since KRCS’ establishment,
- KRCS co-chairs a cash working group with the National Drought Management Authority (NDMA) and which several development partners including DFID is a member of.
- Working with parliamentarians to advance the National Disaster Management Bill 2018. Progress on the development and passage of this Bill has been slow over the past 10 years as a result of a number of factors including changes in Government. If passed, this would be a breakthrough in Kenya’s approach to disaster management.
- The programme supported 21 county governments to develop disaster contingency plans.
- By May 2018, KRCS reported to have raised £81K locally from 15 counties and £950K from private sector partnerships.

Although these achievements point to success in KRCS’ own sustainability strategy, careful consideration should be made to ensure that this does not substitute for or undermine Government responsibility. There are a number of steps that can be taken to ensure that this does not happen: i) the passing of the National Disaster Management Bill. This will ensure that GoK commits itself to the creation of a National Risk Management Authority to coordinate disaster response measures in liaison with County governments. Also, in providing funds for disaster preparedness, mitigation, response and recovery measures; ii) the support of county covernments to have in place legislative frameworks for disaster management. All 47 counties in Kenya are prone to a number of disasters, more so, the 23 counties found in the Arid and Semi-Arid Lands (ASALs). With localized disaster management policies, counties can lead, coordinate and finance disaster management activities within their jurisdiction. At the time of review, the DFID Humanitarian Team is working with DFID Kenya’s Governance and Security team on potential support for county governments on capacity building on disaster management in any future devolution programming

Date of last narrative financial report	December 2018
Date of last audited annual statement	October 2018

G: MONITORING, EVIDENCE & LEARNING

Monitoring

EPRP had effective monitoring systems in place to capture progress against quarterly work plans and log frame indicators. Over the life of the programme, DFID worked closely with KRCS through BRCS to strengthen monitoring systems, including improving data collection tools and ensuring that the programme log frame was ‘fit for purpose’. BRCS maintained oversight of KRCS and submitted quarterly and annual progress reports to DFID, together with quarterly financial reports.

DFID’s Humanitarian Team carried out a number of field visits including with the DFID Governance and Security Team to interact with KRCS regional office staff, beneficiaries to assess the quality of interventions and to understand KRCS’s engagement with county governments and other actors. The second field visit, was a joint visit with ECHO and both the British and Kenya Red Cross. This was to monitor DFID support to the 2018 floods and to assess to what extent Government systems supported emergency management.

This Project Completion Review was undertaken in February and March 2019 by the DFID Kenya Humanitarian Team. The process involved: interviews with several key stakeholders in Nairobi (KRCS, BRCS, ECHO); and field visits in Kilifi, Tana River, Bomet, Makueni, Homa Bay and Kisumu counties. The latter involved meetings with county government officials, members of the private sector, KRCS field staff and beneficiaries. The DFID Kenya County Lead for Kisumu accompanied the team during the field visits in Kisumu and Homa Bay.

Evidence

An independent evaluation of the programme was concluded in December 2018 by Acacia Consultants Limited. The evaluation covered the entire programme period (December 2014 – December 2018) and to all eight regions where the programme was implemented. The regions were coast, lower eastern, north eastern, upper eastern, north rift, south rift, central and western. The evaluation assessed the impact, appropriateness, relevance, effectiveness and sustainability of the programme. It used both quantitative and qualitative approaches.

The evaluation concluded that the programme was strategic and relevant to the needs of the disaster affected populations, the priorities of the national and county governments as well as those of the partners. The evaluation also found that the programme had supported significant improvements to KRCS’s organizational systems, skills, knowledge and standardization of practice. For example, the Red Cross Actions Teams, establishment of SOPs were determined to have worked well. In terms of what did not work well, there was limited evidence of the uptake of the lessons learned,

Learning

Some of the key lessons identified from the programme include:

Building of Government systems: There is need for KRCS to gradually transition leadership and coordination of emergency management to GoK. Through the programme, KRCS has been successful in building its systems to deliver timely and effective relief assistance. However, this has over time been seen to seemingly replace GoK responsibility to lead, coordinate and finance emergency preparedness and response interventions. Whilst DFID acknowledges that KRCS is mandated by GoK as a first line responder to provide assistance to the first 150,000 displaced population of any emergency, their role has increasingly replaced the various GoK agencies. For example, the 2018 floods response was disparate with no clear lead or visibility from GoK at the onset.

Looking ahead, KRCS, must provide technical support to both national and county governments to lead and coordinate the various agencies and interventions on disaster management, including financing and in passing of legislative frameworks. To note, however, drought interventions are much better coordinated than floods and disease outbreaks and this approach should be replicated. Drought interventions are coordinated through the National Drought Management Authority (NDMA), established in 2016 through an Act of Parliament. This gives NDMA legal mandate to manage drought risks unlike, floods and other emergencies that struggle without a clear mandated authority. This review does not propose an authority for every risk but, advances the need for a one disaster management authority to be established as proposed by the Bill as set out in Sustainability section of this review.

Collaborative working on emergency management: To realise maximum value for money, there is need for collaborative action amongst humanitarian partners. It is important for partners to provide emergency relief within the sectors that they have comparative advantage or experience. The programme was able to draw on the strength of KRCS especially in providing shelter and non-food items to affected populations. However, the delivery of the health component during the 2018 floods was delayed due to challenges in procurement of medical supplies. In a future response, this could be resolved through partnerships with the Kenya Medical Supplies Agency (KEMSA) in the procurement of medical commodities and supplies rather, than in continuing with a parallel process. There is also need to step up collaborative working on key processes such as on the Kenya Inter-Agency Rapid Assessment (KIRA[13]). The KIRA has proved credible, effective and contributed to enhanced planning and increased coordination amongst humanitarian partners. However, the lack of resources (funds and staff) has meant that critical activities such as reviews of assessment tools, quarterly meetings and trainings don’t happen. Deliberate collaborative action is required to sustain the significance of KIRA’s contribution to emergency management.
[13] KIRA is a joint assessment mechanism that aims to provide timely information on humanitarian needs and support strategic decision-making in the early stages of a sudden onset emergency – both for anticipated events such as the elections, but also for unanticipated rapid onset events like conflicts and floods. The implementation of KIRA assessments is being undertaken by key humanitarian stakeholders including national- and county-level authorities and line ministries, the Kenya Red Cross Society, international and national NGOs, UN agencies, and faith-based organizations, in consultation with members of the affected communities.

Effective programme delivery: Overall the programme was successful in building KRCS systems to prepare and respond to emergencies. However, the programme experienced several challenges especially in providing relief assistance through the contingency fund. Having analysed these challenges, the programme identifies the following lessons:

- In the design of any future programme, KRCS should involve staff across its departments and offices. The EPRP was largely an organisational development programme that needed participation from all departments within KRCS. This review was able to determine that only technical staff were involved in the design of the programme. Other key departments such as Operations, Monitoring, Learning and Evaluation and field staff were left out. Greater results could have been achieved if such departments had been included.
- KRCS needs to ensure that effectiveness of using cash is improved through training of more KRCS staff and volunteers on cash programming. Use of the mobile money cash platform (M-pesa) was cheaper and more effective than in kind assistance. However, a number of challenges were experienced in 2018 when cash was given to communities to help in recovering their livelihoods. The DFID team visiting one of the communities receiving cash were able to determine that; relatively large amounts of cash were electronically received by many community members at the same time. This led to inflation of prices for assets such as goats that the families were required to buy as a condition of the transfer. Also, there was mixed messaging on the use of the cash. Some families bought the prescribed assets including farm equipment even when they did not need them.
- There is need for KRCS to fully operationalise its on-line stock management system. This would allow for easy monitoring and replenishment of stocks as and when needed.

Maintaining emergency response capacity: One of the key achievements of the programme was the establishment of the Red Cross Action Team (RCAT) that comprises 1,738 volunteers. This has created a local structure that is available to deploy during an emergency. However, KRCS has struggled to manage the high levels of attrition of the volunteers, weakening this critical response capacity. There needs to be deliberate effort in motivating the teams to ensure there is sufficient retention levels. This could be achieved through recruiting more RCATs as Trainers of Trainers and providing the necessary tools or equipment. Additionally, KRCS needs to consider providing employment opportunities to qualified RCATs and provision of some stipend to enable RCATs access to relevant on-line courses and to perform their role better (sharing information with communities and other responders through on-line platforms). Having said this, it is well noted that since this is a volunteer role and the majority are young people, they are likely to leave for other opportunities when and if they become available.

Progress on recommendations from annual reviews for this programme

Recommendation	Status	Responsibility	Timeframe
Given the timeframe of the programme, KRCS needs to focus on roll out and application of existing SOPs rather than developing new ones. For those that are under development, focus should be on reviewing and finalising them.	Since the time of review in 2017, KRCS did not review or develop new SOPs or guidelines. Instead, emphasis was on dissemination.	KRCS	Complete
To increase usage of the VfM template, KRCS needs to consider making it more user friendly whilst drawing on best practice. It should build a pool of VfM ‘champions’ that could be drawn upon for support.	The tool is now simple to use with limited technical support required. All departmental heads are value for money champions and as such has been institutionalized.	KRCS	Complete
It is important that the RCAT’s majority of who are the first responders are continually motivated. KRCS need to consider undertaking a review of the trainings offered to RCAT’s to ensure that they are appropriate and ‘fit for purpose’. KRCS need to ensure that all RCAT’s are provided with the requisite equipment (protective clothing) and resources (funds) needed for an effective response.	The trainings offered to RCATs now reflect the training needs assessed through a needs assessment. RCAT teams are mostly well resourced, though there is further remove for improvement.	KRCS	Complete
KRCS needs to build additional internal technical capacity on cash programming that can support cash responses. This will free up HQ focal points to focus on more strategic work rather than being absorbed in implementation work.	Capacity exists at the counties that can support cash programming. KRCS has a pool of RCAT who have been tested during responses such as drought and the recent flood- livelihood and shelter interventions. However, technical oversight from KRCS HQ is required.	KRCS	Ongoing
There is need for KRCS to standardise data collection for disaster responses, particularly for those targeting over 600 people.	Automation of the M&E/ MIS system is 90% complete. The system will ensure efficiency in data collection and reporting.	KRCS	Ongoing
There is need for KRCS to streamline and strengthen its data collection and learning across its different offices, staffing levels and its volunteer base to continuously improve on its practices. For example, sharing learning on good practice between RCAT’s, sharing lessons from simulation exercises and harmonising data held in the Emercency Operations Centre database with that held by the disaster management operations team.	Streamlining of data collection is ongoing. Completion of the M&E system will further enhance this. Learning has been embedded across the programme. RCATs and volunteers hold a retreat after every response to provide opportunity for reflection and learning to improve future responses.	KRCS	Ongoing
Using the DAC evaluation standard would be ideal. However, KRCS is experiencing difficulties with this due to the challenges raised above. KRCS should consider sampling a few that provide the essential quality assurance required rather than evaluate all. Additionally, KRCS should be encouraged to further strengthen the After Action Review practice.	AAR has been strengthened with a set of clear tools. This process has been localized at the branch level with technical support from HQ with the aim of empowering and building adequate capacity. DAC evaluation standard is the de facto standard for KRCS evaluations/ assessment due to their universal adoption as a best practice and as such KRCS will continue to strengthen its application and build adequate capacity.	KRCS	Ongoing
There is need for KRCS to undertake a value for money analysis to get a better sense of how efficient cash programming is as compared to in-kind support. It also needs to conduct a comparative analysis to better understand personnel cost savings achieved through use of local staff and its volunteer base.	This analysis was not undertaken given the nature of work that KRCS undertook in 2018 - responding to a number of large scale emergencies, drought and floods.	KRCS	Ongoing – without DFID funds
To assess the programme’s efficiency KRCS needs to undertake a cost per beneficiary analysis and how it compares with other emergency interventions operating in similar regions.	This was not undertaken. There is no concrete information on this for now. KRCS intend to undertake this in the near future and once comparisons are available.	KRCS	To be determined.

Annex A

Results framework for floods response

Outcome, Result area/ Output and / Activity name as per log frame	Outcome, Result area/ Output and activity indicator(s)	Level of Performance Target as per ITT	Achievement/Actual as per ITT
Result Area 1: Improved Shelter among flood affected population	Number of households supported with emergency NFI shelter kits meeting sphere standards	2,000 households	2,000 households
	Number of complete shelter NFIs Kits distributed	2,000	2,000
Output 1.1: Immediate shelter and settlement needs of the target population in affected areas are met	Proportion of people reporting satisfaction with the quality of the NFIs they received	80%	100%
Activity 1.1.1: Procure kitchen sets	Number of kitchen sets procured	2,000 pieces	2,000 pieces
Activity 1.1.2: Procure tarpaulins	Number of tarpaulins procured	4,000 pieces	4,000 pieces
Activity 1.1.3: Procure jerry cans	Number of jerry cans procured	4,000 pieces	4,000 pieces
Activity 1.1.4: Procure mosquito nets	Number of mosquito nets procured	4,000 pieces	4,000 pieces
Activity 1.1.5: Procure bar soaps	Number of bars of soap procured	4,000 pieces	4,000 pieces
Activity 1.1.6: Procure sleeping mats	Number of sleeping mats procured	4,000 pieces	4,000 pieces
Activity 1.1.7: Procure blankets	Number of blankets procured	4,000 pieces	4,000 pieces

Result Area 2: Rehabilitation of community water points	Number of community water systems rehabilitated	6	11
Output 2.1: Increased access to safe and clean water by the affected communities	Number of households having access to sufficient and safe water for domestic use	2,300 households	11,050 households (Approximately 66,300 people)
Activity 2.1.1: Conduct rapid assessment of the water, sanitation and hygiene situation in targeted communities	Number of affected counties covered by the WASH assessments	6 Counties / (Garissa, Kilifi, Isiolo, Makueni, Baringo, Kitui)	8 Counties / (Garissa, Kilifi, Isiolo, Baringo, Kitui, Tana River, Taita Taveta and Kirinyaga)
Activity 2.1.2: Rehabilitate water supply systems in (6 key systems to be prioritized)	Number of community water points rehabilitated	6 key water systems	11 key water systems
Output 3.1: Target population is provided with rapid medical management of injuries and diseases	Number of people reached through integrated health and nutrition services	41,622 people	89,031 people
Activity 3.1.1: Integrated medical outreaches conducted in displaced camps through deployment of mobile medical teams	Number of integrated medical outreaches carried out	Not determined	152 outreach sessions
	Number of community members reached during health outreaches	Not determined	22,017 people
Activity 3.1.2: Procurement of essential medical supplies for medical outreaches (including first line drugs for NCDs, NCD screening equipment, supplementary Inter-Agency Health kits (IEHK), basic IEH kits, non-pharmaceuticals, cholera kits, anti-venom, assistive mobility devices and dignity kits)	Number of supplementary Inter-Agency Health kits (IEHK) procured	3 kits	3 kits procured
	Number basic IEH kits procured	2 kits	2 kits procured
	Assorted non-pharmaceutical supplies procured	Assorted	Assorted supplies procured
	Number of cholera kits/ supplies procured	2 kits	2 kits procured
	Number of antivenom kits procured	1 kit	1 kit procured from over seas
	Assorted assistive and mobility devices procured	Assorted	Assorted devices were procured
	Number of dignity kits procured	1,000 kits	1,000 kits procured
Activity 3.1.3: Conduct integrated nutrition and health outreaches	Number of integrated nutrition and health outreaches done	60 outreaches	152 outreach sessions conducted
	Number of people reached (disaggregated by gender)	Not determined	22,017 people (8,987 male and 13,030 female) reached
	Number of people screened for malnutrition	Not determined	19, 795 people (7,401 PLW and 12,394 under-fives) screened for malnutrition
	Number of referrals made for management of acute malnutrition and other chronic ailments	30 cases of Emergency Obstetric care	No case was referred for obstetric care however 1,820 cases were referred for other ailments
Activity 3.1.4: Conduct health education sessions for awareness creation among the affected communities	Number of people reached	Not determined	85,828 people reached
Activity 3.1.5: Conduct debriefing sessions for staffs and volunteers involved in the response	Number of staffs and volunteers reached	Not determined	156 RCAT members reached (89 Males & 67 Females) (18 staffs and
Activity 3.1.6: Conduct psychosocial support sessions for people affected by floods	Number of sessions conducted	Not determined	42 sessions done
	Number of people reached	Not determined	1,473 people (671 males and 802 females) reached
Activity 3.1.7: Train response teams in Disability Inclusion and Humanitarian Hands on Tool (HHoT)	Number of response staffs and volunteers trained	90 staffs and volunteers	19 Red Cross Action Team (RCAT) members trained
Activity 3.1.8: Train front line health workers on data demand and use for disease surveillance	Number of front line health workers trained	100 people	94 frontline health care workers trained (43 males & 51 females)
Output 4.1: Household income is maintained for floods affected communities where income sources were disrupted	Number of households/people directly benefiting from improved agricultural production and/or food security and livelihoods restoration activities.	4,500 households (approximately 10,000 people)	4,515 households with approximately 17,360 people supported with livelihoods recovery interventions
Activity 4.1.1: Conduct livelihoods and markets assessment	Livelihoods needs of the affected community and market support systems are determined.	Carry out an integrated livelihoods and market assessment in West Kenya	Assessment done, and findings used to adjust the response strategy using cash transfer
Activity 4.1.2: Rehabilitation of irrigation schemes infrastructure/systems (purchase and repair of pumps, pipeline repairs, irrigation fittings)	Number of irrigation scheme infrastructure/systems rehabilitated	To be determined by the livelihoods and WASH assessment findings	9 irrigation schemes rehabilitated
	Hectares of farm lands under improved farming/agricultural methods
Activity 4.1.3: Procurement and distribution of seeds, fertilizers and pesticides for farmers	Number of households supported with sufficient seeds to plant including fertilizers/pesticides	2,000 farmers/households	2,345 farmers
Activity 4.1.4: Carry out one off unconditional cash transfer for livelihoods recovery in West Kenya	Number of households supported with one off unconditional cash transfer to replenish their livelihood support structures/assets.	2,500 households	2,170 households supported with one off unconditional cash transfer of ksh. 13,000 for each household
	Percent of households reporting satisfaction with the cash transfer they received	80%	99.7%
	Percent of beneficiary households using cash assistance for farm inputs	100%	100%
Activity 4.1.5: Procure and distribute water pumps to farming groups in West Kenya	Number of farming groups/households/people supported with water pumps for irrigated crop farming	To be determined by the livelihoods assessment findings	16 farming groups (10 in Homabay and 6 in Busia) each group consisting of 10 households translating into 160 households with a population of approximately 960 people supported
Activity 4.1.6: Conduct cash post distribution monitoring	PDM carried out after cash transfers	1 PDM	1 PDM done