Annual Review - Summary Sheet

Title: Contributing to universal coverage of Long Lasting Insecticidal Nets (LLINs) in Uganda to reduce the burden of malaria
Programme Value: £19,900,000		Review Date: November 2014
Programme Code: 203671	Start Date: 13 December 2012	End Date: 31 December 2015

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A+
Risk Rating	Medium	Medium

Summary of progress and lessons learnt since last review

In August 2014, Uganda marked the end of the universal net distribution campaign, the largest universal net coverage campaign anywhere in the world. Over 21 million Long Lasting Insecticidal Nets (LLINs) were distributed across the country with the aim being to get at least one net into each household, and on average one net for every 1.8 people in the country (Uganda’s definition of universal coverage). 4.45 million nets were procured for the campaign with UK funds. A further 1.6 million have been procured for routine distribution targeted to pregnant women and under 5s from now on. In addition, DFID funded the distribution of 12.1 million nets funded by other development partners including the Global Fund.

By the end of the campaign, it was estimated that 93% of people that registered for a net had received one. However, the population estimates used to calculate the number of nets required for the campaign were lower than the population turned out to be, resulting in fewer nets than were required distributed in Kampala and Wakiso. (DFID support to Uganda’s census will improve the planning of such programmes in future.) In addition, there were challenges with data management for the universal net campaign.

Behaviour change communication (BCC) activities were conducted to raise awareness on the benefits and care of LLINs. This included mass media campaigns on bill boards, radio spots and talk shows. While mass media campaigns are a good channel for raising awareness, interpersonal communication (IPC) to promote behaviour change, necessary for the utilisation and care of the LLINs could have been strengthened.

Summary of recommendations for the next year

To ensure utilisation and proper care of LLINs, there is need for concerted efforts in post distribution behaviour change communication with a big focus on interpersonal communication.

To ensure the most in need receive the 1,600,000 DFID funded LLINs that arrived in November 2014, it will be important to have a clear distribution plan that targets the poorest and most vulnerable.

Partners implementing IPC activities at the community level using tools developed by Communication for Healthy Communities (CHC) should remain accountable to CHC, providing information on population reached with messages on the use and care of LLINs.

Maintain quarterly monitoring and evaluation meetings following production of quarterly reports, with actions from those meetings listed and tracked.

Follow up recommendations from this annual review at quarterly meetings.

Ensure log frame updated every six months and updated version available on development tracker.

Ensure effective evaluation of the campaign, using data from UK-funded Malaria Indicator Survey.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:
DevTracker Link to Log frame:

Outline of the programme

Reducing the high levels of morbidity and mortality associated with malaria in Uganda will require sustained delivery of proven prevention and treatment strategies at scale. The three primary interventions recommended by WHO’s Global Malaria Project to tackle malaria are: a) distribution of insecticide-treated nets, more specifically Long Lasting Insecticide Treated nets (LLINs), to achieve universal coverage; b) indoor residual spraying (IRS) of houses to reduce and eliminate malaria transmission; and, c) diagnosis of malaria cases and treatment with effective medicines. Uganda’s inability in the past to take these proven anti-malarial interventions to scale means that malaria prevalence and malaria related deaths have remained high. DFID Uganda is funding all three interventions.

With support from partners, Uganda has prioritised universal LLIN coverage as a prevention strategy to decrease malaria related morbidity and mortality. By achieving universal LLIN coverage, Uganda will not only be able to protect the large number of people sleeping under these nets but may also be able to protect other households in the vicinity not using nets. Universal coverage and high use of LLINs would be likely to significantly reduce the burden of malaria in Uganda over the next three years which in turn would lead to wider socio-economic benefits through increased educational performance, reduced absenteeism from work and school, savings in healthcare spending and lives saved. To carry out this initiative, Uganda needed at least 21 million LLINs for an estimated population of 34 million. The Global Fund to fight AIDS, Tuberculosis and Malaria (GFATM) committed to providing 15 million LLINs; Government of Uganda (GoU) requested DFID support for the procurement and distribution of an additional 5 million LLINs while World Vision International committed to provide 500,000 LLINs.

DFID provided £19.9 million through a delegated cooperation arrangement with the United States Agency for International Development (USAID) to support procurement and distribution of five million LLINs, distribution of LLINs procured by the GFATM, as well as a behaviour change communication campaign designed to increase rational use of LLINs; and an evaluation that will seek to understand the impact of the campaign and what aspects worked well, to help other countries implement similar approaches. The original DFID budget at approval of the project in November 2012 was £17 million; however following a request from Ministry of Health in late 2013 to cover a gap in the distribution budget, an additional investment of £2.9 million was approved on 20 November 2013. This cost extension was to enable DFID to support distribution of an additional 4.5 million LLINs, procured by the GFATM. The programme is being implemented through two existing USAID partners; the Stop Malaria Project (SMP) and DELIVER (a private contractor) – various subcontractors, including the Malaria Consortium, were involved in distribution and behaviour change communication (BCC) activities.

The universal coverage campaign was launched on 10 May 2013 in Soroti district at an event presided over by His Excellency the President of the Republic of Uganda. Fifteen months after its launch, the end of the campaign was officially marked at a ceremony presided over by the President of Uganda. It is a major initiative of the National Malaria Control Programme (NMCP) of the Government of Uganda (GoU) and its partners, to achieve universal coverage of LLINs in Uganda. As per the World Health Organization (WHO) recommendations, LLINs were distributed at no cost to all Ugandan households through a one-off mass distribution campaign, and routinely thereafter to all pregnant women and mothers of infants during ante-natal and immunisation visits.

## PERFORMANCE AND CONCLUSIONS

Annual outcome assessment

The two main outcomes for this programme are: proportion of children under five who slept under a LLIN/ITN the previous night; proportion of pregnant women who slept under a LLIN/ITN the previous night. The outcome assessments will be conducted in future using results from the Malaria Indicator Survey (MIS) and the Uganda Demographic Health Survey (UDHS). The MIS is currently underway, co-funded by DFID, and the UDHS will be conducted in 2016.

Overall output score and description: A+

Based on the progress to date, the programme moderately exceeded expectation.
Achievements
Over 21 million nets were distributed in the just concluded universal LLIN distribution campaign, the largest attempt to achieve universal coverage with nets anywhere in the world. By the end of the campaign, it was estimated that 93% of people that registered for a net had received one. The national coordination of the campaign was impressive with strong leadership from the GoU and the involvement of key stakeholders including the Armed Forces that provided security during the distribution exercises. At the district level, district leaders were highly engaged through the district task forces which contributed to the success of the campaign. Over 110,520 Village Health Teams (VHTs) participated in the registration and distribution of the nets, sensitising communities on the benefits of the LLINs.
Challenges
The major challenge was the delay in net delivery and distribution. The former was caused by an upsurge in global net orders, with the result that net manufacturers could not deliver according to earlier estimated timelines. Delays in distribution were a result of delays in finalising the net distribution schedule and micro planning among major malaria stakeholders in the country. In some parts of the country, bad weather and a poor road network contributed to delays in the arrival of nets to final distribution points. In addition, there were challenges managing the large volumes of data generated in a timely manner. Lastly, the population estimates used to calculate the number of nets required for the campaign were lower than the population turned out to be resulting in fewer nets than were required distributed in Kampala and Wakiso. DFID support to Uganda’s census will improve the planning of such programmes in future, resulting in more efficient use of funds right across Uganda’s public service delivery.

The programme has been extended for one year to allow collection of data relevant to assessment of the effectiveness of the programme. This includes data from the MIS and a DFID funded evaluation currently underway.

Key lessons

The DFID/PMI joint programme on malaria has been an important avenue to strengthen donor harmonisation and effectiveness on influencing policy and malaria programming in Uganda. This was demonstrated by the role of DFID and PMI on the National Coordination Committee.

The Delegated Cooperation Agreement with USAID provides a good mechanism to enhance donor harmonisation and effectiveness, reducing DFID transactional costs. However it is not without its challenges. On some occasions, US policies have made it difficult to fund key activities conducted by government agencies and government officials resulting in delays in implementation of activities. In addition, it may reduce visibility of DFID. However, DFID’s ability to work more flexibly with government partners has also enabled us to significantly increase the effectiveness of substantial levels of funding from PMI (and also the Global Fund).

Bulk procurements with partners, particularly through existing procurement mechanisms offer an opportunity to produce cost savings and efficiency gains.

The management of data generated in a campaign of this magnitude requires a well-coordinated effort and to the extent possible automation (such as entry of data into tablets) right from the point of registration at the household level.

Key actions

To ensure utilisation and proper care of LLINs, there is need for concerted efforts in post distribution behaviour change communication with a big focus on interpersonal communication.

In anticipation of the next universal campaign, possibly in 2017, due consideration must be given to the set-up of an automated system linked to the data base created during the just concluded campaign. This will improve data management during the campaign reducing delays between quantification and distribution of the LLINs.

Distribution of the additional 1,600,000 LLINs should be done in a manner that ensures that the most in need, particularly in hard to reach areas with high malaria endemicity are targeted.

DFID to continue to engage actively in all programme fora to ensure DFID visibility including clear branding is maintained.

Work to begin now to identify source of funding for next universal coverage campaign or alternatively, most cost-effective alternative solution.

Has the log frame been updated since the last review?

No. The original project duration was for one year. However, in November 2013, the project was approved for further cost and time extension until 31 December 2014. The log frame was revised in November 2013, to reflect a cost and time extension reflecting results for the additional cost to the project to enable distribution of nets bought by GFATM. The expected impact and outcome did not change.

## C: DETAILED OUTPUT SCORING

Output Title	Increased ownership of LLINs
Output number per LF		1	Output Score	A+
Risk:		Medium	Impact weighting (%):	80%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress	Status
1.1 Proportion of households with at least one LLIN.	85%	93% of registered persons received an LLIN	Moderately exceeded expectation / A+
1.2 Number of LLINs procured and delivered through DFID support in 2013	9,650,000	16, 510, 326	Substantially exceeded expectation / A++

Key Points
Estimates from data collected during the campaign show that 93% of registered people received a LLIN during the universal net distribution campaign. This statistic will be triangulated with data collected during the recently completed national population census and the malaria indicator survey currently underway. These surveys will provide an accurate assessment of household ownership of LLINs.

Over 21 million LLINs were distributed during the campaign. 4,450,000 of these LLINs were procured with DFID funding, delivered in three consignments in December 2013, March 2014 and May 2014. In addition, DFID funding supported the distribution of an additional 12,060,326 LLINs procured by the Global Fund.

Savings on the procurement of nets has enabled procurement of an additional 1,600,000 LLINs with DFID funding. These nets were delivered in November 2014 and will be distributed through routine channels at antenatal and immunisation clinics to maintain universal coverage and protect vulnerable populations from malaria.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: The implementing partners should continue monitoring the pipeline to ensure that the distribution process continues to be carried out according to plan.
The population estimates used to calculate the number of nets required for the campaign were lower than the population turned out to be. Because of the gap in the number of nets, a collective decision was taken to rationalise and use targeting to cover the districts of Kampala and Wakiso, the last districts to receive LLINs in the campaign. This was based on the fact that Kampala has one of the lowest malaria prevalence rates in the country and net coverage in Kampala is higher than the rest of the country.

Recommendations

To ensure the most in need receive the 1,600,000 DFID funded LLINs that arrived in November 2014, it will be important to have a clear distribution plan that targets the poorest and most vulnerable.

## C: DETAILED OUTPUT SCORING

Output Title	Increased awareness of the importance of using LLINs
Output number per LF		2	Output Score	B
Risk:		Low	Impact weighting (%):	20%
Risk revised since last AR?		N/A	Impact weighting % revised since last AR?	N/A

Indicator(s)	Milestones	Progress	Status
2.1 Awareness among women age 15 to 49 years about the benefits of using LLINs	85%	Data will be available after MIS	N/A
2.2 Percentage of villages covered through community sensitisation drive during mass LLIN campaign	85%	93%* / *-To be triangulated with data from census and MIS	Met expectation / A

Key Points
As part of the LLIN registration exercise, Village Health Teams (VHTs) were trained and mandated to raise awareness on the benefits and the care of LLINs during visits to households. During distribution, one of the VHTs would demonstrate how to hang up a net and repair a damaged net. Some of the VHTs visited households after distribution to check that the nets had been hanged and to encourage those that had not hang them to do so.

From July 2014, through the USAID programme Communication for Healthy Communities (CHC), BCC activities were conducted to raise awareness on the benefits and care of LLINs. This includes mass media campaigns on bill boards, radio spots, radio and TV talk shows and DJ led conversations. Because of myths and misconceptions on the use of LLINs, formative research shows that IPC is the backbone of any communication campaign to increase utilisation of nets. This includes community dialogues and one on one discussion’s with VHTs. Over the next year, CHC will use a life stage approach that will incorporate messaging on malaria into a phased implementation of mass media campaigns on key health issues. Tools to facilitate IPC to promote LLIN use have been developed and are to be distributed to implementing partners across the country.

Summary of responses to issues raised in previous annual reviews (where relevant)
Recommendation: Implementing partners should continue to monitor data management through the established and now functional data centre.

Each district submitted the LLINs distribution forms (the primary data where beneficiaries signed) to the Resource Centre at the MoH for entry into a data base that would generate the final distribution data for the campaign. The main challenge was the delay in the setup of the database which led to accumulation of data and therefore the potential for entry errors was high.

Recommendations
To ensure utilisation and proper care of LLINs there is need for concerted efforts in post distribution behaviour change communication. Formative research points to the importance of interpersonal communication as a means to strengthen utilisation and proper care of LLINs.

Partners implementing IPC activities at the community level using tools developed by Communication for Healthy Communities (CHC) should remain accountable to CHC, providing information on population reached with messages on LLIN use.

In future, data should be entered into the data base as soon as each wave is completed to minimise errors and provide room for feedback/improvement for field teams in case field errors are detected during data entry.

In anticipation of the next universal campaign, possibly in 2017, due consideration must be given to the set-up of an automated system linked to the data base created during the just concluded campaign. This will improve data management during the campaign reducing delays between quantification and distribution of the LLINs.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE

Key cost drivers and performance

The main cost drivers were nets themselves, and therefore the procurement process and economies of scale that were used to drive costs down; and the logistics costs of distribution by the sub-recipient, Malaria Consortium.

VfM performance compared to the original VfM proposition in the business case

Savings on the unit cost of the LLINs from $3 to $2.79 resulted in the procurement of an additional 1,600,000 LLINs. These nets will be channelled through routine distribution at antenatal and immunisation clinics resulting in additional lives saved. These savings were made possible because of bulk procurement through USAID’s procurement partner DELIVER. Logistics costs rose slightly due to poor planning in the early stages of the programme and also the additional number of nets distributed by DFID.

Assessment of whether the programme continues to represent value for money

Pooled procurement of LLINs by DELIVER has been a key cost saver for the programme. Data from an ongoing evaluation of the net distribution campaign and the Malaria Indicator survey, both supported by DFID will assess the cost effectiveness (“efficiency” in the NAO VFM framework) of the LLIN campaign. This data will be available late next year and will provide additional data on the VfM performance of the programme. The inputs to the programme (“economy”, in the NAO VFM framework) have been exceptional value for money as demonstrated above by the drop in LLIN prices below the business case benchmark for nets, in spite of unprecedented global demand. And the “effectiveness” of the programme should be high, given the inclusion of LLINs on the GMP list of three priority interventions for tackling malaria.

Quality of financial management
All funding for this programme has been disbursed to USAID. USAID has delivered quarterly narrative and financial reports. USAID has continuously followed up with implementing partners on financial reports and shared them with DFID, including disclosure of realised savings from bulk procurement of nets. The savings were used to procure additional 1,600,000 LLINs. This indicates good financial management, open communication and follow up by the Lead Donor.

Date of last narrative financial report	USAID: January – June 2014.
Date of last audited annual statement	Not yet due.

E: RISK

Overall risk rating: Medium

Overview of programme risk

Fiduciary risk: there is a risk for misuse and theft of funds by downstream partners. However, USAID applies rigorous accounting processes to funds under their management, and seeks to recover any funds identified as misused.

Delivery risk: there have been significant delays in finalising the process evaluation (phase 1) of the net distribution campaign, a component funded by DFID. In addition data from the phase 2 of the evaluation will be necessary for an assessment of the impact of the programme. Therefore any delays in finalising the evaluation will significantly affect closure of the programme in December 2015.

Reputational risk: Misuse of LLINs distributed through this programme would bring DFID funding into disrepute. Lastly, while working through USAID brings enormous advantages, this too presents risks including decreased visibility of DFID.

Outstanding actions from risk assessment
1. DFID to maintain strong engagement with the MoH and other partners and manage effectively any risks resulting from policies of the US government and maintain DFID visibility.
2. DFID to maintain strong oversight on implementation of the evaluation of the campaign.
3. DFID to follow up on implementation of post distribution BCC activities to ensure that LLINs are used for the purpose for which they are intended.

F: COMMERCIAL CONSIDERATIONS

Delivery against planned timeframe
The LLIN distribution covering the entire country was completed in 15 months, three months more than the originally planned 12 months, due to unanticipated delays in arrival of the required LLINs and the long clearing process at the National Drug Authority (NDA). One of the reasons for the delay of net delivery was a fire at the manufacturing plant of one of the suppliers. DELIVER also indicated delays due to vastly increased demand for nets globally, which made lead times volatile and unpredictable.
The phase 1 process evaluation of the campaign is yet to be completed. With the MIS just getting started, the results of which will also be important in judging the impact of the programme, the programme has been extended to December 2015 to enable collection of relevant data.

Performance of partnership (s)
The DFID/USAID partnership played a key role in the universal campaign through the National Coordination Committee. Both DFID and USAID provided technical guidance and oversight instrumental in the implementation of the campaign. The partnership has produced efficiency gains in procurement of the LLINs resulting in a cost saving worth 1,600,000 LLINs. USAID downstream partners Stop Malaria Project, the DELIVER project and the Malaria Consortium brought good experience in delivering this programme.

Asset monitoring and control
Three laptops were procured with DFID funding: 2 by the Stop Malaria Project for the LLIN Programme Specialist and the LLIN Finance and Compliance Specialist; and 1 by Malaria Consortium for the LLIN Programme Coordinator. These assets are tracked in the partner’s inventory list detailing their specifications, date of acquisition, tracking number, location and the condition. Each of the laptop users signed for the laptop on receipt and is responsible for the asset. When leaving the organisation, the user has to be cleared after handing over the asset(s) in their possession to the office before their final payment. There is a high level of confidence in the management of programme assets by USAID.
G: CONDITIONALITY

Update on partnership principles

The last Partnership Principles assessment in May 2014 was agreed by the DFID team and the British High Commission. The Governance, Security and Humanitarian team have confirmed that there have been no significant changes since the last Partnership Principles assessment except for the repeal of the Anti-Homosexuality Act by the High Court.

While there is no financial aid through this programme, a one off funding was provided through UNICEF to cover the travel and accommodation costs of GoU officials to participate in an evaluation field trip the campaign. The SoS has agreed that we can provide funding to GoU systems via 3rd party organisations where we consider the fiduciary risks to be well managed. The total funding provided to GoU officials was approximately $785 and in line with UNICEF’s standard terms for support to government staff expenses. UNICEF has provided assurance on the checks and controls and the MDG Team is satisfied with the level of assurance that fiduciary risks have been well managed.

H: MONITORING & EVALUATION

Evidence and evaluation

Data from an ongoing evaluation of the net distribution campaign and the MIS, both supported by DFID will be discussed with the NMCP, DFID and USAID as well as at the Roll Back Malaria Forum to identify, agree and implement actions to improve programme implementation. This information will also be shared with other countries, including through publication in peer reviewed journals.

Monitoring progress throughout the review period
Support supervision visits were conducted for all waves (I – VIII) to selected distribution sites including stores at all levels i.e. district and sub county during net distribution. DFID participated in the National coordination committee meetings that provided oversight and guidance for implementation of the LLIN universal campaign. In addition, beneficiaries of the campaign were visited in Bulambuli and Wakiso districts. This included discussions with VHTs involved in the net distribution campaign.
DFID has put in place quarterly meetings which bring together DFID, USAID and the GoU to discuss issues pertinent to the programme including: progress towards attainment of agreed milestones for the year, risks and their management and financial updates. There have been three quarterly meetings in the last year. USAID provides a quarterly report for monitoring purposes, including a summary of activity and spend. In addition there are more regular informal contact between DFID, USAID and GoU.

DFID Annual review: 24th November – 28th November 2014

The review was conducted by the DFID Uganda MDG team. It was based on a desk review of the business case, logframe and monitoring and reporting documents as well as key stakeholder meetings. Meetings were held with Ministry of Health, GFATM Focal Coordination Office, Malaria Consortium, CHC, Global Fund Focal coordination office, USAID/PMI and Stop Malaria Project.