DFID - Annual Review of the Government of Uganda/United Nations Joint Programme on Population

Tony Daly
December 2014
List of abbreviations
ADPR	Annual District Performance Report
AR	Annual Review
BEONC	Basic Emergency Obstetric and Neonatal Care
CoC	Continuum of Care
CPR	Contraceptive Prevalence Rate
CSO	Civil Society Organisation
CYP	Couple Years of Protection
DDP	District Development Plan
DFID	Department for International Development
EmONC	Emergency Obstetric and Neonatal Care
FP	Family Planning
GoU	Government of Uganda
HC	Health Centre
HMIS	Health Management Information System
HRH	Human Resources for Health
IEC	Information, Education and Communication
ILO	International Labour Organisation
JPP	Joint Population Programme
LMNA	Labour Market Needs Assessment
LFS	Labour Force Survey
LMIS	Labour Management Information System
MAG	Male Action Group
MH	Maternal Health
MMR	Maternal Mortality Ratio
MNM	Maternal and Neonatal Mortality
MTR	Mid-Term Review
M&E	Monitoring and Evaluation
MoH	Ministry of Health
MSU	Marie Stopes Uganda
NAPYE	National Action Plan on Youth Employment
NDP	National Development Plan
NMS	National Medical Stores
NPP	National Population Policy
OR	Operational Research
RHU	Reproductive Health Uganda
UDHS	Uganda Demographic Health Survey
UNFPA	United Nations Population Fund
UNICEF	United Nations Children’s Fund
WHO	World Health Organisation
VfM	Value for Money
YFC	Youth-Friendly Corner
YFSs	Youth-Friendly Services

Executive summary
An agreed time extension to the JPP has necessitated an annual review. With all DFID funds already transferred to UNFPA, and the independent evaluation being the only substantive activity remaining, there is limited scope for an AR to influence programme delivery. Therefore this AR was relatively light-touch and focused its recommendations on the forthcoming evaluation and potential future funding to population activities. A Project Completion Report will be started in July 2015 after programme end.
Managing Uganda’s population is a major developmental priority. Unmet need for family is very high, as is unemployment and the demand for labour with the right skills. The JPP focuses on fertility reduction, maternal health, youth employment and population policy and planning. Progress has been made in all areas. Not all targets are likely to have been met, but there are sufficient results to score the project an A – outputs met expectations. Most recommendations from the 2013 AR have been implemented, except those requiring data collection and analysis which have largely been incorporated into the evaluation commencing now.
Recommendations are as follows:
Evaluation
1. There are potential areas for evaluation that would inform future scale up that are not apparent in the evaluation TORs. Explicit mention in the TORs should include:
  1. The implications of the differences in methodology for the baseline and MTR should be highlighted to evaluation bidders and carefully considered when deciding on the methodology.
  2. Comparison of whether district planning interventions resulted in i) better informed planning decisions; and ii) increased resources for population activities.
  3. MAGS should be included in the VFM analysis in 5.2; but also the range of youth interventions (corners, educators, youth outreach) should be included under ‘youth friendly services’.
  4. The main report should also include operations research recommendations for scale up of interventions.
  5. Analysis and recommendations should include costing of scale up and comments on affordability and feasibility.
  6. Recommendations in general should be with reference to the national Costed Implementation Plan (for family planning in Uganda) and the Sharpened Plan (for reproductive and maternal health services in Uganda).
New programme
1. Any new programme should ensure:
  1. It builds on the lessons learned from the evaluation and other commissioned studies by DFID.
  2. Data for VFM analysis agreed in advance so that data is available when needed.
  3. The impressive policy gains are consolidated and built on, with continued advocacy and data generation.
  4. Implementation learning is integrated into delivery planning.
  5. If a UN joint programme is selected as a delivery mechanism, that DFID capacity is sufficient to mitigate performance risks.
Introduction
With an average per capita income of around US$600, Uganda remains a very poor country and far from middle-income status. In 2012, Uganda ranked 161st of 187 countries on the Human Development Index. From 2008 until 2013, the Ugandan GDP annual growth rate averaged 5.2%. Subdued export performance, high inflation and subsequent tightening of the monetary policy to restore macroeconomic stability reduced GDP growth to 3.4% in 2012. GDP growth rose from 3.4% in 2012 to 5.2% in 2013. To achieve better development outcomes, Uganda’s economy has to be transformed so as to reach a higher productivity level. This transformation will hinge on how the country manages its resources, in particular the fast-growing and youthful population. To reap the demographic dividend, Uganda must invest in fertility reduction, among other things.

Uganda has one of the youngest and most rapidly growing populations in the world. The provisional results of the 2014 Census estimate the current total population at 34.9 million[1]. With a total fertility rate estimated at around 6.2 children per woman, the country’s population growth rate is currently at 3.03%. The fertility levels are higher in rural areas compared to urban areas with 6.8 and 3.8 respectively. Over half of Uganda’s population is younger than 15, well above Sub-Saharan Africa’s average of 43.2% and the world average of 26.8%. The very high youth dependency ratio represents a major challenge for Uganda in the short and medium term.
[1] National Population and Housing Census 2014, Provisional Results, November 2014, UBOS
Uganda’s maternal mortality ratio (MMR) has remained relatively high, although decreasing from 505 deaths per 100,000 live births in 2001 to 438 deaths in 2011. About 44% of all pregnancies are unintended, with unsafe abortion representing around 30% of maternal mortality[2]. The burden of unwanted pregnancy and its consequences disproportionately falls on poor women and adolescents. The national panel survey in 2012 showed that the contraceptive prevalence rate (CPR) has increased from 24% to 30%.[3] However, there is still a large unmet need for FP of around 34% and thus there are opportunities to increase the uptake of modern FP. The Uganda Demographic Health Survey (UDHS) (2011) found the teenage pregnancy rate to be 24%, and that by 15 years of age 30% of young women have had sex and by 18 years of age it has risen to 72%; this suggests that information on safe sex and modern FP is needed early so young girls are able to make informed choices.
[2] Uganda Demographic Health Survey (2012). Uganda Bureau of Statistics.
[3] Uganda National Panel Survey WAVE 111 (November 2013). Uganda Bureau of Statistics.
The JPP
The goal of the JPP is to accelerate the onset of beneficial demographic transition in Uganda. The purpose is ensuring that the national, community, cultural and issue-based leaderships are managing the acceleration of a downward trend in population growth. The JPP supports the Government of Uganda’s (GoU) National Population Policy (NPP) and National Development Plan (NDP). The programme is now being implemented in 19 districts (which includes the recent inclusion of four districts in the East) through nine UN agencies, and the funding is managed by UNFPA.
There is a steering committee on which there are representatives from all sector ministries, all the heads of the UN agencies and DFID. It is chaired by the Population Secretariat and the UN Resident Coordinator. It meets every six months, discusses performance and approves work plans and budget allocations. There are four output technical working groups, each chaired by the lead agency for that output. These groups meet regularly to oversee implementation and the JPP carries out joint field visits twice a year. There have been three DFID ARs so far and the JPP received the following scores:
- 2011 (3) – purpose is unlikely to be met; and
- 2012 (B) – moderately did not meet expectations
- 2013 (B) – moderately did not meet expectations
After the second B score, a Performance Improvement Plan was agreed. A baseline survey was carried out by the JPP in 2012 but it only covered eight districts. In 2013, an MTR was carried out covering 15 districts. This MTR used a methodology that is different to that used during the 2012 baseline, which had presented a problem in defining the JPP baseline. As the MTR covered 15 districts, it would seem that it should be used as a baseline for the final evaluation in 2015, using the 2012 data as additional information.
An agreed time extension to the JPP has necessitated an annual review. With all DFID funds already transferred to UNFPA, and the evaluation being the only substantive activity remaining, there is limited scope for an AR to influence programme delivery. Therefore this AR was relatively light-touch and focused its recommendations on the forthcoming evaluation and potential future funding to population activities.

# 2. Report against the logframe
## Output 1: Fertility reduced in line with choices of individuals and couples (especially young people)
Output 1: Score and performance description – Score B

Output 1 has three indicators, none of which could be measured during this AR. The score has to be based on likelihood of achieving the target. Progress with activities has been used to inform this judgement and is described below.
Output 1: Progress against indicators
Indicators	Baseline	Milestone / (Jan 2014– Dec 2014)	Achieved [4] / (Jan 2013–Nov 2013)
1.1 Proportion of young people (10–24 years) with accurate information on use of contraceptive pills, male condoms and emergency pills in target districts.	N/A	15%	N/A / Below target in 2013 AR.
1.2 Number of Health Centre (HC) IIIs and HC IVs providing youth-friendly services (YFSs) in target districts.	4 (HC IV) / 0 (HC III) / (UNFPA report 2011)	15 (HC IV) / 80 (HC III)	N/A / Exceeded target in 2013 AR.
1.3 Proportion of health facilities in target districts without stock-outs of the three most commonly used contraceptive methods (pills, male condoms, depo-provera) in the past three months.	N/A	75%	N/A / Almost met 2014 target in 2013, but current stock out of pills.
[4] Government of Uganda/UN. JPP Mid-Term Review (September 2013). Centre for Sustainable Development. Aberdeen.

1.1 Proportion of young people (10–24 years) with accurate information on use of contraceptive pills, male condoms and emergency pills in target districts:
Provision of information to young people was accelerated. 24 facilities and 18 schools increased the number of female peer educators. IEC materials were translated into local languages. Community dialogues took place. Peer educators were employed by some facilities for casual labour to help with retention. Almost 300,000 young people have accessed SRH messages and services so far in 2013. Without population denominators and equivalent numbers from last year, it is difficult to estimate whether this represents an increase and by how much. The project was substantially off-track last year and there is nothing to suggest a dramatic step-change in intensity of activities (provisional sub-score B).
1.2 Number of Health Centre (HC) IIIs and HC IVs providing youth-friendly services (YFSs) in target districts:
Given last year’s targets were substantially exceeded and assuming the trajectory has continued, then this target is likely to have been met (provisional sub-score A+).
1.3 Proportion of health facilities in target districts without stock-outs of the three most commonly used contraceptive methods (pills, male condoms, depo-provera) in the past three months:
This target was exceeded last year, but at the time of this AR, Microgynon was not available at facility level. Stocks at national level to fill the 2015 year’s needs have been received so this indicator is likely to be achieved by project end (provisional sub-score A).
Conclusion: Score B as 2/3 targets likely to have been achieved. This is a conservative judgement.

### Progress against recommendations in the 2013 AR
There were five recommendations in the last AR:

Output 1 Recommendations	Implementation
Carry out analysis of each district, identifying successes and challenges, so that the programme can build on what is working. This should be done before preparing the 2014 annual work plan.	Not done. District analysis to identify successes and challenges to build on what is working, was not done and is to be incorporated into the evaluation.
The JPP should radically review its approach to increasing knowledge in young people to develop a joined-up approach between UN agencies and across the 15 districts, including: / An assessment of why Oyam and Kitgum have done so well in terms of increasing knowledge levels; / Formative research to understand the messages and channels for reaching young people at scale with accurate information, including a review of the impact of the Healthy Choices radio programme; and / The production and distribution of IEC materials in local languages by January 2014.	There has been much improvement in a joined-up approach. The same guidelines have been adopted by all; approaches related to community involvement, support to youth friendly services have been standardised; the same equipment has been provided to all 15 districts, and providing common guidelines and messages to MAGs has been achieved. / Formative research was not done. / IEC materials have been translated into local languages and have been distributed, but not yet reached all HCs (they were not available at the HC visited by the AR team).
Spending on YFCs should be suspended. Retrospective operational research (OR) (including on VfM) should be carried out on the various models of YFSs/YFCs and this information should be used to scale up YFSs and inform future practice in the 15 districts and nationally by June 2014.	Retrospective research not done, but has been incorporated into the evaluation to inform future work with young people.
WHO should work with the MoH to ensure that YFS training becomes part of pre-service training (based on lessons learnt from the OR).	This has been largely achieved, though not informed by the OR. Adolescent SRH has been integrated into courses provided by Makerere University, and tutors from 23 training schools have been trained; but official curriculum adoption remains outstanding.
The training of health workers in FP should be scaled up at all levels of the health system and there should be a discussion of the benefits of distributing LTFP commodities at lower levels of the health system.	It is expected that 120 health workers will have been trained in FP by the end of 2014.

Although much of the research and analysis has not been done, what has been included in the evaluation TORs will be of use for future programming.

## Output 2: Prepared, protected and healthy mothers, children and youth
Output 2: Score and performance description – A

Output 2 has two indicators, both of which met expectations.
Output 2: Progress against indicators
Indicators	Baseline	Milestone / (Jan 2014 – Dec 2014)	Achieved / (Jan 2014–Nov 2014)
2.1 Number of girls retained in school through the secondary bursary programme	0 / (2010)	1,000	1,000 (including those who have completed)
2.2 Proportion of deliveries occurring in health facilities in the 15 target districts	31% / (HMIS 2010/11)	50%	49% (estimated from Jan-Oct 41%) / HMIS 2014

2.1 Number of girls retained in school through the secondary bursary programme
This activity is on-track. UNICEF negotiated to pay the schools in advance for next year to ensure the JPP’s end date does not impede completion. 896 scholarships will continue into 2015. UNICEF is exploring how to source funding to support the beneficiaries post bursary (provisional sub-score A).
2.2 Proportion of deliveries occurring in health facilities in the 15 target districts
Based on the Jan-Oct result of 41%, a proportionate increase covering the remainder of the year suggests 49% will be achieved by year end. Additionally, there is probably delay in some reports being submitted for October, giving a significant likelihood that this target has been met/exceeded, assuming deliveries Nov-Dec are not usually lower than the average across other months. Regarding service effectiveness, the number of caesarean sections has increased in the target districts, which is encouraging, but disaggregated data for non-intervention districts was not available for comparison. The HCIV visited were conducting caesarean sections, but insufficient data precludes drawing any conclusions.
Alongside service delivery support, an RMNCH prioritised plan has just been finalised: A Promise Renewed: RMNCH Sharpened Plan for Uganda. It is based on a bottleneck analysis, is prioritised, includes many innovative activities and addresses many service delivery bottlenecks. It emphasises high impact cost effective interventions and focuses on population groups and geographical areas. Although some capacity supplementation is included such as Assistant District Health Officers, and score cards are included for better accountability, it is not so clear where the substantial additional funding will come from, and whether a higher level of accountability will be achieved. An excellent document, but perhaps needs to be followed up with demonstrable commitment from a high level within the MOH (provisional sub-score B).
Conclusion: score A, both targets met or likely to be met.
### Progress against recommendations in 2013 AR
There were two recommendations in 2013, both largely implemented.

Output 2 Recommendations	Implementation
The JPP strategies need to be more joined up between the UN agencies and across the 15 districts along a CoC. Provision of support to health facility deliveries should be organised along a CoC and the JPP should increase the training in BEmONC and Comprehensive EmONC to ensure that quality maternal services are provided in all 15 districts by the end of the programme. In addition, through the CoC opportunities to integrate FP services should be sought so as to increase the uptake of FP.	The field trip and key stakeholders confirmed that a) common approaches/interventions across all districts were adopted/implemented, regardless of which UN agency was leading; and b) FP has been integrated into maternal health, to an impressive extent in the HC IV that we visited.
WHO should take an increased role in advocating and supporting the implementation of the HRH strategy, particularly the aspects of the strategy that will improve redistribution of the existing workforce and incentives for health workers to work in under-served areas.	Advocacy has been on-going, however the lack of resources and wage bill ceilings have undermined progress. This is perhaps a broader issue of health sector financing that requires much broader and concerted policy dialogue. The recruitment, sponsorship and bonding of midwives to hardship areas seems to have been largely successful, and is based on international lessons learned for equitable distribution of health workers.

## Output 3: An improved policy context for youth employment and opportunities
Output 3: Score and performance description – A

Output 3 has two indicators, one of which has been fully met, the other is on-going. However, the significant achievements in related areas warrants a score of A.
Output 3: Progress against indicators
Indicators	Baseline	Milestone / (Jan 2014–Dec 2014)	Achieved / (Jan 2014–Nov 2014)
3.1 Number of key policy documents developed on youth employment	0	4	4
3.2 An institutional mechanism of collection, analysis and exchange of labour market information in place	N/A	1	In progress

Upstream policy work for this outcome has been impressive, both in achievement as well as national ownership and alignment. Early next year there will be a web portal available providing a data bank on labour market information. This will establish a one-to-many data flow rather than the more inefficient pre-programme situation of many-to-many. The LMIS is being designed to facilitate employers accessing those with the right skills through an online job matching facility, which can interface with other related databases. Labour needs assessments have been conducted for hotel and food and processing sectors. After improving the methodology and capacity, more assessments have been started covering ICT, financial intermediaries and oil and gas, among others. Focus areas have been selected to align with NDPII. The participatory approach, government leadership and alignment with national planning are major achievements, and a worthwhile cause of delay.
Conclusion: score A, 1 target met, the other ongoing, but with complementary achievements not cited in the logframe that accentuate the impact of measured results.
### Progress against the 2013 AR recommendations
There were two recommendations in the 2013 AR:
Output 3 Recommendations	Implementation
Indicator 3.1 should be revised so that the expected status of policy documents by 2014 is clearer and should be broadened to cover the use of the different policies.	This indicator remained the same, but did not stop comprehensive implementation of labour market data collection and planning.
In Output 3, one target should be as follows: ‘LMIS in place and evidence that it is being used to inform the employment situation’.	Implemented, see indicators above.

Output 4: An adequately resourced, coordinated and managed national population programme
Output 4: Score and performance description – A
Output 4 has two indicators. Data is not available for either and achievements will be determined during the evaluation. The score of A has largely been awarded because of the 40% increase in national public funding for family planning in the 2014/15 budget.
Output 4: Progress against indicators
Indicator	Baseline	Milestone / (Jan 2014–Dec 2014)	Achieved / (Jan 2014–Nov 2014)
4.1 Proportion of target districts allocating and disbursing funds to population issues	N/A	100%	N/A
4.2 Proportion of district Budget Framework Papers (BFPs) developed based on socio-economic demographic and other data sources.	N/A	100%	N/A

4.1 Proportion of target districts allocating and disbursing funds to population issues
Indicator 4.1 marginally missed its 2013 target. The view of Kampala based interlocutors with the district planning process is that all districts are allocating and disbursing funds to population issues. Much has been done to build capacity of planning units, training champions, for population activities. Whilst funding for development activities has decreased in total during the JPP period, it is unclear whether the % of this funding for population activities has changed (provisional sub-score A).
4.2 Proportion of district Budget Framework Papers (BFPs) developed based on socio-economic demographic and other data sources.
The reviewer was unable to assess the result for this indicator, but achievement for 4.1 suggests at least some progress for 4.2 (provisional sub-score B).
One useful stream of activities is to create a harmonised database so that districts have a full view of the status of developmental services across all sectors. 6/15 districts have a completed integrated database and for most others it is a work in progress. The district visited is not among the most advanced, but was able to provide numerous examples of where they had invested in population activities informed by the harmonised database. For example, school extensions to response to recent population growth from recent migration movements.
The population champions are active at a variety of levels including sub-country, district (planners) and parliamentarians. A major breakthrough was achieved mid-20014 when a demographic dividend was presented at a national conference and the President announced his support for FP. This is in stark contract with the political climate when the JPP started, when the President was promoting large families senior government officials were reluctant to speak publicly in favour of FP (author’s observation in 2011-12 during other FP design work). Along with demographic dividence advocacy and evidence documents, DHS analysis is resulting in 6 papers either being finalised or being peer reviewed for journal publication. An excellent FP Costed Implementation Plan was recently finalised.
Conclusion: although target achievement could not be measured, the activities are clearly making a difference in district planning and informed stakeholders are convinced at least one of the targets has been achieved. With the additional major breakthrough of the paradigm shift in political support, national funding, and other advocacy and planning activities, an A score is justified.
### Progress against recommendations in 2013 AR
There were two recommendations in 2013: Both were implemented.

Output 4 Recommendations	Implementation
Carry out retrospective analysis of the ADPRs for years 2011/12 and 2012/13 by March 2014 to assess whether: / Funds allocated to population issues were released and spent; and / Data on population were used to inform the district plans in three sectors.	Implemented. The analysis revealed a decline in recent years in funding to population issues at district level, but this is mainly attributable to a decline in overall funding from both government and donors. The report did not investigate whether data was used, but anecdotal evidence from the field trip suggests so.
Review the 2014 targets after reviewing the ADPRs.	The LF was reviewed and some indicators and targets were changed. It was not clear whether the ADPR review informed new targets, but the LF targets were largely based on JPP funding, rather than funds for district development plans.

# 3. Progress against the purpose/outcome
The overall purpose of the GoU/UN JPP is that the national, community, cultural and issue-based leaderships are managing the acceleration of a downward trend in population growth. The logframe contains two indicators against which this purpose is assessed.
Outcome progress against indicators
Outcome indicator 1	Baseline	Milestone / (Jan 2014–Dec 2014)	Achieved / (Jan 2014–Nov 2014)
CPR (modern methods: women of reproductive age)	25.6% / (2011)	33.5%	N/A
Teenage pregnancy rate	24% / (2011)	20%	N/A

Although results were not available for 2014, the most recent annual panel survey 2012 showed that the CPR had increased to 30% from 25.6% in 2011. This was an encouraging early result.
The 2011 UDHS shows that 24% of teenagers had begun childbearing, a decline over time from 43% in the 1995 UDHS. There are no new data available to measure this indicator in 2014.
UNFPA is monitoring new users of modern FP that use long term methods. This has increased from 5,642 in 2011 to 45,321 Jan-Oct 2014. This is an encouraging trend, but represents a relatively small proportion of all FP users (and probably represents <1% of women of child bearing age). It therefore does not necessarily suggest the early increase in CPR has continued. This will have to be confirmed during the next national survey.
The UN: Delivering as One
There were a number of concerns in the 2013 AR regarding integration of UN implementation. DFID Uganda has commissioned a review of two joint programmes it funds in Uganda, including the JPP. There are a number of emerging lessons learned from the review that can inform future UN joint programming. Whilst there are many challenges, there are also many benefit of improved UN working, peer accountability and reduction in transaction costs for government as well as UN agencies.

# 4. VfM framework and data
Performance on VfM measures
As with previous ARs, data was not available on expenditure broken down to the level of detail and in the format required to allow a comprehensive assessment of VfM. The 2013 AR included a dedicated consultant to analyse VfM in detail. Without similar capacity, and with VfM being quantified in the end of programme evaluation, the current AR did not attempt a detailed VfM analysis.
Whilst VfM is increasing in importance within some UN agencies corporately, detailed monitoring is not routinely done. That said there were examples of efficiencies that emerged such as the use of mobile technology for birth registration, and reducing the number of schools receiving bursary students.

# 5. Risks and risk mitigation
The GoU/UN JPP programme document contains a set of risk categories against which the overall programme risk can be determined and scored. At this late stage with all funds from DFID disbursed, there are no recommended changes to the risks.
Risks and mitigating strategies
Description of risk	Status and mitigating action	Rating
UN agencies are unable to work closely together and cohere around shared objectives	The UN agencies are doing well at joint planning and field supervision. However, implementation remains very agency focused and is not always based on comparative advantage. This is resulting in a fragmented approach that is affecting performance. The JPP needs to move to joint implementation through a joined-up approach across the districts if outputs are going to be met by 2014.	Probability: high / Impact: high
Participating GoU and national institutions lack implementing capacity	There are eight key sectoral ministries and two government agencies involved in the GoU/UN JPP. As co-chair of the steering committee, government is involved at the highest level in decision making for the programme. However, weak district capacity and structures pose a challenge to coordination on the ground. District capacity-building activities and field monitoring visits are conducted to improve implementation at the district level.	Probability: medium / Impact: medium
Government commitment to programme aims is reduced	Government has consistently shown high levels of commitment to the programme and continues to participate actively at steering committee meetings and in joint monitoring visits.	Probability: low / Impact: high
Increasing demand for FP cannot be met due to supply-side funding gap	DFID and USAID together fund approximately 80% of the contraceptive commodities for the country. Over the last few years, there has been a decline in stock-outs of key contraceptives, although some supply-chain management challenges still exist as there are now excess stocks of certain commodities. There is a need to ensure that the health care workers have the right skills to administer FP methods, particularly at the lower-level health facilities.	Probability: low / Impact: high

# 7. Future programme

The mandate of the UN provides a unique opportunity to implement diverse programmes. Rather than objectively reviewing the options and making strategic choices, the inclination during the proposal development was to share out resources equally without full regard for relative contribution to the purpose and goal. DFID intervention during design phase and early during implementation increased the level of strategic intervention. This contributed particularly to the achievements in Output 3.

The JPP has accelerated progress this year and responded to feedback from DFID. If DFID continues to fund through joint UN arrangements, there will be need to provide regular challenge and feedback, both in design, implementation and monitoring/operations research. A number of innovative activities have taken place to capture the involvement of young people in behaviour change and service delivery as well as to involve men in SRH promotion. Unfortunately, there was little thought to evaluating these initiatives so the JPP is unsighted on whether these are promising activities or a waste of resources. Any new programme should establish expenditure monitoring arrangements and agree operations research priorities and capacity.

# 8. Summary and recommendations

The implementing UN agencies have risen to the challenge in the final year to reduce fragmentation, accelerate progress and respond to some of the recommendations. Population remains a key development priority for the country and implementation of the JPP has demonstrated UN strengths as well as weaknesses. DFID should consider continued funding this area and reflect on the comparative advantage of funding through the UN. The JPP evaluation would help to inform detailed design of any follow on programme. The AR’s recommendations are forward looking, with this in mind. They can be found in the executive summary at the start of the document.

Persons consulted
	Name	Title	Contact	Email
1.	Dr Collins Tusingwire	Assistant Commissioner, Reproductive Heath, Ministry of Health	0774-644-929	drtusingwire@gmail.com; / tusingwirecollin@gmail.com
2.	Dr Zainab Akol	Programme Manager, Family Planning, Ministry of Health		zainabakol@gmail.com
3.	Andrew Mukulu	Director Population, Uganda Bureau of Statistics (UBOS)	0711706040	andrew.mukulu@ubos.org
4.	Johnson Kagugube	Director District Statistics and Capacity Development, UBOS	0712501395/0772501395	johnson.kagugube@ubos.org / jkagugube@gmail.com
5.	Andrew Tiondi	Head M&E Department, Population Secretariat (POPSEC)	0772499354	andrew.tiondi@popsec.org
6.	Dr Betty Kyadondo	Head Family Health Dept, POPSEC	0772507533	bettykyad@gmail.com
7.	Catherine Mbabazi	National Programme Officer, M&E, POPSEC	0701330476/0712644727	cngorok@yahoo.co.uk
8.	James Peter Olemo	National Programme Officer, M&E, POPSEC	0782399230	jamespeter.olemo@popsec.org
9.	Simon Peter Alele	National Programme Officer, POPSEC	0772960275	simonpeter.alele@popsec.org
10	Dr Wilson Mubiru	District Health Officer, Mubende	0772670556	mubiruwh@yahoo.co.uk
11.	Daniel Zziwa	Secretary for Health, Mubende	0783825406	danielzziwa@yahoo.com
12.	Hajj Ziad Kalema	Vice Chairperson, Local Government Mubende	0782401652
13.	Mary Nakitiibwa	Registered Midwife, Kiganda Health Centre IV	0700451608/0773142171	nakitiibwam@gmail.com
14.	Beatrice Kusiima Tinka Akiiki	Senior Nursing Officer/Public Health Nurse, Kiganda Health Centre IV	0782/0702360879	kusiimabeatriceakiiki@yahoo.com
15.	Annet Namagembe	Enrolled Midwife, Kiganda Health Centre IV	0756561872/0778779590
16.	Dr Jude Kiiza	Senior Medical Officer, Kiganda Health Centre IV, Mubende District	0777136236
17.	Ritah Kemigisa	Enrolled Midwife, Kiganda Health Centre IV	0777196169
18.	Proscovia Asaba	Enrolled Midwife, Kiganda Health Centre IV	0781499014
19.	Lydia Nakayaga	Peer educator, Youth Friendly Corner, Kiganda Health Centre IV	0774663060
20.	Bright Lubira	Peer Educator, Youth Friendly Corner, Kiganda Health Centre IV	0754375568
21.	Fred Luyima	Head Teacher, Kiganda High School	0781505994
22.	Gerald Ssewanyana	In –Charge Youth Friendly Corner, Kiganda High School	0701407099
23.	Paul Lukwago	Peer Educator, Kiganda High School	0781424521
24.	Benson Twinamasiko	V/Chairperson, Peer Educator, Kiganda High School	0705782809
25.	Mathias Mumpe	Peer Educator, Kiganda High School	0705794480
26.	Geoffrey Tumwine	Peer Educator, Kiganda High School	0775270023
27.	Rodgers Mugume	Peer Educator, Kiganda High School	0705248823
28.	David Byamukama	Peer Educator, Kiganda High School	0757182026/0777902096
29.	Stephen Opio	National Programme Coordinator, ILO	0771000593	opio@ilo.org
30.	George Ebong	Planning Specialist, UNICEF	0772333741	gebong@unicef.org
31.	Tapiwa Jhamba	JPP Coordinator, UNFPA	0753343015	jhamba@unfpa.org
32	Dr Olive Sentumbwe-Mugisa	Family Health and Population Adviser, WHO	0772473600	sentumbweo@who.int
33.	Florence Tagoola	UNFPA	0712192279	tagoola@unfpa.org
34.	Patrick Orotin	JPP M&E Specialist, UNFPA	0772389036	orotin@unfpa.org
35.	Dr Primo Madra	Programme Officer UNFPA	0772613482	madra@unfpa.org
36.	Lawrence Were	RHCS Coordinator, UNFPA	0702409703	were@unfpa.org