## Sheet1
PROJECT NAME | South African Partnership for Effective Development Cooperation (SAPEDC) [Revision August 2016] | [7 empty] | Notes
IMPACT | Impact Indicator 1 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate)
South African regional development assistance and global policy influence have a transformational impact on poverty in Africa | Number of African countries where South Africa - UK programmatic development partnerships deliver quantified and well-evidenced results for poor women and men | Planned | 0 | 1 | 3 | 5 | 7
Achieved
Source
Implementing partner quarterly and annual reporting
| Impact Indicator 2 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017
| Extent to which the concerns and needs of African youth, the CSO community, and grassroots communities are given attention and priority in the post-2015 development agenda | Planned | Negotiations not yet underway | At least 3 "key asks" identified which are aligned with SA-led youth consultations and UK priorities | "Key asks" reflected at national, continental and international levels of negotation, through SA-led advocacy | "Key asks" reflected in final UN outcome document on post-2015 development framework | South Africa playing recognised leadership role on implementation of the post-2015 development framework in Africa.
Achieved
Source
African Monitor programme quarterly and annual reporting (impact level)
OUTCOME | Outcome Indicator 1 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 | Assumptions
South African regional development interventions are selected, designed and managed for maximum results for poor men and women, in line with international best practice | Status of progress towards establishment of the South African Development Cooperation Agency as a functional organisation. | Planned | Agency business plan presented to Cabinet. Legislation in progress. No staff recruited. | As Aug 2012 | Timetable for SADPA bill to parliament announced. | As at Sep 2015 | As at Sep 2015 | South Africa remains economically and politically influential in Africa. South Africa continues to prioritise African development within foreign policy, including making funding available. South Africa remains politically engaged in post-2015 and Global Partnership processes. UK-South Africa bilateral relationship remains sufficiently strong to enable closer partnership on development issues. South Africa continues to prioritise SADPA as the means of delivering and co-ordinating its development assistance going forward.
Achieved
Source
DIRCO/SADPA quarterly and annual reporting to DFID
| Outcome Indicator 2 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate)
| Number of South African development cooperation initiatives achieving results in other countries with UK support through this programme | Planned | 0 | 2 | 5 (Oct 2014-Sep 2015) | 6 (Oct 2015-Nov 2016) | 8
Achieved
Source
DFID programme records
| Outcome Indicator 3 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017
| Extent to which SAPEDC partners include gender disaggregation within their quarterly reporting | Planned | No systematic gender disaggregation of data under SAPEDC reporting | N/A | New reporting guidance for gender disaggregation provided to SAPEDC partners | SAPEDC partners reporting from October to March 2015 include gender disaggregation in their quarterly reports. | SAPEDC partners reporting from April 2016 to March 2017 include gender disaggregation in their quarterly reports, and actively consider gender equality implications in their programming.
Achieved
Source
DFID programme records
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate) | Assumptions
UK expertise and funding make a significant contribution to the South African Parliament's oversight of Government development and peacebuilding approaches, and the establishment of the South African Development and Co-operation Agency (SADPA) | Number of briefings, training events and publications provided for the Parliamentary Committee for International Relations and Co-operation | Planned | None provided. | N/A | 2 (October 2014-September 2015) | 4 (October 2015-Nov 2016) | 6 | The Parliamentary Committee for International Relations and Co-operation continues to request support in these areas. Development and peacebuilding continues to be an area of focus in parliamentary business during the project period. The committee is able to fit training events into their schedule. | Not under current SAT programme
Achieved
IMPACT WEIGHTING (%) |  | Source | [5 empty] | RISK RATING
10% |  | IGD quarterly reporting to DFID | [5 empty] | Medium
| DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (£) | DFID (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate) | Assumptions
South Africa - UK programmatic partnerships in Africa result in sharing and improving expertise on approaches to development cooperation on both sides | Contribution of UK-South African partnerships to enhanced regional trade and investment in the extractives industry | Planned | No partnerships exist | Case study evidence demonstrates improved regional coordination and cooperation on customs reform in at least 3 countries | Case study evidence demonstrates increased national capacities in customs procedures and improved regional coordination on customs reform in at least 3 countries. The geological survey capacity of key extractives industries is assessed in at least 2 countries. | Case study evidence demonstrates increased national capacities in customs procedures in at least 3 countries. | Case study evidence demonstrates increased national capacities in customs procedures and improved regional coordination on customs reform in at least 6 countries. The geological survey capacity of key extractives industries is assessed in at least 2 countries. | Possible to identify geographical and thematic shared UK/SA priorities for programme partnerships. UK can demonstrate added value to be "partner of choice" in selected areas. South African partners have or can develop sufficient financial and technical capacity to manage programmes effectively. GDP programme in SA continues to function at same level of resourcing in future financial years to allow new programmes to be established. | Not under current SAT programme
Achieved
Source
Quarterly and annual reporting from SARS/WCO and CGS.
| Output Indicator 2.2 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate)
| Contribution of UK-South African partnerships to addressing global challenges in other African countries, including health and climate change. | Planned | No partnerships exist | Opportunities identified for South African expertise to inform regional health sector needs | Case study evidence demonstrates improved health sector performance as a result of South African assistance in at least 1 other country | Development of draft climate change portfolios for 2 countries as a result of South African assistance. | Case study evidence of a) improved health sector performance in at least one other country and b) the development of climate change project portfolios with private sector inputs by at least two countries, both as a result of South African assistance.
Achieved
Source
Quarterly and annual reporting from UNFPA / HLSP and other relevant partners
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate)
50% | Contribution of UK - South African partnerships to building more open and effective governance institutions and more peaceful societies in and between other African countries | Planned | No partnerships exist | At least two UK-supported, SA-led regional networks of expertise in place on issues of governance and open institutions | At least two UK-supported, SA-led regional networks of expertise in place on issues of governance, open institutions and peacebuilding. | Case study evidence of enhanced capacities to promote governance, open institutions and peacebuilding in or between at least 5 African countries as a result of UK-SA partnership | Case study evidence of enhanced capacities to promote governance, open institutions and peacebuilding in or between at least 5 African countries as a result of UK-SA partnership |  | Not under current SAT programme
Achieved
|  | Source | [5 empty] | RISK RATING
|  | Quarterly and annual reporting from UCT, ISS, ODAC, IJR and other relevant partners | [5 empty] | Medium
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate) | Assumptions
South African civil society, academia and think tanks increasingly able to contribute to and constructively shape national and international debate on development issues. | Number of UK-funded, SA civil society-produced research papers or events on South African bilateral and trilateral development policies. | Planned | 0 | 10 | 10 (October 2014-September 2015) | 5 (October 2015-Nov 2016) | 25 | Government of South Africa remains open to analysis and advice from think tanks and civil society to help inform and shape policy. South African organisations have or can develop sufficient skills and expertise to contribute valuably to development policy agenda. | Not under current SAT programme
Achieved
Source
Partner organisation reporting (including ISS, IGD)
| Output Indicator 3.2 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017 (aggregate)
| Number of UK-funded, SA-produced research papers or events on global/regional development policy issues including the post-2015 development agenda and its implementation, financing for development and regional integration | Planned | 0 | 10 | 10 (October 2014-September 2015) | 10 (October 2015-Nov 2016) | 35 |  | This and 3.3 cover AM
Achieved
Source
Partner organisation reporting (including ISS, IGD, UCT, African Monitor)
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017
40% | Level of involvement and influence of South African civil society organisations in support of priority issues on the post-2015 development agenda | Planned | Very low | At least 2 supportive civil society voices on "golden thread" themes identified and strengthened. SAPEDC partners providing recognised regional leadership. | Input of South African civil society actors to UN process recognised positively by DFID post-2015 team. SAPEDC partners providing recognised regional leadership. | South African civil society actors making a positive contribution to the implementation of the post-2015 development goals in Africa. | Key youth and civil society priorities reflected in national development plans or national SDG implementation framewoks in at least 3 African countries.
Achieved
|  | Source | [5 empty] | RISK RATING
|  | SAPEDC partners programme reporting; DFID post-2015 team feedback | [5 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline Aug 2012 | Milestone Sep 2014 | Milestone Sep 2015 | Target November 2016 | Target March 2017
| Level of involvement of women in championing and advocating for issues affecting them in SADC gender protocol and post -2015 development agenda | Planned | 326 local authorities developed gender and gender based violence action plans aligned to the SADC Gender Protocol and Millenium Development Goals. However these did not incorporate SDGs and Post-2015 SADC gender protocol. |  |  | At least 100 councils incorporate the SADC gender protocol targets and SDGs into their gender action plans and form a Community of Practice | At least 326 councils incorporate the Post-2015 SADC Gender Protocol targets and SDGs into their final gender and GBV action plans and form a community of practice for promoting gender equality, empowering women and ending violence | (i) There is political will within the councils to action policy reviews and engage with stakeholders. (ii) Women in the pilot phase have resources and are willing to continue in the programme
Achieved
|  | Source | [5 empty] | RISK RATING
|  | SAT and GenderLinks programme reporting | [5 empty] | Low
INPUTS (£) | DFID (£) |  | Govt (£) | Other (£) | Total (£) | DFID SHARE (%)
INPUTS (HR) | DFID (FTEs)