ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	South Sudan Health Pooled Fund (HPF), ARIES No. 203109
Country or region targeted	South Sudan
Type of cost extension (if applicable)	Financing for scale-up
Original project budget	£56 million
Original project start and end dates	Start Date: 02-01-2012 / (Actual Start Date: 12-10-2012) / End Date: 31-12-2018
Cost extension value (if applicable)	£36 million (for two years) / Cumulative total: £92 (over 5.5 years)
New project end date (if applicable)	The end date remains unchanged
Business Case Quest Document No.	3769141

INFORMATION
What is the project’s purpose?
To support the foundations of an effective public health system that will deliver improved access to quality health services across six states in South Sudan, and respond to emergency needs where required, with a specific focus on reducing maternal and child mortality.
What is the objective of the cost extension or other changes?
The objective of the cost extension is to continue and scale-up a well performing programme to complete its full phase, as envisaged in the approved business case, leading to increased results. / The programme was designed for five and half years, with a six month inception phase; however funding was committed only for the first 3.5 years, mainly due to inability of some co-funding donors to commit beyond three years. All donors had expressed an interest in principle to provide further funds to extend by an additional two years. The current available funds (£107 million) are expected to be spent fully by the end of the first 3.5 years (i.e. March 2016). / This addendum to business case for a cost-extension is to seek funding, additional to the commitment made for the first 3.5 years of the programme, to complete the full phase (five and half years) of the programme as originally approved. Amongst the current HPF donors, Canada, the European Union and Sweden have pledged to provide additional funds for the extension. Only Australia have confirmed their inability to fund the extension which is a result of a global reduction and reorientation of their aid since 2014 and a subsequent pull out from South Sudan. USAID have expressed strong interest in joining the Pooled Fund. If they join, a similar programme in two states (Central and Western Equatorias) currently funded by USAID, will merge into this programme, which currently covers six states (Eastern Equatoria, Western and Northern Bahr el Ghazals, Warrap, Lakes and Unity), bringing the HPF coverage to eight of the ten states in South Sudan. In that case, the cost extension will see a geographic expansion and hence scale up of the programme results.
What is the additional and total support the UK will provide?
The UK will provide an additional £36 million for the final two years of the programme, bringing its total support for the 5.5 years’ programme to £92 million. / The overall budget for the final two years of the programme is expected to be £83 million. This is an early estimate which would cover (i) continuation and scale-up of the current health service delivery, health systems strengthening and community engagement interventions, (ii) increased provision of pharmaceuticals, and (iii) increased flexibility for emergency preparedness and response. A further costing of the programme is currently underway to confirm a more accurate budget. / It is expected that the other donors (Canada, the EU and Sweden) will provide the remaining £47 million. They have pledged the following as tentative commitment: / Canada – £20 million / EU – £18 million / Sweden – £6 million / Total – £44 million / Dialogue is still underway and the donors are exploring with their respective headquarters for potential resources to cover the gap. / The above estimate of £83 million is for the current six HPF states only. If USAID join, and two more states come into the programme, the budget has to be revised. USAID have not pledged a commitment yet, but it is expected that they will contribute proportional resources to cover two additional states. Apart from the contribution mentioned above, the UK will provide an additional £13 million for two years to integrate and scale-up priority nutrition specific interventions through the programme. DFID South Sudan has secured £13 million for 2016/17-2017/18 from the centrally managed ‘Matched Funding for Nutrition’. This funding can be implemented as a separate project ., However integrating it into this programme, through the health systems platform the programme has built already, will enable quicker and at-scale nutrition results and offer excellent value for money. With this ‘matched funding’, the total UK contribution to the HPF will be £105 million over 5.5 years. However, the ‘matched funding’ spend has to be accounted for explicitly under separate ‘nutrition’ codes to ensure DFID’s investment in nutrition is clearly tracked.
What are the expected results?
The overall objective of the extended two years of the programme remains unchanged from the original programme. The overall outcome will be increased access to quality health services, in particular by children, pregnant women and other vulnerable groups. The outputs this programme will deliver to achieve the outcome are: / Strengthened delivery of health services, particularly responsive to the needs of women and children / Increased ownership, governance and demand of communities for health services / Strengthened health systems, especially at decentralised levels / Additional results attributable to DFID in the final two years from the additional funding are: / 621,600 under five year olds seen for a curative consultation / 69,638 women have at least four antenatal visits / 69,638 pregnant women receive at least two doses of intermittent presumptive treatment of malaria as part of their antenatal care / 10,438 additional people start a family planning method / These results are proportionally much higher than the ones agreed in the approved BC. These have been projected based on levels of results the programme has already achieved in the first 2.5 years (listed below). / Despite an extremely challenging and fragile operating environment following the outbreak of an armed conflict in December 2013, the programme has delivered well on its objectives and scored an A in the first two annual reviews (November 2013 and November 2014). The third annual review is due later this year. A mid-term review carried out together with the second annual review in November 2014 also noted that ‘despite difficulties caused by the conflict in the country and the continuing problems in Unity State, the HPF had been successful in achieving its targets in the area of health services delivery’. / As per the business case, the results attributable to DFID to be achieved by March 2016, assuming a three and half year intervention, were: / 254,959 under five year olds seen for a curative consultation / 21,853 women have at least four antenatal visits / 21,853 pregnant women receive at least two doses of intermittent presumptive treatment of malaria as part of their antenatal care / 10,926 additional people start a family planning method / . However, all of these have already been met (and actually exceeded significantly) by June 2015, nine months before the target date. Therefore, assuming a 52% attribution (DFID providing £56 million of the projected spend of £107 million), the following are the achieved results attributable to DFID as of June 2015: / 777,000 under five year olds are seen for a curative consultation [three times the March 2016 target] / 87,047 women have at least four antenatal visits [four times the March 2016 target] / 87,047 pregnant women receive at least two doses of intermittent presumptive treatment of malaria as part of their antenatal care –(four times the March 2016 target) / 13,048 additional people start a family planning method [exceeded the March 2016 target] / Progress against selected few indicators are given in Table A. These validate further that the programme has made significant achievements in health service expansion and utilisation. / Table A: HPF Achievements to March 2016 in selected project indicators / Indicator Baseline March 2016 Target Achievement reported by June 2015 / % of one year olds vaccinated with the third dose of DPT vaccine 11% (18,000) 50% 50.7% (March 2016 target already met) / Outpatient consultations (curative and preventive) of under five children 770,000 1.8 million 1.9 million (March 2016 target already met) / Number of facilities providing comprehensive and basic emergency obstetric and neonatal care (CEmONC/ BEmONC) 3 CEmONC / 0 BEmONC All HPF supported hospitals (including faith based) provide CEmONC / All counties (39) have at least one PHCC with BEmONC All HPF supported hospitals (8 county, 7 faith based and 4 state hospitals) provide CEmONC (March 2016 target already met) / 34 Counties out of 39 have at least one PHCC providing BEmONC (March 2016 target on track to be met) / % of women who attended at least four times for antenatal care during pregnancy 8% 38% 30% (Achievement on track to meet the March 2016 target by December 2015) / % of births attended by skilled health personnel 2.8% (7,300) 15% 8.2% (25,500) (Target slightly off track but likely to be met through the support to hospitals which started late in the programme) / Note: Achievement of this result depends on availability of skilled health personnel, which are in severe shortage in South Sudan. Though the number of births in HPF supported health facilities was 41,653, only 25,500 of these births were attended by skilled personnel. Remaining were attended by trained health workers though they are not classified as skilled health personnel for deliveries. The programme is coordinating with other projects aiming to train new health workers skilled for deliveries. / Source: HPF Annual Report 2015 (draft) / It is strongly evident that the programme is delivering the planned results. The evidence substantiates the assumptions in the theory of change in the business case in terms of achieving outcome through inputs and expected outputs of the programme. Though we do not have evidence on the higher level impact indicator (there have not been any surveys to substantiate impact), consistently high level of achievement of outputs and outcomes in line with the theory of change provides us the assurance of expected impact. / The annual and mid-term reviews have also established that the programme is delivering value for money as elucidated in the business case. Progress in the development of health systems, particularly health and human resources information system, salary reforms, introduction of decentralised operational grants, improvement of pharmaceutical storage and distribution system, county level planning, reviews and supportive supervision, etc., have resulted in infrastructures, mechanisms and processes which will last beyond the project. South Sudan Ministry of Health (MOH) at national and state levels played a substantial role in ensuring the delivery of the programme amidst a fragile environment. They took bold steps to introduce crucial reforms, such as introducing salary harmonisation and scaling up operational grants to decentralised levels now including the primary health care facilities also. This in itself is an important achievement towards the programme’s long term aim of a government led health system that saves lives. / A revised logframe for the two-year extension will be established through a light touch redesign of the programme, which is currently underway (described in the section below). The programme level results (outputs and outcome) will build on the achievements made in the first 3.5 years despite conflict and hence will maintain a similar kind of ambition. However the logframe will take into account the fragility of South Sudan and revisit the assumptions based on the new realities. The results will be aligned to the health outcomes and targets set by the South Sudan Ministry of Health. / If USAID join the pooled fund, the geographic expansion to eight states (with a total population of over 8 million), from the current six (with a population of six million), is likely to deliver increased attributable results and better value for money for all donors, not to mention the benefits in terms of a more unified health system. / Alignment to UK priorities / The programme will help deliver the UK government’s commitments on women and girls, health and nutrition. It will contribute to the results on women and girls, immunisation, family planning, hygiene and nutrition, in line with manifesto commitments and ministerial priorities. The programme aligns to UK’s National Security Council’s Strategy for Sudan and South Sudan, mainly the following: / reducing under-five mortality / strengthening structures for local service delivery / reforms to planning, budgeting and reporting / greater participation of women and communities / This is also consistent with UK’s planned approach in South Sudan following the signing of peace deal in August 2015. UK, as a top-three donor with on-the-ground expertise, will continue provision of essential services to those most in need. It supports the four-year Strategic Goals (2014/15-2017/18) of the UK’s mission in South Sudan (Goal 4: Consistent, inclusive economic growth and development with wider delivery of basic services like health, education and rule of law, supports reduction in poverty). / The programme will contribute directly to three of the seventeen Sustainable Development Goals (Goals 2, 3 and 5 related to nutrition, health, gender equality and empowerment of women and girls) / Gender Equality / The programme is complaint with the International Development Gender Equality Act (2014) and will address gender inequality in health. South Sudan has some of the worst maternal health indicators in the world. The maternal mortality ratio was estimated by the World Bank to be 789 women dying for every 100,000 live births in 2015. In addition, around 88% of deliveries occur at home and only 10% of deliveries are attended by a skilled birth attendant. The contraceptive prevalence rate is low at 3.5%, while the caesarean section rate is only 0.5%. Teenage pregnancy is common with 40.8% of girls married before their 18th birthday[1]. / The programme will focus on the provision of essential maternal health, nutrition services and the protection of the most vulnerable (particularly youth, women and girls) in 8 out of 10 former states of South Sudan. The programme has developed a Gender and Social Inclusion strategy which will be integrated into all stages of the programme cycle including monitoring & evaluation and ensuring results are properly gender-disaggregated. / Specific measures will respond effectively to the needs of women and girls: / Partners are required to complete detailed gender and vulnerability analyses to ensure that the needs of women and girls are prioritised. / Maternal, new-born and child health and nutrition activities target the specific needs of pregnant women and mothers with young children as a group in need of specific assistance. / All relevant outcome and output indicators will be disaggregated and reported on by age, gender and wealth quantile where possible. / The logframe includes specific indicators that target women e.g. indicators on family planning, antenatal care visits and births delivered by skilled birth attendants. It also includes other gender indicators on the “Number and % of health committee representatives that are women” and % of committees that have women in leadership positions”. The current baseline is 38% in 2015. The programme will work with the communities to increase this proportion over–time. / It is also recognised that the involvement of men is of critical importance if issues such as access to health care and family planning are to be addressed effectively. The programme will engage both men and women. / The programme will continue to empower women and girls through training and capacity building activities which target health workers and community health teams (the majority whom are women). / The programme will support gender inequality advocacy to government officials and development partners for a focus on social determinants of health. / The programme will also use the services of a third party monitoring and verification provider to monitor the quality of care, including the gender equality aspects of the programme / .
What is the approach to implementation?
Light Touch Redesign / The two-year extension of the programme provides an opportunity to improve effectiveness and maximise value for money by considering the experience and learning from the HPF implementation, as well as from other primary health care programmes in South Sudan. The programme will hence undergo a light touch redesign without any major changes to the objectives, the core components (health service delivery, health systems strengthening, community engagement), the contractual arrangement (fund manager model) and the channelling of funds (no funds through government system). / DFID has commissioned a team of experts for the redesign, which will be based on recent reviews/evaluations (mainly Mid-Term Review - MTR, November 2014) and an extensive consultation process with a wide range of key stakeholders in South Sudan from August to October 2015. The MTR concluded that / The HPF has been successful in increasing access to health services in six of South Sudan’s states and, while there are as yet no data to show that this is having an effect on overall mortality rates, there is evidence to show improvements in the delivery of health services such as vaccinations and attended deliveries. / The HPF has been effective in engendering government involvement in decision making in the programme through a national Steering Committee and State Oversight Committees in each state (except Unity due to the conflict). These have provided fora for guiding project activities at state and county levels and actively involved MOH officials in decisions over request for proposal design and in the selection of implementing partners for the various contracts. / The HPF has supported the development of the county model of health care delivery in which county-level services are planned, delivered and monitored according to one plan. / Greater emphasis needs to be placed on encouraging an improvement in the quality of services provided. / Without a continuation, in some form, of support for the delivery of primary care services in South Sudan, there is likely to be a significant deterioration in services, with the potential for a loss in the gains already made by the project to date. Therefore it is recommended that the funding partners consider the continuation of funding support for service delivery, health systems strengthening and community engagement beyond April 2016. / The MTR recommended a number of factors to be considered for the extended programme. These factors are being looked into more detail in the redesign process. Preliminary outline of the major changes are given in the section on Key Changes below. These will be refined in the final design document (expected to be produced by the end of October 2015). / Open Tender Process for the Fund Management / DFID will continue the modus operandi of programme delivery through a centrally contracted Fund Manager (FM). The current FM’s contract ends in April 2016 and DFID has decided to enter into a new contract through an open competitive process. DFID will engage a new FM contracted through a direct international competitive tender using OJEU procedure. This will use competition to drive commercial advantage for DFID in line with the original business case. The roles and responsibility of the FM will be slightly redefined based on the redesign and it will be published in the tender documents. However it will include fund management, technical oversight and quality assurance of the programme delivery, and technical assistance to the different levels of the health system and the community as the core. / Procurement of Pharmaceuticals through Framework Arrangement / As noted in the section below, the outer two years of HPF will include an increased provision on pharmaceuticals, with an agreed set of essential medicines and commodities to be supplied in regular intervals (for example, quarterly) to all health facilities in the programme areas for two years. DFID will contract a procurement agent under its framework arrangement to procure and distribute the supply to all programme areas. A central contract ensures economy of scale, consistency of the supplies as well as better quality control and assurance. There is a clear commercial advantage in contracting a procurement agent in the framework as competition and value for money has already been tested and maximised at the centre. / Bridging Contracts / The new FM once contracted will immediately issue bridging contracts for four months to the Non-Governmental Organisations (NGOs) subcontracted by the current FM to continue their support to County Health Departments and hospitals for health service delivery. This will ensure service continuity until the new FM runs an open procurement process to subcontract service providers for the counties and hospitals. It is expected that there will be significantly fewer number of subcontracts (refer to consolidation of contracts in the section below) and hence the procurement process can be managed by the new FM in four months. / Inception Phase / The first four months of the extended phase (April to July 2016) will be the inception phase. The new FM will establish policies and procedures for fund management and programme delivery, adapting the existing policies and procedures or those used by the FM elsewhere in similar programmes in order to swiftly move on to the main implementation phase (August 2016 to March 2018). The FM will also issue bridging contracts to the existing NGOs (implementing partners) and run open tenders to subcontract new implementing partners for long term implementation (August 2016 to March 2018). The FM will also prepare detailed work plans, budget and performance framework for the main implementation phase. / Governance Arrangement and Funding Mechanism / The management, reporting and accountability arrangements will largely remain the same as outlined in the original business case. DFID will be responsible for contracting and managing the fund manager, and be accountable to the co-funding donors. The fund manager will be accountable to the steering committee at national level, jointly chaired by South Sudan Ministry of Health (MOH) and DFID, and oversight committees at the state levels chaired by State MOH. Funds will be channelled through the fund manager and sub-contracted implementing partners. No funds will be channelled through government systems. It is unlikely that public financial management benchmarks, as envisaged in the original business case, will be met or positive Fiduciary Risk Assessment (FRA) possible in the extended two years for DFID to be able to finance the government directly for parts of salary or local services. / Delegated Cooperation Arrangement / DFID, as the lead donor responsible to manage the pooled fund, will sign an Arrangement on Delegated Cooperation (DCA) with each of the co-funding donors to agree on the funding commitments as well as the rules of engagement and accountability. / Risk Management / The risk rating for this programme was Medium in the original BC and in the first annual review of November 2013. However it was scaled up to High in the second annual review in November 2014, largely owing to the increased insecurity and fragility as a result of the outbreak of violence in late 2013. It remains High but the programme has put in place stronger risk management and mitigation measures, which are rigorously monitored by DFID South Sudan including revised risk matrices and regular monthly and quarterly risk register reports. Through careful risk management and a conflict sensitive approach, the programme was able to continue services and deliver modest results even in the conflict affected state of Unity. DFID South Sudan will work closely with the fund manager and the implementing partners to ensure they refresh their analyses and strengthen their conflict sensitivity approach and risk management based on continuous monitoring of the changing nature of the conflict.
Describe any key changes to the original business case
The light touch redesign process will define the major changes to the programme. An extensive consultative process is currently underway to that effect. Preliminary findings of the process suggest the key points listed below. These will be refined and finalised later. / Continuation of the Core Programme Interventions / The programme in the final two years will continue along similar lines to the original BC with a number of modifications based largely on the findings of the HPF Mid Term Review of November 2014. A number of factors argue for maintaining the main design for the final two years also, which are: / The programme has been in operation just for three years, operating under very difficult circumstances and yet it has enabled county health services to record considerable improvements. / The programme has demonstrably delivered expected results despite an extremely fragile and challenging operational environment. Though the situation is uncertain and likely to be fluid for some time, it is evidently likely to contribute to the same outcome and impact. / The relatively short period of two years, as well the continuing difficult circumstances would argue for some continuity in approach in order to sustain, and hopefully improve upon, gains that have been achieved. / While the Government of the Republic of South Sudan (GRSS) and specifically Ministry of Health has demonstrated leadership, partnership and support to health services through increased grants to counties and recently to primary healthcare clinics, and revised salary scales, the current economic situation means that a serious decline in health delivery services could happen without continuation of HPF support at this time. / A number of health systems strengthening activities have only recently started and so will need time to gain traction. / A number of other health systems strengthening elements, notably Public Financial Management, have recorded considerable progress but will need further inputs to expand and sustain them. / .Key areas for changes / Increased focus on quality of care / While health service coverage has expanded under the current programme, it is recognised that more efforts are required to improve quality. The greatest challenge to improving quality will be increasing the number of skilled and motivated staff in health facilities. Additional measures that HPF and its implementing partners can take to improve health service quality include measures, such as the provision of standardised treatment guidelines for rural health workers and strengthening supportive supervision to such as on- the- job training and mentorship, with particular attention to reproductive health and nutrition. In order not to reinvent the wheel, the programme will consider adopting tested quality improvement approaches, such as the one implemented with some success by USAID funded Integrated Service Delivery Project (ISDP) in Central and Western Equatoria States. / Regular and adequate supply of essential medicines and commodities is a key element for a quality service. In the light of a likely deterioration in the pharmaceuticals supplies available in facilities around mid-next year, a greater proportion of project spending will be allocated for drug procurement. It is discussed in further detail in sub-section 8 below. / Increased focus on gender and social inclusion / An improved focus on gender and social inclusion will address issues of access to, and quality of, health services for both women and marginalised communities. The programme developed a Gender and Social Inclusion (GSI) policy and strategy but fell short of developing implementable plans for operationalising the policy, both within HPF itself and amongst its implementing partners or partner MOH health workers. It will be important that this omission is addressed. / The project will develop a GSI Action Plan, with priority activities that give realistic attention to the two-year timeframe and the challenging national and sub-national context. The GSI Action Plan will include activities to support GRSS partners, implementing partners, health workers and community volunteers to better identify vulnerable and marginalised communities and achieve effective operationalisation of GSI-focused interventions. One such activity will be to work to integrate a GSI approach into the proposed refocus on family planning / birth spacing. / Increased focus on family planning / birth spacing / The family planning / birth spacing component, as part of the South Sudan Comprehensive Reproductive Health approach, was not focused within the programme until very recently. A greater emphasis will be placed on child spacing, which will, it is anticipated, result in an increased demand for family planning commodities in South Sudan. There is a need to improve commodity security though partnerships, for example with UNFPA, at no cost to the project. The programme will collaborate with other reproductive health partners to ensure supplies for the commodities are adequate for the anticipated rise in demand following programme’s behaviour change interventions. / The addition of an explicit nutrition component / While nutrition was included in the programme as part of the MOH’s minimum Basic Package for Health and Nutrition, it did not get any particular emphasis. Recent evidence has shown extremely high levels of malnutrition in South Sudan. The programme provides a relatively stable health systems platform to swiftly integrate and scale up priority nutrition specific interventions targeted at under-five children and pregnant and lactating mothers. The programme will continue to support the strengthening of comprehensive county health planning in order to promote coordination between all health and nutrition service providers in a county.The programme will use DFID’s centrally managed ‘Matched Funding for Nutrition’ grant to integrate and strengthen nutrition component in the programme. DFID’s Policy Division’s Nutrition team will provide technical oversight and advice to DFID South Sudan for the component. / Building in greater flexibility into the project to cope with emergencies / HPF and its partners continue to work in a highly volatile environment with periodic flare ups of violence or epidemics that require a rapid response by implementing partners close to the emergency. The programme has been flexible in responding to some emergencies. However it has been learnt that simplified and pre-defined procedures to respond to small to medium scale emergencies can improve the response time and effectiveness. More flexibility will be built into contracts, including for example a budget line or ceiling (a minimal resource sufficient to respond urgently before other help/resources arrive) and defined triggers to use the funds immediately without long and bureaucratic approval process. As part of its support to strengthen comprehensive county health planning, the programme will provide an added emphasis on emergency planning, preparedness and response. / Increased conflict sensitivity / The large-scale violence in South Sudan since December 2013 has highlighted the importance of ensuring that programmes are designed and implemented in a way that, at the very least, does not increase conflict, and hopefully even contributes to reducing conflict. HPF developed a conflict sensitivity strategy in April 2013 and adopted a conflict sensitive approach to programming as part of the Interim HPF Strategy developed in response to the December 2013 onset of violence. The volatile context and diverse and changing nature of conflict seen over the last few years, including a rise in localised conflicts over land and cattle for example, means that the conflict sensitivity strategy needs updating based on a renewed analysis. It also needs to focus on how the programme engages better with the beneficiaries, contributing to peace building through improved service delivery. / Some consolidation of contracting mechanisms / The FM currently manages some 56 contracts with 21 implementing partner NGOs. This requires a great deal of effort from both sides in the partnership. In addition there is a call from the National and State Ministries of Health, who have to spend significant time and resources to coordinate with a large number of partners, to try to reduce the number of contracts in each State. More efficient alternatives, such as contracting at state level with a group of NGOs with one clear lead, will be adopted. The programme will try to ensure well-functioning South Sudanese NGOs are not disadvantaged when it comes to opportunities in the programme, by encouraging them to partner with good national and international NGOs as a consortium. The focus on capacity building of national NGOs will be enhanced. / A more significant allocation for essential medicines procurement / With the end of the Emergency Medicines Fund (jointly funded by USAID, DFID and Norway, managed by USAID) likely to result in drug stock outs commencing at the end of 2015 and a proposed second emergency procurement (jointly funded by DFID and USAID, managed by DFID) likely to last only until mid-2016, the pharmaceuticals situation in South Sudan needs major attention. It is unlikely that the GRSS will be able to take over the full drugs procurement in the next two years as expected in the business case. In such a context, the programme will include a larger proportional expenditure on drugs than the first 3.5 years. However, an important part of this approach would be to agree on a strict partnership with MoH where resources are leveraged from government to cover an increasing share of the drugs supplies, starting with the drugs not covered by the programme (for example, the drugs for tertiary hospitals), and in the long term, to ensure MOH take on the full responsibility for procuring and distributing the drugs. DFID, together with other health donors, will enter into a partnership compact with the MOH formalising GRSS’ commitment to increase investments in health. / Revisiting the technical assistance needs within the project / Much of the technical assistance (TA) at National and State levels commenced very late in HPF and there has been no evaluation of its effectiveness as it has not been in place for long enough. The technical assistance is envisaged to continue at around the same level of inputs but there will be a refocussing towards areas where the programme has comparative advantages. Depending on the conflict sensitivity analysis, a more nuanced approach to TA and capacity building of MOH at national and state levels will be taken.A more harmonised approach to implementing partners’ technical assistance support to County Health Departments will be defined and implemented to ensure the objectives of HPF support at this level are provided. / Community demand for health services integrated into the existing HSD and HSS sub-programmes / Under HPF, Community Engagement was one of the three pillars of the programme (along with Health Service Delivery (HSD) and Health Systems Strengthening (HSS)). In practice most activities were undertaken through the implementing partners under HSD while little central direction took place. It is considered more appropriate to integrate the community engagement programme elements of HPF, as a key component of primary health care, into the HSS stream, for national policy, guidelines and training outline development, and into HSD, for implementation. / The new GRSS policy for community level health care, the Boma Health Initiative, aims at (i) intensifying behaviour change communication to increase health seeking (demand) and healthy behaviours by communities and families, and (ii) increasing their access to primary health care. This is very important in South Sudan where more than half the population do not have an access to a health facility within five kilometres. The programme will support the implementation of this innovative policy, adapted from the successful Health Extension Programme of Ethiopia, through field testing of implementation modalities prior to any scale up. / Expansion of HPF into Western and Central Equatoria states / The merging of the two additional states, currently supported by the USAID funded Health Sector Support and Integrated Service Delivery projects, will contribute to the development of a unified health system in South Sudan. There are strengths within the two state projects that will contribute to improving the HPF programme as well as the other way round. The projects have not supported hospitals in these two states, as opposed to the current HPF states, and hence the programme needs to make new and high level of investments in hospitals. However the quality improvement approaches have been rolled out in these two states already, requiring relatively smaller inputs. The expansion is likely to deliver increased attributable results and better value for money for all donors, with a considerable decrease expected in the overhead and opportunity costs for these states. / Relative increase in cost / Based on the projected spend in the first 3.5 years, the programme currently invests £5 per capita. An early estimate for the outer two years suggests a requirement of £7 per capita. This increase is mainly due to an additional provision of pharmaceuticals, enhanced focus on emergency preparedness and response, scale-up of some interventions (e.g. family planning/ birth spacing) , and rise in cost of operations. More data and analysis are needed to confirm the unit cost of essential health package in South Sudan. The programme covers more than just delivering the essential package; including building long-term capacities and strengthening systems and support to maternal and child health services in the hospitals. In addition the programme has already exceeded most of the expected outputs and outcomes. Based on our theory of change, we can expect that the impact will be achieved; so even with this increase in per capita cost the programme would still represent good value for money.
[1] Source: South Sudan Household Survey 2010