# Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Kolkata Urban Services for the Poor (KUSP)
Programme Value: £5.5 million (Technical Assistance)		Review Date: 19th January 2015
Programme Code:	Start Date: 24 September 2012	End Date: December 2015

Summary of Programme Performance
Year	2013	2014	2015
Programme Score	A	A	A
Risk Rating	Medium	Medium	Medium

Summary of progress and lessons learnt since last review

Good progress has been made during the last year, KUSP programme has met expectations and is on-track to achieve its objectives by the end of project (December 2015). DFID’s Technical Assistance (which follows a successful financial assistance programme which ended in 2012) has enabled the project to achieve many of the purpose level indicators.

As intended, KUSP has played a critical role in supporting the Government of West Bengal (GoWB) in implementation of the national Rajiv Avas Yojna (RAY) and in institutionalising policy and regulatory reforms. As a consequence, the state has been able to access Central funding of £1.8m (Rs.18.4 crores)for preparation of Slum Free City Plan of Action(SFCPoA)’s. Five SFCPoA’s have been prepared (one already approved) so the State can potentially access funds to the tune of £250m (Rs 2,549 crores) for housing and infrastructure development. This support will also help 87,000 slum households to receive property rights.

Other key reform measures have been undertaken which will have sustainable developmental benefits for the poor. Policy support on amending the Thika tenancy act and notification will enable nearly 28,000 slum dwellers to construct their own houses. On institutionalising reforms, e- Governance modules have gone live in more than 30 Urban Local Bodies (ULBs). Draft Development Plans (DDP’s)/and City Development Plans (CDP’s) of 64 ULBs have been prepared and submitted for approval. The programme has helped the state in influencing and drafting of new policies such as the solar roof top policy, PPP guidelines and on affordable housing policies for the urban poor. The policy support on preventive strategy has facilitated in the signing of a Memorandum of Association (MoA) between GoWB and the Ministry of Housing and Urban Poverty Alleviation (MoHUPA) for implementation of reforms to enable making cities slum free.

KUSP has also contributed to the 1HMG priorities by working with the British Deputy High Commission (BDHC) Kolkata on a joint UK-KMC (Kolkata Municipal Corporation) Memorandum of Understanding on low carbon and climate resilient Kolkata. Due to a late start, there has been limited progress in some of the intervention areas such as the setting up of Public Private Partnership (PPP) unit, heritage conservation, service level benchmarking and city sanitation plans. Given that the project has less than a year to run, DFID will need to track progress closely and consider how best to continue support to this component.

One of the key lessons is that progress in KUSP has been largely dependent on political will. Progress has been satisfactory in areas where there was a strong political commitment such as in the preparation of slum free city plans, land tenure security etc. In other areas like revenue reforms and PPP there is little traction and therefore progress has been limited. Moreover, frequent changes in policy priorities of the state or CMU (Change Management Unit) has also led to frequent revision of deliverables for the PMU-2 (Project Management Unit – 2) and this has resulted in slow progress in some of the areas.

DFID and the GoWB agreed that since the capacity of many of the non- KMA ULBs is still very weak, closure of the programme in March as was originally envisaged will severely affect the delivery and sustainability of some of the reforms that are presently underway.

Summary of recommendations for the next year

As this is the last year of the programme, the focus needs to be on banking the gains from our financial assistance which ended in 2012, and the reforms programme that has happened alongside - for instance, through a strong focus on KUSP leveraging additional resources for sustainability, and ensuring that lessons are documented and shared.

- For sustainability and institutionalisation of the reforms process, it is important to extend the contracts of both the technical agencies PMU-1 and PMU-2. The DFID Head of Office has approved the request of extension of the programme; however, approval from GoI is awaited. The contracts will be extended after receiving approval from GoI.
- The priorities of the remaining period of the programme should align with the administrative calendar priorities of the GoWB which is being monitored on a quarterly basis by the Minister and the Chief Minister.
- CMU should ensure that institutionalisation of reforms (e-governance, accounting reforms) and capacity building of ULB’s and allied agencies under Municipal Affairs department should be the other focus areas for both the TA agencies DFID and CMU to prepare a workplan that will allow the KUSP reforms agenda to sustain beyond the ongoing DFID TA support (up to 2015). GoWB will also need to extend CMU till March 2017 for continuation of reforms. (Action: KUSP Project Director and DFID, UADD).

Building on the good work done on drafting of the state policies for housing for the poor, the TA team needs to provide implementation support to GoWB on Housing for All which is a flagship programme of Government of India and a key priority for the state government.

The British Deputy High Commission and the ECGU team need to speed up contracting and delivery of the climate change piece of work which they are carrying out with Kolkata Municipal Corporation. An assessment of progress to be undertaken in April 2015. The Logframe needs to be revised to capture the climate change work and reflect the changing priorities of GoWB under Output 2 (by March 2015).

DFID to consider by March 2015 the appropriate focus and approach for an assessment and a project completion report which will need to align with the project closures).

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	KUSP Intervention Summary
DevTracker Link to Log frame:	KUSP Logframe

Outline of the programme
DFID has allocated a £5.5 million technical assistance (TA) support (2012-2015) to Government of West Bengal to improve the quality of life of poor people in Kolkata Metropolitan Area (KMA). This is an extension of the earlier £102.7 million programme (£94.06 million FA and £8.64 TA; 2004-2011). The FA support came to a close on 31 March 2011 as part of DFID’s graduation from West Bengal and a £5.5 million TA-only extension was agreed up to March 2015. Under this support, 2 Project Management Unit’s (PMU) have been set-up to support the GoWB to access Rajiv Aawas Yojana (RAY) – the slum free cities initiative of Government of India and to take ahead second generation urban reform measures in West Bengal especially focusing on planning, public financial management, and sanitation.

The state has 126 urban local bodies and around 35% of the urban population of KMA lives in slums and informal settlements largely constituting Scheduled Castes and Muslims. They live in a degraded environment and lack basic services. Strained state fiscal resources and lack of capacities within state institutions were acting as a barrier for providing access to basic services to the poor in an inclusive manner.

The UK support upto 2011 (FA and TA) took a three-pronged approach. First, KUSP introduced inclusive urban planning and governance; second, it provided basic services in the worst-off slums in Kolkata Metropolitan Areas as well as filled-in critical infrastructure gaps at the town-level and inter-municipal level that directly benefits the poor; and third, it supported a process of local economic development aimed towards skill building and micro-credit development among the poor. Intrinsic to all three approaches was capacity building targeted at state and local governments, non-government organisation (NGOs) and community groups (comprising of slum residents).
In 2010, the Government of India launched a Rs.33,000 crore (£3.3 billion) centrally sponsored scheme called Rajiv Aawas Yojana (RAY) as part of its slum-free cities initiative.RAY supports a whole-city whole-slum approach to slum upgradation with a focus on in-situ (at-site) up gradation through community-based planning, implementation and monitoring structures. RAY also provides grant assistance for housing up gradation and/or construction of new housing for slum residents.
States and cities interested in accessing RAY have to implement three mandatory reforms (pro-poor earmarking of municipal budgets, land reservation for low-cost housing development, and tenure security to all beneficiaries), prepare memorandum of agreement (MoU) committing to reforms, prepare a slum free city plan of action (SFCPoA), prepare detailed project reports (DPRs); and put in place institutional reforms necessary to sustain the reform action in each state. While some states have accessed RAY, capacity constraints in West Bengal have so far precluded its urban local bodies from accessing this scheme. Considering that Kolkata Metropolitan Area (KMA) has over 2.5 million poor residing in slums and informal settlements, access to RAY can help improve the quality of life of the city-region.
In the TA-only phase (2012-15), the UK is supporting GoWB and 50 urban local bodies to access the benefits offered under the RAY initiative, as well as embed first generation KUSP reforms within the existing institutional structures to ensure sustainability, and introduce second generation reforms’ targeting improved DPR’s that enhance access to improved sanitation.
The Municipal Affairs Department is the lead department for this project. A Change Management Unit (CMU) has been set up under the Municipal Affairs Department to oversee the implementation of the programme.
In the TA-only phase (2012-15), DFID’s Technical Assistance is being delivered through two Project Management Units (PMU), located within the GoWB’ s Change Management Unit (CMU). These PMU’s were sourced through an international competitive bidding process:
PMU 1, contracted to Deloitte, is focused on supporting RAY is situated within the Change Management Unit (CMU).

PMU2, contracted to ICF-GHK, functions as a Technical Assistance Support Unit to help sustain first generation KUSP reforms and initiate second generation KUSP reforms, create improved access to sanitation, and support the adoption of service benchmarks in municipal governments. The PMU2 will undertake the critical function of embedding two generations of KUSP reforms in CMU, so that the institution can be sustained beyond DFID support.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual outcome assessment

The project is on track to achieve its objectives of achieving an improved quality of life for poor people in the municipal areas of West Bengal. The outcome indicators which included efficient implementation of the RAY programme and number of poor people who secure access to land as an asset have been met. The remaining period of the programme will focus on achieving the targets on water and sanitation.

Most of the Logframe indicators in Outputs 1 and 2 have met expectations or moderately exceeded expectations. Substantial progress has been made related to developing SFCPoA‘s, policy and regulatory frameworks, institutionalising municipal reforms and leveraging GoI resources. However, limited progress has been achieved in revenue augmentation, public private partnerships, service level benchmarking and city sanitation plans. It is highly recommended that in order to sustain the reforms and achieve better outcomes of the ongoing work it is important to extend the programme and contracts beyond March 2015.

Overall output score and description
Overall, the project scores an ‘A’ (outputs met expectations). Both the outputs have met expectations and scored an ‘A’. CMU continues to influence policy and strategy development around urban poverty alleviation and its support is instrumental in leveraging and accessing central funds. Though there has been good progress on Output 2, targeted support and interventions need to continue to address the capacity and service delivery gaps.

Has the Logframe been updated since the last review?

Yes The Logframe was updated in 2014 to reflect the changes in deliverables proposed by the CMU.
DETAILED OUTPUT SCORING (1 page per output)

Output Title	Output 1: Improved Urban Planning and Governance in KMA urban local bodies (ULBs
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	60
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicator(s)	Milestones	Progress	Score
1.1 Institutional, policy, regulatory and systemic reforms undertaken to access reform linked pro-poor programs	PPP policy developed and accepted by Government / Thika tenancy Act amended and notified / Affordable housing policy or urban drafted. / Pro-poor earmarking in municipal budget (25%)	PPP policy drafted and guidelines submitted for GoWB. Decision pending from Government. / Thikka tenancy act amended and notification issued to enable slum dwellers to construct own house with occupancy certificate issued to occupiers of Thika and khatal land. Estimated 28,000 dwellers to be benefited. / Restrictive Land laws amended to allow for large housing projects. / Affordable Housing policy for urban drafted and submitted to government. / State level Action plan for achieving Housing for All have been prepared and submitted to MoHUPA. / Upto 27% of the ULB budget earmarked for pro-poor spending.	A +
1.2 Domestic resource mobilization (own tax revenue of KMA ULBS in Rs. Lakh)	Study on revenue enhancement in non-tax revenues / Assessment of conversion to unit area based system for one local authority.	Draft completed, thereafter discontinued. / Study on valuation methods in progress. Draft findings & recommendations likely to be presented in March 2015.	B
1.3 Number of ULBs in which six critical e-governance modules fully operational	20 municipalities to have functional modules on: Birth and death registration / Trade licensing / School information system / Public grievance redressal / Administration, MIS, health, Financial Accounting Systems and (PuroHisab) – debugging support	Nearly 40 municipalities have been covered and they are at various stages of implementation and capacity building initiatives. / Birth and death: registration In 37 KMA ULB’s has gone live and training has been provided. / Trade licenses: Training has been provided in 33 municipalities and the module has gone live in 17 ULB’s. / School information: Training has been provided in 11 schools though none have gone live as yet. / Public grievance and redressal: Training provided to 11 municipalities and none have gone live as yet. / Payroll, Admin and MIS: Gone live in 39 ULBs and staff trained.	A
1.4 Number of SFCPOAs prepared and approved.	5 SFCPoA’s prepared and submitted to GoI	Five SFCPoAs have been prepared and submitted. One SFCPOA is approved by MoHUPA, GoI. A further three SFCPoA’s are under preparation by TA team / PMU-1 is also providing support to GoWB in the bid management process for selection of agencies for preparation of SFCPoA’s and will quality assure them. .	A

Progress against expected results:
Indicator 1.1: Institutional, policy, regulatory and systemic reforms undertaken to access reform linked pro-poor programs
The DFID-supported PMU has played a critical role in adoption and implementation of the two mandatory RAY reforms in West Bengal, thus helping the state to access RAY funding.
The TA teams have helped the state in preparation of PPP guidelines for Municipal Affairs Department and ULB’s which is under consideration of GoWB. The TA team has also helped in the preparation of a Preventive Strategy for making the city slum free, Property Rights Legislation and Amendment of restrictive land laws for large housing projects. A draft on affordable housing policy for Urban West Bengal has been prepared and submitted to GoWB. Additionally, a state level action plan for achieving housing for all has been prepared and submitted to MoHUPA.

The policy support on land rights has helped in a new notification which will enable around 28,000 slum dwellers to construct their own houses on thika and khatal land.

Indicator 1.2: Domestic resource mobilisation (own tax revenue of KMA ULBS in Rs. Lakh)
There has been limited progress. The programme has a mandate of helping the Municipal Affairs Department and municipalities to augment tax revenue. A study had been initiated to assess the potential for enhancing non tax revenue in ULB’s, however it was discontinued mid-way due to changes in priorities of the department. Government has now requested PMU2 to undertake a study on valuation methods, the draft findings & recommendations of which are likely to be presented during February 2015. A study has also been commissioned to assess the revenue potential for migrating to unit area taxation in Naba Diganta Township.
Indicator 1.3: Number of ULBs in which six critical e-governance modules have been rolled out
Progress has been satisfactory considering the weak infrastructure and capacity gaps in non- KMA ULBs. Against a target of 20 ULB’s the e-governance module has been rolled out in 40 ULBs but in in a phased manner. The six critical governance modules are at different stages of implementation. The birth and death registration modules have gone live in 37 ULBS; the payroll, admin and MIS have gone live in 39 municipalities. Trade license training has been provided in 33 municipalities but has gone live in only 17 municipalities. The modules on school information system and infrastructure management system are yet to go live in any ULBs.
Indicator 1.4: Number of SFCPOAs prepared and submitted
Five SFCPoA’s have been prepared to access funds worth Rs. 2540 crores for housing and infrastructure development. This will also help around 87,000 slum households to achieve property rights. One of the SFCPoA’s has already been approved by MoHUPA. Three more SFCPoA’s are under preparation and are expected to be completed by March 2015.The TA team is supporting the department in selection of agencies for preparation of the remaining 46 SFCPoA’s and they will also be responsible for quality assuring the SFCPoA’s prepared by the agencies.

Key Points
- There needs to be greater clarity from the side of the government on the revenue augmentation issues and the nature of support they require from PMU-2.
- There is a huge capacity gap in non-KMA ULB’s, and proper incentives to recruit qualified personnel along with focused capacity building initiatives should be prioritized for sustaining and implementation of the reforms process.
- PPP guidelines for Municipal Affairs Department and Urban Local Bodies need to be approved at the earliest.

Summary of responses to issues raised in previous annual reviews (where relevant)

- DFID supported PMU has prepared and submitted four additional SFCPoAs as recommended in the previous AR. Additionally, the PMU is preparing three more SFCPoA’s which are expected to be completed in this quarter.
- DFID PMU has focused on critical policy priorities including e-governance roll out. A Number of new polices have been drafted and e-governance modules have been rolled out in around 40 ULB’s which are at different stages of implementation.
- As recommended, PMU-1 has drafted the Affordable housing policy for urban West Bengal and a state level action plan for achieving Housing for All has been drafted and submitted to MoHUPA.

Recommendations
- PMU-1 needs to complete the ongoing three SFCPoA’s, carry out 6 more SFCPoA’s through a hired agency and take on 2 more with their own in-house resources.
- PMU-1 to support GoWB in implementation of the Housing for All scheme after it is formally launched. It will provide technical support to the State Urban Development Agency (SUDA) for the Housing for Urban Poor programme.
- After approval of the PPP guidelines, PMU-2 needs to prepare sector specific guidelines and training materials for housing programmes, services and commercial projects.

Output Title	Output 2: Supporting reforms implementation in target ULBs: Met expectations
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	40
Risk revised since last AR?		No	Impact weighting % revised since last AR?	No

Indicators	Milestone	Progress (2014)	Score
Status of service level benchmarking (SLB)	SLB: PIP and ISIP prepared for five towns.	Preparation of PIP and ISIP kept in abeyance as per recommendations of State SLB Committee;	C
Slum boundary delineation, slum mapping, and validation of Urban Statistics for Human Resource and Assessments (USHA) data	(a) ULB’s completing slum boundary delineation: 40 / (b) ULB’s completing GIS mapping: 20 / (c) ULB’s completing Slum MIS: 20	44 out of 48 ULB’s have completed the task of slum boundary delineation. / GIS City base maps completed in 33 ULBs leveraging the DDP spatial data and Remote sensing imagery procured for 50 ULBs. / 22 ULBs completed slum mapping	A++
RAY DPR’s	RAY DPR: 5 approved	RAY DPR: 6 Approved projects that are valued at around Rs. 875 crores.	A+
Access to Better Water Supply and Sanitation Services	Pilot city sanitation plan in 5 ULB’s initiated / DPRs prepared for Solid Waste Management (SWM) projects for 5 towns.	No progress due to change in priorities of CMU / PMU – 2 directed to prepare a Solid Waste Management Strategy Paper in November 2014, this will be a guiding document for SWM projects in the State of West Bengal.	C

Progress against expected results: Overall, the output on supporting reforms implementation in target ULBs has met expectations. Implementation support work on preparing the basic groundwork in 40 KMA ULBs on accessing RAY funding has performed extremely well due to the efforts of CMU with support from the DFID-supported PMU. Work on slum boundary delineation, geographic information system (GIS) mapping and creation of slum management information system (MIS) has progressed strongly. However, there have been delays and changes to the milestones and scope of work of the PMU2 on Service Level Benchmarking which has impacted the performance of output indicators.
The work on making Kolkata climate resilient has been initiated and the solar rooftop policy and capacity building initiatives have been launched, based on the agreement signed between the British High Commission and the Kolkata Municipal Corporation. This piece of work started in November 2014, and was therefore not included in the last Logframe revision as an indicator. The Logframe will be revised by March 2015, when the project team will also assess progress and take a decision on forward actions.
Indicator 2.1: Status of service level benchmarking (SLB)
There has been no progress against this indicator. Preparation of Performance Improvement Plans (PIP) and Information System Improvement Plans (ISIP) has been kept in abeyance as per recommendations of the State SLB Committee. This will be revisited in April 2015 and the Logframe will be revised based on the findings.
Indicator 2.2: Slum boundary delineation, slum mapping, and validation of USHA data
In all, 44 out of 48 target ULBs have completed slum boundary delineation. Thirty Three ULB’s have completed GIS (Geographic Information Systems) mapping and work is in progress in another 17 ULBs. Similarly 22 ULBs have completed slum mapping and validation of slum household data across 57 parameters. These are absolutely essential for preparation of SFCPoAs, DPRs for identified slums which will then be in a position to access central funding of around £20m.
Indicator 2.3: RAY DPR’s
Six DPRs of project value £87M have been approved by the GoWB and submitted to GoI for approval and for funding under RAY. Implementation of these DPR’s will help around 2000 slum dwellers with improved infrastructure housing and property rights.
Indicator 2.4: Access to Better Water Supply and Sanitation Services.
There has been very limited progress. The preparation of five pilot city sanitation plans (CSPs) under KUSP has not taken off due to changes in strategic thinking in GoWB. The DPR’s for Solid waste management could not be commissioned due to lack of clarity and changing priorities of the department. In November 2014, CMU had made a request for preparation of a state level strategy option paper on solid waste management which is now underway. Based on the strategic options paper, PMU-2 will be responsible for the preparation of one typical detailed project report for one municipal body or cluster of municipal bodies for each strategic option.

Summary of responses to issues raised in previous annual reviews (where relevant)

A separate indicator on accounting reforms has not been included in the revised Logframe since the role of the TA team in this has been rather limited. The TA team is responsible for deputing accountants at the ULB level who would be responsible for work under the ULB’s guidance to finalise outstanding accounts till annual year 2011-12.

DFID supported PMU have taken a more active role in the preparation of DPR’s and in selection of agencies and monitoring of DPR’s. However, a more active role is desired from the PMU for ensuring preparation and submission of more number of DPR’s.

Due to change in priorities of CMU/department there has been no progress in service level benchmarking and city sanitation plans.

Recommendations
- PMU1 to focus on preparation, monitoring and quality assurance of DPRs. Around 30 DPRs have been targeted to be completed in the calendar year.
- Solid waste management strategy paper to be completed and two to three DPR’s prepared and piloted by December 2015.
- PMU2 to extend support to the preparation of Capacity Building plan for municipal bodies under the Comprehensive Capacity Building Programme (CCBP) of Union Ministry of Urban Development where solicited by CMU and MA Department.
- Support to operationalization of the remainder of the components of the CCBP where solicited by the CMU and the Municipal Affairs Department.

D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1 page)

Key cost drivers and performance

The key cost drivers are the two TA contract agencies mobilised under KUSP. The DFID-supported PMU-1 contract includes 63% cost for services/fees, 27% cost for administration/out of pocket expenses, and 10% for a resource pool. The PMU 2 (PMU2) contract includes 44% cost for services/fees, 16% cost for out of pocket expenses, and 40% for resource pool.

Expenditure in 2014-15 has been approximately £0.7 Million, which is roughly 35% of the forecasted amount of 2 million for F/y 2014-15. Around £0.1M has been spent till January 2015 on subcontracting / resource pool which has been mostly used for deploying resources at the municipality levels for institutionalising reforms process.

 Snapshot of finances is as below:
Total Budget:     5.5M

Technical Assistance contracts value:

PMU 1: £ 1.7M
PMU 2: £ 1.7M
Total Spend (As of February 2015):      £1.4 M

Year wise breakup of spend:

	2011	2012	2013	2014	2015
Budget	1.1M	0.5M	0.3M	2M	1.5M
Spend	Nil	0.5M	0.17M	0.7M	Nil
% of spend	O	100%	57%	35%	Nil

Low levels of spending have been due to delays in finalisation of the deliverables, particularly of the PMU2 due to changing priorities of the GoWB.

The PMU-1 contract is presently valid till March 2015 and expansion of scope to accommodate preparation of additional slum free city plan of actions (SFCPoAs), as requested by GoWB, is being structured and will add to the costs. A further no cost extension upto December 2015 is also envisaged for PMU-2 on request from the GoWB.

VfM performance compared to the original VfM proposition in the business case
No Business case or VfM analysis has been done for this programme since it was started a long time back in 2004. When Financial Aid support to the GoWB through KUSP came to an end in 2011, the programme was extended to provide TA support to GoWB towards implementation of RAY and institutionalising reforms in non- KMA municipalities. It is therefore not possible to compare VfM with the original business case.
Commercial Improvement and Value for Money
Towards ensuring VfM through TA consultants, the entire set of TA support areas agreed between DFID and GoWB have been structured into two large umbrella contracts, rather than a series of medium-sized contracts. This ensures saving of administration time within DFID, and makes it easier for both GoWB and DFID to monitor progress of the TA support, and ensure overall quality control in delivery of the projects.
Programmatic support to the British High Commission’s climate change initiatives has also been built into the existing PMU2 contract in order to ensure cross learning and value for money.
The role of project partners remains strong. GoWB has agreed to sustain CMU until December 2015 and strong performance of CMU on mobilising RAY funding is likely to further support its sustenance upto 2017. CMU is leading on policy and strategy engagement within GoWB on pro-poor reforms that are necessary for accessing RAY and urban reforms support.
Going forward, based on the Government of India’s approval for extension of programme there is a possibility of a costed extension for PMU-1 and no cost extension of PMU-2 till December 2015. A final decision on this will be taken in March 2015 based on actual spend and GoWB priorities.

Assessment of whether the programme continues to represent value for money

The programme represents value for money on the effectiveness, economy and efficiency parameters.

Economy

The economy aspect of the programme has been considered during the contracting of the TA teams in 2012&2013. This was reflected in the previous annual review. The focus on this year was ensuring the delivery. The economy aspect was considered during the course of the year in the subcontracting process. The recruitment and subcontracting of individuals and services were done at ensuring proper process and VfM.

Effectiveness

The preparatory phase support on RAY has already helped GoWB to access around £2m for preparation of SFCPoA’s. This itself is nearly double the amount spent by DFID on TA agencies from 2012 onward and represents a Cost-Benefit ratio of 2The support on preparation of 5 SFCPoA’s and DPR’s is expected l help GoWB to leverage around £250m of central funding. Preparation of SFCPoAs and support on amendment of Thika Tenancy Act will also provide tenure rights and housing to around 100,000 slum dwellers. However, the benefits of this cannot be monetised.

Efficiency
The support on rolling out of e-governance in 40 municipalities will lead to an increase in efficiency of service delivery in ULB’s though it cannot be quantified in monetary terms. Proper roll out of the e-governance modules will help in improving transparency and in reducing transaction time for the common citizens.

Quality of financial management

Expenditure on KUSP is incurred through payments to the two PMU’s who are paid on the basis of a combination of input and output related milestones. Both of these are monitored closely by the CMU and a streamlined approval process is being followed. Payments are linked to milestones and are reimbursed against invoices (with necessary documentation) and evidence of satisfactory delivery. The PMU’s are required to maintain supporting vouchers and other documentation for claims made under their contract along with an asset register.

DFID carries out regular checks on documentation and expenditure. Both the PMU’s prepare an annual work plan and budget which is agreed with DFID India. This is monitored by DFID on a quarterly basis and forecasts adjusted according to the progress on deliverables.

DFID monitors PMU’s expenditure and performance based on the review of Monthly and Quarterly Progress reports which are first approved by the Project Director, CMU and subsequently by DFID.
DFID additionally undertakes financial risk assessment as per internal guidance.

E: RISK (½ page)

Output Risk Rating: Medium
Assessment of the risk level
The original output risk rating of ‘medium’ continues, primarily on account of concerns of delays and changes to the deliverables of the TA support and upcoming state elections in 2016 that may hamper taking ahead new reform measures.

Overview of programme risk

Low. Since the programme only provides for TA support (directly managed by DFID), risks of funds not being used as intended is very low. There is a risk of delay in delivery of the climate change work. The risk matrix will be revisited in April 2015 after assessing the progress on the climate change piece of work and political environment of post Kolkata municipal elections.

Outstanding actions from risk assessment: NA

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe

The programme is having a low spend and is expected to continue to do so. The deliverables and performance of PMU-1 are on track. There has been slow progress in PMU-2 due to change in leadership and frequent changes in priorities of GoWB. It is expected that around £3.5M will be spent till December which is close to the contracted values. Programme outputs and deliverables have been dynamic and have changed to reflect the changed perspective of the GoWB.

Despite various delays (start-up, procurement and changing priorities), the project is likely to achieve most of the Logframe milestones by the end of project provided the GoWB continues its support and DFID continues to engage frequently to ensure challenging timelines are met.

Performance of partnership (s)

The TA teams have earned consistently positive feedback from the GoWB in the delivery of the KUSP programme. This has been noted by the Project Director CMU and by the Municipal Affairs Department and recorded in the minutes of the Steering Committee Meetings. Both PMU’s have met their role as a knowledge and service partner to the GoWB.

Asset monitoring and control

In accordance with DFID guidelines on the Procurement of Goods & Equipment, both PMU teams maintain a Fixed Asset Register as an inventory of all project goods and equipment which are procured through the project funds. The Register is updated monthly and shared with DFID on a bi-annual basis.

For all assets costing over Rs. 5,000, three quotations are called and a timeframe given to vendors to submit. The quotations will be judged by the respective PMU requiring the items. A vendor is then selected based on cost, quality, reputation and availability.

No project assets have been written off to date, however in the case that this happens; this will be reported to DFID as necessary and noted in the Asset Register. The need for disposal of assets will be assessed on a case by case basis and agreed between DFID and the PMU teams as necessary. The last asset inventory was conducted in October 2014 (EDRM 4661176).
G: CONDITIONALITY (½ page)

Update on partnership principles (if relevant)

DFID’s four Partnership Principles (PPs) are not specifically detailed in the formal agreement of KUSP to support the GoWB. However the articulation of DFID support to GoWB through KUSP both imbue these principles and support broader goals as detailed below:

1. A commitment to reducing poverty and achieving the Millennium Development Goals (MDGs): The GoWB is committed to the implementation of pro poor reforms in the State and has initiated several actions towards this. Development of urban spaces, housing for all simplification of transactional process with the Government and streamlined services all contribute towards helping poor people achieve a better quality of life.
2. A commitment to respecting human rights and other international obligations: The GoWB has through the KUSP programme demonstrated a commitment to improve the provision of services to citizens and increase accountability and transparency within the administration. This will help poor people achieve better access to services and develop a better standard of living. In particular the Housing schemes for poor people will reflect positively on health, education and sanitation services.

A commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption: KUSP has helped GoWB to introduce stronger systems and procedures for strengthening public financial management and safeguards against corruption. These include mandatory use of financial management and procurement manual for all programme expenditure, bi-annual reviews, internal and external evaluations.

A commitment to strengthening domestic accountability: KUSP reforms remain a priority for the Government of West Bengal. GoWB is focused on reducing the barriers between public and government by promoting e-governance, and access to services.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation

In 2011, at the end of the FA spending and original project period an independent project evaluation had been carried out. For the TA only phase, an independent evaluation and value for money assessment will be carried out by the end of project that will capture the effectiveness and impact of the KUSP programme including the TA support on the wider urban development strategy. These lessons will also help to inform DFID India’s wider approach to Technical Assistance post 2015.

Monitoring progress throughout the review period

The KUSP programme has been monitored jointly throughout the review period by the Principal Secretary, Municipal Administration, GoWB with the Project Director CMU, the Managing Trustee WBMDF and the DFID team. Quarterly steering committee meetings have taken place and progress on the ground has been assessed by the DFID team comprising Shantanu Das (Senior Responsible Officer) and Radhika Singh (Programme Manager). Both TA teams provide monthly and quarterly progress reports which are signed off by the Project Director CMU.

The joint annual review was led by Principal Secretary, Municipal Administration, and GoWB and supported by Project Director CMU, Managing Trustee WBMDF, the DFID-sponsored PMU team and the PMU2 team. DFID was represented by the Task Team Leader and the Urban Advisor. The entire CMU team and concerned nodal officers from the MA Department were present, as were representatives of both TA team’s. The team reviewed progress over the last reporting year through a series of presentations and discussions. Data/information provided in this annual review has been supplied by CMU and PMU. Project scoring has been done by DFID.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate programme scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action on previous recommendations
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives (including corporate results targets). Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the outcome by the end of the programme
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Key lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Key actions / Any further information on actions (not covered in Summary Sheet) including timelines for completion and team member responsible
Has the Logframe been updated since the last review? What/if any are the key changes and what does this mean for the programme?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the Logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the Logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessment
Key points
Summary of response to programmessues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at programme approval. If so, why?
VfM performance compared to the original VfM proposition in the business case? Performance against VfM measures and any trigger points that were identified to track through the programme
Assessment of whether the programme continues to represent value for money? / Overall view on whether the programme is good value for money. If not, why, and what actions need to be taken?
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / What are the changes to the overall risk environment/ context and why? / Review the key risks that affect the successful delivery of the expected results. / Are there any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks? / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from risk assessment / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment/ Programme risk matrix / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the programme and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / How could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for where it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year, including on human rights? / If yes, what were they? / Did you notify the government of our concerns? / If yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the programme / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the programme design working out in practice in this programme? Are modifications to the programme design required? / Is there any new evidence available which challenges the programme design or rationale? How does the evidence from the implementation of this programme contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process