Annual Review - Summary Sheet

This Summary Sheet captures the headlines on programme performance, agreed actions and learning over the course of the review period. It should be attached to all subsequent reviews to build a complete picture of actions and learning throughout the life of the programme.

Title: Somaliland Development Fund (SDF)
Programme Value: Overall £38.9m / (DFID’s contribution £20m)		Review Date: January 2015
Project Code: / 202946	Start Date: / December 2012	End Date: / August 2017

Summary of Programme Performance
Year	2013	2014
Programme Score	A	A
Risk Rating	Medium	Medium

Summary of progress, lessons learnt and headline actions

The Somaliland Development Fund is designed to support the Government of Somaliland (GoSL) in addressing immediate and critical development needs by funding the recurrent and capital costs of projects that are aligned to the National Development Plan (NDP) 2012-2016. This is consistent with the underpinning principles of the Somaliland Special Arrangement (SSA) which sets out clear expectations that current and future development programmes will align with overall Government priorities and sector policies and plans. In this context the programme delivers a portfolio of high priority fiscal investments across a range of sectors and has aligned to Government priorities whilst at the same time building a strong sense of ownership. Although still in the early stages of implementation, the SDF is proving to be a model for adaptive programming in the context of the New Deal.

The Impact of the Somaliland Development Fund (SDF) is a more stable and prosperous Somaliland and the Outcome is improved and better resourced core state functions for the people of Somaliland. There are five Outputs associated with this:
1. Improved water and road infrastructure to promote economic and socially equitable development,
2. Improved productive sectors enhancing incomes, food security and livelihoods,
3. Improved capacity of GoSL institutions to manage development projects,
4. Enhanced citizen perception of Government priorities, activities and expenditure, and
5. Improved capacity to prioritise development objectives and plan and budget development activities.

The Fund has successfully leveraged other Donors to contribute and DFID’s initial contribution of £20m and DANIDA’s investment of £12.4m has now been supplemented with additional resources from Norway (£3m) and The Netherlands (£3.1m) and the EU also committed to joining in 2015.

The Implementation Phase of the SDF has seen significant progress in 2014. At the time of preparing this report, all six first wave projects (roads rehabilitation, soil and water conservation, livestock holding grounds, forests and grazing reserves, urban water and rural water) were fully operational having set up Project Management Units (PMUs) within the various Ministries and government agencies, recruited staff and launched tendering processes for procurement of implementing partners (contractors). One project (road rehabilitation) has completed the process of procuring the contractor and commenced work on the ground. The other first wave projects are at various stages of procurement (tendering) whilst the second wave of projects are at various stages of concept and full proposal development.

A significant factor in the Somaliland Development Fund’s (SDF) planning and delivery is its alignment with the ethos of the Somali Compact and the Somaliland Special Arrangement (SAA). While not strictly part of the SDRF funding apparatus, the prioritising and decision making processes and the degree of Government ownership of the planning, tendering and delivery of projects, fits with the expectations of New Deal delivery. A key strength of the Fund is the powerful sense of partnership that has been established with the Government stakeholders and their resulting sense of ownership of the funded projects from the very outset. The SDF is the Government’s preferred aid modality as set out in the SSA.

The major challenge in most cases has been the limited capacity to plan coherent projects in the Ministries and Mott MacDonald has been at pains to develop these programmes at a pace that ensures Government leadership at all times. This result has seen some slower delivery than expected when the log frame was updated by all key stakeholders in August / September 2014.

In addition to developing, testing and putting the administrative procedures and protocols into operation, during the early months of 2014, the Secretariat and Managing Agents (Mott McDonald), have started to turn the SDF concept into reality by taking two page concepts from four Ministries and two parastatals and turning them into approved comprehensive programme documents by the end of the year.

The start of the year was dominated by the finalisation of the inception period. Mott MacDonald used this break in the contract to demonstrate the effectiveness of its systems – finance, procurement, poverty analysis, political economy and gender analysis, and embedding a team in country that was fit for purpose. The Government, DFID and DANIDA unanimously endorsed Mott MacDonald for full contract implementation.

From the award of the implementation contract in April to the year-end, Mott MacDonald has front loaded technical assistance to finalise project documentation to a high standard and have worked meticulously through an impressive rate of contracts for service delivery and infrastructure in an unpredictable procurement landscape. For example, 72 tenders have been submitted to both the domestic and international market during 2014. This number reflects the challenges of the projects under design that in all cases have multiple contracts required – for example the roads maintenance has separate contracts for the laboratory equipment, vehicles, and actual road maintenance.

During the implementation phase of the Fund some early lessons and actions are:

1. The capacity building approach with intensive government involvement takes longer for preparatory activities such as proposal development. Such an approach has resulted in strong ownership by the government. For example, it takes an average of 120 days to transition from concept note to full project proposal. It is proposed that Mott MacDonald explore ways of reducing these timelines as capacities and acceptance of new ways of working become embedded in government.
2. Consolidating project focus in the same thematic areas for second wave projects considerably reduces the amount of time it takes to develop a new project. An example of this is the second Roads project which took about a half of the time the first one took to develop and commence implementation. This is a reflection of the learning that has already taken place with the Roads Development Agency during the development of the first project.
3. The focus on the measurable benefits to citizen beneficiaries, including women and marginalised groups. While the monitoring and evaluation framework established by the programme managers is appropriately robust, there is a rich emerging evidence on projects’ impact on citizens’ wellbeing that to date is relatively untapped; but this will addressed by the citizens’ perception survey in the first quarter of 2015 and by the extensive survey work planned by the Communications Hub within the Ministry of Planning and National Development (MPOND).
4. The time required to establish systems that enable government to deliver against the project cycle, the relatively dormant private sector, and appropriate adherence against our risk appetite in Somaliland has seen some slower delivery that expected. It is worth stating at this annual review that the envisaged timeframe for the SDF (4 years) may be too short in this context and given the level of challenge. Therefore, a decision point on whether to request a no-cost extension should be made, based on results delivered, by the next annual review at the latest. There are lessons here for the much larger World Bank and UN multi donor trust funds under design.

A. Introduction and Context (1 page)

DevTracker Link to Business Case:	http://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/
DevTracker Link to Log frame:	http://devtracker.dfid.gov.uk/projects/GB-1-202946/documents/

Summary of Programme

The SDF is managed by a private sector managing agent (Mott McDonald) who won the contract following an OJEU tender process which ran from January to August 2013. The founding Donors, DFID and DANIDA, are testing the market and broadening the range of implementing partners in Somalia both to improve choice and to drive performance improvements and value for money. The Fund has an inclusive governance structure with a JSC at the strategic, decision making level. This body now meets every quarter and comprises both the Minister of Planning and State Minister of Finance and Donor representatives with the secretariat provided by Mott McDonald. This is underpinned by a more regular monthly Programme Board, comprising teams from the Ministries implementing projects, and deals with more operational issues and challenges.

The programme’s design is rooted in an understanding of the processes by which stability and prosperity can be effectively achieved in fragile environments and informed by best practice in operating pooled donor funds in such contexts; the key lesson from which is that the greater a government’s level of responsibility and ownership of a fund is, the more likely it is to have long-term sustainable impact on its core capacity.

The SDF was designed to be as close to government systems as fiduciary risk allows (e.g. funds are aligned to Government priorities and are on budget but do not flow through government systems). The public financial management (PFM) reforms are a clear part of the SDF’s future. The pace of PFM reform has had its challenges in 2014 and the SDF has ensured that its joint steering committee (JSC) and public financial management (PFM) steering group meetings are held back to back. This ensures the latter happens and that Ministerial presence is ensured to keep the reform moving. It is the civil service reform area that the SDF has had the most influence over in 2014 by similarly influencing the agenda and training civil servants via the Civil Service Institute. Alongside improvements in Public Finance Management and more general Public Sector Reform it is intended that the SDF will progress from being an investment fund to an incentive fund incrementally as key benchmarks are met. This includes an ongoing commitment by Government to increase its own domestic revenues and share of the Budget committed to development expenditures.

The SDF partner institutions are: Hargeisa Water Authority, Roads Development Authority, Land Commission and the Ministries of Planning, Agriculture, Livestock, Environment, Water Resources, Health, Education, Fisheries, Labour and Social Affairs and Planning; which plays a key communication, facilitating and coordinating role in SDF. SDF supported activities cover a wide spectrum including initiatives relating to water management, roads development, environmental improvement and livestock export management. In keeping with the objective of promoting a more stable and prosperous Somaliland, SDF supports public information activities, communicating the results of funded initiatives as a contribution to strengthening the relationship between citizens and the State.

## B: PERFORMANCE AND CONCLUSIONS (1-2 pages)

Annual Outcome Assessment
Since the beginning of the Implementation Phase in April 2014, the programme has developed a steady and increasing momentum of activity and achievement. 2015 milestones were set to reflect progress as of February 2015 but this annual review has been undertaken in December 2014/January 2015; hence in some cases milestones as recorded as being ‘on track’ rather than already achieved.

OUTCOME	Outcome Indicator 1	Baseline / (2013)	Milestone / (2015)	Target (2016)	Progress
Improved and better resourced core state functions for the people of Somaliland	Number of beneficiaries of services attributable to SDF	0	750,000	1,300,000	On track to meet the 2015 milestone of 750,000 beneficiaries through implementation of the Hora Hadley and Ayaha Water Projects (57,000) and the roads rehabilitation project (700,000).
	Outcome Indicator 2
	% of population who report direct experience of improved government service delivery	0	TBD	TBD	The data for this indicator will come from the perception survey which is being conducted in January 2015.

It is difficult to ascertain a precise assessment of the outcome statement, given the timing of this review very early in 2015, but outcome indicator 1 is well on track given the contracts for implementation of both the water and roads rehabilitation projects were awarded in August and October 2014 respectively and are well underway. Significant progress has been made on outcome indicator 2, as the SDF established the Communication Hub project with a team based at the Ministry of Planning in October 2014. This team is already working with the various project teams in promoting SDF funded projects as Government of Somaliland development initiatives.

The administrative, decision making, tendering, project delivery, monitoring and evaluation frameworks are robust and proving effective in implementation. There is a strong partnership between the Fund managers and the counterpart Somaliland institutions, particularly with the Ministry of Planning and with the Minister personally. While, as is the case with many similar Funds, disbursement has been slower than hoped for, it is clearly accelerating; while retaining the robust systems in planning, procurement and financial control, as set out in the Fund’s operating manuals.

Ministers and officials in the beneficiary institutions that were interviewed in the course of this review were fulsome in their praise of the SDF processes and benefits. Numerous informants commented on the importance of the Government being in control of the prioritising and budgetary decisions. The profile and benefits of the SDF are frequently cited, including by President Silanyo at the High Level Aid Co-ordination Forum in November 2014. With four Donors now contributing to the Fund and the EU committed to joining in 2015, the SDF is also developing into a platform for improved donor co-ordination and coherence under the New Deal.

Aggregate Output Score and Description

Output	Score
1. Improved water and road infrastructure to promote economic and socially equitable development.	A
2. Improved productive sectors enhancing incomes, food security and livelihoods	A
3. Improved capacity of GoSL institutions to manage development projects	A+
4. Enhanced citizen perception of Government priorities, activities and expenditure	B
5. Improved capacity to prioritise development objectives and to plan and budget development activities.	A

This review was conducted in December 2014/January 2015 in line with DFID procedures. However, there is ample evidence currently available to conclude that the aggregate Output score is A.

Has the logframe been updated since the last review?
Because the programme’s original log frame was drafted before the National Planning Commission had selected the priority sectors, the log frame was updated in August / September 2014. It is against the revised logframe that this review has been conducted.

## C: DETAILED OUTPUT SCORING (1 page per output)

Output Title	Improved water and road infrastructure to promote economic and socially equitable development.
Output number per LF		1	Output Score	A
Risk:		Medium	Impact weighting (%):	35%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline	Milestone / Feb 2015	Target / 2016	Progress
Quantity of cubic meter of water per day available for distribution in urban water systems	0	448	2991	Rated B as the 2015 target is partially met. 145 cubic metres of water available for distribution by February 2015 and work is well underway for drilling of 3 boreholes, construction of 25 KM pipeline and mini distribution system for Dara-salaam village and a small water distribution system for Ayaha 1 & 2.
Number of water points constructed or rehabilitated with SDF support.	0	3	70	Rated A+ as the 2015 milestone has been exceeded. 9 water points partially constructed by February 2015 (3 water points for a school, community centre and market in Dara-salaam and additional 6 watering points (Kiosks) at Ayaha 1 & 2).
Reduced travel time on roads rehabilitated with SDF support	0	17%	52%	Not Rated as too early to establish reduced travel time. The first 40km of road is under construction and due for completion by March 2015.
Length of roads rehabilitated to all weather conditions with SDF support.	0	40km	125km	Rated A as 30 km of road rehabilitated by February 2015 and the 40 kms on track to be completed by early March. The first SDF project to be implemented and the project was launched by President Silanyo in November 2014.

Key Points
This output scores an A overall given the significant progress against all of the 2015 milestones and the projects being delivered by Hargeisa Water Authority and Ministry of Water Resources are well planned and appropriately targeted. One indicator of the effectiveness and appropriateness of the projects is the planned construction of 3.5km distribution pipe and six kiosks in Ayaha 1 and 2 IDP settlements, providing more accessible potable water supply to a community of 7,000 people. In a broader context the construction and linking of several water storage facilities will directly benefit 250,000 people.

Indicator 1.1 measures the amount of water in cubic metres that will be introduced to the urban water systems as a result of the SDF interventions. The baseline is assumed to be zero as at April 2014 because there was no reliable data during the project development phase. The 2015 milestone for the project is 448 cubic meters of water contributed to as follows:
- Hora Hadley and Ayaha 1 &2 project in Hargeisa town– 360m3.
- Berbera springs – 87 m3.
Although the indicator is only partially met at the time of the Review, the feasibility phase activities (feasibility, environmental impact and conflict sensitive programming assessments) are complete, detailed design and tendering for all the components had been completed, and contracts awarded.

Indicators in the SDF logframe are being met by activities from different projects. For example, indicator 1.2 will be met by the construction of three Dar Salam watering points under the Hora Hadley project. An important point of note is that, following a major shortfall in the estimated cost of an associated EU funded water programme, on which the success of the SDF funded project was dependent for its success, the Fund Managers, in cooperation with the Government, EU and German donors arrived at a co-financing arrangement to enable all elements of the inter-linked water projects to proceed. This provides evidence of the degree of partnership that has been established and the flexibility with which the Fund has operated to the benefit of those who are much in need of improved water supplies.

The road rehabilitation project is scheduled to be completed on time as is the framework for monitoring journey times. As part of the review there was a site visit to the project: the work was progressing at a good pace and there was evidently good supervision and oversight by the SDF team. There were local people employed in the construction work and regional expertise engaged to operate heavy machinery. The contractor stated that his company and staff were learning considerably from delivering the contract, from the tendering process through to managing the technical challenges. In a brief conversation with some villagers they were fulsome in their praise for the immediate employment that the project has brought and in anticipation of economic benefits from increased traffic flow through their community.

Summary of responses to issues raised in previous annual reviews (where relevant)

While this Output was not in place at the time of the annual review in January 2014 a relevant comment from that review was that “There are few if any baselines for the indicators. These need to be added if the frameworks are to be useful for monitoring and evaluation”. The baselines for the water and roads project are in place with clear deliverables against each intervention which is aggregated up to meet the output milestone. Mott MacDonald reports against them at the newly installed monthly programme board.

The 2014 review commented to the effect that ‘water sector is also a challenging sector to work in and vulnerable to corruption. In some parts of Somalia, water is extremely expensive, due to the arid conditions, and there are people willing to pay for it. Water is a politically sensitive resource and touches everyone, rich or poor. There are anecdotes of corruption and politically-determined distribution of water resources in some towns. These risks also need to be mitigated, including through sector-based technical assistance.’ In the course of this review the Ministry and Water Authority officials acknowledge that there was a degree of profiteering in respect of the sale of water in areas with poor access otherwise; and pointed to the fact that the increased supply would ensure that water became much cheaper. In districts where water is scarce, such as Las Anod, the project is engaging local government and water associations in water management structures to further mitigate this risk. This will also be captured in the baseline Perceptions Survey to be undertaken in early 2015 to ensure that the project adapts to this context.

Recommendations

For the most part, the indicators for this Output relate to technical achievements; the reduction in travel time in respect of road rehabilitation being the exception. It is recommended that the indicators take fuller account of the positive implications for people’s wellbeing as a consequence of the initiative within this Output. The roads project is already focusing on economic benefits and the water projects might look to such indicators as cost for the poorest, and the reduction in childhood gastrointestinal illnesses; both of which can be correlated to improved access to potable water.

Output Title	Improved productive sectors enhancing incomes, food security and livelihoods
Output number per LF		2	Output Score	A
Risk:		Medium	Impact weighting (%):	25%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2014	Milestone / Feb 2015	Target / 2016	Progress
Production of staple food (Sorghum) in Maroodi-jeex Upper Catchment	0.8 t/ha	0.8 t/ha	1.2 t/ha	Rated A as the February 2015 milestone has been met (although the baseline and 2015 milestones are constant as cuts across two planting seasons).
Number of hectares of land conserved or rehabilitated with SDF support	0	3,000 hectares	22,879 hectares	Rated B as February 2015 milestone partially met. The most advanced project sites are in agriculture (MUC) where 700 hectares have been supported by water and soil conservation activities and in the forest project, under MoERD, an additional 700 hectares have been conserved. Later in 2015, the agricultural sites in Aroori will contribute an additional 20,000 hectares in large part contributing to the 2016 target.
Number of livestock processed through improving holding grounds	0	0	140,434	Rated A given that construction has started on one of the holding grounds, and following resolution of community resistance in Aroori LHG, a tender for fencing 80KMs was launched and awarded in December 2014. Upon the signature of the memorandum of understanding between MoL and Aroori community, the construction of the fence is expected to start by May 2015.

Key Points
This output is rated as an A overall reflecting achievement of the 2015 milestone for indicator 1.1 and significant progress on indicator 1.3 despite local conflict surrounding one of the livestock holding grounds at Aroori. The construction of the second livestock holding ground has become a matter of controversy with local communities objecting to the enclosure of what they consider to be common pasture land.

The conflict assessment that accompanied the preparation for the project identified the potential for community resistance at both planned locations; and while a flexible response to use of land that allowed for partial fencing and community access to grazing land when not needed for holding purposes was acceptable to the community in one location, it was not in the other. The Ministry of Livestock has offered various explanations, from manipulation by outside interests to acceptance that some households will be displaced and thus deserving of financial compensation for this. What it emphasises is the need for thorough public consultation and negotiated compromises as an integral part of the project planning process. The Ministry of Planning Communication Hub might have a consultation and/or brokering role to play in this and the issue should also be captured in the baseline Perceptions Survey. It is not possible to offer any definitive critique of the conflict assessment in this case; but it is clear that the decision on the part of the SDF team to step back and await local resolution was appropriate.

For Indicator 1.2, the Ministry of Agriculture anticipates that the 2015 milestone for the production of staple food will be achieved by the end of the year. As explained by the Ministry, the terracing of agricultural land is an effective means of preventing soil erosion and increasing the utilisation of land; and in this context they are keen to extend the initiative.

Summary of responses to issues raised in previous annual reviews (where relevant)
This Output was not in place at the time of the annual review in January 2014.

Recommendations
The local conflict around one of the livestock holding grounds underlines the need for continuous and pro-active conflict analysis to be embedded and managed throughout the life of SDF projects, in close consultation with Government officials. The Ministry of Livestock, Ministry of Environment and Natural Resources and the technical assistance from Mott MacDonald should continue to work through the local communities to find a solution to the controversial livestock holding ground to the South of Hargeisa. However, a time limit should be imposed on this process which has now been on-going for just under one year. For example a mid-2015 cut off point might be considered for the JSC to consider re-programming these resources and not going ahead with the project. The team should also continue with the Aroori livestock holding ground and ensure a degree of lessons learning that could reduce the tension South of Hargeisa could be considered.

Output Title	Improved capacity of GoSL institutions to manage development projects
Output number per LF		3	Output Score	A+
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Milestone / Feb 2015	Target / 2016	Progress
Size of the Development Budget (national and external sources)	$36.3m	$39m	Rated A+ given the significant increase in the Government Development Budget from $19,005,307 in 2014 to a Development Budget of $36,691,355 in February 2015. During the period, DFID, Danida, Norway and the Netherlands contributed $17,686,048 to Government led development expenditure through the SDF mechanism.
SDF projects executed on time and within budget	2	4	Rated A+ given four projects (Hargeisa Water, Roads, Agriculture and Environment), out of the first six projects, are on time having procured private sector contractors and awarded contracts for the main activities. This is substantially higher than the two projects foreseen in the February 2015 milestone.

Key Points
The evidence gained during the field mission for this review and the documentary examination underlines that the Output has been exceeded overall.

Indicator 3.1 - The SDF was the first development project in Somaliland to be recorded on the Government’s Budget in 2014. SDF resources have grown with contributions from 2 new Donors and are fully on Budget (although not channelled through Government systems) and fully aligned to Government priorities by the NPC.

There is clear evidence of the transparency of SDF finances, the Fund’s systems prompt better development prioritising through the National Planning Commission and the Government represents the Fund activities as being funded on budget. The SDF has taken the first step by informing the government – through the Ministry of Planning and National Development to the Ministry of Finance – of its annual expenditure profile. The transparency of this action can clearly be seen in reporting by the Somaliland Sun which shows the budget made up of three components: recurrent costs, development budget, SDF. This way of working is clearly part of the reason the SDF is the preferred aid modality. Looking ahead the SDF needs to be more integrated in government planning and budget negotiations. This can be done by informing the budget committee earlier in line with the budget circular. The vision is for the SDF to make up budget negotiations so that the Council of Ministers are aware of future SDF investments so that they can make considered decisions on how to bets make use of the limited government development budget.

Indicator 3.2 - To get a sense of scale the four projects delivered on time alone included a total of 72 procurement processes for services, good and works. SDF projects have been developed and implemented by embedded PMUs within line ministries with support from the Secretariat and their pool of expert TA. The Fund Managers have worked closely with embedded PMUs to move from the planning stage to full execution with significant progress demonstrated during 2014. 72 tenders have been submitted to both the domestic and international market. 201 tender committee meetings (an average of 2 to 3 sessions per tender) have been considered, always including a key owner of each project from government and inclusion of the national tender board, mainly for high value contracts. 67 contracts have been awarded by the end of 2014. As explained earlier each project intervention has multiple contracts associated with it, and many have been re-tendered because of the emerging private sector market and challenges with full compliance with the tender procedures.

Summary of responses to issues raised in previous annual reviews (where relevant)
This Output was not in place at the time of the annual review in January 2014, but Outputs 1 & 3 of previous Log Frame was similar. In the 2014 review there were recommendations relating to the framework documentation, which has since been addressed by the programme managers.

In respect of capacity development, the last review commented that “current plans to set up small units in each ministry working very closely with international technical assistance (TA), look like a good solution. It is preferable to keep this TA inside ministries to minimise the risk that staff will leave for other jobs. In terms of maintaining the relationship with Government, Donors will need to be clear when benchmarks have been met and therefore putting in place a specific plan with stages would be appropriate”. The capacity surge, known within DFID as increasing public sector investment capacity, has proved to be a high calibre response to this as is the allocation of technical assistance to each participating ministry and government institution.

Recommendations
It is recommended that the Indicators for this Output be revised and include the measurable achievements of the Capacity Surge. It is further recommended that the activities of the Capacity Surge be extended beyond the present time frame and focus on moving professional capacity within the participating institutions toward more advanced knowledge and skills in project planning, implementation, monitoring and evaluation.

Output Title	Enhanced citizen perception of Government priorities, activities and expenditure
Output number per LF		4	Output Score	B
Risk:		Medium	Impact weighting (%):	10%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2013	Milestone / Feb 2015	Target / 2016	Progress
% of people who report improved access to water in Hargeisa	0	TBD	TBD	Rated B as the Perception survey which was scheduled to take place in Q4 to provide information for baseline and milestones will be undertaken in Q1 of 2015.
% of people who report improved journey time on SDF rehabilitated roads.	0	TBD	TBD	Rated B as the Perception survey scheduled to take place in Q4 to provide information for baseline and milestones will now take place in Q1 of 2015.

Key Points
The baseline Perceptions Survey has been delayed; hence the B score for this output overall, but the objectives, activities and achievements of the Communication Hub’s community engagement strategy should also be reflected in the assessment of progress. The main objectives of this initiative are:
- Establish standard process for community engagement
- Encourage and support community participation in development projects
- Enhance citizen awareness on government services, priorities and expenditure
- Establish proper complaints response mechanism (feedback) for SDF funded projects
- Empower local people and improve community participation to improve acceptance of local development projects
- Develop sustained collaboration, partnership and new ways to involve and empower the community to achieve sustainable community participation in development.

Although it is not reflected in the Indicators and milestone progress narrative, the evidence gained during the field mission for this review points to there being substantial progress toward meeting the Output target. For example, there has been wide coverage in the local media of SDF projects and successes such as President Silanyo cutting the ribbon at the official launch of the Lafaruk – Berbera – Sheikh Road Rehabilitation Project in November 2014.

Summary of responses to issues raised in previous annual reviews (where relevant)
The January 2014 review recommended that: ‘Given the paucity of good quality data on Somaliland it will be important for some of the SDF work, such as the perceptions survey, to link in with wider work underway by other partners such as the UN and the World Bank’. This has to date not been followed up by SDF.

The last review assumed that the baseline citizens’ perception survey would be completed before this review took place and made recommendations with regard to geographic spread and disaggregation. Since the survey has yet to take place (due to slow start up of the first wave of projects) these recommendations continue to stand.

The recommendations in relation to the development and implementation of a communications strategy have been fully and positively responded to. Also recommended was the development and refinement of the Communication Strategy which has been addressed during this reporting period.

Recommendations
It is recommended that the Indicators for this Output be reviewed so that they more accurately reflect the spectrum of citizens’ perceptions of Government priorities, activities and expenditure.
It is also recommended that SDF explore the potential for cooperation and collaboration with other programmes in respect of survey activities; as recommended in the January 2014 review.
The role of the Communications Hub and its contribution to successful project planning and monitoring should be expressed in an indicator and engaging with ART at an early stage will make this more useful.

Output Title	Improved capacity to prioritise development objectives and to plan and budget development activities.
Output number per LF		5	Output Score	A
Risk:		Medium	Impact weighting (%):	15%
Risk revised since last AR?		N	Impact weighting % revised since last AR?	N

Indicator(s)	Baseline / 2013	Milestone / Feb 2015	Target / 2016	Progress
Average aggregate disbursement deviation from forecasts	0	5%	5%	Rated A as the 5% variance target has been met since August 2014. Due to some variance on forecasting in early 2014, explicit attention focused on ensuring a more robust and accurate financial system in the second half of the year.
Average time from approved concept note to approved project proposal	0	120 days	120 days	Rated A as the average timeline for projects under development has been met and the Mott Mc Donald team are working with Government to further reduce this timeline and ensure a more stretching target for 2016.

Key Points
The 2014 milestones for both indicators have been met hence the A score and there are plans underway for further refinements.

Indicator 1.1 – Following a significant investment of time and effort between the DFID programme team and Mott McDonald’s Finance Team the accuracy of monthly forecasting has improved significantly and a detailed cash flow system is now in place reflecting both payments and commitments by sub-contractors. The JSC in December 2014 also agreed a proportionate split of Donor resources which has further streamlined financial planning.
Indicator 1.2 - To improve speed and enhance consistency a Project development template was designed for the first phase of projects and are now becoming familiar with Government counterparts. For example, the second roads rehabilitation project saw key business processes reduced in time because our main partners could use them with minimum guidance. Additionally, Mott McDonald are using the same consultant from their short term TA pool for second round projects and spending less time familiarising themselves with the Somaliland context, hence, substantially reducing design time. Finally, the inclusion of a civil engineer in the Mott McDonald team based in Hargeisa has meant that adhoc engineering related tasks have been dealt with in house and again within a shorter timeframe.

Summary of responses to issues raised in previous annual reviews (where relevant)
The last review commented that ‘the challenge is now to proceed to implementation quickly to meet the significant expectations which have been built up’. Given the thoroughness of the process of project approval, tendering and start-up the Fund has met this challenge. Ministers and officials interviewed in the course of this review were unanimous in their understanding and acceptance of the processes involved and indicated that their expectations of the Fund’s delivering as planned are being met. The last review commented to the effect that there is:
- Need to think hard now about a strategy for building up government involvement.
- Need to phase in government involvement gradually, starting with planning and budgeting, even procurement, before moving to using government systems for spending.
- It may be helpful to develop a written strategy bringing together formal learning, on-the-job learning and PFM reforms, with some sense of the changes SDF donors will require before funds are passed through GoSL systems.
- To integrate into the SDF and into government the processes that will maximize its impact on democracy, equality, participation and sustainable development, e.g. implementing the gender policy or procurement procedures. Furthermore, the SDF could initially hire local, well-qualified staff, perhaps by secondment from Ministries, to develop local capacity.

At the time of this review the recommendations in respect of government involvement have in the Fund’s management have been realised.

Recommendations
Given that there is little flexibility in the procurement process with regard to timelines, any economies of time management need to be found in the time between approval of concept notes and project approval. It is recommended that the programme reviews the project approval process with a view to reducing the current average of 120 days.

## D: VALUE FOR MONEY & FINANCIAL PERFORMANCE (1-2 pages)

The framework for VfM reporting of the project is currently being finalised. A DFID economist provided initial training on VfM to the Mott team in Hargeisa in 2014, subsequent to which they have done some initial analysis. This is to be finalised in a follow-up meeting, which has had to be delayed.

Performance of key cost drivers
The key costs are currently personnel costs (53%) and project expenses (15%). Personnel costs include the SDF secretariat staff costs and technical support costs from the sector expert pool. The project expenses total 15% of the budget. This will change in the next reporting period due to the implementation of projects. The SDF Secretariat has identified 2 to 3 activities for each project that constitute about 70 – 80% percent project costs, and will systematically assess them as part of the VfM framework.

Mott McDonald still need to complete DFID’s VfM Actions Template in order to get a consistent picture of what actions they are taking to maximise VfM. However, there is some good anecdotal evidence of VfM in terms of Economy and Efficiency. The tendering processes are specified in a comprehensive SDF Procurement Manual the content of which is compliant with World Bank standards. Two examples provide evidence of high VfM. They worked with the Somaliland authorities to ensure that the budget ceiling for tenders for road contracts was set at the lowest level to avoid firms bidding to a high ceiling, which brought down road unit costs significantly compared to other programmes (see below). They did a local tender for car rental and also got very competitive rates (see below).

How does VfM performance compared to the VfM proposition in the Business Case?
The project may be assessed against the following VfM measures:
- Economy:
  - Car rental rates per day: we have compared daily car rental rates (including driver and fuel) with two other programmes operating in Somaliland, and found the SDF’s to be much lower.
- Efficiency:
  - Fund management costs: programme management costs are estimated at 21.3% over the lifetime of the SDF (see table below). This needs to be benchmarked more closely to other funds that DFID is supporting in Somalia, but experience from elsewhere suggests that it should range between 20-25% depending upon the precise management functions, and so this looks acceptable.
  - Cost per km road rehabilitated: SDF costs between $80,000 and $90,000, while comparable projects elsewhere in Somaliland cost approximately $150,000 per km.
- Cost Effectiveness and Economic return: no measures are currently available.

Does the project continue to represent value for money?
The programme remains excellent VfM based on the following:
- Results: the Output score is A and the Outcomes are on track to be achieved.
- Theory of Change: this remains valid.
- Risks: remain stable at Medium.
- VfM practices: the examples given suggest high VfM for Economy and Efficiency.
- VfM measures: the indicators suggest high VfM for Economy and Efficiency.

Quality of financial management
The programme managers have a comprehensive Financial Management and Accounting Manual, the provisions of which are adhered to. There is a quarterly report that provides a summary of financial activity during the reporting period. By December 2014, the financial position of the SDF was as follows:

Application of the programme funds:
Description	Amount (USD)
Total Programme Funds Available	51,634,821
Approved Projects	38,196,931
Projects under development	6,240,000
Unallocated by Nov, 2014	7,197,890
Totals	51,634,821

While the disbursement rate in 2014 has been lower than expected it is anticipated to accelerate as contracts come online, expenditure begins to be incurred and contractors submit invoices; this is particularly the case in respect of roads, water and agriculture projects.

In November 2014 KPMG conducted an expenditure verification audit which involved the appraisal of the fees and expenditures claimed and disbursed by the SDF management to confirm their eligibility in accordance with the terms and conditions of the Contract for supply of Services. While they reported that these were in order, KPMG also noted that this did not constitute an audit or a review. The financial records of the SDF Secretariat are scheduled to be audited again in September 2015.

Date of last narrative financial report	30/11/14
Date of last audited annual statement

Recommendations:
Finalise the VfM reporting framework with SDF, including completion of the VfM Actions Template, agreement on VfM indicators, and selection of comparable funds for benchmarking.
Commission research comparing their road rehabilitation unit costs with other programmes in Somalia to verify their claims and (if valid), learn lessons.

Timely completion of 2015 audit is also a priority for the Fund Managers.

E: RISK (½ page)

Overall risk rating:

The overall risk rating for the SDF is Medium. See Annex 1 for overview of risks that will be included in the next review of the risk matrix in March 2015.

Outstanding actions from risk assessment

There are no outstanding actions from the risk assessment.

F: COMMERCIAL CONSIDERATIONS (½ page)

Delivery against planned timeframe
While there were and will be inevitable delays in project roll out (for example the need to get laboratory testing of road service materials undertaken out of country in advance of commencing the contract), the evidence clearly points to the programme meeting its target in a timely manner.

Performance of partnership (s)
The programme’s partnership with the government institutions in Somaliland is a particular strength in SDF achieving its Output. There is a particularly strong working relationship with the Ministry of Planning and within it the Minister and Director General who act as focal point for SDF within the government.

Asset monitoring and control
SDF Secretariat maintains the asset record on a regular basis in line with DFID’s inventory guidance with submission of six-monthly updates. The DFID Programme Officer is actively involved in the monitoring and control of the programme assets by ensuring that assets register is regularly updated and shared with DFID. The SDF Secretariat last updated their register in September 2014.

All SDF assets belong to DFID until when the projects come to a close. For example, the project vehicles are allocated to the projects for use but technically belong to DFID. In this regard, the SDF provides guidelines for use of the vehicles. SDF secretariat jointly with the line Ministries vetted all the drivers who drive the vehicles. This has been seen by some Ministries such as Agriculture as too strict. However, from a fiduciary point of view, all assets including vehicles are the responsibility of the SDF secretariat until such time as they are handed over to the government.

G: CONDITIONALITY (½ page)

Update on partnership principles
DFID and Danida signed an MOU, underpinning the SDF and reflecting the Partnership Principles, with the GoSL in November 2014. The Government of Somaliland has a clearly demonstrated commitment to reducing poverty and achieving the Millennium Development Goals (MDGs) and the SDF is seen as playing an important role in achieving these. Within this is a commitment to addressing the enablers and constraints to poverty reduction and progress against the MDGs (and successor goals) and the promotion of the cross-cutting themes, transparency and consultation on the part of SDF contributes to this. There is a clear commitment on the part of the Government of Somaliland to respecting human rights, and in particular the economic, social and cultural right as well as civil and political rights of poor people; and SDF’s commitment to challenging discriminatory practices plays a part in this.

While the World Bank PFM programme is the main capacity building facilitator in support of the Government’s commitment to strengthening financial management and accountability, and reducing the risk of funds being misused through weak administration or corruption, the tendering and financial oversight arrangements in SDF are contributing elements in this. The Government’s commitment to strengthening domestic accountability is reinforced by SDF’s promotion of community consultation, transparent programme processes and public communication strategy.

H: MONITORING & EVALUATION (½ page)

Evidence and evaluation
Although the Output definitions have changed, the Theory of Change, as outlined in the Business Case provides a firm and continuing foundation for SDF. While the fundamentals of the approach continue to meet much of the programme’s needs, the emerging projects that focus on health and education service delivery will need some readjustments to take account of activities contributing to Outputs and contributing to the programme’s Outcome.

It is too early in the programme’s operation to be able to comment with authority on the effectiveness of the internal monitoring and evaluation framework. It is, however, evident that in the preparation of each funded project full consideration is given to gender, environmental and conflict issues and that these are integrated into the projects’ monitoring and evaluation regimes.

Monitoring progress throughout the review period
In the course of this annual review of SDF a wide range of programme reports, operational manuals, and individual funded project documents were examined as well as DFID documentation on Somalia Operational Plan and Partnership Principles.

There were two visits to Somaliland undertaken by a consultant from 6th- 9th and 14th – 18th December 2014. During these missions the consultant undertook site visits to a roads rehabilitation project and interviews were conducted with:
- DFID officials
- SDF Managing Agents and Secretariat (Mott McDonald)
- Ministers of Planning, Livestock, Agriculture, Environment and Water Resources
- Project Management teams at Hargeisa Water Authority, Roads Authority, Ministries of Livestock, Agriculture, Environment and Planning.
- Phone/Skype calls with representatives of Netherlands and Norway
- People living along the reconstructed road, the contractor and local people being employed on the project.
The final annual review reflects a mix of independent consultants and DFID opinion.

Smart Guide

The Annual Review is part of a continuous process of review and improvement throughout the programme cycle. At each formal review, the performance and ongoing relevance of the programme are assessed with decisions taken by the spending team as to whether the programme should continue, be reset or stopped.

The Annual Review includes specific, time-bound recommendations for action, consistent with the key findings. These actions – which in the case of poor performance will include improvement measures – are elaborated in further detail in delivery plans. Teams should refer to the Smart Rules quality standards for annual reviews.

The Annual Review assesses and rates outputs using the following rating scale. ARIES and the separate project scoring calculation sheet will calculate the overall output score taking account of the weightings and individual outputs scores / Description Scale / Outputs substantially exceeded expectation A++ / Outputs moderately exceeded expectation A+ / Outputs met expectation A / Outputs moderately did not meet expectation B / Outputs substantially did not meet expectation C

Teams should refer to the considerations below as a guide to completing the annual review template.

Summary Sheet
Complete the summary sheet with highlights of progress, lessons learnt and action headlines.
Introduction and Context
Briefly outline the programme, expected results and contribution to the overall Operational Plan and DFID’s international development objectives. Where the context supporting the intervention has changed from that outlined in the original programme documents explain what this will mean for UK support
B: Performance and conclusions
Annual Outcome Assessment / Brief assessment of whether we expect to achieve the project Outcome by the end of the project
Overall Output Score and Description / Progress against the milestones and results achieved that were expected as at the time of this review.
Lessons / Any key lessons you and your partners have learned from this programme / Have assumptions changed since design? Would you do differently if re-designing this programme? / How will you and your partners share the lessons learned more widely in your team, across DFID and externally
Actions / Any further information on actions (not covered in Summary Sheet)
Has the logframe been updated since the last review?
C: Detailed Output Scoring
Output / Set out the Output, Output Score
Score / Enter a rating using the rating scale A++ to C.
Impact Weighting (%) / Enter the %age number which cannot be less than 10%. / The figure here should match the Impact Weight currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Revised since last Annual Review (Y/N).
Risk Rating / Risk Rating: Low/Medium/High / Enter Low, Medium or High / The Risk Rating here should match the Risk currently shown on the logframe (and which will need to be entered on ARIES as part of loading the Annual Review for approval). / Where the Risk for this Output been revised since the last review (or since inception, if this is the first review) or if the review identifies that it needs revision explain why, referring to section B Risk Assessmen
Key points
Summary of response to issues raised in previous annual reviews (where relevant)
Recommendations
Repeat above for each Output.
D Value for Money and Financial Performance
Key cost drivers and performance / Consider the specific costs and cost drivers identified in the Business Case / Have there been changes from those identified in previous reviews or at project approval. If so, why?
Is the project value for money / Overall view on whether the programme is good value for money / Performance against vfm measures and any trigger points that were identified to track through the programme
Quality of Financial Management / Consider our best estimate of future costs against the current approved budget and forecasting profile / Have narrative and financial reporting requirements been adhered to. Include details of last report / Have auditing requirements been met. Include details of last report
E Risk
Output Risk Rating: L/M/H / Enter Low, Medium or High, taken from the overall Output risk score calculated in ARIES
Overview of Programme Risk / Changes to the overall risk environment/ context / Review the key risks that affect the successful delivery of the expected results. / Any different or new mitigating actions that will be required to address these risks and whether the existing mitigating actions are directly addressing the identifiable risks. / Any additional checks and controls are required to ensure that UK funds are not lost, for example to fraud or corruption.
Outstanding actions from due diligence / Describe outstanding actions from Due Diligence/ Fiduciary Risk Assessment / Describe follow up actions from departmental anti-corruption strategies to which Business Case assumptions and risk tolerances stand
F: Commercial Considerations
Delivery against planned timeframe. Y/N / Compare actual progress against the approved timescales in the Business Case. If timescales are off track provide an explanation including what this means for the cost of the project and any remedial action.
Performance of partnership / How well are formal partnerships/ contracts working / Are we learning and applying lessons from partner experience / Could DFID be a more effective partner
Asset monitoring and control / Level of confidence in the management of programme assets, including information any monitoring or spot checks
G: Conditionality
Update on Partnership Principles and specific conditions. / For programmes for which it has been decided (when the programme was approved or at the last Annual Review) to use the PPs for management and monitoring, provide details on: / Were there any concerns about the four Partnership Principles over the past year? / If yes, what were they? / Did you notify the government of our concerns? / If Yes, what was the government response? Did it take remedial actions? If yes, explain how. / If No, was disbursement suspended during the review period? Date suspended (dd/mm/yyyy) / What were the consequences? / For all programmes, you should make a judgement on what role, if any, the Partnership Principles should play in the management and monitoring of the programme going forward. This applies even if when the BC was approved for this programme the PPs were not intended to play a role. Your decision may depend on the extent to which the delivery mechanism used by the programme works with the partner government and uses their systems.
H: Monitoring and Evaluation
Evidence and evaluation / Changes in evidence and implications for the project / Where an evaluation is planned what progress has been made / How is the Theory of Change and the assumptions used in the project design working out in practice in this project? Are modifications to the project design required? / Is there any new evidence available which challenges the project design or rationale? How does the evidence from the implementation of this project contribute to the wider evidence base? How is evidence disaggregated by sex and age, and by other variables? / Where an evaluation is planned set out what progress has been made. / Monitoring process throughout the review period. / Direct feedback you have had from stakeholders, including beneficiaries / Monitoring activities throughout review period (field visits, reviews, engagement etc) / The Annual Review process