Sign off:	Sian Rasdale	From:	Jenna Taylor, Programme Manager
		Contact:	07767383453, J-Taylor@dfid.gov.uk
		Division:	Research and Evidence Department
		Date:	15/05/2019

## Programme Completion Report Summary of infoDev 112024

Title: infoDev Core contribution
Programme Value £ (full life): £2,460,000		Review Date: April 2019
Programme Code: 112024	Start Date: February 2006	End Date: December 2013
Programme Summary Score: B

Summary and Progress
Information for Development was a World Bank based multi-donor programme working on the role of Information Communication Technologies (ICT) as a tool for development in combatting poverty and promoting sustainable economic growth. DFID funding ended in 2012, but the programme continued to be operational and deliver with an extension amendment to reflect Sweden’s contribution to the mobile and entrepreneurship agenda. Therefore, a project completion report was not completed at that time. With the multi-donor trust fund now closed and DFID’s contribution coming to an end in 2012 a light touch project completion report is appropriate and in-line with DFID rules and procedures.
DFID co-funded infoDev through a multi-donor trust fund, together initially with seven other[1] donors, that acted as a research capacity building and advisory service. It worked with emerging economies, developing countries and their international partners to use information and communication technologies effectively as tools of poverty reduction and sustainable development. It aimed to catalyse ICT friendly policy development and reform an ICT driven business generation in targeted low- and middle-income countries.
[1] Canada, Denmark, Finland, Republic of Korea, Brazil, India, South Africa.
The infoDev programme activities were shaped by three main themes i) Mainstreaming ICT as tools for development, ii) enabling access for all, and iii) innovation, entrepreneurship and growth. These themes were known as i) Transform, ii) Connect and iii) Innovate.
This programme completion scores the extent to which the programme delivered against expected outputs and outcomes. This has been assessed as B, meaning outputs moderately did not meet the full expectation. While there is evidence of progress against outputs, there is insufficient evidence that they have all been fully met.
Programme successes include:
Research and knowledge pieces. The fund supported the production of a variety of toolkits and knowledge products, the most notable being a flagship ICT toolkit and regulation handbook which is widely regarded amongst regulators as a useful resource.

A business incubation training program that had high demand among women entrepreneurs designed to educate on how to start up and manage successful incubators[2]. This served as an exemplar programme for other donors: Canada went on to further fund a similar programme in the Caribbean known as EPIC, whilst Finland funded Mobile Labs in Africa.
[2] Business incubation is a process designed to nurture businesses from idea generation to start-up companies and, through a comprehensive business support program, help them establish and accelerate their growth and success. http://www.infodev.org/sites/default/files/m1_traineemanual_20101029.pdf

The trust fund provided opportunities for forging new relationships among partners and developing countries. infoDev was able to start a successful partnership with Department of Science and Technology in South Africa that led to the signing of a Memorandum Of Understanding between the World Bank and the government of South Africa to develop a new innovation agenda. Additionally, activity under this trust fund contributed to increased attention within the World Bank around areas of innovation and entrepreneurship which led to the establishment of a World Bank community of practice.

DFID funding was used to encourage research on ICT related themes that were of high policy interest in the broader development agenda. The trust fund had the opportunity to test out different innovative pilots in the areas of incubation, digital entrepreneurship and was able to develop cutting edge research and analytical tools which continue to be widely used both in the Bank and by external users.

In Paraguay, infoDev materials were used to reform Internet regulation to improve access to public information and collect data on rural citizens and in Dominica infoDev materials were used to research policies on sound internet regulation and youth engagement in ICT programs.
A 2012 independent evaluation noted that the partnership between DFID and infoDev was productive and efficient. It highlighted that each DFID funded project had also leveraged funding from other donors helping to secure the sustainability and scalability of the programme and gathered interest reflecting the importance of the issues.
Background
infoDev’s work was broadly organised under three distinct[3], but not mutually exclusive[4], themes: Innovate: supporting developing countries and their international partners maximize the contribution and impact of the private sector; Transform: examining how ICTs are used as building blocks to shape a knowledge society and Connect: build partnerships for access and use of ICT infrastructure, applications and services that maximise private investment and leverage public resources where necessary.
[3] Access For All (CONNECT) Annual Review 2011
[4] Evaluation report on DFID funding of infoDev’s work program on information and communications for development (ICT4D) 2010-2012
DFID funding started in 2006 with £960,000 that contributed to the core funding of the programme. A submission was approved in March 2009 for additional funding of £1,500,000 for a further three years 2009 - 2012 bringing the total programme contribution to £2,460,000.
DFID contributed to the Connect theme and the core costs of the infoDev team. Connect worked with developing countries, international partners, World Bank and International Finance Corporation to help inform choices and develop effective partnerships for enabling access to information infrastructure, applications and services in sustainable ways that maximised private investment and leveraged public resources. Projects sponsored through this theme included research and analysis to identify global best practices, published surveys, reports, handbooks, toolkits, best practice guides, case studies, briefs and seminar materials. Of the 311 incubators in the infoDev network, 86 were specifically targeted at female entrepreneurs.
Value for Money and Outputs
The programme logframe was developed at the start of the programme. Annual reviews from the infoDev trust fund provided by the World Bank and an independent evaluation on behalf of DFID recorded output level progress. The programme delivered on all its outputs and leveraged funds from other donors beyond what was expected resulting in the extension of the trust fund beyond DFID’s funding.
infoDev set up a Women’s Empowerment and Entrepreneurship Group, of 311 small business incubators in the network, 86 of them specifically targeting women. The group presented recommendations on how to better support women’s business incubation in developing countries. This led to the development of an incubators training program comprised of a series of modules on how to start and manage a successful incubator. The training programme was successful and had high demand.
DFID funding in 2009-2012 had the following outputs:
Output Title	Update and disseminate products on ICT regulation / A revised (10th anniversary) edition of the Telecommunications Regulation Handbook / Updates to the ICT Regulation Toolkit, including new and updated modules and new mechanisms for user generated content
Output number per LF		1
Impact weighting (%):		40%
Score		A

Indicator(s)	Target	Progress
Unique visitors and downloads from developing countries of the revised Telecommunication Regulation Handbook and ICT Regulation Toolkit.	Handbook -100 downloads per month / Toolkit – 676 unique visitors per month	Targets exceeded / 600 to 800 per day between 2009 and 2011 / Averaging 17,300 users per month in 2010 and 24K in 2011
Number of people trained using the material from handbooks and ICT Regulation Toolkit	480	1075 people trained as of 2010

The ICT Regulation Toolkit and the Telecommunications Handbook were two of the flagship products of the infoDev -DFID partnership. The tenth anniversary edition of the Telecommunication Regulation Handbook was drafted and published. It was launched at Global Symposium for Regulators with 437 participants, made up of regulators and policy makers from 81 countries. The handbook was made available online free of charge, with a printed version disseminated globally via an outreach strategy designed to put it in the hands of policymakers.
In 2011 infoDev quoted in their annual review of the programme that the handbook was downloaded 800 times a day, exceeding the original logframe target. The hand book is an essential guide for telecom regulators and policy makers and was frequently used as a one stop shop for the telecommunications sector. The 2010 annual review noted that 33% of surveyed online users between June 2009 and January 2010 said that they used the toolkit to review or draft legislation. In the same survey respondents reported to have used the toolkit in regulatory training. Some confirmed figures for example in Peru DIRSI[5] trained 1000 people and in Ecuador an engineer at ESPOL[6] trained 75.
[5] Reginal Dialogue on Information Society
[6] Coastal Polytechnical School
Several modules of the ICT Regulation Toolkit were updated, new features were added to become more interactive with users. It provided a global overview of how telecom policy is best implemented with practical materials highlighting experience and results. Users accessing the toolkit continued to grow; in 2010 the toolkit averaged 17,300 users per month with 29.5% of those being users from Asian countries including Malaysia, the Philippines and Indonesia and a further 9% from India. 25% of the users were returning visitors, indicating people used the tool repeatedly and at length. Again, these results far exceeded the original targets.
Output Title	Three studies and overall report developed, completed and disseminated on the role of ICTs in post-conflict reconstruction
Output number per LF		2
Impact weighting (%):		33.3%
Score		B

Output partially met. In 2012 the DFID evaluation reported that two cases studies in Tunisia and Rwanda were completed. A final report was completed and published including cases studies from Tunisia, Rwanda, Timor-Leste, Sri Lanka, Afghanistan and Liberia after being peer reviewed.
The logframe set a target of 10,000 global downloads and 3 instances of use. The report was made freely available online and was used to deliver workshops at the Information Communication Technology Development 2012 event, disseminating the outputs with policymakers, practitioners and researchers. More in-depth uptake work was undertaken with the ICT4Peace Foundation; however, the target of 10,000 global downloads and 3 instances of use were not verified. Therefore, overall delivery against this output was scored as a B.

Output Title	Execution and dissemination of a study on the Developmental Impact of Broadband
Output number per LF		3
Impact weighting (%):		10
Score		B

Output partially met. A study on the developmental impact of broadband was completed and published[7] as per the output and milestones in the logframe. This was part-funded by DFID and the Organisation for Economic Co-operation and Development. There is some evidence of dissemination activity through workshops at global conference events. However, progress towards the logframe target of 10,000 global downloads has not been reported, so overall assessment for this output is a B.
[7] ICTs for Development: Improving Policy Coherence
DFID engagement helped to encourage funding contributions from other donors including from the government of Korea to develop a module of a new Broadband Strategies Toolkit and a second module of the toolkit that presents case studies of broadband development in a range of developing countries[8].
[8] Including Kenya, Brazil, Morocco, Sri Lanka, St Kitts, Nevis and Turkey.

Output Title	Execution and dissemination of a study on the Development Potential of the Virtual Economy
Output number per LF		4
Impact weighting (%):		16.7
Score		B

Output partially met. A Knowledge Map of the Virtual Economy was completed with the draft presented to peers for comments as per the output. The research study mapped the size of the virtual economy with specific focus on the developing world, and through a research by doing approach it investigated the scope for entrepreneurship using infoDev’s expertise in small business creation.
In 2010 a workshop was held at ICTD2010 conference on the Development Potential of the Virtual Economy of which there were sixty participants. The research described the goods and services that exist only digitally and found that income opportunities exist for semi-skilled and unskilled workers in developing economies.
infoDev attributed how DFID funding was used to generate knowledge on the development potential of the virtual economy that was shared at major international conferences and used to leverage funds and expertise from other partners, such as International Development Research Centre, Nokia and the Finnish Ministry of Foreign Affairs. This was a direct benefit of the Knowledge Map alongside a report that was produced, together they formed the bases for another phase of work that focused on Mobile Microwork that was funded by these other donors.
However, the target indicators of 10,000 global downloads and at least 3 firms who have developed a virtual economy business has not been reported, meaning this output has scored a B.

Lessons Learnt
- The targets for output 1 should have been revised during the programme to ensure it remained a stretching target; this would have encouraged greater dissemination and potentially have led to greater programme impact.
- The programme could have reported in more depth on the output level contribution and the impact on developing countries and reducing poverty.
- A positive lesson from the incubation training programme was that the high demand potentially could have been driven by an online training manual that can be accessed any time free of charge. This feature enables a greater outreach to potential incubation managers and allows people to develop their knowledge and understanding in their own time, revisiting modules as they see fit with no financial burden.

This light touch PCR was completed by Evidence into Action team part of DFID’s Research and Evidence Division. The desk-based review incorporated progress documentation supplied by the World Bank, infoDev annual reviews and independent evaluations. Historical DFID programme documents were also used alongside information obtained via the infoDev website.

The documentation has allowed an assessment of progress against the outputs to be made against the original logframe indicators and expected targets. In some instances, progress against targets could not be assessed or targets appear to have been exceeded, in these instances reporting was always based on the factual information and targets available noting the limits in scope of the review.