Annual Review – Summary Sheet

Title: RURAL AND AGRICULTURE MARKETS DEVELOPMENT PROGRAMME FOR NORTHERN NIGERIA (PROPCOM MAIKARFI)
Programme Value: £51m		Review Date: 28 January – 03 March 2019
Programme Code: 202098	Start Date: 01/08/2018	End Date: / 31/03/2021

Summary of Programme Performance
Year	2013	2014	2015	2016	2017/18	2018/19
Programme Score	A+	A	A	A	A++	A+
Risk Rating	Medium	Medium	Moderate	Medium	Moderate	Moderate

DevTracker Link to Business Case:	http://iati.dfid.gov.uk/iati_documents/21248892.odt
DevTracker Link to Log frame:	https://devtracker.dfid.gov.uk/projects/GB-1-202098/documents

A. Summary and Overview

Programme Code: 202098;	Risk rating: Moderate

Summary of Programme
Propcom Mai-karfi (PM) is a £51 million, DFID-funded rural and agricultural market development programme currently in a 31-month extension phase with an end date of March 2021.

The programme uses a “Making Markets Work for the Poor” (M4P) approach, in which the core focus is to tackle systemic constraints in markets to unlock opportunities for target beneficiaries. For the extension, this approach has been adapted to accommodate market engagements in conflict zones and beneficiaries to re-engage in sustainable livelihoods and markets. PM at DFID’s request has reduced its implementation footprint from 19 to 9 states[1] to focus on northeast Nigeria and now works with private sector businesses, international non-governmental organisations (INGOs), NGOs and some Government agencies to identify constraints in market systems and facilitate systemic changes which enable rural markets to work better for the benefit of poor people.
[1] Borno, Adamawa, Yobe, Bauche, Taraba, Gombe, Kano, Kaduna, Jigawa.

The programme aims to increase the incomes of 352,000 and improve the resilience of 440,000 poor men and women in northern Nigeria (by April 2021) by: (a) stimulating sustainable, pro-poor growth in selected rural markets and, (b) improving the position of poor men and women within these market systems, by making the markets more inclusive for poor people. This combination of existing and new mandates is captured in the present programme objectives:
1. Expand the programme into conflict affected states in the North East of Nigeria to work towards sustained stability and economic recovery that improves livelihoods of the rural poor.
2. Increase resilience of the rural poor to climate change by growing a portfolio of Climate Smart Agriculture (CSA) interventions from existing PM activities and new areas through pioneering CSA approaches.
3. Continue to facilitate inclusive growth in rural and agricultural markets to address the growing levels of rural poverty and vulnerability.
PM has continued to work across 8 main areas: agricultural inputs, poultry and livestock, agricultural mechanisation, Women’s Economic Empowerment (WEE) initiatives, environmental initiatives, Access to Finance (A2F), partner engagements, aggregation and offtake. Climate Smart Agriculture (CSA). Women’s Economic Empowerment (WEE) and policy are crosscutting initiatives inherent to all PM’s work.

Overview of progress and score

For this reporting period, PM has exceeded expectations despite the challenges with moving to the NE and working in a volatile and conflict-affected area.

High-level results include:
Expanding the implementation footprint into the north east, Gombe, Bauchi and Taraba (GBT) states constituted 33% of all access outreach while Borno, Adamawa and Yobe (BAY) states represented 26% of the total. Given the mandate for PM to expand its operations into the NE and adapt its approach accordingly, the proportion of results achieved in the NE indicates significant potential for the subsequent 2 years of the programme.

Similarly, the identification and collaboration with a wide spectrum of development and private-sector partners willing to operate within the challenging environment of the NE has been encouraging. In addition, some existing partners with whom PM has already been working have invested in markets in the NE.

Significant results in some key markets as shown below:

	Income - Beneficiaries [Male]	Income - Beneficiaries [Female]	Income - Beneficiaries [Overall]
Fertiliser distribution	47,906	20,493	68,399
Poultry vaccination with NDV-i2	14,601	23,823	38,424
Certified seeds with Premier Seed	22,133	1,689	23,822

Fertiliser: PM has achieved significant results again this year with its Fertiliser intervention where it facilitated the sale of fertiliser through its Distribution Partners (DPs) and their network of Retail Promoters (RPs). With the inclusion of 50kg bags, in addition to the existing small packs (1kg, 10kg and 25kg), more sales were made this year than in previous years. Over 3 billion Naira (GBP 6.16M) worth of sales were recorded through various fertiliser bags, helping to reach over 68,000 farmers. The average income increase per farmer was around 108,000 Naira (GBP 222.00), leading to an aggregate income increase of NGN 7.4B (GBP 15.2M).

Poultry Vaccination: Over 35,800 vials of NDV-i2[2] have been sold between April 2018 and March 2019. This has helped PM to reach an additional 38,400 farmers, 62% of whom were women. The average additional income per farmer was around 9,060 (GBP 20.00) Naira per annum[3] for leading to an aggregate income increase of NGN 348M (GBP 727K).
[2] NDV-I2 is the thermotolerant vaccine for Newcastle disease of poultry.
[3] The difference between a user of the vaccine and a non-user of the vaccine is the value of three birds based on a flock size of vaccinated birds of about 22 birds.

Premier Seed: Over 11.5 MT of certified seeds were sold by major seed distributors and retailers of Premier Seeds. This helped us to reach over 23,800 farmers in total. However, the reach of women farmers was smaller for this intervention, with only 1,600 female farmers being reached. The income increase per farmer was 21,000 Naira (GBP 43.00) on average, leading to an aggregate total of NGN 508M (GBP 1.04M).
Description of Indicators Indicator number Target numbers Actual figures % Achieved / Number of Partners and market actors that invest in pro-poor innovations Output 1.1 (Total) 12 31 258% / Output 1.1 (NE) 6 16 267% / Amount of investment leveraged through market players and key actors Output 1.2 (NGN) ₦ 503,660,000 ₦ 5,103,093,088 1,013% / Output 1.2 (GBP) £1,000,000 £10,530,091 1,053% / Number of poor farmers and small-scale rural entrepreneurs who access new inputs, services, technology as a result of programme activities Output 1.3 (Total) 150,000 245,234 163% / Output 1.3 (Female) 31,500 86,967 276% / Number of case studies demonstrating the link between Propcom interventions and indirect impact. Output 1.4 3 3 100% / Number of interventions that contribute to the improved resilience of farmers and small- scale entrepreneurs. Output 2.1 14 12 86% / Number of interventions that contribute to increased agricultural productivity. Output 2.2 10 11 110% / Number of interventions that contribute to the reduction of GHG emissions. Output 2.3 1 5 500% / Number of interventions targeting the North East region. Output 2.4 6 12 200% / Number of farmers and small -scale rural entrepreneurs with increased resilience to climate change as a result of the programme's CSA activities Output 2.5 (Total) 60,000 194,430 319% / Output 2.5 (Female) 12,600 64,071 458% / Number of regulatory changes, policy reforms, or release of funds by state and federal government to facilitate activities that is supported by the programme. Output 3.1 2 4 200% / Number of actors or organisations (development projects, non-government organisations, farmer organisations and trade associations) that have been supported or influenced by the programme Output 3.2 (Total) 6 10 167% / Output 3.2 (NE) 5 8 160% / Number of 'green shoots' interventions initiated by the programme. Output 4.1 2 2 100% / Despite 2018 being a very challenging year for the project, with the uncertainty surrounding the extension at the beginning of the year, coupled with the challenges of working in a volatile and conflict-affected area, PM has achieved significant results in the first 9 months of the extension. As shown in the table above, the project has significantly exceeded all its Outcome targets for the first year, as well as most of its Output targets for this period. The extremely high achievements in Outcome 2 and Output 1.2 can be attributed to: / Working in mature markets where PM has a long history of engagement. The fertiliser distribution intervention accounted for 69.5% of the total income increase. It should be noted that now that farmers have gained confidence in the quality of fertiliser provided by PM’s fertilizer Delivery Partners having scaled up from 1 kg, 10kg and 25 kg bags that more farmers are now recognising the value and savings in purchasing 50 kg bags from the DP’s and sales have increased in 2018/2019. PM were only documenting the sale of smaller bags but are now recording the increased sale of 50 kg bags form the DP’s. / Working in high value markets (sesame). Sesame accounted for 12.6% of the overall income increase. / The shortfall in Output 2.1 can be explained by the fact that 3 key partners, namely International Committee of the Red Cross (ICRC), Development Exchange Centre (DEC) and Gesellschaft für Internationale Zusammenarbeit (GIZ) have not provided substantial support yet, and therefore do not warrant inclusion in the overall results within the review period. / PM continue to embed best practice gender and Women’s Economic Empowerment (WEE) across interventions and strategic areas, building on the learning from the previous phase. The programme extension will currently increase the resilience of 487,500 rural entrepreneurs and smallholder farmers in northern Nigeria, 162,500 of which will be women and over 250,000 will be based in the north east. Alongside increased resilience, the extension will increase incomes of 120,000 women and 230,000 men, of which over 175,000 will be located in the north east. By the end of the programme at least £4.5m of investment will have been leveraged for climate smart agricultural activity in northern Nigeria. Crucially, because interventions will address major constraints in the way markets operate, these benefits will be sustained and grow beyond the programme’s duration

Recommendations for the year ahead
The recommendations for next year are:
1. Output 1: Selected rural and agricultural market systems work more effectively for poor farmers and small-scale rural entrepreneurs. For sustainable investments, PM will need to explore early how and what entity or system continues to facilitate the linkages that will create investment opportunities after the programme ends.
2. PM will also benefit from a recalibration of its targets based on the learning from 2018 on the significant scale up of Tractor and Fertiliser initiatives that have been running since Propcom 1 to help shape future programming and develop appropriate indicators.

Output 2: Adoption of CSA practises within selected rural and agricultural markets across N. Nigeria, including the NE region.
1. PM should follow through potential investment opportunities with international financial institutions such as Alpen Capitals (based in South Africa), and Symbiotics (a Geneva based organisation).
2. PM should review its logframe targets for maximum impact especially in relation to deepening of the NE interventions.
3. PM should use a climate smart lens in assessing value chains rather than retrofitting activities under the definition of climate smart agriculture to maximise opportunities towards reduction of Greenhouse Gas (GHG) emissions. PM should consider the use of a Climate/Environment Adviser in supporting this work.
4. PM should pursue the interest by ICRC in using solar dyers in northern Yobe and Borno states for fish drying to reduce the present use of firewood for smoking fish.

Output 3: Private investors, government, non-government organisations and development agencies make changes in their approach to northern Nigeria as a result of programme influence.

1. PM to consider working with DFID Social Development Advisors (SDAs) to solidify AAH’s approach on potential e-voucher scheme
2. PM to monitor and engage with Office of the National Security Adviser (ONSA), Fertiliser Producers and Suppliers Association of Nigeria (FEPSAN) and Federal Ministry of Agriculture and Rural Development (FMARD) in the dialogue around the issue of banning fertiliser where Urea or Ammonium Nitrate can be extracted.
3. PM to ensure present PM Fertilizer Partners of ONSA Strategy and requirements of tracking and registration.
4. PM to follow up with the Borno Blending Plant to establish what controls will be in place if the plant starts operating.
5. PM to pull back from engagement and funding for Distribution Partners (DPs) for Purchase of Fertilizer for 2019 if tracking and oversight is not clear.

Output 4: Implement high-risk interventions that have the potential to bring about significant change in market systems

PM and DFID to better articulate indicators around this output to explain better the potential transformation and potential impact.

General
1. A more frequent review of risks is recommended to help direct programming especially with the deteriorating situation in the North East.
2. DFID Nigeria LEAD team should work with PM to showcase good practice to the wider office around disability data collection and how that is disaggregated.
3. The programme should propose to DFID a new and more easily interpreted way to capture the equity dimension of value for money. Since costs cannot be disaggregated across different groups, this may focus simply on the proportion of farmers female, poor and living with disabilities.
4. The programme risk assessment will need to be refreshed more frequently as the security situation continues to unravel to allow real time changes to programming where required as, currently, risk discussions are held with DFID on a quarterly basis. This would also allow any changes to expected results.

## B: DETAILED OUTPUT SCORING

Output Title	Selected rural market systems work more effectively for poor farmers and small-scale rural entrepreneurs
Output number per LF		Output 1	Output Score	A++
Impact weighting (%):		40%	Impact weighting % revised since last AR?	Yes. Was 50%. Outputs were added and the % recalibrated.

Indicator(s)	Milestone(s) for this review	Progress	%
1.1 Number of partners and market actors that invest in pro-poor innovations that the programme helps to pilot	12 (overall) / 6 (North East)	31 (overall) / 16 (North East)	258% / 267%
1.2 Amount of investment leveraged through market players and key actors	1,000,000 GBP	£10,530,091 GBP	1053%
1.3 Number of poor farmers and small-scale rural entrepreneurs who access new inputs, services, technology as a result of programme activities	TOTAL: 150,000 / Partner states – 75,000 / GBT states – 50,000 / BAY states – 25,000	Total: 245,234 / 35% Women / 77,541 / 92,664 / 51,720	163.5%
1.4 Number of case studies demonstrating the link between Propcom interventions and indirect impact.	3	3	100%

The output score is A++ as all targets were either met or substantially exceeded expectation.

Output 1.1: Despite the challenges of slow and bureaucratic and centralised institutional processes of these organisations initial engagements in the North East (NE) was possible. These partnerships included international and local non-governmental organisations (NGOs/INGOs. The programme was able to partner with 31 market actors who invested in pro-poor innovations along with the program’s support. Out of this number, 18 were new while 13 were old partners. Details are provided in Annex 1.

Of these 31 partners, a total of 16 have invested in the NE, exceeding the target i.e. about 267% of the planned target for the period. For example, the intervention with Premier Seeds to introduce certified seeds was initially targeted at 3 states: Kaduna, Bauchi and Gombe. However, Premier Seeds adapted the business model introduced by the programme to 4 other states, Adamawa, Kano, Jigawa and Taraba, helping to reach an additional 20,000 farmers. Each of these farmers have had annual income increases of NGN 21,000 (GBP 43) on average.

Output 1.2: Over NGN 5.1B (GBP 10.5M), investment has been leveraged through partners and market players (please see Annex 2 for breakdown of amount of investment leveraged through market players and key actors (NGN/GBP). This has been a remarkable achievement as it represents an achievement of over 10 times the target of £1m.

Over the years, commercial banks have become interested in investing in the mechanisation space. However, this year, international financial institutions such as Alpen Capitals (based in South Africa), and Symbiotics (a Geneva based organisation) are interested in making investments. The programme has become associated with the success of the tractor hiring model and funding of private sector fertiliser distribution in Northern Nigeria and is considered an honest facilitator with no institutional vested interest in these commercial spaces.

Output 1.3: About 245,000 farmers have accessed goods, services and technologies as a result of programme activities with almost 87,000 of them, women, representing around 35% of the total. Significant results were seen especially for women’s access to improved poultry production inputs (99.3%) and cookstoves (about 96%).

Output 1.4: During the period, Propcom has undertaken 3 research studies to explore and demonstrate evidence of indirect impact in the following interventions:
- Feed Finishing
- CropLife Spray Service Providers (SSPs)
- Improved Local Chicken Production (LoCIP)

Data collection and analysis for the case studies have been completed and the findings are being collated to inform future programming.

Lessons identified this year, and recommendations for the year ahead linked to this output
Overall, there has been a higher than expected engagement by the private sector in the NE leading to an overachievement of the planned targets. The investments leveraged have been larger than anticipated and with the programme meeting and exceeding its targets, there are considerations of the potential to do more. The targets for the future will need to be recalibrated, in line with the learning the programme has had in the first year of the extension.

Recommendations for 2019:
For sustainable investments, PM will need to explore early how and what entity or system continues to facilitate the linkages that will create investment opportunities after the programme ends.

PM will also benefit from a recalibration of its targets based on the learning from 2018 on the significant scale up of Tractor and Fertiliser initiatives that have been running since Propcom 1 to help shape future programming and develop appropriate indicators.

PM should follow through potential investment opportunities with international financial institutions such as Alpen Capitals (based in South Africa), and Symbiotics (a Geneva based organisation). Continue on-going discussions Sahel Capital to look at the potential of commercial shea production in new areas especially the NE.

Output Title	Adoption of Climate Smart Agriculture (CSA) practises within selected rural and agricultural markets across N. Nigeria, including the NE region.
Output number per LF		Output 2	Output Score	A++
Impact weighting (%):		25%	Impact weighting % revised since last AR?	No

Indicator(s)	Baseline	Milestone(s) for this review	Progress	%
2.1 Number of interventions that contribute to the improved resilience of farmers and small-scale entrepreneurs. / Cumulative	9	14	12	86%
2.2 Number of interventions that contribute to increased agricultural productivity.	7	10	11	110%
2.3 Number of interventions that contribute to the reduction of GHG emissions	1	1	5	500%
2.4 Number of interventions targeting the North East region	2	6	12	200%
2.5 Number of farmers and small-scale rural entrepreneurs with increased resilience to climate change as a result of the programme's CSA activities		Partner states – 30,000 / GBT – 20,000 / BAY states – 10,000	TOTAL: 194,430 / (64,071) women	325% / 453%

The output score is A++ where 4 outputs have exceeded expectations and one falling short, only achieving 86% of the target i.e. interventions that contribute to improved resilience of farmers and small-scale entrepreneurs were not fully met, the review team believe the other interventions under this output were achieved within challenging situations especially in the number of interventions targeting the NE.

Outputs 2.1 & 2.2 Over the period, a total of 12 interventions have contributed to improved resilience of farmers and small-scale entrepreneurs and increased agricultural productivity through the adoption of climate Smart Agricultural (CSA) practices and technologies. These are shown in Table 1 below. The interventions considered for this indicator (2.1) exhibit one or more of the following categories (as defined by the FAO)[4]:
[4] http://www.fao.org/climate-smart-agriculture/overview/en/

- Sustainably increasing agricultural productivity and incomes;
- Adapting and building resilience to climate change; and
- Reducing and/or removing greenhouse gas emissions where possible.
The programme’s work promoting certified seeds with Good Agriculture Practice (GAPs) through Local Seed Suppliers (Premier Seed) has gained traction. An essential input for climate smart crop production is quality seeds and planting materials of well adapted varieties. Farmers in developing countries obtain seeds from unregulated sources which includes saving seeds from their own harvests, purchasing seeds from local markets or exchanging seeds with family members (FAO, 2017). In developing countries, where extreme weather events persist such as drought, floods and extreme temperatures these practises of obtaining seeds for crop production as well as poor agronomic practises results in low agricultural productivity and therefore low income.

The programme partnered with a private seed production and distribution company: Premier Seed Nigeria Limited (PSNL). The company produce and market improved seeds of hybrid and open pollinated seeds for crops such as maize, rice, sorghum, millet, soybeans and others. PM worked with PSNL to promote 9 seed varieties to farmers by identifying and training 84 rural seed promoters (RSPs) and 150 major seed distributors (MSDs) in selected states in Northern Nigeria (Bauchi, Gombe and Kaduna). However, the seeds were bought by farmers in multiple states. Seeds promoted and sold by RSPs included cowpea, rice, soybeans sorghum and maize. Over 23,800 farmers bought these certified seeds across northern Nigeria.

A verification study conducted in September 2018 confirmed that the farmers have used the improved seeds. The inherent characteristics of the varieties that were promoted and sold to farmers in these states are expected to make farmers more resilient to external shocks. Farmers who plant the maize varieties promoted will be more resilient to drought and their crops will be tolerant to diseases such as maize streak virus, downy mildew, Striga spp, rust, leaf blight and leaf spot. Farmers who grow the promoted rice varieties will also have low incidence of rice blast disease. Farmers will have higher yields which when sold will translate to higher income. Most of the varieties that were promoted are early maturing varieties which means they will be ready for harvest in a shorter amount of time compared to the local varieties. This will allow farmers who plant these varieties sell early to gain an advantage due to high prices and possibly escape destructive insect cycles that will result in higher yields.

11 interventions specifically contributed to increased agricultural productivity Output (2.2) as shown in Table 1 below.

Output 2.3: There were 5 interventions that contributed to the reduction of GHG emissions as shown in Table 1 below.

Improved cookstoves: An assessment done in 2017 by the programme estimated that households using improved cookstoves reduce their fuel consumption and associated costs by 40-50% compared to traditional ones and can recoup their initial investment in just two weeks.

The use of Mechanisation services using tractors identified local booking agents that helped in identifying clusters of farmers who wish to use tractor services in a more rational and economic manner within a given location where a minimum of 150ha can be cultivated. Where over 500 tractors are being dispatched to farmer clusters identified by the booking agents in rural areas of northern Nigeria significant savings in fuel consumption and reduction GHG emissions can be achieved. With tractor operators, land preparation is done in a manner that reduces soil compaction over time. With well-adjusted ploughs, harrows and threshers, greater efficiency is achieved reducing GHGs of a given tractor and associated increase in productivity through reduced fuel use.

PM also engaged with Action Against Hunger (AAH) to expand the cultivation of soybean: Soybean is a leguminous crop, therefore fixes nitrogen in the soil. Expansion in the cultivation of soybean reduces the subsequent use of inorganic fertiliser, helping to reduce GHG emissions.

PM also supported Fertiliser distribution using Distribution Partners (DPs) and their Rural Partners (RPs) networks: The use of sealed bags reduces the levels of nitrate gaseous emissions when bags are open to the atmosphere. It is important to note that some fertiliser brands sold to farmers in an unregulated environment allows adulteration, changes in weight and deterioration of the product because of the opening of the sealed bags. Secondly, the aggregation of demand by distributors allows the manufacturer to efficiently supply the fertiliser reducing the number of journeys and associated GHG emissions which contribute to reduced GHGs. When GAPs complement proper fertiliser application (timing, quantity, and placement method) better uptake is achieved by plants and there is reduced leaching and gaseous emissions into the atmosphere.

PM also supported the use of Solar dryers initially designed to reduce firewood consumption for drying tomatoes and to replace unhygienic sun drying. ICRC has also expressed interest in this improved design for use in northern Yobe and Borno states for fish drying to reduce the present use of firewood for smoking fish.

Output 2.4: There were a total of 12 interventions targeted at the NE region. The programme was able to successfully double its target with the NE interventions. These are shown in Table 1 below.

Table 1 Interventions contributing to Outputs 2.1 – 2.4

	Output 2.1 Improved resilience of farmers and small-scale entrepreneurs	Output 2.2 Interventions specifically contributing to increased agricultural productivity	Output 2.3 / Reduction of GHG emissions	Output 2.4 / Interventions targeted at the NE region
Poultry vaccination using NDV-i2
CropLife SSPs
Olam Sesame
Mechanisation services using Tractors
Certified seeds with Premier Seed
Action Against Hunger (AAH)
Improved local chicken production (LoCIP)
Fertiliser distribution using DPs and their RP networks
Improved cookstoves
ICRC Partnership
Rice production with Food Security Agricultural Company
PPR vaccination (small ruminants) with several veterinary partners
Sesame production & marketing (Olam)
Millet & Hibiscus (Green Sahel)
16.Tractor service provision
17. Solar Dryers
Warehousing & input financing (AFEX)

Output 2.5: The programme also supported farmers and small-scale rural entrepreneurs with improved resilience to climate change as a result of CSA activities. The table below highlights the significant strides achieved exceeding the target by 315% including also exceeding the gender targets.

Improved resilience by intervention as a result of the programme's CSA activities:
	Resilience [Overall]	Resilience [Female]	Resilience [Female] (%)
Fertilizer distribution	68,399	20,493	30.0%
Poultry vaccination with NDV-i2	38,424	23,823	62.0%
Certified seeds with Premier Seed	23,822	1,689	7.1%
Spray service provision (CropLife)	22,637	3,500	15.5%
Warehousing & input financing (AFEX)	10,253	782	7.6%
Sesame production & marketing (Olam)	10,043	1,321	13.2%
Improved poultry production (LoCIP)	9,233	9,172	99.3%
Tractor service provision	5,521	272	4.9%
Millet & Hibiscus (Green Sahel)	3,197	177	5.5%
Action Against Hunger	1,462	1,462	100.0%
Improved cookstoves	1,438	1,380	96.0%
Grand Total	194,430	64,071	33.0%

Income increase through increased resilience and improved productivity:
	Income (NGN)	Income (GBP)
Fertiliser distribution	7,387,020,436	15,242,912
Sesame production & marketing (Olam)	1,341,426,243	2,767,996
Certified seeds with Premier Seed	508,401,514	1,049,072
Spray service provision (CropLife)	453,551,730	935,891
Poultry vaccination with NDV-i2	347,950,666	726,643
Warehousing & input financing (AFEX)	319,953,991	660,216
Improved poultry production (LoCIP)	76,650,204	158,166
Tractor service provision	59,163,493	122,082
Millet & Hibiscus (Green Sahel)	40,129,915	82,807
Improved cookstoves	746,642	1,541
Grand Total	10,534,994,832	21,747,327

Recommendations for the year ahead linked to this output
Despite the deteriorating and fluid security situation in the NE, the programme leveraged existing NGOs and INGOs to enter the conflict affected areas and focused on sustainable market recovery, yielding very strong results in the first 9 months of the extension. The lessons learned will be used to inform future programming and review the targets going forward.

1. PM should review its logframe targets for maximum impact especially in relation to deepening of the NE interventions.
2. The overall climate smart element of the programme needs to be strengthened and PM should use a climate smart lens in assessing value chains rather than retrofitting activities under the definition of climate smart agriculture to maximise opportunities towards reduction of GHG emission reduction. PM should consider the use of a Climate/Environment Adviser in supporting this work.
3. PM should pursue the interest by ICRC in using solar dyers in northern Yobe and Borno states for fish drying to reduce the present use of firewood for smoking fish.

Output Title	Private investors, government, non-government organisations and development agencies make changes in their approach to northern Nigeria as a result of programme influence.
Output number per LF		Output 3	Output Score	A+
Impact weighting (%):		20%	Impact weighting % revised since last AR?	Yes. Was 25%. Outputs were added and the % recalibrated

Indicator(s)	Milestone(s) for this review	Progress	%
3.1 Number of regulatory changes, policy reforms, or release of funds by state and federal government to facilitate activities that is supported by the programme.	2	4	200%
3.2 Number of actors or organisations (development projects, non-government organisations, farmer organisations and trade associations) that have been supported or influenced by the programme	Overall - 6 / NE – 5	Overall -10 / NE – 8	167% / 160%

The score for this output is A+ as the output generally exceeded expectation. The programme began to make some key connections with INGOs and NGOs supporting a shift from humanitarian response to early recovery and longer-term development of their beneficiaries in conflict and post-conflict areas and should continue to develop these relationships. There has also been good coordination between the DFID Partnership, Engage, Reform, Learn Programme (PERL) -Engaged Citizen Participation (ECP) and Propcom Mai-Karfi programmes.

Output 3.1: Whilst no discernible progress has been made on the National Fertiliser Bill which the programme facilitated in the previous year, the programme continues to seek opportunities to influence regulatory or policy changes across the state and federal government. There is a range of activities and partnerships involving federal, state and local institutions and the DFID PERL-ECP programme complements the scope of the work done by the Propcom Mai-Karfi programme. For example, the programme has influenced PERL- ECP to change focus from working on national fertiliser policy to seed standards in Nigeria. ECP subsequently initiated a comprehensive institutional review of the Nigerian Seed Council to identify constraints for it to deliver its mandate of ensuring quality seeds are correctly sold to smallholder farmers (SHFs) in northern Nigeria when sold through commercial markets. ECP (PERL) has taken up supporting reforms in the Nigerian Seed Council both Nationally and at State Level remedy this constraint while PM has engaged with commercial seed producers to identify the production of certified seeds and its delivery to SHFs.

Propcom Mai-Karfi is partnering with Department of Livestock, Jigawa state to establish the community animal health workers (CAHW) training program with a view to develop a network of CAHWs to deliver affordable veterinary products and services to rural livestock producers and improve disease reporting and surveillance. So far, the Jigawa State government has invested in “training of trainers’ session, with 8 veterinarians trained as State-based trainers. They have shared the cost of training 60 CAHWs, and have invested in ambulatory kits for the CAHWs, providing them with motorbikes for mobility.

In Borno state, Inter Products has signed a Public Private partnership (PPP) with the state government initially facilitated by the programme as part of a strategy to increase the supply of specific blends of fertiliser for the Borno, Yobe and Adamawa axis. Other discussions facilitated by PM ran in parallel with a similar attempt at revitalising the government-owned blending plant in Yobe. This did not materialise primarily as Golden Fertiliser considered that their existing fertiliser plant in Kaduna could cover the volumes demanded in Yobe and surrounding states.

PM also, in collaboration with ECP (PERL), has engaged in public policy dialogue on agricultural policy and improved service delivery at state level (Kano, Kaduna and Jigawa) in this reporting period. This included private sector, government and farmer associations. Future work is required to improve state and LGA budgetary allocations and adequate oversight by government and beneficiaries as part of PERL’s service delivery mandate.

Output 3.2: A total of 10 actors and organisations have been supported or influenced by PM as listed in Annex 3 and of these, 8 have worked in the NE.

Some unintended but valuable results have emerged as through these interventions. For example, through the programme’s work with Action Against Hunger (AAH) there is a move towards shifting from a ‘rapid response’ portfolio to a more sustainable market recovery focus and discussions are ongoing around a potential for change from direct procurement to use of e-voucher schemes for supply of goods to beneficiaries by AAH i.e. stimulating the local market.

Also, some Spray Service providers (SSPs) in Jigawa and Kano states have mobilised themselves to form a registered cooperative association to enhance their individual businesses. A total of five groups each are present in both states. Potentially these groups could gain some financial advantage in bulk purchases of CPPs from companies and allow them to gain access to information on best spray service practices.

Recommendations for the year ahead linked to this output
1. PM to consider working with DFID (SDAs) to solidify AAH’s approach on potential e-voucher scheme
2. PM to monitor and engage with Office of the National Security Adviser (ONSA), Fertiliser Producers and Suppliers Association of Nigeria (FEPSAN) and Federal Ministry of Agriculture and Rural Development (FMARD) in the dialogue around the issue of banning fertiliser where Urea or Ammonium Nitrate can be extracted.
3. PM to ensure present PM Fertilizer Partners of ONSA Strategy and requirements of tracking and registration.
4. PM to follow up with the Borno Blending Plant to establish what controls will be in place if the plant starts operating.
5. PM to pull back from engagement and funding for DPs for Purchase of Fertilizer for 2019 if tracking and oversight is not clear.

Output Title	Implement high-risk interventions that have the potential to bring about significant change in market systems.
Output number per LF		Output 4	Output Score	A
Impact weighting (%):		15%	Impact weighting % revised since last AR?	N/A New Output

Indicator(s)	Milestone(s) for this review	Progress	%
4.1 Number of 'green shoots' interventions initiated by the programme.	2	2	100%

The output score is A – the output met expectations. The programme undertook two high risk interventions with potential for transformational change beyond the end of the programme working with a private sector company (Arla) and pursuing solar drying technology uptake.

Commercial sourcing of liquid milk from local communities.
Arla, a European dairy processing cooperative with significant presence in the UK, is a key player in the importation of milk powder into Nigeria. The company has recognised that there is commercial potential to substitute importation of milk and milk products with local production, based around a number of models. One such model is to seek to improve the productivity of the traditional Fulani dairy cattle, belonging to the settling, but previously migratory, Fulani communities in the North West of Nigeria. This is a commercial proposition, where Arla establishes cold chain facilities at or near such settlements. Arla reached out to PM in the selection and training of such communities to meet required production and quality standards for onward processing.

Arla is working on a strategy which is being implemented through a partnership with MILCOPAL, a milk processing plant jointly owned by cooperatives of Fulani pastoralists (called the MILCOPAL project). Arla is also partnering with Kaduna state government on developing a 6,000 hectares dairy estate for 1,000 pastoral households in Kubau LGA (called the Damau Household project). Arla, through MILCOPAL, would procure fresh milk from Fulani pastoralists and process into yogurt for sale in the local Nigerian market. This complements Arla’s line of products which includes the “DANO Milk” brand. This is a high-risk initiative as the situation of the target Fulani communities has been politicized, and their traditional migration across Africa to follow feed sources for their livestock has led to repeated clashes with communities along their traditional migration routes and grazing reserves. Therefore, these influences may distort attempts to engage with Fulani milk producers in a sustainable way. Propcom has partnered with Arla to provide baseline information, technical support and group management training in sequence to the installation of four milking units in selected LGAs in Kaduna state. The installation and commissioning of this equipment is expected in March 2019.

Solar Drying: Discussions are on-going to include an intervention on Solar drying. This is the provision of solar drying services via SMEs to smallholder farmers to address the challenge of post-harvest losses (reportedly up to 45% loss), contaminants, theft, poor quality of dried products and labour intensity associated with traditional practices (non-uniform drying and time required). It requires investing in a suitable solar-drying technology, mapping out the market and designing and implementing a service provision model that is sustainable. The plan is to first target the vegetable and root production corridor, and subsequently, the fruits, fish and meat jerky areas especially in the North East. Significant investment ($14,000-$20,000 for a solar drying unit which may serve between 100-500 farmers for a fully optimized design) will be required for start-up and will have a slow start, as such, may not yield returns in the first few years. An SME (a Potential Partner.) would need to invest in at least 2-5 of such machines for it to make business sense. PM has started to work with Creed Energy whose technology is undergoing modification to better align with market realities. They have also undertaken some market assessment to design a feasible financing and service model that would interest an SME, be it a social entrepreneur or fabricator. A major risk here is the high upfront cost for the SME. The availability of the technology within Programme States is totally dependent on access to finance and the risk appetite of the Entrepreneur. PM is currently refining the business model to ensure a good pitch is produced that would attract investors.

If this technology is expanded, the impact could be transformational – new technology adoption, behaviour change at the farmgate and market actor level, increased productivity, job creation, income increases, etc. With proof of concept and interested Partners, simply deploying 10 solar dryers across locations will lead to at least 50 jobs created, reach about 5,000 farmers in one production cycle with triple benefits – eliminate post-harvest losses, premium prices for improved product quality and freeing up women’s unpaid time who typically are involved in post-harvest activities. The utility of the technology and profitability of the model for the SME is expected to catalyse the market – more SMEs deploying the machines and more farmers across multiple value chains accessing the service and resultant benefits. Access to finance can be used to scale up the availability of Dryers, potentially reducing the price and making it more affordable for SMEs.

Solar-dryers offer clean energy (eliminating the need for wood) in the production of dried and meat jerky. The Dryers will be a major part of PM CSA portfolio and they would intend to actively pursue this in all project sites.

Recommendations for Output 4 include:
PM and DFID to better articulate indicators around this output to explain better the potential transformation and impact.

## C: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change holds true with interventions designed to overcome identified market constraints leading to greater access to market related goods and services that positively impact on increased incomes of poor households. This increased income in turn constitutes to the households increasing their resilience and decreasing their levels of poverty.

The Evaluation affirms the validity of the Theory of change and no changes to are proposed this year

Is the programme on track to contribute to the expected outcomes and impact?
The programme is on track to deliver at outcome and impact level. It exceeded outcome level targets this year as shown below.

Description of Indicators	Indicator number	Target numbers	Actual figures	% Achieved	Deficit
Number of poor farmers and small scale rural entrepreneurs recording net additional income change as a result of programme activities.	Outcome 1 (Total)	40,000	190,198	475%
	Outcome 1 (Female)	8,400	59,857	713%
Aggregate net additional income among poor farmers and small scale rural entrepreneurs in selected rural markets as a result of programme activities.	Outcome 2 (NGN)	₦ 755,490,000	₦ 10,534,994,832	1,394%
	Outcome 2 (GBP)	£1,500,000	£21,747,327	1,450%

Explain major changes to the log frame in the past year
The logframe prior to the extension was purely an M4P oriented programmatic approach. This has been redesigned to focus on Climate Smart Agriculture (CSA) with emphasis by the UK government towards addressing agricultural livelihoods and market reengagement in post-conflict areas in the NE, notably in Borno, Yobe, and Adamawa states (subsequently defined as BAY states). The extension was designed to take PM’s market development expertise to this higher-risk environment, together with continuing work in the crisis-affected states of Bauchi, Gombe and Taraba (defined as GBT) and continued engagements in DFID “Partner States” of Jigawa, Kano and Kaduna using a more traditional M4P approach.

The logframe was significantly changed to reflect the extension given to PM. This reflects the transitioning from 19 to 9 states and the new geographic footprint and focus of the NE. This needed the retention of some indicators, addition of some new ones pertaining to CSA, and removal of some which no longer had relevance. Some of the indicators were disaggregated by overall milestone targets and targets for the different geographic areas (BAY, GBT and Partner states). Resilience and income increase were separated into 2 different indicators. A series of discussions were held on the tracking of nutrition and disability issues as a result of program activities by PM or partners. These discussions are still on-going to clarify what can be expected, and what is possible, by PM. Detailed discussions were also held with the SRO to clarify the definition of resilience as a key aspect of the PM theory of change.

This annual review is based on the revised logframe and milestones.

Describe any planned changes to the log frame as a result of this review (1/2 page)

Two of the programme markets (fertiliser and mechanisation) are legacy markets from Propcom 1. These two programmes are responsible for over 44% of the programme beneficiaries and for over 40% of the programme’s female beneficiaries. Much is often made of M4P’s alleged “hockey stick” beneficiary outreach over time, where markets reach exponentially larger numbers of clients over longer periods of time. These two markets, inherited from the earlier iteration of the programme, have gained traction over about 15 years of activity resulting in these significant outreach numbers

The logical framework will be refined to reflect this ‘hockey stick’ outreach but some caution will need to be applied in significantly increasing beneficiary numbers. Recorded impact this year has far exceeded expectations with ‘new’ farmers being serviced by PM partners. Next year it is likely that the PM partners will focus on deepening their engagement markets with these new clients as repeat customers who will not be recorded in PM results as direct beneficiaries. There is the likelihood that, due to this focus, the numbers of new clients would be reduced.

The new logical framework proposed will:
Increase the overall numbers of beneficiaries as shown below.

	Indicator		Current	Proposed	% increase
Access Beneficiaries		Year 2	325,000	375,000	15%
Resilience beneficiaries		Year 2	180,000	300,000	67%
Income beneficiaries		Year 2	125,000	240,000	92%

Increase the percentage of beneficiaries in the BAY and NE State as shown below.

	Indicator		Partner states Increase	GBT / states / Increase	BAY states / Increase	NE Increase	Overall / Increase
Access Beneficiaries		Year 2	0%	21%	16%	18%	15%
Resilience beneficiaries		Year 2	58%	73%	78%	75%	67%
Income beneficiaries		Year 2	94%	108%	122%	114%	92%

Other revenue related indicators will be agreed in the coming weeks.

## D: VALUE FOR MONEY

Nine value for money indicators were agreed in the PM Monitoring and Results Measurement strategy (June 2018). Performance against these indicators for 2018 and the preceding years are reported below.
It is important to note that whilst the comparison between 2018 and the previous two years is favourable it is not necessarily a like for like comparison. 2018 is the first year of the programme extension where costs were lower than expected (because of the delays with contracting and staff) but results from established interventions continued to roll in.

VFM Dimension	Ref #	VFM Indicator	2016	2017	2018	Equity
Economy	A1	Total operational costs/total costs.	34.4%	33.2%	24.5%
Efficiency	B1a	Cost per farmer/small scale rural entrepreneur reached through inputs, services or technology.	£20.5	£20.7	£16.1	
	B1b	Cost per female farmer/small scale rural entrepreneur reached through inputs, services or technology.	£118.1	£100.7	£44.1	
Effectiveness	C1a	Cost per farmer/small scale rural entrepreneur benefitted.	£35.2	£32.0	£20.0	
	C1b	Cost per female farmer/small scale rural entrepreneur benefitted.	£200.7	£148.0	£63.5	
	C2	Beneficiary income gain per £ spent.	£1.02	£1.28	£5.72	
	C3	Private sector investment leveraged per £ spent.	£1.72	£2.30	£2.77

In terms of economy, the ratio of operational costs to total costs remains low.

Efficiency is measured in by the cost per farmer or entrepreneur accessed. Access can include, for example, purchasing agricultural inputs, or accessing training or other services as part of the PM interventions.

Effectiveness is measured by the cost per farmer who actually benefits from PM in terms of an improved income. This compares very favorably with the benchmark of £88 from DFID’s “Commercial Agriculture Portfolio Review”. At the same time for every £1 spent beneficiary incomes have increased £5.72 and £2.77 of private sector income was leveraged.

These indicators are already used a basis for appraising and benchmarking potential new interventions and will become more powerful when later this year when PM is able to disaggregate the cost effectiveness of different interventions.

Equity is partly measured by the cost per female accessed and benefiting (B1b and C1b). But these indicators should be treated extremely cautiously. Conceptually it is impossible to disaggregate the costs of reaching women and men. So, the cost per female accessed is calculated as the total expenditure for the year divided by just the female farmers. In other words, even if half the people accessed were female, then the cost per female would by this method appear to be double the overall cost per farmer.

As well as indicators B1b and C1b equity is also measured by whether the farmers accessed and benefiting include women, people estimated to poor and people with disabilities. This indicated in the table by a simple tick.

It is commendable that PM have deployed the Washington Group Question (among the first data collections to do so in Nigeria) to disaggregate data for disability by gender and age. The tables below provide a summary of some results.

By State:
State	Respondents	W/disability	Prevalence (%)
Bauchi	466	34	7%
Jigawa	386	18	5%
Kaduna	313	10	3%
Taraba	166	3	2%
Gombe	336	6	2%
Yobe	555	2	0%
Borno	30		0%
Total	2,252	73

By Gender:
Gender	Respondents	W/disability	Prevalence (%)
Female	841	33	4%
Male	1,411	40	3%
Total	2,252	73

By Intervention:
Intervention Name	Respondents	W/disability	Prevalence (%)
Olam Sesame	611	25	4%
Green Sahel	328	13	4%
CropLife	393	14	4%
Tractor	414	14	3%
Arla Dairy	157	5	3%
Action Against Hunger	197	2	1%
Improved Cookstoves	62		0%
DEC A2F	90		0%
Total	2,252	73

By Type of Disability:
Type of Disability	W/disability
Difficulty seeing	33
Difficulty hearing	27
Difficulty remembering or concentrating	15
Difficulty walking or climbing steps	7
Difficulty with self-care	4
Difficulty communicating or being understood	2

From a VfM perspective – especially a cost effectiveness perspective – this programme continues to represent excellent value for money and should continue.

Recommendation:
1. DFID Nigeria LEAD team should work with PM to showcase this good practice to the wider office.
2. In the next six months PM should propose to DFID a new and more easily interpreted way to capture the equity dimension of value for money. Since costs cannot be disaggregated across different groups, this may focus simply on the proportion of farmers female, poor and living with disabilities.

E: RISK

Overview of programme risk (noting the rating from p.1) and mitigation

The overall Programme risk rating has remained at Moderate since the last annual review. The Business Case and ToRs for the Extension described in detail the risk of climate change, environmental degradation and operational challenges in Northern Nigeria. These risks are exacerbated in BAY and GBT States of the NE Region, and those risks remain.

The potential that the programme risk rating could change is highly likely as a result of the context of the deteriorating security in the North East, which could directly translate to physical / security risk of PM staff if travelling and working in affected areas. As this is dependent upon where work is being undertaken there needs to be assessments in the conflict prone states/areas of the NE along with Southern Kaduna that should be increasingly disaggregated on an LGA by LGA basis. Some of this risk is mitigated by Palladium having in place a dedicated security advisory team.

Recommendation: The programme risks are currently reviewed on a quarterly basis. This will need to be reviewed and refreshed more frequently as the security situation continues to change to allow real time changes to programming where required and changes in the expected results.

The security situation has the potential to impact on the programme’s fertilizer intervention where there will be restrictions on fertiliser movements in the North by Nigerian military for security reasons. The programme will need to continue to engage with the office of National security Adviser and State Ministries of Agriculture to balance the security and agriculture needs in fertiliser market. DFID will work with the programme to see if there are opportunities for escalating with key political and technical bodies to help reduce the impact of restriction on sales and transportation of granular fertilizer. If this gains traction, the programme will also need to work jointly with commercial fertiliser companies, political office holders and local security agencies to develop a practical approach to the movement and use of both granular and liquid fertiliser.

The programme managed its delivery risks well over the period and exceeded targets by scaling up and investing more in the activities demonstrating good results as well as improving income for the female farmers like poultry vaccination, hibiscus, shea and acha processing. Other risks of Crop Failure / Pests (Fall Army Worm) / Drought and the severe flooding in Jigawa, northern Yobe, NE Borno, Adamawa and Taraba meant however the timely delivery of some milestones for 2018/19 in respect to field data slipped due to late planting and extensive flooding in a number of States where PM works.

The programme also trained farmers in the safe handling of agro chemicals and inputs to mitigate any risk to health and to the environment, effectively managing safeguarding risks.

Since moving into the North East, PM has managed the fiduciary risks, associated with working in states in NE Nigeria where governance structures are predominantly weak. Partnerships with NGOs and INGOs have seen the introduction of more stringent delivery chain mapping with more regular updates and reported quarterly. PM has implemented stricter due diligence, conflict of interest and associated background checks, and more responsibility delegated to technical team to improve the required partnerships, collaboration and trust.

F: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Performance of partners and DFID, notably on commercial and financial issues (1-2 pages)
With regard to DFID
The programme has performed well over this period, considering this was the start of the extension phase and scaling into the North East. Whilst there have been a number of staff changes in PM since signing the contract, these have been managed well overall as well as maintaining good relations with DFID offering support where required. The certainty of the extension, signed off in August 2018, allowed the team to enter into longer term contracts with partners, and to positively plan interventions for the medium to long term. New initiatives have seen traction, notable for example is the Islamic non-interest loan products being taken up by agricultural input distributors, leading to improved fertiliser supply. During the reporting period, PM also played a major role in demonstrating the work of UKAID projects in Nigeria to His Royal Highness (HRH) the Prince of Wales, who was visiting Nigeria as Head of the Commonwealth. Interventions showcased were poultry and acha, with demonstrations by the PM technical staff. The programme also supported a visit by the Deputy High Commissioner to Kaduna, where opportunities for UK trade and investment were explored with partners.

The programme successfully pivoted into the North East and was able to quickly work though and adapt to the challenges, demonstrate sufficient traction and identify market potential and has delivered on targets, exceeding some results in key areas. The lessons have been captured and will be used to shape future programming as well as delivery targets.

The programme’s good performance will allow the programme to scale up in with Tranche 2 funds of approximately £10.2m as stipulated in the contract; this will be in addition to Tranche 1 funding at the end of the first year of the extension. The initial tranche was split 50:50 between NE and CSA focused work, and the second tranche will be split 80:20 (in favour of NE intervention).

Quality and Timeliness of narrative reporting:
The quarterly reports have been received on time over the reporting period and have been of very good quality. They have reported progress against the outputs, providing details of progress against the interventions as well as new ones on the horizon, including how cross cutting issues of women’s economic empowerment and disability are addressed. PM has also followed up with action points from the quarterly reports to DFID’s satisfaction.

Quality and Timeliness of Audited Financial Statement
PM is managed by Palladium and DFID has received the annual edited statements for June 2017. The 2018 audited statement is expected in June 2019. Palladium’s Annual Audited Statement is received annually and there are currently no issues of concern.

DFID commissioned its second independent financial and programme audit in 2017, which covered the period July 2014 – February 2017 and was unqualified. Recommendations from this audit have been tracked and good progress has been recorded. The third audit covering March 2017 – December 2018 has now been completed and is unqualified. Recommendations from this is currently being discussed and will be taken forward over the coming months.

 Quality of Financial Management
PM’s total expenditure for the financial year 2018/19 is £3,832,369.82by, against a forecasted budget of £3,783,201 showing an overspend of £49,168.82 (1%) for 2018/19 financial year. The details of 2018/19 financial year budget expenditure and variance analysis are as below:

Period	Forecast	Actual Spend	Variance	% variance
Q1	£834,656	£861,603	-£26,947	-323%
Q2	£983,196	£970,291.72	£12,904	-6.67%
Q3	£1,208,901	£1,228,452	-£19,551	2.51%
Q4	£756,448	£772,023	-£15,575	0.98%
Total	£3,783,201	£3,832,370	-£49,169	-1.30%

We recorded major improvements in PM’s forecasting accuracy compared to previous years

Period	Budget	Actual Spend	Variance	Variance (%)
FY15/16	£4,869,131.00	£4,879,481.37	-£10,350.37	-0.21%
FY16/17	£4,458,740.00	£4,221,976.00	£236,764.00	5.31%
FY17/18	£3,248,281.00	£3,362,049.00	-£113,768.00	-3.50%
FY18/19	£3,783,201.00	£3,832,369.82	-£49,168.82	-1.30%
Average				0.07%

Delivery Chain Map:
The Programme’s delivery chain mapping has been updated to follow the fund flow, especially since moving into the North East, to identify key risks and put the necessary controls in place. Please see attached as Annex 1.

Assets:
DFID programme team conducted a spot check on the assets in November 2018 and recommended that the register be updated by the PM team to highlight assets no longer repairable and therefore due for disposal. The asset register has now been updated and approval will be sought by the DFID programme team for disposal of unwanted assets. Recommendations on assets from the DFID commissioned audit will also be taken forward with the PM team.

Commercial performance:
PM is managed by a contract with Palladium. The procurement is undertaken by DPSA/AECOM through a call down contract issued by PCD. Third party independent evaluation was undertaken through a contract with Upper Quartile. This contract ended in December 2018. There is an audit contract, procured through a single source on the basis that the same audit company that conducted the last audit of Propcom Maikarfi performed well.

Date of last narrative financial report(s) / Propcom Maikarfi	December 2018 (covering October to December 2018)
Date of last annual audited statement Palladium	September 2018 (covering 2017) – palladium commissioned / March 2019 (covering March 2017 – December 2018 – DFID commissioned,

G: MONITORING, EVIDENCE & LEARNING

Monitoring
 Monitoring throughout the review period included:
- SRO weekly meetings with PM.
- SRO attendance at Quarterly Programme Management Boards.
- Independent evaluation by WYG consulting (previously Upper Quartile).

Studies on the systemic effects and impact on farmers and households of Poultry interventions, Electronic Warehousing, Feed Finishing and Crop Protection Products have been undertaken by PM. These have validated PM internal monitoring reports and the data in their Dynamic and Adaptive Monitoring System (DAMS) which is linked to a comprehensive Geographical Information System (GIS) system.

Evidence and evaluation
To date PM’s recorded beneficiaries monitored are direct beneficiaries. This review notes that monitoring exclusively direct beneficiaries has actually resulted in significant under reporting. Work is currently in progress to try to quantify how many indirect farmers have been reached through these interventions.

The recently completed Independent third-party final evaluation/monitoring by WYG consulting (previously Upper Quartile) stated that conclusive evidence showed that the programme interventions were relevant in overcoming both demand and supply side constraints in most of the markets evaluated. Access to information, access to finance and last mile distribution were common demand side constraints. Access to sufficient quantity of suitable quality goods and services were common supply side constraints.

Impact
In seven of the nine evaluated markets, incomes of participating households increased. Given the wide range of sources, the evidence was conclusive that the programme interventions contributed to increased household incomes. In Poultry Health, the average increase was by a factor of 2.7 and in the Babban Gona households maize related incomes doubled. Households across all seven markets reported buying assets with their increased incomes, in some cases increasing their involvement in the income producing activity, and in other cases reporting diversifying their income streams. Households also reported spending additional income on school and medical fees and on improving their living standards.

Where women reported being in control of an asset, such as chickens or maize farming, they also reported benefitting from the increased income as a result of increased productivity. This suggests that women who were reached and included in these interventions did experience benefits, potentially to the same level as their male counterparts, however the number of women included varied substantially across the various interventions sampled.

Effectiveness
In the evaluation, effectiveness speaks to changes within the core (i.e. the household) market. Again, conclusive evidence pointed to programme interventions that have, increased awareness which has led to increased demand for the product, stimulating delivery and increasing use of this product. This in turn has led to greater productivity and resulted in increased incomes, increases resilience and decreased poverty.

Not all of the realised benefits might however be attributable to the programme. Increased demand for local produce and the resultant blocking of imported goods has also led to increased prices and therefore will have contributed to increased household incomes. This being said, increased awareness and increased knowledge of products and services and the resultant increased demand for these, are very likely attributable to the programme. Over the longer term, these behaviour changes increase household resilience which contributes to decreased poverty over the longer term.

Sustainability
In one set of villages that affected by kidnapping and banditry, displaced villagers who had earlier realised benefits from a programme intervention immediately adopted their changed behaviour on their return to their home village. This speaks to the ongoing uptake of the previously unavailable goods and services, and the behaviour change resultant from programme interventions.

Similarly, conclusive evidence speaks to ongoing delivery of these goods and services due to this increased and ongoing demand, at various levels of the market system. Copying, where one household recognises and adopts an intervention behaviour was observed and reported in numerous market interventions; notably in poultry health, maize farming and Electronic Warehousing Receipts System (EWRS). Crowding in, where market system players adopt and refine a programme business model has been observed and reported on in poultry health. These behaviours are indicative of practices and models that are seen to be proven and profitable and that have traction within the market system.

Women’s Economic Empowerment
The programme demonstrates clear evidence on a great deal of work being undertaken, or planned, to improve women’s economic empowerment. The targets to reach women and to improve their incomes are clearly underpinned by (and being achieved through) a wide range of activities to improve women’s participation in the labour market, and their productivity, through value chains most accessible to and ‘acceptable’ for women. It is less clear if and how the programme seeks to pave the way for women to enter into more profitable but less traditional sectors/value chains.

The good work being undertaken does not seem to be placed within a wider strategic framework, however. This also applies to wider inclusion aspects within the programme, and to the programme’s approach to ‘doing no harm’ and promoting the protection of vulnerable groups. For example:
- the programme now collects very useful data on inclusion of persons with disabilities within the programme. This gives a basic profile of the characteristics of people with disability (PWDs) within the programme, which could be helpfully augmented with qualitative research to understand PWD participants experiences of the programme (and barriers to those not participating in the programme), in order to identify enablers and constraints, and develop the programme’s approach to enhancing inclusion of PWDs.
- there is an awareness within the programme that child protection needs to be considered more deeply, particularly when it comes to children’s engagement in economic activities. DFID should connect the programme to technical specialists in this field, and the programme should update its due diligence assessment at a minimum. Child labour and child protection should also be considerations within a wider strategic approach to social inclusion.

There also does not seem to be a systematic approach embedded within the programme to seek out and analyse beneficiary/community feedback within the programme. Such a mechanism could be usefully scoped out and included as part of the proposed gender and social inclusion strategic framework. The proposed gender and social inclusion framework should take a wide view of how to improve Women’s Economic Empowerment and situate Women’s economic empowerment (WEE) within the different contexts the programme is working. This should also take a broader view of how the programme can, at a minimum, seek to avoid perpetuating exclusion of marginalised groups and endeavour to ‘do no harm’. It should also set out how far the programme intends to go in terms of actively empowering marginalised groups other than women.

This could include consideration of:

1. ‘Do no harm’/avoiding exclusion: Undertake research into social barriers to economic participation/empowerment (e.g. harassment and discrimination, ability to build networks, spousal support, parental influences, access to information) and build strategic approaches to address or work around these barriers. These might include:
  1. Beneficiary feedback mechanisms to better understand barriers to inclusion and ways to promote inclusion of marginalised groups
2. Empowerment of women and other marginalised groups:
  1. Undertake analysis (if not done already) of factors driving lower productivity of female farmers (assuming this is the case)
  2. Undertake analysis of occupational segregation and its impact
  3. Develop approaches to including women in higher productivity sectors or value chains where appropriate
  4. Work with ‘Inclusion Works’ (new CMP in Nigeria) to learn from best emerging practices in inclusion of PWDs in the labour market.

Quotes from Beneficiaries

“I gained better understanding on how to raise chickens from the Propcom train. My production has improved and I’m now earning more income. My flock size has increased from 5 chickens to 22 chickens”. – Amina Hassan – Poultry farmer, Kaltungo LGA, Gombe state

“I give special thanks to Propcom and CropLife. My livelihood has changed since I received the training. I can dream of being an agrodealer so that when people call me to come and spray for them I can immediately go and render the service instead of needing to go and buy chemical first”. – Musa Isah – Crop service provider, Gwarzo, Kano state

“There were never any interventions in hibiscus and millet in the state, both from NGOs or government. Farmers had no training. There were no input or output markets. But Propcom came and things have changed now. Fertiliser companies are offering fertilisers to farmers on credit, companies are buying their harvests”. – Mohammad Ahmad Adamu – CEO, Green Sahel

‘A lot of people are expectantly waiting to plant the same millet seedlings next year. The technique that was brought for thinning surprised many observers but when they saw the yield they have all come back to request for the seeds”. – Umar Yusuf – Millet farmer, Gagarawa, Jigawa state

“I give special thanks. Before we don’t get fertilisers. Before if they bring fertilisers they will join 3 or 4 farmers together to share a bag. But now we have more access which I am grateful for. Our benefits have multiplied. I pray that the programme continues so that more people can benefit and there will be less problems in communities. A hungry man is an angry man”. – Idris Abdullahi – Yanyawai, Jigawa state

Media Links

https://reliefweb.int/report/nigeria/uk-support-helping-nigeria-move-beyond-aid

https://www.gov.uk/government/news/the-prince-of-wales-and-the-duchess-of-cornwall-visit-nigeria

https://leadership.ng/2018/11/11/british-royal-visit-rekindles-uk-nigeria-alliance/

https://www.thisdaylive.com/index.php/2017/07/25/making-smallholder-chicken-production-viable/

https://de-de.facebook.com/palladiumimpact/videos/making-markets-work-for-the-poor-Propcom-mai-karfi/1873200199408668/

https://thepalladiumgroup.com/research-impact/Raising-incomes-of-the-rural-poor-while-increasing-profits-for-business

http://thepalladiumgroup.com/research-impact/prince-charles-vaccinates-chickens

https://leadership.ng/2018/11/10/small-hold-farmers-seeks-uk-invention-to-boost-agriculture/
http://www.Propcommaikarfi.org/wp-content/uploads/2018/07/Propcom_Lessons_Learned_WEB_FINAL.pdf

http://www.twipu.com/tag/RoyalVisitNigeria.

Learning
Various warehousing options are being developed in view of the challenges faced where multiple partner coordination is required and deadlines have to be met for storage of harvest produce. In the case of AFEX warehousing in Adamawa and Borno private sector partners capacity will be utilised to aggregate and store grains. Storage capacity outside these states is another alternative. For instance, the warehouse in Gombe is used to store produce from Southern Borno and possibly Adamawa.

The strategic direction in a number of INGOs is often significantly directed by one or two key staff members. When these key personnel leave, strategies change dramatically which can create difficulties in forward planning on the part of PM. This may lead to redesign of program activities. Regular feedback meeting and taking opportunities for wider discussions with the technical teams in both organizations has mitigated the impact of staff changes both in the INGO and PM.

Communication between INGO field staff who enjoy a significant level of autonomy in the field in order to respond to changing circumstances and their head office has created gaps when PM staff have been given mandates from the head office while the staff in the field have not been informed of agreements already made. Prioritisation and timeframes are often at variance with those of PM and often found out once implementation has started, which leads to frustration and distrust among all parties. Better planning and improved communications at all levels is needed.

The changing security situation in the NE forces INGOs to consistently redesign their strategy making long term planning difficult. It is important that programmes categorise intervention implementation into short-, medium- and long-term strategies.

Current procedures for the procurement and ownership of equipment in some interventions make supply and use difficult. Initial demonstration of utility and impact is critical for facilitating targeted or specific procurement. For instance, the purchase and deployment of two-wheel tractors in northern Nigeria requires evidence of the equipment working in these environments and evidence of commercial model. PM will explore the use of a leasing agreement from third parties.

The economic challenges that exist in the tractor supply space includes double digit interest rates, short duration for repayments of loans, high initial exchange rate for import of tractors and unavailability of spare parts all work against the viability of a tractor hire model. The team intends to increase the tractor density by working with TOHFAN and other mechanisation service providers. Where a successful track record has been established by a partner such as TOHFAN, existing structures, staffing and processes require a significant overhaul to maintain the confidence of investors and beneficiaries. The team has recognised the danger of working with a potential monopoly and in response has explored with a number of alternative organizations interested in the space. In collaboration with National Agricultural Mechanization Equipment Leasing (NAMEL), PM will explore the development of other Mechanisation service providers (MSPs).

In response to increasing demand for non-interest loans in Northern Nigeria by SMEs, PM collaborated with Jaiz bank to facilitate an amount of 460M naira (949,197 GBP) to Hulhulde international, (a fertiliser distribution partner) with a possibility of increasing the loan facility to a billion naira.

Hibiscus which is a traditional African crop consumed as a vegetable with medicinal properties and as a non-alcoholic drink has an expanding export market to especially South and Central America. The present value on the international market is 10-12USD/ Kg with a medium-term export potential of 5,000MT. A majority of the present production is in Jigawa state and some NE states where increased production is possible. PM will work with TOON (commercial company exporting Hibiscus) to improve availability of good local planting material to improve potential yield.

Progress against recommendations from the previous annual review include:
The present nuanced transition from the states that are outside the implementation footprint of states needs to be continued, with results and lessons generated in those 10 States being captured during the first year of implementing the extension.
Response: This has been fully implemented with 10% of the overall results coming from the transition states.

The issue of secondary and tertiary players getting involved in an emerging market space and crowding-in around existing interventions requires more definition, to justify these potential beneficiaries receiving skills / behavioural change and increased income through attributable support from PM. In DFID Partner States this work has to be implemented and extended from the present examples of crowding-in with poultry vaccinations and the commercial model for tractor hiring.
Response: PM has seen some evidence of crowding-in of the private sector in mature interventions. Crowding-in has continued to happen in the poultry and tractor interventions. The Poultry vaccination intervention has seen three new partners Jigawa state, Ambuvet and FDH providing vaccination services to farmers through campaigns. The tractor intervention has begun discussions with NAMEL to provide technical assistance to identified tractor service providers in NN. The fertiliser intervention has seen Jaiz bank providing loans to one distributor and fertiliser distributor (Hulhulde and Interproducts ) in the North East. There have also been an additional 3 new distributors that have adopted the PM fertiliser distribution model. A majority of the interventions are not mature enough to generate the evidence in order to attract commercial interest.

Linkages with other DFID and INGO / Donor programmes in all nine states where added value can be found is a critical part of the agreed approach to extend the momentum of field work in a future; a period which is expected to be a politically unstable either side of the upcoming National and State elections. Joint offices and associated services as part of economy savings as part of any future VfM strategy for the extension.
Response: PM has collaborated with 10 INGOs/Donor/DFID programmes in all Nine states. Joint offices established in Abuja with three programs as well as with ECP in Kaduna / MNCH2 in Damaturu and GIZ in Maiduguri.

An agreement between PM and DFID is needed to achieve better management of the financial variance between committed / planned financial forecasts against actual expenditure should be found.
Response: PM worked with staff and DFID on the following procedures to improve the accuracy of monthly forecasting;
- Better management of unplanned staff leave
- Stronger interrogation of staff and partners in justification of projected budgets up to the point of submission of the budget
- Improvements have been noted in the sharing of information on invoicing on joint cost expenditure with partners, Palladium Corporate and other third-party contractors.
This has led to a marked improvement in the variance over the reporting period with a significant improvement in second half.

Tracking of unintended benefits impacting on indirect beneficiaries numbers must be improved. While the challenges of potential double accounting exist, building on exiting beneficiaries to date must be reconciled to give a more accurate overview of the impact of PM over a number of years. PM should systematically examine existing beneficiaries in partner states – to check if there is additional income from adopting a second intervention in additional to the economic benefits accrued from the first intervention.
Response: Three case studies to assess the impact of the programme on indirect beneficiaries were done during the reporting period in the Poultry production, CropLife and Feed finishing interventions. The results from the first two interventions which are still being implemented will inform future extrapolation on the impact of these interventions on indirect beneficiaries.

The programme should continue to develop value for money indicators and approaches, in particular to develop gender measures which reflect the true cost of achieving results for women. Some estimation will be required here as it is difficult to accurately disaggregate the costs associated with reaching the women when many interventions have beneficiaries from both genders.
Response: All PM results are disaggregated by gender. However, disaggregating costs by gender presents a significant challenge since gender has been mainstreamed throughout the programme and estimating the cost of reaching just women is not feasible or practicable.

Annex 1:
Number of partners and market actors that invest in pro-poor innovations that the programme helps to pilot

1. Action Against Hunger (AAH)
2. AFEX Commodities Exchange Limited (AFEX)
3. Agriproject Concept International (ACI)
4. Ambuvet Konsult Nigeria Ltd
5. Arla
6. Catholic Relief Services (CRS)
7. Continental Fertilizer
8. CREEDS Energy/Blue Camel Energy
9. CropLife
10. FDH Agrovet Nig. Ltd (FDH)
Fertiliser distributors:
1. Alhaji Ali Gambo Maiduguri
2. Alhaji Saidu Maiduguri
3. Alhaji A. A. Lawal Adamawa
4. Food Security Agricultural Company (FSAC)
5. Gesellschaft für Internationale Zusammenarbeit (GIZ)
6. Golden Fertiliser
7. Green Sahel Agro Ventures (GSAV)
8. Hulhulde
9. Inter Products Link Ltd
10. Jaiz Bank
11. L&Z Integrated Farms
12. Ministry of Agriculture, Jigawa state
13. National Veterinary Research Institute (NVRI)
14. Nkataa Mart Ltd
15. Olam International
16. Premier Seed Nigeria Ltd
17. Roshan Global
18. TOON Consolidated Company Ltd
19. Tractor Owners and Hiring Facilities Association of Nigeria (TOHFAN)
20. Tropical Poultry Services (TPS)
21. Veterinary Council of Nigeria (VCN)

16 below have invested in the North East:
1. ACI
2. Action Against Hunger (AAH)
3. Alhaji A. A. Lawal Adamawa
4. Alhaji Ali Gambo Maiduguri
5. Alhaji Saidu Maiduguri
6. Continental Fertilizer
7. CRS
8. CropLife
9. Food Security Agricultural Company
10. Green Sahel Agro Ventures
11. NVRI (reopened an outstation in Maiduguri)
12. Olam
13. Premier Seed Nigeria Limited
14. Roshan Global
15. TOON Consolidated Company Ltd
16. Inter Products Link Ltd (taken over the fertiliser plant in Maiduguri)

Annex 2
Amount of investment leveraged through market players and key actors (NGN/GBP).

Name of Partner	Total (GBP)	Total (NGN)
Jail Bank	949,197	460,000,000
Fertilizer Distributors	6,194,065	3,001,768,100
CropLife	50,241	24,347,630
Premier Seed Nigeria Ltd.	6,809	3,300,000
TOHFAN	115,554	56,000,000
Traxi	2,280,137	1,105,000,000
Green Sahel Agro Ventures	30,952	15,000,000
Food Security Agricultural Company	123,808	60,000,000
AFEX	15,476	7,500,000
CRS	1,032	500,000
GIZ	4,127	2,000,000
Olam	239,128	115,886,300
Roshan Global	5,214	2,527,000
CREEDS Energy	2,683	1,300,000
ACI	30,746	14,900,000
Ambuvet	1,944	942,000
FDH	628	304,200
NVRI, Bauchi Outstation	6,690	3,241,889
NVRI, Kano Outstation	4,210	2,040,169
NVRI, Vom	367,347	178,023,800
Ambuvet	1,238	600,000
Tropical Poultry Services	970	470,000
L&Z	16,817	8,150,000
Arla	81,078	39,292,000

Annex 3.
Actors and organisations have been supported or influenced by PM

National Veterinary Research Institute (NVRI) - PM has been working with NVRI since the inception of the programme in 2012, with the initial interaction mostly centred on advocacy to the Institute to ensure vaccine availability to PM’s private sector partners. Then, the thermotolerant NDV-i2 vaccines had little or no demand and the Institute mostly supplied to government agents and large farmers and constantly experienced vaccine expiration and wastage. In 2015, PM went into partnership with NVRI with the aim of expanding supply (production and distribution) and building their capacity to position their outstations as a Rural Veterinary Solution Providers; a core part of their organization’s mandate with a more commercially viable focus. The improved access by small farmers for controlling Newcastle disease in rural poultry was the entry point to the production of vaccines and the development of veterinary channels to reach rural small-scale poultry and livestock farmers. In the past year, the work has focused on the North-East of Nigeria, with improved delivery of veterinary vaccines and services through their outstations. Bauchi is in full operation and upgrading activities have begun in Adamawa and Maiduguri outstations. So far, NVRI has invested in their production facility to ensure regular supply of NDV-i2, PPR and CBPP vaccines to the outstations; has recruited 2 new staff for the Maiduguri outstation; and has invested a significant amount in renovating Kano and Bauchi outstations.

Catholic Relief Services (CRS) - CRS established and strengthened over 1,400 producer groups operating under 92 marketing committees (in the NE and North West Nigeria) under the USAID Feed the Future project. CRS used its “SMART skills approach” of group organization, natural resource management, marketing basics, and financial management to strengthen these groups. They also implemented a self-sustaining Savings and Internal Lending Community (SILC) based on a private sector model as well as a community seed enterprise model to enhance group members’ access to improved seed. With all this capacity development, a number of key areas were omitted and identified by CRS including access to other farm inputs, off taking skills, aggregation and storage. PM was invited by CRS to assist in filling these gaps. PM introduced AFEX to the CRS producer groups in Borno and Adamawa where market engagement had been a serious challenge. Following this, AFEX has gone ahead to select outreach officers from the producer groups with the view of creating awareness of AFEX’s services as well as to drive adoption of the services. GIZ were invited to assist AFEX in the rehabilitation of existing warehouses in Borno and Adamawa due to the lack of existing storage capacity in the area.

CropLife - CropLife is an umbrella organization representing the interests of manufacturers of crop protection products in Africa and the Middle East. PM engaged CropLife in 2016 to pilot the Spray Service Provider (SSP) grassroot delivery model in 3 states (Kaduna, Kano and Jigawa). Based on the success of the pilot, the programme was scaled up to include 2 additional states in the NE (Bauchi and Gombe) with over 1,000 SSPs trained. The “SSP Delivery model” has proven to be viable. Not only has it led to increased incomes of over 25,000 farmers and SSPs, it has also led to increased sales for Crop Protection Product (CPP) companies. In order to make the model more sustainable, CPP companies are encouraged to adapt the model and invest in training more SSPs. Initially, CropLife trained commercial farmers and government agencies. This is the first attempt at confronting the challenges of last mile delivery. CropLife invested in the identification and training of SSPs in a sustainable and cost-effective manner. CropLife cost-shared with PM in the training of over 1,000 farmers as SSPs in Kaduna, Kano, Jigawa, Bauchi and Gombe. A total of NGN 24,347,630 (GBP 50K) was invested in the 5 states with NGN 4.8M (GBP 9,857) in each of the NE states (Bauchi and Gombe).

Gesellschaft für Internationale Zusammenarbeit (GIZ) - GIZ is interested in constructing and rehabilitating warehouses and other infrastructure in the North-East with the objective of providing smallholder farmers with access to modern storage facilities, markets and other product offerings and services that can be delivered through the AFEX warehousing model. To overcome the contractual constraints GIZ faces, PM will implement some aspects of the work required for the rehabilitation of the identified warehouses and aggregation points. This for GIZ was a significant broadening of their normal scope of work and represented a steep learning curve for their technical staff.

Action Against Hunger (AAH) - AAH is a key INGO working in the North East in both humanitarian and early recovery work. The working relationship with PM has included the training of women in conflict affected areas on soybean, groundnut production, micro-gardening and small ruminant production and management. 48 women (2 women group representatives from 11 wards) have been trained in soybean and groundnut production and have in turn trained another 1,502 beneficiaries. A similar approach has been used where 19 extension agents have been trained on soybean, groundnut production, micro-gardening and small ruminant production and management. These extension agents have provided technical training to 3,000 farmers in 11 wards in Nangere LGA in Yobe state. 331 women have been trained on small ruminant production and each of them have received two goats as part of an AAH start-up package. A validation exercise was undertaken by PM in Yobe state to confirm that the women received the small ruminants as part of the start-up package. It was also to assess the nature of household spaces for the small ruminant production as well as potential for layering the poultry intervention. PM has identified 2 local suppliers within Yobe state that could potentially be engaged to supply small ruminants for AAH’s women under an e-voucher scheme. PM contributed to the development of the AAH training materials used for trainings in small ruminant production, soybean, groundnut and micro-gardening. Finally, AAH have shared the logframe for the implementation of a program funded by Swiss Agency for Cooperation and Development. The project targets 15,000 persons, mainly women, with special emphasis on agroforestry, income generating activities and Water/Sanitation and Health (WASH). Meetings have been conducted between PM and AAH to begin the process of outlining potential areas of collaboration

Development Exchange Centre (DEC): DEC is a reputable microfinance institution (MFI) primarily for women and women groups with a focus on northern Nigeria. They provide bespoke short-term loans for micro- and small-enterprises to enhance their capacity for sustainable development. PM has helped DEC identify potential clients who engage in home-based enterprises.

The International Committee of the Red Cross (ICRC): ICRC, an INGO, partnered with PM to introduce innovative business models to add a layer of sustainability to the support the Economic and Security team (ECOSEC) were already giving to post conflict communities. Through this collaboration beneficiaries who received humanitarian aid in the form of seeds and fertiliser and in some cases assets from ICRC were trained by PM on group dynamics, good agricultural practices and access to markets that were issues deficit in the support previously given. PM has been involved with ICRC’s annual planning cycle. This partnership has expanded with ICRC showing interest in adopting the Community Animal Health Worker (CAHW) manual and handbook, developed with PM’s assistance, for their own trainings. ICRC is interested in facilitating the training of CAHWs in the NE to assist farmers which allows a wider livelihood strategy to be adopted in post conflict post humanitarian aid situations.

Inara Foundation: Inara Foundation is a non-profit organization embarking on poverty alleviation and economic empowerment projects in Borno State aimed at assisting low-income people in business and enterprise development in rural communities, especially women and youth. PM has completed a DD process and drafted a collaboration agreement with Inara to explore opportunities for homebased women enterprise opportunities identified in the WISE WEE NE research document. Inara is known for their work around children with special needs and equipping learning centres such as libraries. Inara have responded to an expression of interest sent out by PM to cover capacity building activities within the North east especially Borno and Yobe. Initially PM was to support Inara under the anchor borrower scheme (AFEX and NIRSAL) targeting 1,000 farmers for dry season farming in Borno. The restructuring of the anchor borrowers’ scheme with an alternative guarantor may create future opportunities that INARA can respond to with the support of PM.

Ministry of Agriculture, Jigawa State: PM is partnering with Jigawa State to establish the CAHW training program with a view to developing a network of CAHWs to deliver affordable veterinary products and services to rural livestock producers and improve disease reporting and surveillance. So far, the Jigawa State government has invested in ‘training of trainers’ session, with 8 veterinarians trained as state-based trainers; shared the cost of training 60 CAHWs, and plan to equip the CAHWs with ambulatory kits as well as motorbikes for mobility.

1. DFID Partnership, Engage, Reform, Learn Programme (PERL) - Engaged Citizen Participation (ECP): PM has influenced PERL- ECP to change focus from working on national fertiliser policy to seed standards in Nigeria. ECP subsequently initiated a comprehensive institutional review of the Nigerian Seed Council to identify constraints for it to deliver its mandate of ensuring quality seeds are correctly sold to smallholder farmers (SHFs) in northern Nigeria when sold through commercial markets. ECP (PERL) has taken up supporting reforms in the Nigerian Seed Council both Nationally and at State Level remedy this constraint while PM has engaged with commercial seed producers to identify the production of certified seeds and its delivery to SHFs.
Attachments

Revised Delivery Chain Map

Risk Assessment